## in
Date recorded | Category | Initiative name | Original planned end date | Initiative stage | Quality | Planned end date | Explanatory notes | Date data current at | Priority | Original total estimated expenditure | Cost | Category name | Percentage complete | Actual cost to date | Time-frame | Overall status | _id | Investment objectives | Revised total estimated expenditure | Actual start date | Department
30/4/2018 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Initiate | G | 2018-12-31T00:00:00 |  | 2018-02-28T00:00:00 | High | 5600000 | G | eHealth Queensland | 13 | 461528 | G | G | 1 | This project aims to establish a robust, highly available and secure contemporary platform that has the capability to support the agile eHealth Strategy. | 5600000 | 2017-07-03T00:00:00 | DH
30/4/2018 | HSQ | AUSLAB Re-hosting project | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-02-28T00:00:00 | High | 1691324 | G | Health Support Queensland | 32 | 425294 | G | G | 2 | Delivery of a replacement hardware and visualisation solution for the AUSLAB and AUSCARE systems that will achieve improved resiliency of the architecture, updated operating system and inclusion of virtualisation. AUSLAB and AUSCARE are critical to support laboratories and patient clinical care. | 1554952 | 2017-08-28T00:00:00 | DH
30/4/2018 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2016-08-01T00:00:00 | Delivery | G | 2018-07-30T00:00:00 |  | 2018-03-16T00:00:00 | High | 1858668 | G | Metro North | 50 | 1023772 | G | G | 3 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 30/4/2018, 30/4/2018,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Women 30/4/2018,92s Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 30/4/2018, 30/4/2018,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 2482431 | 2015-06-01T00:00:00 | DH
30/4/2018 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-02-28T00:00:00 | High | 11180394 | G | eHealth Queensland | 12 | 268218 | G | G | 4 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 30/4/2018,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work. 30/4/2018,a0 Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 11180394 | 2017-07-03T00:00:00 | DH
30/4/2018 | MNHHS | Business Intelligence - Enterprise Data Warehouse | 2018-06-29T00:00:00 | Delivery | G | 2018-06-28T00:00:00 | February: The scope of this project is being re-evaluated by the governance committee, with finances being reviewed in line with the proposed stage 2 scope. | 2018-03-16T00:00:00 | High | 2114991 | G | Metro North | 72 | 1530252 | G | G | 5 | This project will introduce Business Intelligence and Data Warehousing capabilities at MNHHS. The project will deliver BI & DW technical skills, system infrastructure, data automation tools, a pilot dataset, data governance processes and quality control framework at MNHHS. Metro North Finance and MNIT are jointly managing the project. | 1480182 | 2016-11-01T00:00:00 | DH
30/4/2018 | MNHHS | Central Patient Monitoring Equipment Replacement | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-03-16T00:00:00 | High | 1236416 | G | Metro North | 51 | 414773 | G | G | 6 | Metro North IT has been approached by Metro North Procurement Services (MNPS) to provide ICT advice and guidance into the Central Patient Monitoring Equipment Replacement (CPMER) Project. The Health Technology Equipment Replacement (HTER) program for central monitoring systems is providing funding in financial years 16/18 for physiological monitoring equipment requiring replacement across MNHHS hospital facilities. There is an estimated 312 pieces of equipment, primarily Physiological Monitoring devices, to be replaced under the program across MNHHS hospital facilities. MNHHS implementations are being co-ordinated by MNPS. | 1236416 | 2017-06-28T00:00:00 | DH
30/4/2018 | MNHHS | CISS (Community, Indigenous and Subacute Services) Wi-Fi | 2018-06-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-03-16T00:00:00 | Medium | 1280798 | G | Metro North | 51 | 777860 | G | G | 7 | The Community, Indigenous and Subacute Services (CISS) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the internal areas of the prioritised CISS sites. 30/4/2018, 30/4/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1280798 | 2017-07-28T00:00:00 | DH
30/4/2018 | EHQ | Cloud First Project | 2018-06-30T00:00:00 | Delivery | G | 2018-07-02T00:00:00 |  | 2018-02-28T00:00:00 | High | 4250000 | G | eHealth Queensland | 49 | 2478969 | G | G | 8 | The Cloud First project will build internal capability and establish processes within Queensland Health to appropriately utilise cloud services on an ongoing basis. | 4107007 | 2017-01-01T00:00:00 | DH
30/4/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Clinical Notes project (release 3.0) | 2018-02-06T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-02-28T00:00:00 | High | 1415000 | G | Clinical Excellence | 80 | 1625078 | G | G | 9 | Upgrading the CIMHA Mental Health Act module to accommodate a re-architecture of the CIMHA clinical notes module is required to deliver benefits to the clinical workforce associated with data entry efficiencies; improved data sharing across digital platforms; patient level information transfer to third parties to support service integration and data mining to support service improvement and research. | 1969365 | 2017-02-20T00:00:00 | DH
30/4/2018 | EHQ | Critical Network Hardware | 2018-02-28T00:00:00 | Delivery | G | 2018-05-31T00:00:00 | February: This project has returned to 'on track'. 30/4/2018, 30/4/2018,January: The project is reporting 'Amber' due to limited resource availability and additional technical requirements, impacting the schedule of the project | 2018-02-28T00:00:00 | High | 8636364 | G | eHealth Queensland | 62 | 7386821 | G | G | 10 | The objectives of the project include: 30/4/2018,a) Mitigate the Department of Health risk that core network switches at QH facilities will no longer be supported by the manufacturer from February 2018. 30/4/2018,b) Invest in the replacement of critical ICT network hardware to maintain current capability and reliability of the data network for 120+ enterprise clinical and business applications and provide the foundation for future capability in the enterprise data centres. 30/4/2018,c) Ensure hardware replacement occurs with minimal impact to business operations in Hospital and Health Services or Corporate offices. 30/4/2018,d) Update logical and physical design and architecture documentation for ease of maintenance and management. | 8371607 | 2017-03-06T00:00:00 | DH
30/4/2018 | EHQ | Digital Collaboration Platform Program | 2018-06-30T00:00:00 | Delivery | G | 2019-02-28T00:00:00 | February: Project activities have continued to be delayed, resulting in this project reporting 'Red'. A project change request has been submitted to the project's governance committee. 30/4/2018, 30/4/2018,January: This project is experiencing delays in pre-migration activities. | 2018-02-28T00:00:00 | High | 11000000 | A | eHealth Queensland | 33 | 9475712 | R | R | 11 | This program will deliver digital collaboration tools for any time, any where, any device including: 30/4/2018, 30/4/2018,95 Email and Archiving 30/4/2018, 30/4/2018,95 Establishment and Collaboration 30/4/2018, 30/4/2018,95 Productivity Suite Enablement | 18467291 | 2015-10-29T00:00:00 | DH
30/4/2018 | EHQ | File Services Migration | 2017-06-30T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-02-28T00:00:00 | High | 3400000 | G | eHealth Queensland | 27 | 2790119 | G | G | 18 | The purpose of this investment is to adopt a contemporary, simplified file management solution for Queensland Health that enables a more cohesive customer experience. | 9907925 | 2016-08-01T00:00:00 | DH
30/4/2018 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate | G | 2017-12-31T00:00:00 | February: The current proposed date of completion is the 31 December 2019, which is subject to project board approval. | 2018-02-28T00:00:00 | High | 1500000 | G | Queensland Ambulance Service | 40 | 529326 | G | G | 12 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 4167216 | 2015-12-01T00:00:00 | DH
30/4/2018 | QAS | e-ARF Redevelopment for iPad | 2016-12-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | February: Implementation and rollout of the system was completed in late November 2017. The project is currently finalising end of project reporting processes. | 2018-02-28T00:00:00 | High | 2624000 | G | Queensland Ambulance Service | 99 | 1877680 | G | G | 13 | This is an initiative to provide the electronic Ambulance Report Form (eARF) electronic patient care solution via iPads in the field. | 1910813 | 2015-09-02T00:00:00 | DH
30/4/2018 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | February: Further solution clarification is required, which has impacted on the overall delivery timeframe of this initiative. | 2018-02-28T00:00:00 | High | 1283000 | G | Chief Health Officer and Prevention | 54 | 68000 | A | A | 14 | ?Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1283000 | 2017-07-24T00:00:00 | DH
30/4/2018 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery | G | 2018-11-30T00:00:00 |  | 2018-03-16T00:00:00 | High | 4827917 | G | Metro North | 60 | 2655106 | G | G | 15 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (ieMR) program. 30/4/2018, 30/4/2018,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 30/4/2018, 30/4/2018,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. | 4827917 | 2016-07-01T00:00:00 | DH
30/4/2018 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 |  | 2018-02-28T00:00:00 | High | 3792744 | G | eHealth Queensland | 7 | 215612 | G | G | 16 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment. 30/4/2018,a0 30/4/2018,a0The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access. 30/4/2018,a0 | 3792744 | 2017-07-05T00:00:00 | DH
30/4/2018 | QAS | Enterprise Rostering System | 2018-12-31T00:00:00 | Paused | G | 2018-12-31T00:00:00 |  | 2018-02-28T00:00:00 | High | 1000000 | G | Queensland Ambulance Service | 10 | 505297 | G | G | 17 | The initiative is to provide a centralised electronic rostering system to replace existing aging and disparate manual systems currently being utilised across the state. | 1194682 | 2016-12-01T00:00:00 | DH
30/4/2018 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Delivery | G | 2018-12-31T00:00:00 | February:The project is currently monitoring several schedule risks impacting a number of configuration activities. | 2018-02-28T00:00:00 | High | 105000000 | G | Metro North | 55 | 49985595 | A | A | 19 | The current Queensland Health Finance, Asset and Materials Maintenance Information System (FAMMIS) system is based on a heavily customised solution which is almost 20 years old and no longer supported. 30/4/2018,The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 30/4/2018, 30/4/2018,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 30/4/2018,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 30/4/2018, 30/4/2018,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
30/4/2018 | EHQ | Follow Me Desktop - Deployment | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-02-28T00:00:00 | High | 3952980 | G | eHealth Queensland | 37 | 897676 | G | G | 20 | Follow Me Desktop Deployment Project will deliver 30/4/2018,a0the Follow Me Desktop service (FMD) to HHS 30/4/2018,92 in alignment with the Infrastructure Remediation Program (IMP) and ieMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 3676980 | 2017-07-03T00:00:00 | DH
30/4/2018 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-02-28T00:00:00 | High | 3301500 | G | eHealth Queensland | 14 | 134264 | G | G | 21 | Project Purpose: 30/4/2018,a0To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 2490769 | 2017-07-01T00:00:00 | DH
30/4/2018 | EHQ | ICT Regional Wireless Infrastructure Initiatives | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-02-28T00:00:00 | High | 4170000 | G | eHealth Queensland | 38 | 2435249 | G | G | 22 | The Regional eHealth Project (ReHP) is a Wireless LAN and Network Infrastructure uplift project so that sites in Far North Qld are ready to rollout their new eHealth Application. | 3489114 | 2017-07-01T00:00:00 | DH
30/4/2018 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 |  | 2018-02-28T00:00:00 | Critical | 1120000 | G | eHealth Queensland | 40 | 400043 | G | G | 23 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. | 1120000 | 2017-07-05T00:00:00 | DH
30/4/2018 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-02-28T00:00:00 | High | 3215000 | G | eHealth Queensland | 40 | 4435258 | G | G | 24 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 12318334 | 2015-06-22T00:00:00 | DH
30/4/2018 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery | G | 2019-12-30T00:00:00 |  | 2018-03-02T00:00:00 | High | 33827000 | G | Clinical Excellence | 18 | 10828000 | G | G | 30 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 39408218 | 2017-03-01T00:00:00 | DH
30/4/2018 | EHQ | ieMR Program (Funding Packages 3 and 4) | 2019-04-30T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-02-28T00:00:00 | High | 0 | G | eHealth Queensland | 25 | 0 | G | G | 25 | ieMR will enable improved patient care through the development of a state-wide, authoritative single source of the patient records. 30/4/2018, 30/4/2018,The ieMR will provide clinicians with the ability to: 30/4/2018,* access data that is integrated, accurate and clinically relevant 30/4/2018,* support decision making and better use of information 30/4/2018,* optimise management of patients, resources and provision of services 30/4/2018,* support interaction across a network of providers by making it easier to find providers, transfer information and collaborate with multidisciplinary providers. 30/4/2018,The Program scope (all tranches) is to roll out the ieMR system to 24 hospitals across Queensland. 30/4/2018, 30/4/2018,Please note that financial information for ieMR is Commercial in Confidence | 0 | 2016-11-17T00:00:00 | DH
30/4/2018 | EHQ | Infrastructure Capacity FY 17-18 | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-02-28T00:00:00 | Medium | 1000000 | G | eHealth Queensland | 42 | 424529 | G | G | 26 | Project Purpose: 30/4/2018,a0 30/4/2018,The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified 30/4/2018,91organic growth 30/4/2018,92 requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. | 2000000 | 2017-07-01T00:00:00 | DH
30/4/2018 | EHQ | Infrastructure Maintenance Program | 2022-06-30T00:00:00 | Initiate | G | 2022-06-30T00:00:00 |  | 2018-02-28T00:00:00 | Medium | 1161415 | G | eHealth Queensland | 3 | 302374 | G | G | 27 | The Infrastructure Maintenance Program (IMP) 30/4/2018,a0will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 30/4/2018,The scope includes: 30/4/2018,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 30/4/2018,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and 30/4/2018,a0 30/4/2018,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1161414 | 2017-07-03T00:00:00 | DH
30/4/2018 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery | G | 2022-06-30T00:00:00 |  | 2018-02-28T00:00:00 | High | 14673739 | G | Clinical Excellence | 10 | 1336461 | G | G | 28 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 30/4/2018,The ongoing program of work aims to continue and build upon existing functionality by: 30/4/2018, 30/4/2018,95 Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 30/4/2018, 30/4/2018,95 Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 30/4/2018, 30/4/2018,95 Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 30/4/2018, 30/4/2018,95 Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 30/4/2018, 30/4/2018,95 Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
30/4/2018 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate | G | 2022-12-21T00:00:00 |  | 2018-02-28T00:00:00 | High | 6300000 | G | Queensland Ambulance Service | 19 | 446725 | G | G | 29 | Phased delivery of a system supporting QAS business intelligence. | 6300000 | 2017-01-03T00:00:00 | DH
30/4/2018 | EHQ | Queensland State-wide ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-02-28T00:00:00 | High | 3246247 | G | eHealth Queensland | 37 | 481679 | G | G | 49 | Will replace or uplift out of date end of life ICT assets. | 3246247 | 2017-07-01T00:00:00 | DH
30/4/2018 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 1 | 2016-11-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | February: Approval delays in obtaining additional funding and a slightly extended schedule has impacted the project's schedule, with approvals expected in the upcoming reporting month. 30/4/2018, 30/4/2018,January: Additional scope requirements have caused the project to extend the schedule and request additional finances, which is progressing through the project 30/4/2018,92s governance committee. | 2018-02-28T00:00:00 | High | 8200000 | R | Health Support Queensland | 89 | 22024483 | R | R | 31 | The IWFM project involves: 30/4/2018,- configuring additional functionality (currently available and licensed, but unutilised) within the existing Rostering and Payroll business solutions 30/4/2018,- partnering with HHSs to develop refined business models and business processes to support the roster-to-pay process 30/4/2018,- undertaking extensive training and change management to support the adoption and effective usage of new functionality and processes | 25060122 | 2016-02-17T00:00:00 | DH
30/4/2018 | EHQ | Interoperability Project | 2016-04-29T00:00:00 | Delivery | G | 2019-09-29T00:00:00 |  | 2018-02-28T00:00:00 | High | 23850000 | G | eHealth Queensland | 23 | 11941704 | G | G | 32 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 30/4/2018,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 30/4/2018,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 30/4/2018, | 39189509 | 2015-02-01T00:00:00 | DH
30/4/2018 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Delivery | G | 2020-12-21T00:00:00 |  | 2018-03-06T00:00:00 | High | 64000000 | G | Health Support Queensland | 46 | 16794104 | G | G | 33 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 30/4/2018,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. | 64000000 | 2015-08-28T00:00:00 | DH
30/4/2018 | MNHHS | Learning and Performance Management Project | 2017-06-30T00:00:00 | Initiate | G | 2018-11-26T00:00:00 |  | 2018-03-16T00:00:00 | High | 1178190 | G | Metro North | 75 | 1078840 | G | G | 34 | Implement an integrated Learning Management and Performance Management system with the capability to deliver online learning and training content, facilitate performance development and maintain centralised records for reporting purposes. | 1178190 | 2016-07-11T00:00:00 | DH
30/4/2018 | GCHHS | Medical Imaging Informatics Solution (MIIS) Risk Mitigation | 2018-12-31T00:00:00 | Delivery | G | 2018-12-31T00:00:00 |  | 2018-02-07T00:00:00 | High | 5000000 | G | Gold Coast | 18 | 643136 | G | G | 35 | The Medical Imaging Informatics Solution (MIIS) Risk Mitigation project has identified an Imaging solution which will address the risks and opportunities described in the Case for Change including the mitigation of patient safety risks, increased efficiency and productivity, improvi.ng medical imaging billing revenue collection and cash flow. The solution has user endorsement from radiologists and clinicians and will be specifically configured to meet GCHHS 30/4/2018,92s needs. | 5000000 | 2017-04-03T00:00:00 | DH
30/4/2018 | EHQ | Project, Program and Portfolio Management Application | 2018-03-31T00:00:00 | Initiate | G | 2018-06-29T00:00:00 |  | 2018-02-28T00:00:00 | Medium | 1344177 | G | eHealth Queensland | 30 | 443659 | G | G | 47 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 30/4/2018, | 1473632 | 2017-05-02T00:00:00 | DH
30/4/2018 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery | G | 2018-11-30T00:00:00 |  | 2018-03-16T00:00:00 | High | 4030460 | G | Metro North | 40 | 1592217 | G | G | 36 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 30/4/2018, 30/4/2018,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 30/4/2018, 30/4/2018,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
30/4/2018 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | February: The project is continuing to report 'Red' due to continued due to delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-03-16T00:00:00 | High | 6299780 | R | Metro North | 75 | 5927846 | R | R | 37 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 6299780 | 2014-06-01T00:00:00 | DH
30/4/2018 | EHQ | Metro South and East Queensland ICT Infrastructure Replacement Initiative | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-02-28T00:00:00 | High | 4160449 | G | eHealth Queensland | 61 | 801900 | G | G | 38 | Will replace or uplift out of date end of life ICT assets. | 4160448 | 2017-07-01T00:00:00 | DH
30/4/2018 | EHQ | Metro South East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-02-28T00:00:00 | High | 2182844 | G | eHealth Queensland | 38 | 153318 | G | G | 39 | Will replace or uplift out of date end of life ICT assets. | 2182843 | 2017-07-01T00:00:00 | DH
30/4/2018 | EHQ | Mobile Application System for Bring Your Own Device | 2018-06-30T00:00:00 | Delivery | G | 2018-07-06T00:00:00 |  | 2018-02-28T00:00:00 | High | 1639698 | G | eHealth Queensland | 65 | 877852 | G | G | 40 | This project leverages the investment of the previous Bring-Your-Own-Device (BYOD) 30/4/2018,a0projects to extend the capability of device mobility by building the foundations of a Mobile Application Ecosystem - the processes, products and services to enable the managed development of low/no code applications by Health and Hospital Services (HHS). 30/4/2018,a0 This project will also complete the deployment of BYOD laptops and provide recommendations on how cost savings can be made by the organisation around Corporate devices and data plans. 30/4/2018,a0 | 1639698 | 2017-07-01T00:00:00 | DH
30/4/2018 | CED | Queensland Integrated Safety Information Project (QISIP) / Risk Management | 2017-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-03-01T00:00:00 | High | 4333120 | G | Clinical Excellence | 89 | 7805389 | G | G | 48 | This initiative will source a state wide system to replace existing enterprise risk management systems to support patient and staff incident reporting, feedback, case management and risk management processes. | 16273520 | 2013-01-25T00:00:00 | DH
30/4/2018 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery | G | 2018-12-19T00:00:00 | February: This project is experiencing delays in pre-migration activities and delays experienced in another dependent project. Further finances are required for additional project resources, with the schedule and finance issues being managed via the project's governance committee. 30/4/2018, 30/4/2018,January: This project is experiencing delays in pre-migration activities and delays experienced in another dependent project. | 2018-02-28T00:00:00 | High | 14100000 | R | eHealth Queensland | 42 | 15861053 | R | R | 41 | This project will move Queensland Health to a modern end user workspace that is: current; delivering collaboration and productivity benefits; able to be accessed anywhere, anytime and on any device; reducing the reliance and expense of on premise infrastructure and support and not constraining the business from taking advantage of modern applications and services. | 27427900 | 2016-05-12T00:00:00 | DH
30/4/2018 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-02-28T00:00:00 | High | 1500000 | G | Queensland Ambulance Service | 83 | 602640 | G | G | 42 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1744000 | 2015-10-01T00:00:00 | DH
30/4/2018 | CHOPD | Notifiable Conditions System Replacement | 2019-06-29T00:00:00 | Delivery | G | 2020-02-28T00:00:00 |  | 2018-02-28T00:00:00 | High | 12000000 | G | Chief Health Officer and Prevention | 36 | 2306499 | G | G | 43 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 30/4/2018,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
30/4/2018 | EHQ | Patient Administration System (PAS) Replacement - Business Case Development Project | 2017-06-30T00:00:00 | Initiate | G | 2019-03-29T00:00:00 |  | 2018-02-28T00:00:00 | Medium | 3850000 | G | eHealth Queensland | 54 | 3673452 | G | G | 44 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients 30/4/2018,92 journeys, and ensure that accurate information about our patients is readily available when and where required. 30/4/2018, 30/4/2018,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 30/4/2018, 30/4/2018,95 support for patient engagement 30/4/2018, 30/4/2018,95 integrated care 30/4/2018, 30/4/2018,95 clinical research 30/4/2018, 30/4/2018,95 population health (for patients using public health services) 30/4/2018, 30/4/2018,95 performance transparency 30/4/2018, 30/4/2018,95 resource planning. | 11890865 | 2015-11-01T00:00:00 | DH
30/4/2018 | MNHHS | Picture Archiving and Communication System (PACS) | 2017-09-29T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | February: The project is continuing to report 'Red' due to continued delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-03-16T00:00:00 | High | 3114694 | R | Metro North | 75 | 3435569 | R | R | 45 | Procure and implement a contemporary Picture Archiving and Communication (PACS) system and functionality that will ensure improved service delivery for the MNHHS Medical Imaging Departments (and other PACS users) through replacement of RBWH PACS ensuring that it is scalable and able to meet the ongoing needs of Metro North Hospital and Health Service. | 3656297 | 2016-07-11T00:00:00 | DH
30/4/2018 | CSD | Practice Management Enterprise Solution | 2018-11-01T00:00:00 | Initiate | G | 2018-11-01T00:00:00 |  | 2018-03-06T00:00:00 | High | 1470000 | G | Corporate Services | 49 | 514351 | G | G | 46 | The main practice management software used by HHSs to conduct private practice services and billing activities is being replaced. The initiative will procure and implement "like for like" functionality enterprise solution for participating HHSs (15 in total). | 1470000 | 2017-08-01T00:00:00 | DH
30/4/2018 | EHQ | Queensland State-wide ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-02-28T00:00:00 | High | 3283431 | G | eHealth Queensland | 65 | 1808771 | G | G | 50 | Will replace or uplift out of date end of life ICT assets. | 3282431 | 2017-07-01T00:00:00 | DH
30/4/2018 | MNHHS | Quick Flow Project | 2019-02-01T00:00:00 | Initiate | G | 2019-06-30T00:00:00 |  | 2018-03-16T00:00:00 | High | 6408600 | G | Metro North | 35 | 938097 | G | G | 51 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 30/4/2018,The key objectives of the project are to: 30/4/2018, 30/4/2018,95 Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 30/4/2018, 30/4/2018,95 Improve the outpatient experience across MNHSS facilities and community services 30/4/2018, 30/4/2018,95 Improve clinic resource utilisation 30/4/2018, 30/4/2018,95 Increase the efficiency of clinical and administrative processes 30/4/2018, 30/4/2018,95 Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
30/4/2018 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Initiate | G | 2019-12-31T00:00:00 |  | 2018-03-08T00:00:00 | High | 34950000 | G | Cairns and Hinterland | 57 | 9203708 | G | G | 52 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patient 30/4/2018,92s home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
30/4/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-02-28T00:00:00 | High | 4260336 | G | eHealth Queensland | 38 | 267563 | G | G | 53 | Will replace or uplift out of date end of life ICT assets. | 4260336 | 2017-07-01T00:00:00 | DH
30/4/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-02-28T00:00:00 | High | 2150147 | G | eHealth Queensland | 59 | 577405 | G | G | 54 | Will replace or uplift out of date end of life ICT assets. | 2150147 | 2017-07-01T00:00:00 | DH
30/4/2018 | EHQ | Regional South & East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-02-28T00:00:00 | High | 1651750 | G | eHealth Queensland | 38 | 249954 | G | G | 55 | Will replace or uplift out of date end of life ICT assets. | 1651750 | 2017-07-01T00:00:00 | DH
30/4/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-02-28T00:00:00 | High | 4245973 | G | eHealth Queensland | 64 | 1105759 | G | G | 56 | Will replace or uplift out of date end of life ICT assets. | 4245973 | 2017-07-01T00:00:00 | DH
30/4/2018 | EHQ | Service Delivery Excellence Project (SDEP) Stage 1 | 2018-02-28T00:00:00 | Delivery | G | 2018-03-22T00:00:00 |  | 2018-02-28T00:00:00 | High | 4822000 | G | eHealth Queensland | 18 | 396148 | G | G | 57 | The Service Delivery Excellence Project (SDEP) aims to improve the service delivery functions of eHealth Queensland to help the organisation achieve its Customers and services Foundation and Shared Goal: 30/4/2018,Enhance value for customers by streamlining end to end services, processes and delivery models so that we can provide an exceptional customer experience. 30/4/2018,Stage 1 has the primary objective of delivering the Project Initiation Document (PID) for the Service Delivery Excellence Project (SDEP) Stage 2. | 7136880 | 2017-11-21T00:00:00 | DH
30/4/2018 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Initiate | G | 2020-09-30T00:00:00 |  | 2018-02-28T00:00:00 | High | 10500000 | G | eHealth Queensland | 10 | 437087 | G | G | 58 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 10500000 | 2017-07-03T00:00:00 | DH
30/4/2018 | MNHHS | Royal Brisbane & Women's Hospital Wi-Fi | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 |  | 2018-03-16T00:00:00 | High | 5000000 | G | Metro North | 12 | 2027194 | G | G | 59 | The RBWH Wi-Fi Project will provide an uplift and renewal to the latest Queensland Health (QH) standard for wireless local area network (WLAN) coverage within the internal areas of prioritised RBWH buildings in order to support digital healthcare. 30/4/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for the RBWH in the near future. | 5000000 | 2017-10-22T00:00:00 | DH
30/4/2018 | EHQ | Storage Asset Replacement | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-02-28T00:00:00 | High | 1671556 | G | eHealth Queensland | 25 | 170813 | G | G | 60 | The Storage Asset Replacement (SAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the SAR and Backup Asset Replacement (BAR) projects. 30/4/2018,The SAR project seeks to outline architecture for storage that will provide a cost effective, scalable and fit for purpose environment for the future of storage services within Queensland Health. 30/4/2018,a0 Utilising space saving technologies which will enable further cost savings and reduce the requirement for capacity expansion in the short to medium term. | 1671555 | 2017-07-03T00:00:00 | DH
30/4/2018 | EHQ | Telehealth Asset Replacement FY 17-18 | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-02-28T00:00:00 | High | 1960000 | G | eHealth Queensland | 65 | 1369607 | G | G | 61 | Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector 30/4/2018,a0 30/4/2018,and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. 30/4/2018,The Department of Health defines Telehealth as: 30/4/2018, 30/4/2018,95Live, audio and/or video inter-active link for clinical consultations and educational purposes 30/4/2018, 30/4/2018,95Store and forward Telehealth - this model can involve digital images, video, audio and clinical data being captured ("stored") on the client computer; then at a convenient time transmitted securely ("forwarded") 30/4/2018,a0 to a clinic at another location where they are studied by relevant specialists 30/4/2018, 30/4/2018,95Teleradiology for remote reporting and clinical advice for diagnostic images 30/4/2018, 30/4/2018,95Telehealth services and equipment to monitor people 30/4/2018,92s health in their home. 30/4/2018,Benefits of Telehealth 30/4/2018, 30/4/2018,95Improve patient access to health care 30/4/2018, 30/4/2018,95Reduce travel and inconvenience for patients, families, carers and health professionals 30/4/2018, 30/4/2018,95Provide health professionals with access to peer support and education. 30/4/2018,The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. 30/4/2018,a0 30/4/2018,The priority is to replace those end-of-life assets which pose the greatest risk to effective health service delivery. | 1960000 | 2017-07-03T00:00:00 | DH
30/4/2018 | MNHHS | The Prince Charles Hospital (TPCH) Wi-Fi | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 |  | 2018-03-16T00:00:00 | High | 1408388 | G | Metro North | 35 | 947826 | G | G | 62 | The Prince Charles Hospital (TPCH) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the hospital campus for prioritised TPCH buildings. 30/4/2018, 30/4/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1408388 | 2017-07-27T00:00:00 | DH
30/4/2018 | EHQ | Sunshine Coast University Hospital (SCUH) Stage 2 ICT Expansion | 2018-06-30T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | February: This project has been reported for the first time. | 2018-02-28T00:00:00 | High | 3180000 | G | eHealth Queensland | 49 | 1557830 | G | G | 63 | Sunshine Coast University Hospital (SCUH) ICT Stage 1 delivered the ICT required to achieve the successful commissioning of SCUH in March 2017. The SCUH Stage 2 ICT Expansion covers the investment period from 1 July 2017 to 31 December 2018 and is intended to support the planned expansion of SCUH to increase capacity and establish new services. | 3180422 | 2017-07-03T00:00:00 | DH
30/4/2018 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | There have been delays to the project schedule from reprioritisation of resources to community recovery activities associated with Cyclone Debbie. Additionally, the vendor, SMS Management and Technology, has not delivered within the contracted timeframes and we are negotiating with the vendor to ensure completion of the solution. | 2018-03-31T00:00:00 | High | 2208000 | G | Whole of Department | 87 | 3179000 | G | G | 1 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3483000 | 2016-07-01T00:00:00 | DCCSDS
30/4/2018 | Cross-Gov | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery | G | 2019-12-24T00:00:00 | The Queensland Fire and Emergency Services (QFES) Human Capital Management on-boarding and recruitment functionality was introduced into full business operation in February 2018. Workplace Health and Safety and Case Management functionality will be implemented for QFES in May 2018. 30/4/2018, 30/4/2018,The approach to transition for the Queensland Ambulance Service payroll to Aurion has been reviewed and approved with the implementation timeframe changed from March 2018 to November 2018. 30/4/2018, 30/4/2018,The Executive Steering Committee has also approved the revised program end date which accommodates the introduction of the additional project for the time and attendance solution and the revised schedule for the Queensland Fire and Emergency Services Payroll transition to Aurion. | 2018-02-28T00:00:00 | Critical | 101500000 | G | Cross-Government program led by DSITI | 57 | 54983899 | G | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 30/4/2018, 30/4/2018,* Sustainable and supported HR and Payroll service delivery 30/4/2018,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 30/4/2018,* Strategic HR capability that supports the development, performance and safety of the departments workforce 30/4/2018,* Business Intelligence capability that provides real timely, integrated HR information 30/4/2018,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 30/4/2018,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 30/4/2018,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
30/4/2018 | QPS | Online National Police Certificate | 2017-06-30T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | Since the successful launch of Online National Police Certificates 72% of all applications have been submitted online. The overall number of applications submitted online, has doubled from December 2017 to January 2018. 30/4/2018, 30/4/2018,National Police Certificate campaign material has been distributed to all Police Districts for display in all Stations and Police Beats. External marketing via social media will commence in April 2018. 30/4/2018, 30/4/2018,Feb 2018: The revised project budget has been amended from previously published figures to reflect the increased investment in promotional products. | 2018-04-18T00:00:00 | High | 275000 | G | Queensland Police Service | 95 | 218000 | G | G | 1 | The Online National Police Certificate Project will implement an online service for the community to apply and pay for Name Only National Police Certificates online, rather than presenting at a police station, or using the online services of an Australian Crime Intelligence Commission accredited broker. This will provide improved customer service to the community through a more efficient and reliable QPS service, with no requirement to present at a police station, as well as provide efficiency and time savings to local police stations and the Police Information Centre. | 250000 | 2017-01-01T00:00:00 | QPS
30/4/2018 | QPS | Police Integrity and Professional Standards | 2018-08-24T00:00:00 | Delivery | G | 2019-08-31T00:00:00 | Project Board has approved a revised end date of 31 August 2019. Previous Invitation to Offer considered and not proceeded with as it was deemed financially un-viable. Meeting with relevant stakeholders held to discuss way forward. Project now reviewing budget and some requirements with a view to establish if a smaller funding request is viable. 30/4/2018, 30/4/2018,Note: original planned end date amended as previously published information was incorrect. | 2018-04-18T00:00:00 | High | 4142000 | A | Queensland Police Service | 30 | 176151 | A | A | 2 | This initiative will deliver a new integrated Police Integrity and Professional Standards IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The Police Integrity and Professional Standards system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The Police Integrity and Professional Standards Project will also complement the Complaints Reform Project established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of the Police Integrity and Professional Standards system will place the QPS in a strong readiness position to fully implement Complaints Reform Project generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 4142000 | 2017-03-07T00:00:00 | QPS
30/4/2018 | QPS | Advanced Data Analytics | 2017-07-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to deliver new capability in all streams with most capability available for use during the 2018 Commonwealth Games. Current focus is on expanding the capability developed by the project into 2017-18 as business-as-usual capability and positioning the outputs/products of the project for developing the next phase of QPS advanced analytics capabilities. | 2018-04-18T00:00:00 | Low | 1730000 | G | Queensland Police Service | 92 | 2154400 | G | G | 3 | Develop the QPS Advanced Data Analytics proof-of-concept. This proof-of-concept is intended to inform a larger suite of data analytics integration and intelligence over the next four years, including the development of predictive and alert models to enhance the operational response to threats, incidents and events. | 2350000 | 2017-02-19T00:00:00 | QPS
30/4/2018 | QPS | Body Worn Cameras | 2018-02-28T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Project completed the deployment of all Stage Two body worn cameras in December 2017 and is now preparing closure activities and transition to business as usual by 30 June 2018. 30/4/2018, 30/4/2018,Feb 2018: The original approved budget was $6.03M. In May 2017 the QPS Demand and Resource Committee approved an additional $0.860M, making the total approved budget $6.890M. | 2018-04-18T00:00:00 | Medium Low | 6030000 | G | Queensland Police Service | 90 | 6890000 | G | G | 4 | The Queensland Police Service Body Worn Camera Project is deploying 5100 body worn cameras to frontline police officers. Body worn cameras will be deployed to 168 police stations, 16 tactical crime units, 47 road policing units, and specialist units including dog squads and the Public Safety Response Team in two stages. The cameras integrate with the QPS mobility devices, allowing officers to add metadata to videos and to review videos in the field. A system for storage and allocation of digital camera data will also be implemented as well as policy related to use of the cameras. | 6890000 | 2014-08-25T00:00:00 | QPS
30/4/2018 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-06-30T00:00:00 | Delivery | G | 2018-12-31T00:00:00 | Objectives: This project will deliver a secondary DR site and hyper-converged system to provide resilience for all departmental applications in the event of disaster. 30/4/2018, 30/4/2018,Secondary datacentre with new hyper-converged infrastructure established. As at Feb 2018 - Project schedule is on track and within budget. 30/4/2018, 30/4/2018,Core infrastructure 70% complete. Estimated completion March 2018. All migrated production system successfully replicating to secondary DR site. 30/4/2018,Oracle infrastructure 50% complete. Estimated completion June 2018. SPER databases successfully migrated to CITEC. QWIC migration in progress. 30/4/2018,By the end of project, all end-of-life ICT infrastructure ready to be decommission which provide stability and life extension to existing business critical applications. 30/4/2018, 30/4/2018,Original planned end date was changed from 30 June 2018 to 31 Dec 2018 due to: 30/4/2018, 30/4/2018,- initial delays in securing project resources (2016-17 Christmas/New Year shutdown) 30/4/2018, 30/4/2018,- high level of project design complexity (heterogeneous environments) 30/4/2018, 30/4/2018,- conformity with appropriate probity and procurement governance. 30/4/2018, 30/4/2018,- requirement to develop a Significant Procurement Plan (SPP). 30/4/2018, | 2018-03-13T00:00:00 | High | 7460674 | G | Corporate Services | 60 | 3390115 | G | G | 1 | * Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 5917255 | 2016-10-01T00:00:00 | DJAG
30/4/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2018-03-31T00:00:00 | End of project closure report is being finalised. Closure is expected by 31 March 2018. There is a slight decrease in February cost to date compared to January cost to date due to an accounting adjustment. 30/4/2018, 30/4/2018,During delivery of the project there was a change in scope to include an additional business unit which was identified to move into Terrica Place. However this business unit was later removed from scope and a separate project was established to deliver their specific and detailed technical requirements, ensuring the CBD Consolidation - Terrica Place Relocation Project remained within budget. | 2018-02-28T00:00:00 | Medium | 800000 | G | Chief Information Office | 99 | 897169 | A | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | HPW
30/4/2018 | QSS | Legacy Finance Archiving Project | 2018-03-29T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2018-02-28T00:00:00 | High | 845949 | G | Queensland Shared Services | 95 | 803499 | G | G | 2 | This project will archive finance data for legacy finance solution into a standard archive/enquiry solution. | 845949 | 2016-09-01T00:00:00 | HPW
30/4/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2018-03-16T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2018-02-28T00:00:00 | High | 1800000 | G | Queensland Shared Services | 96 | 1754386 | G | G | 3 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | HPW
30/4/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The automated payment solution has been established as a separate project with key dependencies to the PCI activities. The timeframe is achievable and continues to be closely monitored by the Project Board. 30/4/2018, 30/4/2018,The project had previously been extended to cover additional requirements required as a result of changes to PCI industry standards and also dependencies on projects such as Telephony Replacement Project and the Automated Payments Solution Project. | 2018-02-28T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 88 | 1019423 | A | A | 4 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | HPW
30/4/2018 | SSQ | Automated Payments Solution | 2018-07-31T00:00:00 | Initiate | G | 2018-07-31T00:00:00 | This project is currently in the procurement phase and is on track. | 2018-02-28T00:00:00 | Critical | 1500000 | G | Smart Service Queensland | 0 | 0 | G | G | 5 | The Automated Payments project will implement an improved capability for offering secure payment card transactions via the telephone. This is a dependency for achieving compliance meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1500000 | 2018-01-29T00:00:00 | HPW
30/4/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | The Project Board continues to closely monitor the dependencies with the Content Delivery Solution Project. All other aspects of the project remain on track. 30/4/2018, 30/4/2018,The project timeframe has been delayed from the original date as a result of the complexity in technology design specifications, re-allocating resources to assist in the response to TC Debbie in March 2017 and the technical dependency on the Content Delivery Solution project, which must be implemented prior to TRP go-live. Accordingly, the Project Board approved a revised project closure date of 31 July 2018. | 2018-02-28T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 77 | 3104527 | G | A | 6 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 30/4/2018, 30/4/2018,* reduce operating costs 30/4/2018,* increase capacity 30/4/2018,* improve customer experience 30/4/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | HPW
30/4/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-04-30T00:00:00 | The testing phase of the CDS Project is continuing. The Project Board endorsed an approach to extend the planned end date to 30 April 2018 and expand the current testing approach to ensure the product meets the needs of users from a functionality and performance perspective. | 2018-02-28T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 79 | 1724536 | A | A | 7 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | HPW
30/4/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. | 2018-02-28T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 79 | 2034483 | G | G | 8 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | HPW
30/4/2018 | QSA | Digital Archiving Program - Tranche 1 | 2019-12-31T00:00:00 | Delivery | G | 2019-12-31T00:00:00 | The procurement activity is progressing to planned timeframes and milestones. | 2018-02-28T00:00:00 | Critical | 12701000 | G | Queensland State Archives | 65 | 1125681 | G | G | 9 | To ensure the delivery of an as-a-Service eco-system to effectively archive, manage and enable search and discovery of Queensland's permanent high value records. The new digital services will support the Queensland Government's blueprint for innovation and collaboration, providing better outcomes for Queenslanders. | 12701000 | 2017-07-01T00:00:00 | HPW
30/4/2018 | CITEC ICT | z14 Mainframe Upgrade | 2018-07-31T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | Data migration activities have commenced and are progressing well. | 2018-02-28T00:00:00 | High | 4720752 | G | CITEC ICT | 64 | 4521721 | G | G | 10 | The project will replace the two existing z12 Mainframes (Production and Disaster Recovery) with upgraded z14 Mainframes and migrate the existing data from the old to the new. 30/4/2018, 30/4/2018,The current z12 platform is unable to be upgraded and cannot provide sufficient capability for increasing client requirements. The continued use of the z12 platform represents significant risk to business continuity. 30/4/2018, 30/4/2018,The upgrade will reduce ongoing operating costs, enable improved services to clients and provide for clients' future capacity requirements. 30/4/2018, | 4720752 | 2017-12-18T00:00:00 | HPW
30/4/2018 | Housing | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery | G | 2019-03-31T00:00:00 | Following approval of the business case for the second stage Tenancy Release, Program Budget and Planned end date were re-baselined in January 2018. 30/4/2018, 30/4/2018,The Program continues to progress planning for the second of the two releases, Tenancy, which will remove the operational dependency on the existing ICT housing solution entirely. Planning outcomes will be presented to the Program Board in March 2018. 30/4/2018, 30/4/2018,The Program continues to progress planning for the second of the two releases, Tenancy, which will remove the operational dependency on the existing ICT housing solution entirely. Planning outcomes will be presented to the Program Board in March 2018. | 2018-02-28T00:00:00 | Critical | 56286000 | G | Housing Services | 55 | 66760458 | G | G | 11 | Replace the existing ICT housing solution with an integrated ICT system. | 121597695 | 2013-07-01T00:00:00 | HPW
30/4/2018 | PWAM | iSpace External Hosting Migration Project | 2017-01-31T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The iSPACE upgrade went live on Friday 16th February 2018. 30/4/2018, 30/4/2018,The project was delivered with some adjustments to the original scope which were made during the procurement and planning phase, to take advantage of emerging opportunities and manage dependencies with other initiatives. | 2018-02-28T00:00:00 | High | 735000 | A | Queensland Government Accommodation Office | 96 | 877519 | A | A | 12 | Version upgrade and migration of the hosting of Queensland Accommodation Office core system to a hosted managed service arrangement. | 1415203 | 2016-05-01T00:00:00 | HPW
30/4/2018 | QGP | Fleet Management System Replacement Project (FMSRP - QFleet) | 2019-09-30T00:00:00 | Initiate | G | 2019-09-30T00:00:00 | The project is tracking to plan. The project is currently subject to procurement activities. | 2018-02-28T00:00:00 | High | 13939200 | G | QFleet | 2 | 341650 | G | G | 13 | The project will deliver for the Department of Housing and Public Works, Public Safety Business Agency and Queensland Ambulance Service a fleet management solution to replace existing aging legacy systems. | 13939200 | 2017-10-19T00:00:00 | HPW
30/4/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 30/4/2018, 30/4/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 30/4/2018,October 2017 - The project is progressing as planned. 30/4/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 30/4/2018,June 2017 - Revised Schedule approved returning the project to Green. 30/4/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 30/4/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 30/4/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 30/4/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 30/4/2018,December 2016 - The project is progressing as planned. | 2017-12-21T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 30/4/2018, 30/4/2018,* register and maintain their information 30/4/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
30/4/2018 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 30/4/2018, 30/4/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 30/4/2018,August 2017 - Approved extension of timeframe. 30/4/2018,June 2017 - The project is progressing as planned. 30/4/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 30/4/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 30/4/2018,October 2016 - Progress is continuing as planned. 30/4/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 30/4/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 30/4/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-21T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 30/4/2018, 30/4/2018,* support compliance with legislation 30/4/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 30/4/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 30/4/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 30/4/2018, | 1390000 | 2012-04-01T00:00:00 | DEWS
30/4/2018 | BQ | Biosecurity Information Management System Program | 2017-05-31T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | The program is progressing as planned, awaiting formal closure. 30/4/2018, 30/4/2018,December 2017 - Program delivery is complete, however, the final end date has been extended by three months to allow for full transition to business as usual, project and program closure activities and final assurance reviews. 30/4/2018,November 2017 - The planned end date has been extended by one month; this remains within acceptable program tolerances. 30/4/2018,March 2017 - The program is progressing as planned in line with approved change to scope, timeframe, benefits and cost. 30/4/2018,January 2017 - A small scope increase has been proposed, currently progressing through governance processes. 30/4/2018,November 2016 - Note, a scope review is currently under way. 30/4/2018,May 2016 - Program is continuing as planned. Note a small extension to planned end date. 30/4/2018,March 2016 - A re-baseline has brought all parameters back to Green. 30/4/2018,January 2016 - Timeframe, Cost, and Quality remain Amber, pending a business case update due early April 2016. 30/4/2018,November 2015 - Program is still Amber while the Timeframe is being re-baselined. 30/4/2018,September 2015 - The Exception Report has been accepted by the Program Board. Timeframe remains Amber pending a business case update. 30/4/2018,July 2015 - Resources continue to be redirected to assist with emergency response to the Panama banana disease. An Exception Report is being developed to address this. 30/4/2018,May 2015 - As anticipated, the emergency response to the Panama Banana disease outbreak has impacted both the project cost and the Timeframe. 30/4/2018,March 2015 - There is currently an outbreak of Panama banana disease which has potential to impact the schedule of this project. 30/4/2018,January 2015 - Actions are being taken to resolve some current scheduling issues. | 2018-04-27T00:00:00 | Critical | 18080000 | G | Biosecurity Queensland | 98 | 18230000 | G | G | 1 | Deliver an integrated toolkit consisting of various information management technologies and enhanced business processes to improve the management of biosecurity risks in Biosecurity Queensland's day-to-day business operations and in emergency responses. | 19409000 | 2013-07-01T00:00:00 | DAF
30/4/2018 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | An extension to the planned end date has been approved, returning the project status to Green. 30/4/2018, 30/4/2018,March 2018 - A minor scope increase has been proposed, affecting both timeframe and cost, which is progressing through the governance process. 30/4/2018, 30/4/2018,March 2018 - The project is progressing as planned. 30/4/2018, 30/4/2018,December 2017 - A variation to scope was approved, resulting in a change to the planned end date and total estimated expenditure. 30/4/2018, 30/4/2018,November 2017 - The project is continuing as planned. 30/4/2018, 30/4/2018,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2018-04-27T00:00:00 | Medium | 608146 | G | Forestry Queensland | 90 | 906918 | G | G | 2 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 30/4/2018, 30/4/2018,* the capture, management and integration of data 30/4/2018,* value-adding opportunities for business improvement 30/4/2018,* management of risk associated with ongoing use and maintenance of disparate systems. | 976431 | 2016-06-15T00:00:00 | DAF
30/4/2018 | BQCC | Communication and Stakeholder Engagement Solution | 2018-06-29T00:00:00 | Delivery | G | 2018-04-27T00:00:00 | A change to the planned end date and cost has been approved. 30/4/2018, 30/4/2018,March 2018 - Note adjustment to planned end date corrected due to typographical error. 30/4/2018, 30/4/2018,February 2018 - The project is progressing as planned. 30/4/2018, 30/4/2018,December 2017 - The project was approved to move into delivery in October 2017 and is being published for the first time. | 2018-04-27T00:00:00 | Medium | 694000 | G | Biosecurity Queensland Control Centre | 32 | 493000 | G | G | 3 | Implement a simple, easy to use system that will facilitate the collection of information associated with the National Red Imported Fire Ant Eradication Program and the National Electric Ant Eradication Program. This will include contact management, complaints management, history of interactions, event management, training management, social media interactions, marketing campaign and reporting. | 694000 | 2017-06-01T00:00:00 | DAF
30/4/2018 | ASQ | Portfolio Activity Reporting Information System | 2018-06-30T00:00:00 | Paused | G | 2018-06-30T00:00:00 | The project is paused until a funding source is identified. 30/4/2018, 30/4/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-04-27T00:00:00 | High | 500000 | G | Agri-Science Queensland | 10 | 231622 | G | G | 4 | Review and consolidate the variety of processes and technologies currently being used to manage the department's research, development and extension, and other projects. | 500000 | 2015-08-13T00:00:00 | DAF
30/4/2018 | Ag | Risk Reduction for Customer Service Centre | 2019-04-19T00:00:00 | Delivery | G | 2019-04-19T00:00:00 | The project is continuing as planned. 30/4/2018, 30/4/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-04-27T00:00:00 | High | 1767000 | G | Agriculture | 15 | 274102 | G | G | 5 | Implement a solution to mitigate risk of end of life for the agency's call centre logging application. | 1767000 | 2015-01-30T00:00:00 | DAF
30/4/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
30/4/2018 | PSBA | Emergency Services Computer Aided Dispatch (ESCAD) Upgrade Program | 2016-09-30T00:00:00 | Delivery | G | 2018-07-03T00:00:00 | The updated ESCAD system cut over for Queensland Ambulance Service (QAS) completed successfully on 17-01-2018, and the Queensland Fire and Emergency Services (QFES) also completed successfully on 24-01-2018. The decommissioning of hardware in the obsolete environments is currently underway. The ESCAD System Upgrade Project, as major initiative in the program of works, experienced significant technical and implementation issues causing an approved rebaseline in January 2017. This resulted in a revised timeframe from the original plan of 30-09-2016 to 3-07-2018 and a revised estimate at completion from the original of $6,774,820 to $9,789,600 for the Program. | 2018-04-27T00:00:00 | Critical | 6774820 | G | Public Safety Business Agency | 88 | 9026125 | G | G | 1 | A program of work for Queensland Ambulance Service and Queensland Fire and Emergency Services to upgrade the Emergency Services Computer Aided Dispatch System,including infrastructure, operating system and application software. | 9789600 | 2015-01-15T00:00:00 | PSBA
30/4/2018 | PSBA | Emergency Vehicle Priority (EVP) Project | 2017-06-30T00:00:00 | Delivery | G | 2018-10-31T00:00:00 | All rollouts of devices into vehicles will be completed by 30-06-2018. Procurement of a managed service for operational support and maintenance has required an extension of the project schedule. This resulted in a revised timeframe from the original planned end date of 30-06-2017 to 31-10-2018, and a revised budget from the original expenditure plan of $3.4 million to $4.4 million. | 2018-04-27T00:00:00 | High | 3370000 | G | Public Safety Business Agency | 87 | 4062462 | G | G | 2 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 30/4/2018, 30/4/2018,* Responsive vehicle movements 30/4/2018,* Improve road safety 30/4/2018,* Congestion management 30/4/2018,* Community safety | 4370331 | 2013-01-01T00:00:00 | PSBA
30/4/2018 | PSBA | Inter-CAD Electronic Messaging System (ICEMS) | 2016-08-31T00:00:00 | Delivery | G | 2018-03-16T00:00:00 | The ICEMS system cut over for Queensland Police Service (QPS) and Queensland Ambulance Service (QAS) completed successfully on 28-07-2017, and ICEMS for the Queensland Fire and Emergency Services (QFES) completed successfully on 24-01-2018. Project closure activities are being finalised. The ICEMS Project experienced significant technical and implementation issues causing multiple approved re-baselines between November 2015 and September 2017. This resulted in a revised timeframe from the original planned end date 31-08-2016 to 16-03-2018 and a revised budget from the original planned expenditure of $560K to $1,571K. The original planned end date has been updated to 31-08-2016 as it was previously incorrectly reported. | 2018-04-27T00:00:00 | Critical | 560000 | G | Public Safety Business Agency | 99 | 1570683 | G | G | 3 | To implement the ICEMS protocol between the Queensland Police Service (QPS), Queensland Ambulance Service (QAS) and Queensland Fire and Emergency Services (QFES) computer aided dispatch systems to enable Triple Zero data sharing between agencies. | 1571139 | 2015-10-06T00:00:00 | PSBA
30/4/2018 | PSBA | PSBAIGEM Office 365 Implementation Project | 2018-02-20T00:00:00 | Delivery | G | 2018-05-11T00:00:00 | Project budget has been increased to $1.1 million as a result of full rollout planning. 30/4/2018,Project has re-baselined the schedule from 09-03-2018 to 11-05-2018 as a result of moving from pilot to full rollout. 30/4/2018,Schedule was previously re-baselined from 20-02-2018 to 9-03-2018 due to increase in scope, regarding mobility solutions for users. 30/4/2018,To date 235 PSBA users have been successfully migrated to Office 365 services. 30/4/2018,The project is currently working through the preparation tasks for the remaining PSBA users to be migrated to Office 365 (approximately 1100 users). | 2018-04-27T00:00:00 | Critical | 986000 | G | Public Safety Business Agency | 93 | 757613 | G | G | 4 | The project will deliver digital transformation for the Public Safety Business Agency (PSBA) and Inspector-General Emergency Management (IGEM) through the implementation of the Office 365 suite of products to augment the below enhancements to their current business processes. Undertaking smarter meetings; Facilitating better administration; Accessing information anywhere, any time; Engaging and communicating better; Supporting capability development; Facilitating business intelligence; and Enabling efficient workflow and approvals. | 1136000 | 2017-09-20T00:00:00 | PSBA
30/4/2018 | PSBA | QFES Office 365 Implementation Project | 2018-06-30T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | The Queensland Fire and Emergency Services (QFES) Office 365 Project is scheduled to be delivered by 30-06-2018. Underspends for FY17/18 will be requested to be deferred to FY18/19, to fund additional Office 365 projects. | 2018-04-27T00:00:00 | Medium | 2100000 | G | Public Safety Business Agency | 52 | 628395 | G | G | 5 | This project will deliver the most up-to-date Office 365 suite of products to all Queensland Fire and Emergency Services (QFES) staff and enable QFES to mobilise its workforce. 30/4/2018, 30/4/2018,* Upgrade QFES technology fleet to the latest Microsoft Office version 30/4/2018,* Cloud services will enable mobility 30/4/2018,* Bridge the technology gaps between Public Safety Agencies (PSA) and allow better collaboration | 2100000 | 2017-11-01T00:00:00 | PSBA
30/4/2018 | PSBA | QPS Office 365 Implementation Project | 2018-02-28T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | The migration of all QPS mailboxes to Office 365 online services was completed by the original planned end date of 28-02-2018. QPS has approved additional scope to be delivered by 30-06-2018 within the original planned expenditure. The Project Objective has been amended to reflect the scope change. | 2018-04-27T00:00:00 | Critical | 2207000 | G | Public Safety Business Agency | 44 | 1086750 | G | G | 6 | Phase 1 - Mail Migrations The objective of the Queensland Police Service (QPS) Office 365 Implementation Project Phase 1 is to complete the following activities prior to the Frontline and Digital Services Commonwealth Games Change Freeze (mid Feb 2018): 30/4/2018, 30/4/2018,* migrate email, contacts and calendars to Office 365 online services for all QPS staff; and 30/4/2018,* enable anywhere, anytime, any device access to email, contacts and calendar via bring your own (BYO) phone, QPS Officers operational tablets (QLiTEs) and home use for all QPS staff. 30/4/2018, 30/4/2018,Phase 2 - a data migration and a pilot migration of email archives to Office 365 online | 2207000 | 2017-09-07T00:00:00 | PSBA
30/4/2018 | OSR | State Penalties Enforcement Registry (SPER) Program | 2017-12-31T00:00:00 | Delivery | G | 2018-10-31T00:00:00 | Expenditure to date: $28.8M has been for the transformation of the SPER function; and $18M has been on the build phase of the ICT Implementation (Software as a Service - SaaS). 30/4/2018,A contract variation has been negotiated and executed as jurisdictional differences required system modifications. | 2018-04-20T00:00:00 | High | 47200000 | G | State Penalties Enforcement Registry | 59 | 46800000 | A | A | 1 | To maintain the integrity of fines as an effective sanction. To uphold confidence in the justice system. To deliver efficient and effective debt management practices which provide value for money to the State. 30/4/2018, | 62150000 | 2014-01-01T00:00:00 | QR
30/4/2018 | RI | Financial Assurance Information Registry (FAIR) | 2018-07-01T00:00:00 | Delivery | G | 2018-07-01T00:00:00 | Project cost to date is at end of March 2018. Project is on track for the system to be operational by 1 July 2018. Due to the delay in legislation being passed, some functionality and enhancements are planned to be delivered in the next financial year. | 2018-04-20T00:00:00 | Medium | 15900000 | G | Insurance Commission | 75 | 3939000 | G | G | 2 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
30/4/2018 | RI | Information Security Program | 2019-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The program is on track according to schedule and budget. | 2018-04-20T00:00:00 | Medium | 1960000 | G | Office of the Chief Information Officer | 35 | 392169 | G | G | 3 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 30/4/2018, | 1960000 | 2017-10-16T00:00:00 | QR
30/4/2018 | OSR | Office of State Revenue (OSR) Transformation Program | 2020-06-30T00:00:00 | Delivery | G | 2020-06-30T00:00:00 | Completed business process re-design sprint for a buisness area. Multiple initiatives in progress focussing on machine learning, analytics and data quality improvements. Overall program is on track. | 2018-04-20T00:00:00 | High | 73548000 | G | Office of State Revenue | 10 | 10589263 | G | G | 4 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 30/4/2018, 30/4/2018,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 73548000 | 2017-08-01T00:00:00 | QR
30/4/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
30/4/2018 | Corporate Services Improvement Systems Board | Learnzone Improvement Project | 2017-06-30T00:00:00 | Closed | G | 2018-02-15T00:00:00 | The LearnZone Improvement project continues to report action required due to delays in finalising approvals of the Project End Report. Once the Project End Report is approved and noted, scheduled 15 February 2018, the project will be marked as closed on the QG ICT Dashboard. It should be noted that both the original total estimated expenditure and revised total estimated expenditure reported last period were incorrect. As per the approved Business Case and subsequent exception report these figures have now been corrected. | 2018-02-28T00:00:00 | High | 350000 | G | Transactional Services Improvement Program | 100 | 449936 | R | R | 1 | Innovate, develop and deliver an improved and centralised digital learning service and management function. 30/4/2018, 30/4/2018, | 442000 | 2016-02-01T00:00:00 | TMR
30/4/2018 | Corporate Services Improvement Systems Board | Lotus Notes Decommissioning | 2016-01-31T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project is on track. | 2018-02-28T00:00:00 | High | 8150000 | G | ERP Projects Board | 63 | 2120899 | G | G | 2 | Deliver improved information platform functions for effective ICT Strategy Alignment | 8150000 | 2015-11-01T00:00:00 | TMR
30/4/2018 | Corporate Services Improvement Systems Board | Stop Cheques - Stage 3 | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Stop Cheques Stage 3 project is on track. | 2018-02-28T00:00:00 | Medium | 200000 | G | ERP Projects Board | 85 | 221972 | G | G | 3 | Cheques are inefficient and costly to use, process and administer for both the customer and department. A range of solutions have been developed to reduce the number of cheques that the department produces or receives including refund to card at counter, Bulk Bpay solutions and the introduction of new payment methods are being delivered to be more in line with contemporary retail offerings. The outsourcing of cheque production produced a more streamlined process. 30/4/2018,The stop cheques initiative includes 3 elements: 30/4/2018,Outsourcing/cost reduction 30/4/2018,Outbound cheques 30/4/2018,Inbound cheques | 200000 | 2015-02-01T00:00:00 | TMR
30/4/2018 | Corporate Services Improvement Systems Board | Risk Management Solution | 2018-07-01T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Risk Management Solution project is on track. Planned expenditure was incorrectly displaying 17/18 budget only. | 2018-02-28T00:00:00 | High | 350000 | G | Corporate Services Improvement Systems Board | 78 | 777613 | G | G | 4 | Replace the current risk management approach through the delivery of a new and contemporary enterprise Risk Management solution for TMR . | 1024435 | 2016-02-01T00:00:00 | TMR
30/4/2018 | Corporate Services Improvement Systems Board | Integrated Records Information System (IRIS) | 2018-07-01T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The IRIS project is on track. | 2018-02-28T00:00:00 | High | 7967972 | G | Information Technology Branch | 35 | 3966166 | G | G | 5 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 7967972 | 2015-07-01T00:00:00 | TMR
30/4/2018 | Corporate Services Improvement Systems Board | Safety, Health and Environment tool (SHE) | 2018-07-02T00:00:00 | Delivery | G | 2018-07-30T00:00:00 | The SHE project is on track. | 2018-02-28T00:00:00 | Low | 680000 | G | Corporate Services Improvement Systems Board | 40 | 224369 | G | G | 6 | The objective of the SHE project is to replace the current Work Health and Safety ICT solution with an industry standard, cost-effective safety management solution that will enable TMR to meet its obligations under the Work Health and Safety 2011 Act, the Right to Information, Information Privacy legislation and the Workers Compensation and Rehabilitation Act 2003 (Qld). | 680000 | 2016-12-05T00:00:00 | TMR
30/4/2018 | Corporate Services Improvement Systems Board | Transactional Services Improvement Program Enhancements | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Transactional Services Improvement Program Enhancements Stage 3 is on track. | 2018-02-28T00:00:00 | Low | 200000 | G | Transactional Services Improvement Program | 80 | 142956 | G | G | 7 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. | 200000 | 2015-02-01T00:00:00 | TMR
30/4/2018 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery | G | 2018-09-30T00:00:00 | The CDOP Online Portal project is on track. | 2018-02-28T00:00:00 | High | 1500000 | G | Customer Services, Safety and Regulation Division | 90 | 999274 | G | G | 8 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal services currently required. | 1441000 | 2016-01-01T00:00:00 | TMR
30/4/2018 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The eLearner project is currently on track. | 2018-02-28T00:00:00 | High | 2500000 | G | Customer Services, Safety and Regulation Division | 95 | 4093456 | G | G | 9 | Implement an online learning and assessment program at the pre-learner and/or learner stage, to replace enhance learning outcomes. | 4176000 | 2015-06-12T00:00:00 | TMR
30/4/2018 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery | G | 2018-06-28T00:00:00 | The Mobile Compliance Information System project is on track. An Exception Report to increase the project's scope and budget was approved by the program board in January 2018. | 2018-02-28T00:00:00 | High | 300000 | G | Customer Services, Safety and Regulation Division | 90 | 757855 | G | G | 10 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 630000 | 2016-11-01T00:00:00 | TMR
30/4/2018 | Customer Service, Safety and Regulation Program | Call Centre VOIP Upgrade | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Call Centre VOIP Upgrade project is on track. | 2018-02-28T00:00:00 | Low | 1140000 | G | Customer Services, Safety and Regulation Division | 50 | 564183 | G | G | 11 | The Call Centre VOIP Upgrade has commenced to upgrade the VOIP telephony platform within the department. The proposed solution will see a reduction in call costs, a shift in capability to a 30/4/2018,contemporary solution utilising an existing investment within the department. | 1140000 | 2017-04-01T00:00:00 | TMR
30/4/2018 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery | G | 2017-12-24T00:00:00 | The Ralph Replacement project is on track. An exception report to rebasline the project's end date is currently being reviewed by the project's governance board. | 2018-02-28T00:00:00 | Medium | 500000 | G | Customer Services, Safety and Regulation Division | 70 | 576018 | G | G | 12 | TMR's current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace the existing application with a contemporary and supportable alternative to assist the department in maintaining its timely updating of fees and charges. | 674000 | 2016-07-01T00:00:00 | TMR
30/4/2018 | Customer Service, Safety and Regulation Program | Voice Comms Mgt System | 2017-06-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | The Voice Comms Management System project is on track. | 2018-02-28T00:00:00 | Medium | 828000 | G | Customer Services, Safety and Regulation Division | 75 | 274738 | G | G | 13 | The Voice Comms Management project consists of two replacement of existing Voice Communication and Control Systems at Townsville and Hay Point. | 828000 | 2016-01-01T00:00:00 | TMR
30/4/2018 | Customer Service, Safety and Regulation Program | CTP Tax Invoice Online | 2017-12-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The CTP Tax Invoice Online project will merge with the Registration Certificates Online project at the next reporting cycle. This is due to both projects having a shared goal to improving the online delivery of related correspondence. | 2018-02-28T00:00:00 | Medium | 300000 | G | Customer Services, Safety and Regulation Division | 25 | 17281 | G | G | 14 | The Compulsory Third Party Tax Invoice Online project will deliver a new online service which will enable Customers to self-serve and print an electronic version of the CTP Invoice, removing the need for TMR to process paper based invoices, avoiding production and postage charges. | 300000 | 2017-05-01T00:00:00 | TMR
30/4/2018 | Customer Service, Safety and Regulation Program | Vessel Traffic Services (VTS) | 2016-01-05T00:00:00 | Delivery | G | 2018-11-30T00:00:00 | The Vessel Traffic Services (VTS) project is on track. | 2018-02-28T00:00:00 | High | 15224694 | G | Customer Services, Safety and Regulation Division | 25 | 6048630 | G | G | 15 | The purpose of the project is procure and implement a replacement decision support tool for the existing Vessel Traffic Service (VTS) used by TMR to track and monitor ship movements within Queensland ports, the Great Barrier Reef and the Torres Strait. | 25569044 | 2014-04-14T00:00:00 | TMR
30/4/2018 | Customer Service, Safety and Regulation Program | R and L Systems Software Upgrade | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The R and L Systems Software Upgrade project is on track. | 2018-02-28T00:00:00 | Medium | 780000 | G | Customer Services, Safety and Regulation Division | 20 | 21799 | G | G | 16 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
30/4/2018 | Infrastructure Management and Delivery | Work Improvement Note (WIN) Replacement | 2016-12-19T00:00:00 | Delivery | G | 2018-02-27T00:00:00 | The WIN Replacement project is on track. | 2018-02-28T00:00:00 | Low | 242612 | G | Infrastructure Management 30/4/2018,and Delivery | 98 | 349325 | G | G | 17 | The Work Improvement Note (WIN) System is used to capture, track, review and report on improvements, potential problems, non-conformances, corrective actions, customer feedback and complaints. The WIN System is an essential component of the overarching business management system as it meets specific certification requirements outlined in international quality, safety and environmental standards. This project will provide a replacement to the existing Work Improvement Note (WIN) system, which is dependent on unsupported technology. | 436375 | 2016-02-15T00:00:00 | TMR
30/4/2018 | Passenger Transport Technology Program | 2018 Commonwealth Games Journey Planner (GJP) | 2017-10-13T00:00:00 | Delivery | G | 2018-04-27T00:00:00 | The 2018 Commonwealth GJP project is project is on track. | 2018-02-28T00:00:00 | High | 450000 | G | Commonwealth Games | 95 | 848048 | G | G | 18 | A dedicated Journey Planner application supports this need by providing a single source of truth for all transport information related to the Games, and also allows for rapid changes to routes, schedules, and stops, if any are required, in order to drive transport behaviour and maintain network efficiency. | 973899 | 2016-10-16T00:00:00 | TMR
30/4/2018 | Passenger Transport Technology Program | Customer Contact Management Solution (CCMS) | 2017-06-30T00:00:00 | Closed | G | 2018-01-16T00:00:00 | The CCMS project has successfully completed its scope and the Program Board endorsed the project closure report in January 2018. The planned expenditure versus the actual cost to date variance has been rectified. The CCMS project will no longer report to the ICT Dashboard. | 2018-02-28T00:00:00 | High | 1279000 | G | TransLink | 100 | 1486927 | G | G | 19 | To implement an industry standard, robust and extensible solution to replace the existing Commentline solution. To achieve better performance of the customer contact management functions. To provide the base platform to support the future implementation of an xRM roadmap 30/4/2018, | 1486927 | 2016-04-01T00:00:00 | TMR
30/4/2018 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery | G | 2018-08-31T00:00:00 | The STAS Auto Forms project is on track. | 2018-02-28T00:00:00 | High | 4166000 | G | TransLink | 59 | 4396781 | G | G | 20 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 5043876 | 2016-04-01T00:00:00 | TMR
30/4/2018 | Policy Planning and Investment Program | Portfolio, Program, Project and Contract Management (3PCM) - Phase 2 and 3 | 2017-03-31T00:00:00 | Delivery | G | 2017-12-22T00:00:00 | The 3PCM project is on track. | 2018-02-28T00:00:00 | High | 12757788 | G | Policy, Planning and Investment Division | 99 | 47794188 | G | G | 21 | Define and implement standard, consistently applied processes for planning, managing and delivering the Transport Infrastructure Portfolio across the domains of portfolio, program, project and contract management 30/4/2018,Source and implement an integrated, strategic information communication technology solution that supports the business process and rules and enables a transition away from legacy applications | 47908928 | 2012-09-01T00:00:00 | TMR
30/4/2018 | CS | Asset Assessment System | 2016-06-30T00:00:00 | Delivery | A | 2018-08-06T00:00:00 | The project is being closely monitored for quality and schedule | 2018-02-08T00:00:00 | High | 1688788 | G | Corporate Services | 82 | 1502089 | A | A | 1 | To improve the reliability and integrity of asset information, the ability to report on asset information by applying best practice asset management principles. | 1957139 | 2014-02-27T00:00:00 | DET
30/4/2018 | SS | Early Start | 2015-07-03T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | High | 70000 | G | State Schools | 74 | 73522 | G | G | 2 | To provide schools with enhanced reporting functionality, improving their ability to analyse Prep to Year 2 student learning data. | 200992 | 2013-04-03T00:00:00 | DET
30/4/2018 | PPP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Delivery | G | 2018-02-27T00:00:00 | The project is being closely monitored for schedule | 2018-02-08T00:00:00 | Medium | 700000 | G | Policy, Performance and Planning | 86 | 1247953 | A | A | 3 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
30/4/2018 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery | G | 2018-12-07T00:00:00 | The project is tracking to plan. The Project is undergoing procurement/commercial activities with no financial information being published. | 2018-02-08T00:00:00 | Medium | 0 | G | Corporate Services | 46 | 0 | G | G | 4 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DET FBS SAP future state landscape for the next five years | 0 | 2017-01-16T00:00:00 | DET
30/4/2018 | CS | Injury Management System | 2017-03-27T00:00:00 | Delivery | G | 2018-10-01T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Critical | 1900000 | G | Corporate Services | 46 | 758816 | G | G | 5 | To improve the management of workplace rehabilitation and claims for injured/ill staff | 1813805 | 2016-10-10T00:00:00 | DET
30/4/2018 | ODG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery | G | 2017-12-29T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 632585 | G | Office of the Director-General | 90 | 817626 | G | G | 6 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
30/4/2018 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery | G | 2019-09-13T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 16670000 | G | State Schools | 50 | 8756279 | G | G | 7 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 23470000 | 2015-08-03T00:00:00 | DET
30/4/2018 | PPP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery | G | 2018-06-13T00:00:00 | The project is tracking to plan. The Project is undergoing procurement/commercial activities with no financial information being published. | 2018-02-08T00:00:00 | Medium | 0 | G | Policy, Performance and Planning | 70 | 0 | G | G | 8 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution | 0 | 2016-03-01T00:00:00 | DET
30/4/2018 | CS | Project Delivery System | 2018-10-01T00:00:00 | Delivery | G | 2019-01-29T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 1817566 | G | Corporate Services | 61 | 773116 | G | G | 9 | To improve the reliability and integrity of under construction asset information, the ability to report on asset project information by applying best practice asset management principles | 2291613 | 2015-04-01T00:00:00 | DET
30/4/2018 | PPP | Research Services 2.0 | 2016-09-30T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 230000 | G | Policy, Performance and Planning | 85 | 404745 | G | G | 10 | To develop a solution that assists in the management of the Department of Education and Training commissioned research proposals and projects, improving resourcing and information dissemination. | 431157 | 2015-11-02T00:00:00 | DET
30/4/2018 | TS | Study Tours Support System Upgrade | 2016-06-30T00:00:00 | Delivery | G | 2018-01-31T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 680000 | G | Training and Skills | 96 | 772580 | G | G | 11 | To replace or upgrade the existing Study Tours system with an online solution that has enhanced functionality, improving processes, data quality and tour management. | 831125 | 2015-08-31T00:00:00 | DET
30/4/2018 | SS | Trial of platform for virtual academies | 2017-10-02T00:00:00 | Delivery | G | 2018-12-31T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 151641 | G | State Schools | 55 | 224017 | G | G | 12 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage. | 151641 | 2016-06-21T00:00:00 | DET
30/4/2018 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery | G | 2020-06-30T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | High | 41000000 | G | Corporate Services | 55 | 27032972 | G | G | 13 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
30/4/2018 | [20 empty] | INVERSTMENT INFO
30/4/2018 | CSGC | Coal Seam Gas Groundwater Monitoring Arrangements | 2017-12-31T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project has recommenced and is nearing completion. Closure activities are now under way. 30/4/2018, 30/4/2018,January 2018 - A change to the planned end date has been approved; there is no impact to cost. Initiative is now paused until early 2018. 30/4/2018, 30/4/2018,August 2017 - Revised total expenditure (budget) updated to include all operating costs not previously reported. 30/4/2018, 30/4/2018,June 2017 - Progress is continuing as planned. Still on schedule to complete December 2017. 30/4/2018, 30/4/2018,December 2016 - Much of the project has been completed and a significant amount of the procurement expenditure for capital equipment has occurred. 30/4/2018, 30/4/2018,October 2016 - Progress is continuing as planned. 30/4/2018, 30/4/2018,August 2016 - Cost returned to Green after a review of costs associated with activities remaining, and a correction in actual cost to date adjustment. 30/4/2018, 30/4/2018,June 2016 - Cost is Amber with a resource review under way. 30/4/2018, 30/4/2018,February 2016 - Progress is continuing as planned. | 2018-04-27T00:00:00 | High | 2380568 | G | Coal Seam Gas Compliance | 99 | 2608283 | G | G | 1 | Enhance availability of groundwater data through improvements to network monitoring of bores for clients and landholders. | 2598256 | 2014-01-13T00:00:00 | DNRM
30/4/2018 | SIMTARS | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery | G | 2019-03-01T00:00:00 | The project is continuing as planned. 30/4/2018, 30/4/2018,February 2018 - A change request was approved to alter the scope and associated percentage complete, time-frame and costs. 30/4/2018, 30/4/2018,December 2017 - Awaiting confirmation of project closure; project is still operating within approved time-frame tolerance. 30/4/2018, 30/4/2018,November 2017 - A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 30/4/2018, 30/4/2018,October 2017 - The project is continuing as planned. 30/4/2018, 30/4/2018,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2018-04-27T00:00:00 | High | 563000 | G | SIMTARS (Safety In Mines Testing and Research Station) | 63 | 660758 | G | G | 2 | The development and delivery of a (replacement) modern and robust Safegas solution: 30/4/2018, 30/4/2018,* risk reduction increasing capability to manage the volume of queries, transactions and data 30/4/2018,* decrease database corruption related to incidents. | 1170000 | 2017-01-25T00:00:00 | DNRM
30/4/2018 | SO | Mines Infrastructure Risk Mitigation Project | 2019-02-18T00:00:00 | Delivery | G | 2019-02-28T00:00:00 | A minor adjustment to scope has been approved; there is no impact to timeframe or cost. 30/4/2018, 30/4/2018,March 2018 - The project is continuing as planned. 30/4/2018, 30/4/2018,November 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-04-27T00:00:00 | High | 1200000 | G | Statewide Operations | 30 | 312339 | G | G | 3 | Migrate systems to supported infrastructure and software to: 30/4/2018, 30/4/2018,* provide a stable, secure, fully supported and flexible solution 30/4/2018,* eliminate the risks to which the geoscience data assets are currently exposed. | 1200000 | 2017-08-08T00:00:00 | DNRM
30/4/2018 | GSQ | MinesOnlineMaps - Spatial Presentation Replacement | 2017-06-30T00:00:00 | Ended | G | 2018-04-30T00:00:00 | Project approved to end on 19 April 2018. 30/4/2018, 30/4/2018,March 2018 - The project is planning to end as the outputs will be delivered by another initiative. 30/4/2018, 30/4/2018,December 2017 - Project is paused awaiting review of a possible change in direction. Cost remains Green while investigation is undertaken to identify if deferral request was processed. | 2018-04-27T00:00:00 | Medium | 531030 | G | Geological Survey of Queensland | 60 | 161000 | G | G | 4 | Provide a web-based mapping solution for the ongoing provision of MinesOnlineMaps (MOMaps) into the future. | 531030 | 2016-08-01T00:00:00 | DNRM
30/4/2018 | LSI | Queensland Globe Improvements | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is continuing as planned. 30/4/2018, 30/4/2018,December 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-04-27T00:00:00 | High | 1002450 | G | Land and Spatial Information | 70 | 637810 | G | G | 5 | Enhancements to Queensland Globe to continue to evolve and improve user satisfaction and experience, such as: 30/4/2018, 30/4/2018,* create and save user-defined topics 30/4/2018,* improve query and access 30/4/2018,* provide editable 'redlining' 30/4/2018,* improve data imports. | 1002450 | 2017-10-09T00:00:00 | DNRM
30/4/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-05-25T00:00:00 | The project is nearing completion. A small extension to the planned end date has been approved to allow for closure activities. 30/4/2018, 30/4/2018,March 2018 - The project is continuing as planned. 30/4/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 30/4/2018,October 2017 - The project is progressing as planned. 30/4/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 30/4/2018,June 2017 - Revised Schedule approved returning the project to Green. 30/4/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 30/4/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 30/4/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 30/4/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 30/4/2018,December 2016 - The project is progressing as planned. | 2018-04-27T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 97 | 882957 | G | G | 6 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 30/4/2018, 30/4/2018,* register and maintain their information 30/4/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DNRM
30/4/2018 | QWSR | Dam Safety Regulation Solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | The project is continuing as planned. 30/4/2018, 30/4/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 30/4/2018,August 2017 - Approved extension of timeframe. 30/4/2018,June 2017 - The project is progressing as planned. 30/4/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 30/4/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 30/4/2018,October 2016 - Progress is continuing as planned. 30/4/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 30/4/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 30/4/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2018-04-27T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 95 | 1370090 | G | G | 7 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 30/4/2018, 30/4/2018,* support compliance with legislation 30/4/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 30/4/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 30/4/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 30/4/2018, | 1390000 | 2012-04-01T00:00:00 | DNRM
30/4/2018 | Natural Resources | Land Condition Assessment Tool | 2018-04-30T00:00:00 | Delivery | G | 2018-06-26T00:00:00 | This project is reporting for the first time and is progressing as planned. | 2018-04-27T00:00:00 | Medium | 414000 | G | Operations Support | 21 | 117926 | G | G | 8 | Implement a solution for government, industry and other stakeholders to objectively and consistently assess land condition, including development of: 30/4/2018, 30/4/2018,* a pictogram-based mobile web application and a data collection tool. | 414000 | 2017-01-12T00:00:00 | DNRM
30/4/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DPC
30/4/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
30/4/2018 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 30/4/2018,* Move operational accountability and responsibility for print and imaging devices to the service provider 30/4/2018,* Reduce print and imaging costs 30/4/2018,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
30/4/2018 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
30/4/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
30/4/2018 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 30/4/2018, 30/4/2018,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
30/4/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
30/4/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 30/4/2018, 30/4/2018,* reduce operating costs 30/4/2018,* increase capacity 30/4/2018,* improve customer experience 30/4/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
30/4/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
30/4/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 30/4/2018, 30/4/2018, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
30/4/2018 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 30/4/2018, 30/4/2018,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
30/4/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
30/4/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 30/4/2018, 30/4/2018,November 2017 - Actual cost to date corrected due to input error. 30/4/2018, 30/4/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 30/4/2018, | 2017-12-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 57 | 733941 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
30/4/2018 | ESR | Environmental Management Register/Contaminated Land Register - replacement | 2017-06-30T00:00:00 | Paused | G | 2017-06-30T00:00:00 | A review of resource availability is under way. 30/4/2018, 30/4/2018,March 2018 - The project remains paused with a new change request under development that will see the project move back into delivery with a Green status 30/4/2018, 30/4/2018,August 2017 - The project is paused awaiting the outcome of a change request for additional scope; this will return the project to a Green status. 30/4/2018, 30/4/2018,April 2017 - A minor correction has been made to the revised total estimated expenditure to include $20,000 operating prior years. 30/4/2018, 30/4/2018,February 2017 - A change request has been approved moving the initiative cost back to Green. 30/4/2018, 30/4/2018,December 2016 - Project is continuing as planned, with a change request under way to return cost to Green. 30/4/2018, 30/4/2018,October 2016 - Project delivery activities formally commenced on 2 October 2016. 30/4/2018, 30/4/2018,August 2016 - The initiative was paused for some time but has now recommenced and moved into delivery. It is progressing as planned. | 2018-04-27T00:00:00 | High | 981680 | A | Environmental Services and Regulation | 78 | 718000 | A | A | 1 | The current system no longer supports efficient delivery of the department's responsibilities. The replacement will: 30/4/2018, 30/4/2018,* mitigate the risks associated with a system that is beyond its useful life 30/4/2018,* improve access to information by individuals, business and industry conducting searches (property lot plan) of the registers 30/4/2018,* support the creation of notices to stakeholders 30/4/2018,* reduce manual tasks through the introduction of automated workflows and customer self-serve and self-correct. 30/4/2018, | 1111680 | 2016-07-01T00:00:00 | EHP
30/4/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 30/4/2018, 30/4/2018,November 2017 - Actual cost to date corrected due to input error. 30/4/2018, 30/4/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 30/4/2018, | 2018-04-27T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 74 | 1166727 | G | G | 2 | Acquire one or more solution components to operate in conjunction with the agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | EHP
30/4/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP
29/8/2018 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-06-30T00:00:00 | High | 5600000 |  | eHealth Queensland | 28 | 3328363 |  | G | 1 | This project aims to establish a robust, highly available and secure contemporary platform that has the capability to support the agile eHealth Strategy. | 5600000 | 2017-07-03T00:00:00 | DH
29/8/2018 | HSQ | Pathology and Forensic Laboratory System Rehosting Project | 2018-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | May: This project was previously known as the 'AUSLAB Rehosting Project'. This project has now returned to green, after receiving governance approval to extend the schedule and budget. 29/8/2018, 29/8/2018,April: Delays have been experienced in project deliverables, with refinements needed to the technical implementation, impacting the project's schedule. | 2018-07-03T00:00:00 | High | 1691324 |  | Health Support Queensland | 47 | 2316000 |  | G | 2 | Delivery of a replacement hardware and visualisation solution for the AUSLAB and AUSCARE systems that will achieve improved resiliency of the architecture, updated operating system and inclusion of virtualisation. AUSLAB and AUSCARE are critical to support laboratories and patient clinical care. | 2963000 | 2017-08-28T00:00:00 | DH
29/8/2018 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2016-08-01T00:00:00 | Delivery |  | 2018-09-30T00:00:00 |  | 2018-07-12T00:00:00 | High | 3692973 |  | Metro North | 95 | 1070953 |  | G | 3 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 29/8/2018, 29/8/2018,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and WomenÃ‚â€™s Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 29/8/2018, 29/8/2018,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 3692973 | 2015-06-01T00:00:00 | DH
29/8/2018 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Delivery |  | 2019-09-30T00:00:00 |  | 2018-06-30T00:00:00 | High | 11180394 |  | eHealth Queensland | 16 | 580259 |  | G | 4 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 29/8/2018,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work.Ã‚Â Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 11180394 | 2017-07-03T00:00:00 | DH
29/8/2018 | MNHHS | Business Intelligence - Enterprise Data Warehouse | 2018-06-29T00:00:00 | Closed |  | 2018-06-29T00:00:00 | June: This project is now complete. This initiative has introduced business intelligence and Data Lake capabilities at the Metro North HHS, improving decision support, analysis and research. 29/8/2018, 29/8/2018,March: Project funding is currently being revised in line with proposed scope for an upcoming stage. | 2018-07-12T00:00:00 | High | 2114991 |  | Metro North | 100 | 1477855 |  | G | 5 | This project will introduce Business Intelligence and Data Warehousing capabilities at MNHHS. The project will deliver BI & DW technical skills, system infrastructure, data automation tools, a pilot dataset, data governance processes and quality control framework at MNHHS. Metro North Finance and MNIT are jointly managing the project. | 1480178 | 2016-11-01T00:00:00 | DH
29/8/2018 | MNHHS | Central Patient Monitoring Equipment Replacement | 2018-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | June: This project is now complete. This project focused on various monitoring systems (physiological monitoring equipment) considered to be at their end of life, often featuring multiple technologies and separate, dedicated networks. This project transitioned these systems onto a single monitoring solution across the Metro North HHS. Some project costs have been 'cost recovered' by Metro North HHS. | 2018-07-12T00:00:00 | High | 1236416 |  | Metro North | 100 | 686067 |  | G | 6 | Metro North IT has been approached by Metro North Procurement Services (MNPS) to provide ICT advice and guidance into the Central Patient Monitoring Equipment Replacement (CPMER) Project. The Health Technology Equipment Replacement (HTER) program for central monitoring systems is providing funding in financial years 16/18 for physiological monitoring equipment requiring replacement across MNHHS hospital facilities. There is an estimated 312 pieces of equipment, primarily Physiological Monitoring devices, to be replaced under the program across MNHHS hospital facilities. MNHHS implementations are being co-ordinated by MNPS. | 1236416 | 2017-06-28T00:00:00 | DH
29/8/2018 | MNHHS | CISS (Community, Indigenous and Subacute Services) Wi-Fi | 2018-06-29T00:00:00 | Closed |  | 2018-06-29T00:00:00 | June: This project is now complete. Guest Wi-Fi is now available at Aspley Community Health Centre, Brighton Health Campus, Jacana Acquired Brain Injury Unit, Nundah Community Health Centre, Pine Rivers Community Health Centre and Zillmere Interim Care allowing patients as well as family and friends access to the internet while in these facilities. This capability also provides the foundation infrastructure for future Digital initiatives. | 2018-07-12T00:00:00 | High | 1280798 |  | Metro North | 100 | 1280539 |  | G | 7 | The Community, Indigenous and Subacute Services (CISS) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the internal areas of the prioritised CISS sites. 29/8/2018, 29/8/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1280798 | 2017-07-28T00:00:00 | DH
29/8/2018 | EHQ | Cloud First Project | 2018-06-30T00:00:00 | Closed |  | 2018-06-29T00:00:00 | June: This project is now complete. This project has established organisational readiness for Cloud Services, including the establishment of Cloud Centre of Excellence (CCoE) to enable cloud services. | 2018-06-30T00:00:00 | High | 4250000 |  | eHealth Queensland | 100 | 3186721 |  | G | 8 | The Cloud First project will build internal capability and establish processes within Queensland Health to appropriately utilise cloud services on an ongoing basis. | 4126918 | 2017-01-01T00:00:00 | DH
29/8/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Clinical Notes project (release 3.0) | 2018-02-06T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | June: This project has been implemented in June, with only final project governance activities remaining. | 2018-07-03T00:00:00 | High | 1415000 |  | Clinical Excellence | 95 | 1943618 |  | G | 9 | Upgrading the CIMHA Mental Health Act module to accommodate a re-architecture of the CIMHA clinical notes module is required to deliver benefits to the clinical workforce associated with data entry efficiencies; improved data sharing across digital platforms; patient level information transfer to third parties to support service integration and data mining to support service improvement and research. | 1969365 | 2017-02-20T00:00:00 | DH
29/8/2018 | EHQ | Critical Network Hardware | 2018-02-28T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | February: This project has returned to 'on track'. 29/8/2018, 29/8/2018,January: The project is reporting 'Amber' due to limited resource availability and additional technical requirements, impacting the schedule of the project | 2018-06-30T00:00:00 | High | 8636364 |  | eHealth Queensland | 80 | 7933393 |  | G | 10 | The objectives of the project include: 29/8/2018,a) Mitigate the Department of Health risk that core network switches at QH facilities will no longer be supported by the manufacturer from February 2018. 29/8/2018,b) Invest in the replacement of critical ICT network hardware to maintain current capability and reliability of the data network for 120+ enterprise clinical and business applications and provide the foundation for future capability in the enterprise data centres. 29/8/2018,c) Ensure hardware replacement occurs with minimal impact to business operations in Hospital and Health Services or Corporate offices. 29/8/2018,d) Update logical and physical design and architecture documentation for ease of maintenance and management. | 8371607 | 2017-03-06T00:00:00 | DH
29/8/2018 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | April: This initiative is now 'in delivery'. | 2018-06-30T00:00:00 | High | 3792744 |  | eHealth Queensland | 17 | 537912 |  | G | 16 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment.Ã‚Â Ã‚Â The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access.Ã‚Â | 3792744 | 2017-07-05T00:00:00 | DH
29/8/2018 | EHQ | Digital Collaboration Platform Program | 2018-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | May: May: This project has now returned to 'green' with the project's revised schedule being approved. 29/8/2018, 29/8/2018,March: Project activities have continued to be delayed, resulting in this project reporting 'Red'. A project change request has been submitted to the project's governance committee. Successful deployment was recently achieved in Townsville. 29/8/2018, 29/8/2018,January: This project is experiencing delays in pre-migration activities. | 2018-06-30T00:00:00 | High | 11000000 |  | eHealth Queensland | 35 | 15044457 |  | G | 11 | This program will deliver digital collaboration tools for any time, any where, any device including: 29/8/2018,Ã‚â€¢ Email and Archiving 29/8/2018,Ã‚â€¢ Establishment and Collaboration 29/8/2018,Ã‚â€¢ Productivity Suite Enablement | 18467291 | 2015-10-29T00:00:00 | DH
29/8/2018 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate |  | 2019-12-31T00:00:00 | June: The current proposed date of completion is the 31 December 2019, which is subject to project board approval. | 2018-06-30T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 40 | 615952 |  | G | 12 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 5697000 | 2015-12-01T00:00:00 | DH
29/8/2018 | QAS | e-ARF Redevelopment for iPad | 2016-12-31T00:00:00 | Closed |  | 2017-12-31T00:00:00 | June: This project is now complete, having completed end project reporting processes. This project has implemented an electronic Ambulance Report Form (eARF) electronic patient care solution, installed on iPads in the field. 29/8/2018, 29/8/2018,February: Implementation and rollout of the system was completed in late November 2017. The project is currently finalising end of project reporting processes. | 2018-06-30T00:00:00 | High | 2624000 |  | Queensland Ambulance Service | 100 | 2095356 |  | G | 13 | This is an initiative to provide the electronic Ambulance Report Form (eARF) electronic patient care solution via iPads in the field. | 2488000 | 2015-09-02T00:00:00 | DH
29/8/2018 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | May: The project has completed a solution evaluation process, with the project requiring additional schedule and financials as originally approved. The project is expecting to return to 'green' upon receiving change request approval. 29/8/2018, 29/8/2018,April: Further solution clarification is required, which has impacted on the overall delivery timeframe of this initiative by a number of weeks. | 2018-06-30T00:00:00 | High | 1283000 |  | Chief Health Officer and Prevention | 72 | 150591 |  | G | 14 | Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1522663 | 2017-07-24T00:00:00 | DH
29/8/2018 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery |  | 2018-11-30T00:00:00 |  | 2018-07-12T00:00:00 | High | 4827917 |  | Metro North | 68 | 3404376 |  | G | 15 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (ieMR) program. 29/8/2018, 29/8/2018,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 29/8/2018, 29/8/2018,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. | 4827917 | 2016-07-01T00:00:00 | DH
29/8/2018 | EHQ | File Services Migration | 2017-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-06-30T00:00:00 | High | 3400000 |  | eHealth Queensland | 30 | 3744146 |  | G | 17 | The purpose of this investment is to adopt a contemporary, simplified file management solution for Queensland Health that enables a more cohesive customer experience. | 9907925 | 2016-08-01T00:00:00 | DH
29/8/2018 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | June: The project is reporting Ã‚â€˜redÃ‚â€™ due to schedule delays and an anticipated funding shortfall associated with integration complexities and change management activities required. A change request is progressing to address these concerns with an outcome anticipated in August 2018. 29/8/2018, 29/8/2018,May: The project is currently reporting 'amber' due to the need to refine business requirements, which may have an impact on the project's schedule. 29/8/2018, 29/8/2018,March: The project has returned to 'green' and is continuing with solution testing activities. | 2018-06-30T00:00:00 | High | 105000000 |  | Metro North | 55 | 60327930 |  | R | 18 | The current Queensland Health Finance, Asset and Materials Maintenance Information System (FAMMIS) system is based on a heavily customised solution which is almost 20 years old and no longer supported. 29/8/2018,The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 29/8/2018, 29/8/2018,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 29/8/2018,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 29/8/2018, 29/8/2018,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
29/8/2018 | EHQ | Follow Me Desktop - Deployment | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-06-30T00:00:00 | High | 3952980 |  | eHealth Queensland | 50 | 1506092 |  | G | 19 | Follow Me Desktop Deployment Project will deliverÃ‚Â the Follow Me Desktop service (FMD) to HHSÃ‚â€™ in alignment with the Infrastructure Remediation Program (IMP) and ieMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 3676980 | 2017-07-03T00:00:00 | DH
29/8/2018 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-06-30T00:00:00 | High | 3301500 |  | eHealth Queensland | 21 | 1003717 |  | G | 20 | Project Purpose:Ã‚Â To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 2490769 | 2017-07-01T00:00:00 | DH
29/8/2018 | EHQ | ICT Regional Wireless Infrastructure Initiatives | 2018-06-29T00:00:00 | Closed |  | 2018-06-29T00:00:00 | June: This project is now complete. This project has improved the wireless network infrastructure in Far North Queensland locations, enabling these sites for new Queensland Health applications. | 2018-06-30T00:00:00 | High | 4170000 |  | eHealth Queensland | 100 | 3471553 |  | G | 21 | The Regional eHealth Project (ReHP) is a Wireless LAN and Network Infrastructure uplift project so that sites in Far North Qld are ready to rollout their new eHealth Application. | 3489114 | 2017-07-01T00:00:00 | DH
29/8/2018 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Initiate |  | 2019-06-28T00:00:00 |  | 2018-06-30T00:00:00 | High | 1120000 |  | eHealth Queensland | 52 | 689488 |  | G | 22 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. | 1120000 | 2017-07-05T00:00:00 | DH
29/8/2018 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery |  | 2020-06-26T00:00:00 |  | 2018-06-30T00:00:00 | High | 3215000 |  | eHealth Queensland | 31 | 5435154 |  | G | 23 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 12318334 | 2015-06-22T00:00:00 | DH
29/8/2018 | EHQ | ieMR Program (Funding Packages 3 and 4) | 2019-04-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | June: The advanced version of the ieMR system has gone live at the Queen Elizabeth II (QEII) Hospital in June, which includes enhancements to the interface between ieMR and the XRay Radiology Information System. 29/8/2018, 29/8/2018,May: The advanced version of the ieMR system has gone live at the Redland Hospital. Additional clinical reporting was also enabled by ieMR in May. 29/8/2018, 29/8/2018,April: The advanced version of the ieMR system has gone live at the Lady Cilento Children's Hospital in April 2018. An upgraded patient scheduling tool has also been deployed to Redland-Wynnum Hospital and Queen Elizabeth II (QEII) Hospital in April, improving inpatient and outpatient scheduling processes. | 2018-06-30T00:00:00 | High | 0 |  | eHealth Queensland | 33 | 0 |  | G | 24 | ieMR will enable improved patient care through the development of a state-wide, authoritative single source of the patient records. 29/8/2018, 29/8/2018,The ieMR will provide clinicians with the ability to: 29/8/2018,* access data that is integrated, accurate and clinically relevant 29/8/2018,* support decision making and better use of information 29/8/2018,* optimise management of patients, resources and provision of services 29/8/2018,* support interaction across a network of providers by making it easier to find providers, transfer information and collaborate with multidisciplinary providers. 29/8/2018,The Program scope (all tranches) is to roll out the ieMR system to 24 hospitals across Queensland. 29/8/2018, 29/8/2018,Please note that financial information for ieMR is Commercial in Confidence | 0 | 2016-11-17T00:00:00 | DH
29/8/2018 | EHQ | Infrastructure Capacity FY 17-18 | 2018-06-29T00:00:00 | Closed |  | 2018-06-29T00:00:00 | June: This project is now complete. This project replaced or upgraded ICT infrastructure within the 2017-18 Financial Year to allow continued efficient ICT service delivery. | 2018-06-30T00:00:00 | High | 1000000 |  | eHealth Queensland | 100 | 1319611 |  | G | 25 | Project Purpose:Ã‚Â 29/8/2018,The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified Ã‚â€˜organic growthÃ‚â€™ requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. | 2000000 | 2017-07-01T00:00:00 | DH
29/8/2018 | EHQ | Infrastructure Maintenance Program Establishment | 2018-06-29T00:00:00 | Delivery |  | 2022-06-30T00:00:00 | March: This initiative has been refocused to the establishment phase of the Infrastructure Maintenance Program, and as such the % complete and original end date have been updated to reflect this phase of the program. The latest approved end date will be updated in a following reporting month. | 2018-06-30T00:00:00 | High | 1161415 |  | eHealth Queensland | 80 | 998376 |  | G | 26 | The Infrastructure Maintenance Program (IMP)Ã‚Â will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 29/8/2018,The scope includes: 29/8/2018,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 29/8/2018,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; andÃ‚Â 29/8/2018,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1156372 | 2017-07-03T00:00:00 | DH
29/8/2018 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery |  | 2022-06-30T00:00:00 |  | 2018-07-02T00:00:00 | High | 14673739 |  | Clinical Excellence | 18 | 2101501 |  | G | 27 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 29/8/2018,The ongoing program of work aims to continue and build upon existing functionality by: 29/8/2018,Ã‚â€¢ Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 29/8/2018,Ã‚â€¢ Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 29/8/2018,Ã‚â€¢ Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 29/8/2018,Ã‚â€¢ Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 29/8/2018,Ã‚â€¢ Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
29/8/2018 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate |  | 2022-12-21T00:00:00 |  | 2018-06-30T00:00:00 | High | 6300000 |  | Queensland Ambulance Service | 25 | 545495 |  | G | 28 | Phased delivery of a system supporting QAS business intelligence. | 9240000 | 2017-01-03T00:00:00 | DH
29/8/2018 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 |  | 2018-06-30T00:00:00 | High | 33827000 |  | Clinical Excellence | 35 | 13224343 |  | G | 29 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 39408218 | 2017-03-01T00:00:00 | DH
29/8/2018 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 1 | 2016-11-30T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | May: The project has experienced a delay to the completion of Stage 1 due to delays in the governance and assurance process and a change in delivery approach. The project is expecting to complete Stage 1 by the end of August 2018, and is currently seeking final governance approval to confirm additional time and funding to complete this stage. 29/8/2018, 29/8/2018,April: The project has experienced a delay to the completion of Stage 1 due to delays in the governance and assurance process. The project is currently seeking approval to obtain additional time and funding to complete this stage. 29/8/2018, 29/8/2018,February: Approval delays in obtaining additional funding and a slightly extended schedule has impacted the project's schedule, with approvals expected in the upcoming reporting month. | 2018-07-03T00:00:00 | High | 8200000 |  | Health Support Queensland | 93 | 24720000 |  | G | 30 | The IWFM project involves: 29/8/2018,- configuring additional functionality (currently available and licensed, but unutilised) within the existing Rostering and Payroll business solutions 29/8/2018,- partnering with HHSs to develop refined business models and business processes to support the roster-to-pay process 29/8/2018,- undertaking extensive training and change management to support the adoption and effective usage of new functionality and processes | 28709863 | 2016-02-17T00:00:00 | DH
29/8/2018 | EHQ | Interoperability Project | 2016-04-29T00:00:00 | Delivery |  | 2019-09-29T00:00:00 |  | 2018-06-30T00:00:00 | High | 23850000 |  | eHealth Queensland | 31 | 16271002 |  | G | 31 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 29/8/2018,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 29/8/2018,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 29/8/2018, | 39189509 | 2015-02-01T00:00:00 | DH
29/8/2018 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Delivery |  | 2020-12-21T00:00:00 |  | 2018-06-30T00:00:00 | High | 64000000 |  | Health Support Queensland | 51 | 19579882 |  | G | 32 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 29/8/2018,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. | 63558771 | 2015-08-28T00:00:00 | DH
29/8/2018 | MNHHS | Learning and Performance Management Project | 2017-06-30T00:00:00 | Delivery |  | 2018-11-30T00:00:00 |  | 2018-07-12T00:00:00 | High | 1178190 |  | Metro North | 90 | 1261263 |  | G | 33 | Implement an integrated Learning Management and Performance Management system with the capability to deliver online learning and training content, facilitate performance development and maintain centralised records for reporting purposes. | 1178190 | 2016-07-11T00:00:00 | DH
29/8/2018 | GCHHS | Medical Imaging Informatics Solution (MIIS) Risk Mitigation | 2018-12-31T00:00:00 | Delivery |  | 2019-12-31T00:00:00 |  | 2018-07-06T00:00:00 | High | 5000000 |  | Gold Coast | 20 | 2179294 |  | G | 34 | The Medical Imaging Informatics Solution (MIIS) Risk Mitigation project has identified an Imaging solution which will address the risks and opportunities described in the Case for Change including the mitigation of patient safety risks, increased efficiency and productivity, improvi.ng medical imaging billing revenue collection and cash flow. The solution has user endorsement from radiologists and clinicians and will be specifically configured to meet GCHHSÃ‚â€™s needs. | 12800000 | 2017-04-03T00:00:00 | DH
29/8/2018 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | June: The latest approved end date of this project remains at 30 June 2018, pending the approval of a revised implementation date. | 2018-06-30T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 90 | 900925 |  | G | 41 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1481000 | 2015-10-01T00:00:00 | DH
29/8/2018 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery |  | 2018-09-26T00:00:00 |  | 2018-07-12T00:00:00 | High | 4030460 |  | Metro North | 80 | 3824466 |  | G | 35 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 29/8/2018, 29/8/2018,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 29/8/2018, 29/8/2018,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
29/8/2018 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | May: This project has returned to 'green', with the project's schedule and budget being monitored by the project's governance committee. 29/8/2018, 29/8/2018,April: The project is continuing to report 'Red' due to continued delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-07-12T00:00:00 | High | 6299780 |  | Metro North | 80 | 6418686 |  | G | 36 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 8280461 | 2014-06-01T00:00:00 | DH
29/8/2018 | EHQ | Metro South and East Queensland ICT Infrastructure Replacement Initiative | 2018-06-29T00:00:00 | Delivery |  | 2019-02-28T00:00:00 |  | 2018-06-30T00:00:00 | High | 4160449 |  | eHealth Queensland | 68 | 1680154 |  | G | 37 | Will replace or uplift out of date end of life ICT assets. | 3632112 | 2017-07-01T00:00:00 | DH
29/8/2018 | EHQ | Metro South East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-04-29T00:00:00 |  | 2018-06-30T00:00:00 | High | 2182844 |  | eHealth Queensland | 55 | 1041573 |  | G | 38 | Will replace or uplift out of date end of life ICT assets. | 2182843 | 2017-07-01T00:00:00 | DH
29/8/2018 | EHQ | Mobile Application System for Bring Your Own Device | 2018-06-30T00:00:00 | Delivery |  | 2018-08-24T00:00:00 | May: This project is now reporting 'red'. Governance pathways and approvals have impacted on the project's overall schedule. The project is progressing with a change request to update the project's deliverables, which will return the project to 'green' upon approval. | 2018-06-30T00:00:00 | High | 1639698 |  | eHealth Queensland | 85 | 1462014 |  | G | 39 | This project leverages the investment of the previous Bring-Your-Own-Device (BYOD)Ã‚Â projects to extend the capability of device mobility by building the foundations of a Mobile Application Ecosystem - the processes, products and services to enable the managed development of low/no code applications by Health and Hospital Services (HHS).Ã‚Â This project will also complete the deployment of BYOD laptops and provide recommendations on how cost savings can be made by the organisation around Corporate devices and data plans.Ã‚Â | 1538302 | 2017-07-01T00:00:00 | DH
29/8/2018 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery |  | 2018-12-19T00:00:00 | May: This project has now returned to 'green' with the project's revised schedule being approved. 29/8/2018, 29/8/2018,April: This project is experiencing delays in pre-migration activities, delays experienced in another dependent project, and requires additional resources. Further finances are required, with the schedule and finance issues being managed via the project's governance committee. 29/8/2018, 29/8/2018,January: This project is experiencing delays in pre-migration activities and delays experienced in another dependent project. | 2018-06-30T00:00:00 | High | 14100000 |  | eHealth Queensland | 55 | 21185251 |  | G | 40 | A managed operating environment means that everyone within the organisation is running a clean, basic operating system with centralised update management. This includes upgrades of all PC operating systems, preparing QH applications for running on recent operating system environments, and Infrastructure remediation activities to ensure the deployment tools are sufficient and ready for production. | 27427900 | 2016-05-12T00:00:00 | DH
29/8/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-06-30T00:00:00 | High | 1651750 |  | eHealth Queensland | 55 | 1305668 |  | G | 54 | Will replace or uplift out of date end of life ICT assets. | 1651750 | 2017-07-01T00:00:00 | DH
29/8/2018 | CHOPD | Notifiable Conditions System Replacement | 2019-06-29T00:00:00 | Delivery |  | 2020-02-28T00:00:00 |  | 2018-06-30T00:00:00 | High | 12750000 |  | Chief Health Officer and Prevention | 41 | 2766295 |  | G | 42 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 29/8/2018,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
29/8/2018 | EHQ | Patient Administration System (PAS) Replacement - Business Case Development Project | 2017-06-30T00:00:00 | Initiate |  | 2019-03-29T00:00:00 |  | 2018-06-30T00:00:00 | High | 3850000 |  | eHealth Queensland | 67 | 5230431 |  | G | 43 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patientsÃ‚â€™ journeys, and ensure that accurate information about our patients is readily available when and where required. 29/8/2018, 29/8/2018,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 29/8/2018,Ã‚â€¢ support for patient engagement 29/8/2018,Ã‚â€¢ integrated care 29/8/2018,Ã‚â€¢ clinical research 29/8/2018,Ã‚â€¢ population health (for patients using public health services) 29/8/2018,Ã‚â€¢ performance transparency 29/8/2018,Ã‚â€¢ resource planning. | 11890865 | 2015-11-01T00:00:00 | DH
29/8/2018 | MNHHS | Picture Archiving and Communication System (PACS) | 2017-09-29T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | May: This project has returned to 'green', with the project's schedule and budget being monitored by the project's governance committee. 29/8/2018, 29/8/2018,April: The project is continuing to report 'Red' due to continued delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-07-12T00:00:00 | High | 3114694 |  | Metro North | 65 | 3365354 |  | G | 44 | Procure and implement a contemporary Picture Archiving and Communication (PACS) system and functionality that will ensure improved service delivery for the MNHHS Medical Imaging Departments (and other PACS users) through replacement of RBWH PACS ensuring that it is scalable and able to meet the ongoing needs of Metro North Hospital and Health Service. | 3656297 | 2016-07-11T00:00:00 | DH
29/8/2018 | CSD | Practice Management Enterprise Solution | 2018-11-01T00:00:00 | Delivery |  | 2019-01-31T00:00:00 |  | 2018-07-04T00:00:00 | High | 1470000 |  | Corporate Services | 65 | 1551201 |  | G | 45 | The main practice management software used by HHSs to conduct private practice services and billing activities is being replaced. The initiative will procure and implement "like for like" functionality enterprise solution for participating HHSs (15 in total). | 2961432 | 2017-08-01T00:00:00 | DH
29/8/2018 | EHQ | Project, Program and Portfolio Management Application | 2018-03-31T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | May: This project has now returned to 'green' with the project's revised schedule being approved. 29/8/2018, 29/8/2018,April: This project is now reporting 'amber' due to re-aligning the project's schedule and finances to meet changing organisational requirements. The project has submitted | 2018-06-30T00:00:00 | High | 1344177 |  | eHealth Queensland | 30 | 654945 |  | G | 46 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 29/8/2018, | 1473632 | 2017-05-02T00:00:00 | DH
29/8/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-06-30T00:00:00 | High | 4245973 |  | eHealth Queensland | 76 | 3072306 |  | G | 55 | Will replace or uplift out of date end of life ICT assets. | 4245973 | 2017-07-01T00:00:00 | DH
29/8/2018 | CED | Queensland Integrated Safety Information Project (QISIP) / Risk Management | 2017-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | June This project is now complete, with all implementation sites having 'gone-live'. This initiative has implemented a cloud-based reporting and management system to support the reporting of patient and staff incidents, feedback, case management, and risk management across Queensland Health. | 2018-06-30T00:00:00 | High | 4333120 |  | Clinical Excellence | 100 | 8334904 |  | G | 47 | This initiative will source a state wide system to replace existing enterprise risk management systems to support patient and staff incident reporting, feedback, case management and risk management processes. | 16273520 | 2013-01-25T00:00:00 | DH
29/8/2018 | EHQ | Queensland State-wide ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-06-30T00:00:00 | High | 3246247 |  | eHealth Queensland | 62 | 2286070 |  | G | 48 | Will replace or uplift out of date end of life ICT assets. | 3246247 | 2017-07-01T00:00:00 | DH
29/8/2018 | EHQ | Queensland State-wide ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-06-30T00:00:00 | High | 3283431 |  | eHealth Queensland | 73 | 2935028 |  | G | 49 | Will replace or uplift out of date end of life ICT assets. | 3282431 | 2017-07-01T00:00:00 | DH
29/8/2018 | MNHHS | Quick Flow Project | 2019-02-01T00:00:00 | Initiate |  | 2019-06-30T00:00:00 |  | 2018-07-12T00:00:00 | High | 6408600 |  | Metro North | 65 | 1645936 |  | G | 50 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 29/8/2018,The key objectives of the project are to: 29/8/2018,Ã‚â€¢ Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 29/8/2018,Ã‚â€¢ Improve the outpatient experience across MNHSS facilities and community services 29/8/2018,Ã‚â€¢ Improve clinic resource utilisation 29/8/2018,Ã‚â€¢ Increase the efficiency of clinical and administrative processes 29/8/2018,Ã‚â€¢ Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
29/8/2018 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Initiate |  | 2019-12-31T00:00:00 |  | 2018-07-06T00:00:00 | High | 34950000 |  | Cairns and Hinterland | 65 | 12699734 |  | G | 51 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patientÃ‚â€™s home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
29/8/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-02-28T00:00:00 |  | 2018-06-30T00:00:00 | High | 4260336 |  | eHealth Queensland | 70 | 2371620 |  | G | 52 | Will replace or uplift out of date end of life ICT assets. | 4260336 | 2017-07-01T00:00:00 | DH
29/8/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-06-30T00:00:00 | High | 2150147 |  | eHealth Queensland | 67 | 1208286 |  | G | 53 | Will replace or uplift out of date end of life ICT assets. | 2678483 | 2017-07-01T00:00:00 | DH
29/8/2018 | EHQ | Service Delivery Excellence Project (SDEP) | 2018-02-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | March: The latest approved end date and percentage complete has been updated. 29/8/2018, 29/8/2018,February: The latest approved end date for this initiative will be updated pending advise from the project. | 2018-06-30T00:00:00 | High | 4822000 |  | eHealth Queensland | 25 | 1429092 |  | G | 56 | The Service Delivery Excellence Project (SDEP) aims to improve the service delivery functions of eHealth Queensland to help the organisation achieve its Customers and services Foundation and Shared Goal: 29/8/2018,Enhance value for customers by streamlining end to end services, processes and delivery models so that we can provide an exceptional customer experience. 29/8/2018,Stage 1 has the primary objective of delivering the Project Initiation Document (PID) for the Service Delivery Excellence Project (SDEP) Stage 2. | 4821750 | 2017-10-03T00:00:00 | DH
29/8/2018 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Delivery |  | 2020-09-30T00:00:00 |  | 2018-06-30T00:00:00 | High | 10500000 |  | eHealth Queensland | 16 | 3036419 |  | G | 57 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 10500000 | 2017-07-03T00:00:00 | DH
29/8/2018 | MNHHS | Royal Brisbane and Women's Hospital Wi-Fi | 2019-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-07-12T00:00:00 | High | 6000000 |  | Metro North | 30 | 3164697 |  | G | 58 | The RBWH Wi-Fi Project will provide an uplift and renewal to the latest Queensland Health (QH) standard for wireless local area network (WLAN) coverage within the internal areas of prioritised RBWH buildings in order to support digital healthcare. 29/8/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for the RBWH in the near future. | 6000000 | 2017-10-22T00:00:00 | DH
29/8/2018 | EHQ | Storage Asset Replacement | 2018-06-29T00:00:00 | Delivery |  | 2018-08-31T00:00:00 |  | 2018-06-30T00:00:00 | High | 1671556 |  | eHealth Queensland | 55 | 1386458 |  | G | 59 | The Storage Asset Replacement (SAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the SAR and Backup Asset Replacement (BAR) projects. 29/8/2018,The SAR project seeks to outline architecture for storage that will provide a cost effective, scalable and fit for purpose environment for the future of storage services within Queensland Health.Ã‚Â Utilising space saving technologies which will enable further cost savings and reduce the requirement for capacity expansion in the short to medium term. | 1659988 | 2017-07-03T00:00:00 | DH
29/8/2018 | EHQ | Telehealth Asset Replacement FY 17-18 | 2018-06-29T00:00:00 | Closed |  | 2018-06-29T00:00:00 | June: This project is now complete. This project replaced or upgraded prioritised, highly utilised and critical videoconference systems in the 2017-18 Financial Year which have reached end of life. | 2018-06-30T00:00:00 | High | 1960000 |  | eHealth Queensland | 100 | 1954417 |  | G | 60 | Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sectorÃ‚Â 29/8/2018,and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. 29/8/2018,The Department of Health defines Telehealth as: 29/8/2018,Ã‚â€¢Live, audio and/or video inter-active link for clinical consultations and educational purposes 29/8/2018,Ã‚â€¢Store and forward Telehealth - this model can involve digital images, video, audio and clinical data being captured ("stored") on the client computer; then at a convenient time transmitted securely ("forwarded")Ã‚Â to a clinic at another location where they are studied by relevant specialists 29/8/2018,Ã‚â€¢Teleradiology for remote reporting and clinical advice for diagnostic images 29/8/2018,Ã‚â€¢Telehealth services and equipment to monitor peopleÃ‚â€™s health in their home. 29/8/2018,Benefits of Telehealth 29/8/2018,Ã‚â€¢Improve patient access to health care 29/8/2018,Ã‚â€¢Reduce travel and inconvenience for patients, families, carers and health professionals 29/8/2018,Ã‚â€¢Provide health professionals with access to peer support and education. 29/8/2018,The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life.Ã‚Â 29/8/2018,The priority is to replace those end-of-life assets which pose the greatest risk to effective health service delivery. | 1957626 | 2017-07-03T00:00:00 | DH
29/8/2018 | MNHHS | The Prince Charles Hospital (TPCH) Wi-Fi | 2018-06-29T00:00:00 | Closed |  | 2018-06-29T00:00:00 | June: This project is now complete. June: This project is now complete. This project has established the standard for wireless local area network (WLAN) coverage within prioritised TPCH buildings, including the Dept. of Emergency & Education Building, Chermside CHC & Melaleuca Unit, Indigenous Health & Conference, and Ellen Barron Family Centre. Benefits of this project include free Guest Wi-Fi for patients, families and friends, as well as enhancing network access for clinical and staff resources. | 2018-07-12T00:00:00 | High | 1408338 |  | Metro North | 100 | 1409426 |  | G | 61 | The Prince Charles Hospital (TPCH) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the hospital campus for prioritised TPCH buildings. 29/8/2018, 29/8/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1408338 | 2017-07-27T00:00:00 | DH
29/8/2018 | EHQ | Sunshine Coast University Hospital (SCUH) Stage 2 ICT Expansion | 2018-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | February: This project has been reported for the first time. | 2018-06-30T00:00:00 | High | 3180000 |  | eHealth Queensland | 78 | 3448194 |  | G | 62 | Sunshine Coast University Hospital (SCUH) ICT Stage 1 delivered the ICT required to achieve the successful commissioning of SCUH in March 2017. The SCUH Stage 2 ICT Expansion covers the investment period from 1 July 2017 to 31 December 2018 and is intended to support the planned expansion of SCUH to increase capacity and establish new services. | 3180422 | 2017-07-03T00:00:00 | DH
29/8/2018 | CHQ | Information Sharing Project Phase 2 | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | June: This project is now reporting 'amber' due to a change in procurement approach, which has impacted on the project's financials and schedule. The project's governance committee is reviewing the updated approach, returning the project to 'green' upon approval. 29/8/2018, 29/8/2018,March: This project has been reported for the first time. | 2018-07-05T00:00:00 | High | 4455455 |  | Children's Health Queensland | 20 | 985160 |  | A | 63 | Department of Health, eHealth Queensland, ChildrenÃ‚â€™s Health Queensland and Mater Health share a common vision for the seamless integration of care across organisational boundaries, in the interests of patient safety, quality, efficiency and improved access to care. This vision of integrated care processes is enabled through seamless access, at the point of care, to necessary health information and efficient transactional capabilities that support the care continuum. | 4455455 | 2018-01-10T00:00:00 | DH
29/8/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Alcohol and Other Drugs (AODS) Consumer Technical Refresh | 2019-06-28T00:00:00 | Initiate |  | 2019-06-28T00:00:00 | May: This project has been reported for the first time. | 2018-07-03T00:00:00 | High | 1248860 |  | Clinical Excellence | 10 | 310120 |  | G | 64 | This project is refreshing the technical implementation of the CIMHA Consumer module, in preparation for the introduction of new Alcohol and Other Drugs (AODS) system functionality. | 1248860 | 2018-04-16T00:00:00 | DH
29/8/2018 | SPP | Queensland Health Integrated Processing System establishment (QHIDSe) | 2019-10-15T00:00:00 | Initiate |  | 2019-10-15T00:00:00 | May: This project has been reported for the first time. | 2018-06-30T00:00:00 | High | 3257000 |  | Strategy, Policy and Planning | 8 | 866805 |  | G | 65 | The QHIDSe project will develop in-house the foundation of an integrated processing system (i.e. QHIDS (Queensland Health Integrated Data System) using agile techniques and software development tools enabling QHIDS to be used as a replacement for the Queensland Hospital Inpatient Processing System (QHIPS, which processes the Queensland Hospital Admitted Patient Data Collection) and extended through future initiatives to provide new functionality. | 3257000 | 2018-05-25T00:00:00 | DH
29/8/2018 | HSQ | Modernised Managed Operating Environment (MOE) and Digital Collaboration Platform for HSQ | 2018-12-31T00:00:00 | Initiate |  | 2018-12-31T00:00:00 | June: This project has been reported for the first time. | 2018-07-02T00:00:00 | High | 1301251 |  | Health Support Queensland | 24 | 1167000 |  | G | 66 | Delivery of a fully functional, production managed operating environment and digital collaboration platform packaged to all desktops, laptops and some smart devices within the Health Support Queensland environment. | 3414000 | 2018-01-01T00:00:00 | DH
29/8/2018 | CHOPD | Mosquito-borne Disease Program: Spatial Database Project | 2019-06-21T00:00:00 | Initiate |  | 2019-06-21T00:00:00 | June: This project has been reported for the first time. | 2018-06-30T00:00:00 | High | 940000 |  | Chief Health Officer and Prevention | 53 | 162672 |  | G | 67 | The vector surveillance and control program requires a state-wide surveillance and control solution to assist with the response to the risk of Dengue, Zika and Chikungunya virus outbreaks in vulnerable North Queensland and the mitigation of emerging risks across Central and Southern Queensland. | 1694000 | 2017-07-31T00:00:00 | DH
29/8/2018 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Project planned expenditure and end date have been revised due to a number of factors: 29/8/2018, 29/8/2018,- The original planned expenditure of $2.2M was a high level estimate and has been refined with the complexity of the processes and system being uncovered as the project was stood up. 29/8/2018, 29/8/2018,- An increased scope and associated effort to ensure maximum benefit is gained from the investment, so that Queenslanders are better supported during natural disasters. 29/8/2018, 29/8/2018,- Delays to project schedule and associated additional resourcing costs as a result of: 29/8/2018, 29/8/2018, - Staff diverted to priority community recovery support roles during activations over the last 12 months, including TC Debbie, TC Nora and the North Queensland floods. During natural disasters, our agency resources are focused on providing critical support to communities and Queenslanders in need. 29/8/2018, 29/8/2018, - Extended vendor delivery times due to defects and quality concerns including system performance. The department is working with the vendor to resolve these issues. | 2018-06-30T00:00:00 | High | 2208000 |  | Department of Communities, Disabilty Services and Seniors | 89 | 3022000 |  | G | 1 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3780000 | 2016-07-01T00:00:00 | DCCSDS
29/8/2018 | Cross-Gov | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | The Queensland Fire and Emergency Services (QFES) Human Capital Management Case Management module delivery has been completed with UAT and Penetration testing finalised for implementation. The Workplace Health and Safety module has completed UAT and will be released into production following completion of agency training. The closure report for this project has commenced. 29/8/2018, 29/8/2018,The Queensland Corrective Services Human Capital Management Business Case has been approved with detailed project planning and resource engagement underway. Gate 3 Investment Decision review has been completed. Project startup planning for implementation has commenced. 29/8/2018, 29/8/2018,The Queensland Ambulance Service (QAS) and QFES payroll projects transitioning to Aurion are progressing to schedule, with QAS being the next for implementation planned for November 2018. 29/8/2018, 29/8/2018,Detailed planning of the Integration requirements for the program continue to be progressed. 29/8/2018, 29/8/2018,At the direction of the Executive Steering Committee (3/07/18) the program scope was increased to include the procurement of a Time and Attendance solution for QFES, QAS and QCS. | 2018-06-30T00:00:00 | Critical | 101500000 |  | Cross-Government program led by DSITI | 65 | 59979631 |  | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 29/8/2018, 29/8/2018,* Sustainable and supported HR and Payroll service delivery 29/8/2018,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 29/8/2018,* Strategic HR capability that supports the development, performance and safety of the departments workforce 29/8/2018,* Business Intelligence capability that provides real timely, integrated HR information 29/8/2018,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 29/8/2018,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 29/8/2018,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
29/8/2018 | QPS | GPS Tracking (Bail) | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | Legislation provisioning for GPS monitoring of court bailed offenders commenced on 31/3/18. QPS established interim GPS tracking capability leveraging existing contract held by Queensland Corrective Services. 29/8/2018,QPS is now undertaking a Whole of Government open Invitation-to-Offer to establish a longer term contract for GPS tracking devices and monitoring of offenders. 29/8/2018,Note: The project is currently undergoing procurement/commercial activity and is therefore not publishing any financial data. | 2018-08-22T00:00:00 | High | 0 |  | Queensland Police Service | 40 | 0 |  | G | 1 | As per the Commencement of the Bail (Domestic Violence) and Another Act Amendment Act 2017 (the Amending Act) on 30 March 2018, Magistrates will be empowered to impose a tracking condition on a defendant granted bail as a condition of their bail undertaking. 29/8/2018,As such the QPS intends to progressively implement an electronic monitoring capability on a State Wide basis. 29/8/2018,An implementation project has commenced to create an electronic monitoring capability for geographically locating and monitoring a defendant on bail for QPS to meet requirements of the Amended Act. 29/8/2018,The GPS Tracking Project is an initial proposal to validate the utility of the technology prior to seeking a longer term solution. | 0 | 2018-03-30T00:00:00 | QPS
29/8/2018 | QPS | Online National Police Certificate | 2017-06-30T00:00:00 | Closed |  | 2018-07-31T00:00:00 | Since the successful launch of Online National Police Certificates 83% of all applications have been submitted online. The project is now officially closed effective 31 July 2018 and has transitioned to business as usual. 29/8/2018, 29/8/2018,Feb 18: The revised project budget has been amended from previously published figures to reflect the increased investment in promotional products. | 2018-08-22T00:00:00 | High | 275000 |  | Queensland Police Service | 100 | 250000 |  | G | 2 | The Online National Police Certificate Project will implement an online service for the community to apply and pay for Name Only National Police Certificates online, rather than presenting at a police station, or using the online services of an Australian Crime Intelligence Commission accredited broker. This will provide improved customer service to the community through a more efficient and reliable QPS service, with no requirement to present at a police station, as well as provide efficiency and time savings to local police stations and the Police Information Centre. | 250000 | 2017-01-01T00:00:00 | QPS
29/8/2018 | QPS | Police Integrity and Professional Standards | 2018-08-24T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | Full funding has now been approved for the Police Integrity and Professional Standards IT system. 29/8/2018, 29/8/2018,The Project has received a green assessment for the Gate 3 Quality Assurance Review and will commence delivery in July 2018 with an approved revised project end date of 31 December 2019. 29/8/2018, 29/8/2018,Feb 18: Note: original planned end date amended as previously published information was incorrect. | 2018-08-22T00:00:00 | High | 4142000 |  | Queensland Police Service | 35 | 307200 |  | G | 3 | This initiative will deliver a new integrated Police Integrity and Professional Standards IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The Police Integrity and Professional Standards system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The Police Integrity and Professional Standards Project will also complement the Complaints Reform Project established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of the Police Integrity and Professional Standards system will place the QPS in a strong readiness position to fully implement Complaints Reform Project-generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 6792000 | 2017-03-07T00:00:00 | QPS
29/8/2018 | QPS | Advanced Data Analytics | 2017-07-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | The Advanced Data Analytics Project was established to progress the QPS advanced analytics strategy and capability. 29/8/2018, 29/8/2018,Demand and Resource Committee on 23 July 2018 noted the Advanced Data Analytics End Project Report and approved the closure of the Advanced Data Analytics Project. 29/8/2018, 29/8/2018,The additional $59,389 expenditure on the project was incurred to extend some resources to support the transition of capabilities into business as usual. This amount is within the accepted QPS tolerance for project variance. 29/8/2018, 29/8/2018,The project delivered more than was proposed in the original submission, leaving legacy capability that has transitioned into business as usual. 29/8/2018, 29/8/2018,Jun 18: The QPS Demand and Resource Committee approved the extension of the project closure date to 30 June 2018 and an additional $1,114,000 in funding to facilitate achievement of the projects objectives. | 2018-08-22T00:00:00 | Low | 1731000 |  | Queensland Police Service | 100 | 2904389 |  | G | 4 | Develop the QPS Advanced Data Analytics proof-of-concept. This proof-of-concept is intended to inform a larger suite of data analytics integration and intelligence over the next four years, including the development of predictive and alert models to enhance the operational response to threats, incidents and events. | 2845000 | 2017-02-19T00:00:00 | QPS
29/8/2018 | QPS | Body Worn Cameras | 2018-02-28T00:00:00 | Closed |  | 2018-06-30T00:00:00 | The Project completed the deployment of all Stage Two body worn cameras in December 2017 and transitioned to business as usual on 30 June 2018. The Project is now going through approval for formal closure. 29/8/2018, 29/8/2018,Feb 2018: The original budget was $6.03M. In May 2017, the QPS Demand and Resource Committee approved an additional $0.860M, making the total approved budget $6.890M | 2018-08-22T00:00:00 | Medium Low | 6030000 |  | Queensland Police Service | 100 | 6890000 |  | G | 5 | The Queensland Police Service Body Worn Camera Project is deploying 5100 body worn cameras to frontline police officers. Body worn cameras will be deployed to 168 police stations, 16 tactical crime units, 47 road policing units, and specialist units including dog squads and the Public Safety Response Team in two stages. The cameras integrate with the QPS mobility devices, allowing officers to add metadata to videos and to review videos in the field. A system for storage and allocation of digital camera data will also be implemented as well as policy related to use of the cameras. | 6890000 | 2014-08-25T00:00:00 | QPS
29/8/2018 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Objectives 29/8/2018,This project will deliver a secondary DR site and hyper-converged system to provide resilience for all departmental business applications in the event of a disaster. 29/8/2018, 29/8/2018,Project Updates 29/8/2018,Core infrastructure DR implementation 80% complete. All migrated production systems successfully replicating to secondary DR site. 29/8/2018,Oracle system DR implementation is 100% complete 29/8/2018,Legacy applications undergoing case-by-case assessment to identify best option for DR implementation: application upgrade, application replacement, defunct applications to be decommissioned. External vendor engaged to assist. Anticipated completion by Dec 2018. 29/8/2018,Oracle applications DR testing successfully completed. 29/8/2018,All end-of-life ICT infrastructure will be decommissioned by Dec 2018. 29/8/2018,The newly implemented infrastructure will provide improved stability and life extension to existing business-critical applications. 29/8/2018,DR recovery procedure development, testing strategy and ICT DR Plan update in progress. 29/8/2018, 29/8/2018, 29/8/2018,Project Schedule 29/8/2018,Some issues have impacted YTD position however it is anticipated the original completion date will be met. These issues include: 29/8/2018,DR failover testing of DJAG and QCS business critical system. Anticipated completion date is October 2018. 29/8/2018,Data centre network upgrade delays are affecting delivery of IT security infrastructure to DR site. Estimated completion date for IT security DR implementation is December 2018. 29/8/2018, 29/8/2018,Expenditure 29/8/2018,The revised total estimated expenditure has changed due to the approval of additional work packages. An additional $750K in budget from 2017/18 carryovers has been approved to cover a project extension until 31/12/2018. 29/8/2018,The Actual cost to date has increased from $4,705,792 in June to $4,836,208 in July. This arises from the required end of financial year accruals and other adjustments e.g. capitalisation that are required at the end of the financial year. 29/8/2018, | 2018-07-31T00:00:00 | High | 7460674 |  | Corporate Services | 80 | 4836208 |  | G | 1 | *Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 6257794 | 2016-10-01T00:00:00 | DJAG
29/8/2018 | HHS | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery |  | 2019-03-31T00:00:00 | The FOPATS Program undertook a significant re-baseline in late 2016 to inform and approve changes to its strategic direction, scope, delivery methodology, timing and costs, including strengthening program governance and revising the Business Case to complete against a two staged implementation, Property and then Tenancy. 29/8/2018, 29/8/2018,Following this review, the Property Release, the first of two stages, was delivered successfully on time on 1 November 2017 and delivered benefits including efficiencies in property management and reporting. 29/8/2018, 29/8/2018,The refreshed business case, the Program budget and planned end date were formally re-baselined in January 2018. This formal approval, coupled with the successful delivery of the first stage Property Release, saw the Program status move to green. 29/8/2018, 29/8/2018,The Program has completed more detailed planning for the second stage Tenancy Release, which will remove the operational dependency on the existing ICT housing solution entirely. Tenancy design activities are now well progressed, with a view to determining a feasible Program end date. 29/8/2018, | 2018-06-30T00:00:00 | Critical | 56286000 |  | Housing and Homelessness Services | 62 | 76536997 |  | G | 1 | Replace the existing ICT housing solution with an integrated ICT system. | 121597695 | 2013-07-01T00:00:00 | HPW
29/8/2018 | QGP | Fleet Management System Replacement Project (FMSRP - Qfleet) | 2019-09-30T00:00:00 | Initiate |  | 2019-09-30T00:00:00 | The project is tracking to plan. The project is currently subject to procurement activities and has commenced lead implementation activities. | 2018-06-30T00:00:00 | High | 13939200 |  | Qfleet | 21 | 655518 |  | G | 2 | The objective of the FMSRP is the procurement and implementation of a new common Fleet Management System that meets QFleet, QPS, QFES and QAS core business requirements and provides best value for money. It will provide a contemporary, sustainable common Fleet Management System that delivers effective and efficient business services for the agencies now and into the future. | 13937796 | 2017-10-19T00:00:00 | HPW
29/8/2018 | QGP | Qfleet Car Sharing Model Implementation Project (CSMIP) | 2018-08-31T00:00:00 | Initiate |  | 2018-08-31T00:00:00 | Procurement activity currently nearing a conclusion. Expecting contract award to occur July/August with implementation to commence soon after. 29/8/2018,The Department has recently updated their publishing criteria for initiatives. This project is publishable under our revised publishing criteria. | 2018-06-30T00:00:00 | High | 454735 |  | Qfleet | 50 | 55665 |  | G | 3 | The objective of the Car Sharing Model Implementation Project (CSMIP) is the procurement and implementation of a fully automated, innovative and sustainable multi-agency car sharing solution delivering effective and efficient short-term motor vehicle hire services for government, now and in the future. | 454735 | 2017-11-20T00:00:00 | HPW
29/8/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Smart Service delivers services on behalf of government via both telephone and counter channels. Some of these services involve financial transactions involving credit card payments. 29/8/2018,The Payment Card Industry (PCI) have stipulated compliance security standards that the government (through Smart Service) has to meet. This project was scoped with ensuring these standards were met. Following a recent external assessment it has been confirmed that this objective has been achieved. The project has completed its planned activities and closed on 29 June 2018. | 2018-06-30T00:00:00 | Critical | 516033 |  | Smart Service Queensland | 100 | 1130918 |  | G | 4 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | HPW
29/8/2018 | SSQ | Automated Payments Solution | 2018-07-31T00:00:00 | Initiate |  | 2018-07-31T00:00:00 | Smart Service Queensland (SSQ) is required to continue to take payments over the phone while remaining Payment Card Industry Data Security Standard (PCI DSS) compliant. 29/8/2018, 29/8/2018,SSQ has commenced the introduction of a VOIP solution to replace the existing analogue telephony capability. This forms the basis of the Telephony Replacement Project (TRP). 29/8/2018, 29/8/2018,To continue to meet ongoing PCI-DSS compliance, additional technology is required to enable secure payments over the phone in a VOIP environment. 29/8/2018, 29/8/2018,The Automated Payment Solution (APS) project will ensure this compliance is maintained and the new technology is implemented. The procurement process is progressing. 29/8/2018, 29/8/2018,Up until June 2018 the APS project has been in a project light, discovery phase - determining if viable solutions were available in the marketplace. This is why the project has reported as amber and the budget spend limited. The project will be re-baselined in July 2018, and a new, more accurate project end date will be determined based upon realistic procurement and implementation timeframes for an off the shelf product. 29/8/2018, | 2018-06-30T00:00:00 | Critical | 1500000 |  | Smart Service Queensland | 5 | 29961 |  | A | 5 | The project will implement an improved capability for offering secure payment card transactions via the telephone. To meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS) when the new VOIP telephony solution is introduced. | 1500000 | 2018-01-29T00:00:00 | HPW
29/8/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | The initial re-planning activity was completed in June 2018. However, further review of the schedule was requested and is underway. Once complete an Exception Report will be created for consideration by the Board. | 2018-06-30T00:00:00 | Critical | 4490634 |  | Smart Service Queensland | 63 | 3729727 |  | A | 6 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 29/8/2018, 29/8/2018,* reduce operating costs 29/8/2018,* increase capacity 29/8/2018,* improve customer experience 29/8/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | HPW
29/8/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Project closure and handover activities are underway. | 2018-06-30T00:00:00 | Critical | 3476245 |  | Smart Service Queensland | 98 | 2083254 |  | G | 7 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2348880 | 2015-11-20T00:00:00 | HPW
29/8/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | SSQ is introducing a new VOIP based telephony platform through the Telephony Replacement Project (TRP). SSQ has also implemented a new agent scripting tool via the Content Delivery Solution (CDS) project. The Technology Platform Project (TPP) is delivering the core underlying technology used by both projects and some other shared ICT centric deliverables, such as Load and Performance Testing, and Security Penetration Testing. The core hardware platform has been successfully delivered and is being utilised by CDS and TRP. The TPP is currently awaiting readiness of some TRP deliverables before progressing the final TPP deliverables. | 2018-06-30T00:00:00 | Critical | 3390862 |  | Smart Service Queensland | 82 | 2435825 |  | A | 8 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution and the call recording solution. | 3390862 | 2017-05-15T00:00:00 | HPW
29/8/2018 | DTS | Digital Archiving Program - Tranche 1 | 2019-12-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | Procurement stage is progressing to planned timeframes and milestones with preferred Offeror identified and contract ready for execution. Government approvals to execute underway. Transition-In planning progressing well. | 2018-06-30T00:00:00 | Critical | 12701000 |  | Digital Technology and Services | 95 | 1872402 |  | G | 9 | To ensure the delivery of an as-a-Service eco-system to effectively archive, manage and enable search and discovery of Queensland's permanent high value records. The new digital services will support the Queensland Government's blueprint for innovation and collaboration, providing better outcomes for Queenslanders. | 12701000 | 2017-07-01T00:00:00 | HPW
29/8/2018 | OSSSIO | Customer Identity and Details Enhancements FY17-18 | 2018-10-30T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | The project is on track to deliver as per the project schedule. 29/8/2018,The Department has recently updated their publishing criteria for initiatives. This project is publishable under our revised publishing criteria. | 2018-06-30T00:00:00 | High | 1200000 |  | One-stop Shop Strategy and Implementation Office | 80 | 1185000 |  | G | 10 | Improved technology and functionality to meet agency requirements in customer identity and details to enable agency adoption and uptake driving further value for customers. 29/8/2018, 29/8/2018,* CDM Blueprint 29/8/2018,* Transition to new platform 29/8/2018,* Auth pilot 29/8/2018,* CDM release 2 pilot | 1200000 | 2017-07-01T00:00:00 | HPW
29/8/2018 | PWAM | Non-Conforming Building Products (NCBP) Website | 2018-08-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | The Safer Buildings website is being developed to support the introduction of proposed changes to the Building Regulation 2006. 29/8/2018,The Department has recently updated their publishing criteria for initiatives. This project is publishable under our revised publishing criteria. | 2018-06-30T00:00:00 | Critical | 770924 |  | Public Works and Asset Management | 50 | 305849 |  | G | 11 | Development of a website (the Safer Buildings Website) for private building owners to register and submit information through a self-assessment checklist to assess their buildings for the existence of potentially combustible cladding. | 770924 | 2018-05-01T00:00:00 | HPW
29/8/2018 | CS | ICT Infrastructure Refresh Project | 2018-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | Progressing as planned. 29/8/2018,The Department has recently updated their publishing criteria for initiatives. This project is publishable under our revised publishing criteria. | 2018-06-30T00:00:00 | Medium | 1173338 |  | Corporate Services | 92 | 647941 |  | G | 12 | To upgrade ICT infrastructure to maintain a fully supported and secure environment and leverage and take advantage of offerings from current DHPW licencing agreements. | 1173338 | 2017-02-13T00:00:00 | HPW
29/8/2018 | ICTSS | Government Wireless Network Contract and Administration Billing System | 2018-06-30T00:00:00 | Initiate |  | 2018-12-31T00:00:00 | There is a requirement to develop a requirements specification for the GWN Wireless Network Contract and Administration Billing System. This has not been completed as it was determined additional resources were required to progress this project i.e. a Project Manager. Originally this digital project was being resourced by existing staff within the GWN Contract Directorate, therefore no expenditure has occurred to date. The procurement process has been delayed for the same reason, but has recommenced now that a Project Manager has been sourced and commenced employment with the GWN Contract Directorate on Monday 13 August. 29/8/2018, | 2018-06-30T00:00:00 | High | 0 |  | ICT Strategic Sourcing | 10 | 0 |  | G | 13 | The GWN Contract Directorate seeks a fully managed software as a service solution to replace existing excel spreadsheets and macros that have organically grown in complexity, improve record keeping compliance, and alleviate current single points of failure and reliance. 29/8/2018,The current contract modification process and Public Safety Agencies (GWN service consumers) invoicing is managed via complicated spreadsheets and macros, colloquially called The Mod Register. The management of contract modifications and invoicing via the Mod Register is manually intensive, cumbersome, is pushing the capabilities of Microsoft Excel, prone to macro errors and due to its size is becoming unwieldly to manage. Also, 29/8/2018,Contractor Performance, including the contractor abatement calculation process, is not centrally managed in one system. A variety of Contractor generated reports are manually validated and reconciled, with problematic auditability. 29/8/2018,Communication of information between GWN Contract Directorate, Public Safety Agencies and Contractor is done via email and attachments of spreadsheets and PDFs in these emails. Management and storage of emails and attachments is problematic, especially version history and control. 29/8/2018,There is now a requirement to procure a purposely designed software system that is fully functional, customisable, redundant, reliable, will meet the current and future requirements of the GWN Contract, and replace current Contract Modification and Contractor Performance processes. | 0 | 2017-11-01T00:00:00 | HPW
29/8/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 29/8/2018, 29/8/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 29/8/2018,October 2017 - The project is progressing as planned. 29/8/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 29/8/2018,June 2017 - Revised Schedule approved returning the project to Green. 29/8/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 29/8/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 29/8/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 29/8/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 29/8/2018,December 2016 - The project is progressing as planned. | 2017-12-21T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 29/8/2018, 29/8/2018,* register and maintain their information 29/8/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
29/8/2018 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 29/8/2018, 29/8/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 29/8/2018,August 2017 - Approved extension of timeframe. 29/8/2018,June 2017 - The project is progressing as planned. 29/8/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 29/8/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 29/8/2018,October 2016 - Progress is continuing as planned. 29/8/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 29/8/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 29/8/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-21T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 29/8/2018, 29/8/2018,* support compliance with legislation 29/8/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 29/8/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 29/8/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 29/8/2018, | 1390000 | 2012-04-01T00:00:00 | DEWS
29/8/2018 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The project is progressing as planned and is on schedule. 29/8/2018, 29/8/2018,July 2018 - The project has re-commenced. Approval has been granted for an extension to the planned end date, and an increase in associated costs. 29/8/2018,June 2018 - Field testing has identified unexpected issues that will impact on the planned end date. Effort is underway with Microsoft to apply a technical fix (patch) to resolve errors. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 29/8/2018,April 2018 - An extension to the planned end date has been approved, returning the project status to Green. 29/8/2018,March 2018 - A minor scope increase has been proposed, affecting both timeframe and cost, which is progressing through the governance process. 29/8/2018,March 2018 - The project is progressing as planned. 29/8/2018,December 2017 - A variation to scope was approved, resulting in a change to the planned end date and total estimated expenditure. 29/8/2018,November 2017 - The project is continuing as planned. 29/8/2018,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2018-08-14T00:00:00 | Medium | 608146 |  | Forestry Queensland | 90 | 999990 |  | G | 1 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 29/8/2018, 29/8/2018,* the capture, management and integration of data 29/8/2018,* value-adding opportunities for business improvement 29/8/2018,* management of risk associated with ongoing use and maintenance of disparate systems. | 1696431 | 2016-06-15T00:00:00 | DAF
29/8/2018 | BQCC | Communication and Stakeholder Engagement Solution | 2018-04-27T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | The project is progessing as planned and is on schedule. 29/8/2018, 29/8/2018,July 2018 - An extension to the planned end date and additional budget has been approved by the governance committee. 29/8/2018,June 2018 - Hidden complexities around integration with other solutions has affect the timing of user acceptance testing and training schedules. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 29/8/2018,May 2018 - A change to the planned end date and cost has been approved. 29/8/2018,March 2018 - Note adjustment to planned end date corrected due to typographical error. 29/8/2018,February 2018 - The project is progressing as planned. 29/8/2018,December 2017 - The project was approved to move into delivery in October 2017 and is being published for the first time. | 2018-08-14T00:00:00 | Medium | 694000 |  | Biosecurity Queensland Control Centre | 90 | 771870 |  | G | 2 | Implement a simple, easy to use system that will facilitate the collection of information associated with the National Red Imported Fire Ant Eradication Program and the National Electric Ant Eradication Program. This will include contact management, complaints management, history of interactions, event management, training management, social media interactions, marketing campaign and reporting. | 1048849 | 2017-06-01T00:00:00 | DAF
29/8/2018 | ASQ | Portfolio Activity Reporting Information System | 2018-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The project is progressing as planned and is on schedule. 29/8/2018, 29/8/2018,June 2018 - Refreshed business case approved, the project has been re-baselined returning it to a Green status. 29/8/2018,May 2018 - Funding has been approved to fully implement the project and it is now in delivery. 29/8/2018,February 2018 - The project is paused until a funding source is identified. 29/8/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-08-14T00:00:00 | High | 978000 |  | Agri-Science Queensland | 10 | 310032 |  | G | 3 | Review and consolidate the variety of processes and technologies currently being used to manage the department's research, development and extension, and other projects. | 978000 | 2015-08-13T00:00:00 | DAF
29/8/2018 | Ag | Risk Reduction for Customer Service Centre | 2019-04-19T00:00:00 | Delivery |  | 2019-04-19T00:00:00 | The project is progressing as planned and is on schedule. 29/8/2018, 29/8/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-08-14T00:00:00 | High | 1767000 |  | Agriculture | 40 | 773858 |  | G | 4 | Implement a solution to mitigate risk of end of life for the agency's call centre logging application. | 1767000 | 2015-01-30T00:00:00 | DAF
29/8/2018 | FQ | Novel Commercial and Recreational Fishing Apps | 2018-09-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | The project was approved to move to delivery in July 2018 and is publishing for the first time. | 2018-08-14T00:00:00 | High | 450000 |  | Fisheries Queensland | 5 | 145954 |  | G | 5 | * Provide up-to-date information on the rules and regulations about fishing and marine park zoning in Queensland 29/8/2018,* Achieve better compliance through access to information 29/8/2018,* Increase uptake of the App by providing regulations from other marine agencies 29/8/2018,* Resolve issues with offline access to information. | 450000 | 2018-02-01T00:00:00 | DAF
29/8/2018 | BQ | Registered Biosecurity Entity (RBE) Renewal Project | 2019-08-30T00:00:00 | Delivery |  | 2019-08-30T00:00:00 | The project was approved to move to delivery in July 2018 and is publishing for the first time. | 2018-08-14T00:00:00 | High | 2821000 |  | Biosecurity Queensland | 5 | 277596 |  | G | 6 | * Develop an efficient end-to-end registration renewal process to allow effective management of renewals 29/8/2018,* Ensure stakeholders are aware of renewal requirements and the importance of maintaining up-to-date information 29/8/2018,* Provide the ability to efficiently communicate with customers about registered biosecurity entity processes and renewals 29/8/2018,* Provide data integration between the online customer portal and the underlying technology solution 29/8/2018,* Minimise administrative overhead. | 2821001 | 2017-11-10T00:00:00 | DAF
29/8/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
29/8/2018 | PSBA | Emergency Services Computer Aided Dispatch (ESCAD) Upgrade Program | 2016-09-30T00:00:00 | Closed |  | 2018-07-03T00:00:00 | The updated ESCAD system cut over for Queensland Ambulance Service (QAS) completed successfully on 17-01-2018, and the Queensland Fire and Emergency Services (QFES) also completed successfully on 24-01-2018. The decommissioning of hardware in the obsolete environments was complete. The Project has concluded on 29-06-2018 as per schedule. 29/8/2018,The ESCAD System Upgrade Project, as major initiative in the program of works, experienced significant technical and implementation issues causing an approved rebaseline in January 2017. This resulted in a revised timeframe from the original plan of 30-09-2016 to 03-07-2018 and a revised approved budget from the original of $6.8 million to $9.4 million for the Program. | 2018-08-17T00:00:00 | Critical | 6774820 |  | Public Safety Business Agency | 100 | 9337507 |  | G | 1 | A program of work for Queensland Ambulance Service and Queensland Fire and Emergency Services to upgrade the Emergency Services Computer Aided Dispatch System, including infrastructure, operating system and application software. | 9380822 | 2015-01-15T00:00:00 | PSBA
29/8/2018 | PSBA | Emergency Vehicle Priority (EVP) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | This reporting period there was a reduction in expenditure due cost recoveries. 29/8/2018, 29/8/2018,EVP rollouts continuing in Rockhampton, Maryborough, Hervey Bay and Gladstone for both Queensland Ambulance Service and Queensland Fire and Emergency Services. Procurement of a managed service for operational support and maintenance in progress with implementation and project closure scheduled for completion October 2018. Procurement of the managed service has required an extension of the project scope and schedule. This resulted in a revised timeframe from the original planned end date of 30-06-2017 to 31-10-2018, and a revised budget from the original expenditure plan of $3.4 million to $4.4 million. The approved/planned expenditure figure has been realigned from the estimate at completion to the total project budget, resulting in a $12,366 difference. 29/8/2018,Deferral of $54,315 is pending approval from Treasury. | 2018-08-17T00:00:00 | High | 3370000 |  | Public Safety Business Agency | 94 | 4128398 |  | G | 2 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 29/8/2018, 29/8/2018,* Responsive vehicle movements 29/8/2018,* Improve road safety 29/8/2018,* Congestion management 29/8/2018,* Community safety | 4382697 | 2013-01-01T00:00:00 | PSBA
29/8/2018 | PSBA | Inter-CAD Electronic Messaging System (ICEMS) | 2016-08-31T00:00:00 | Closed |  | 2018-03-16T00:00:00 | The ICEMS system cut over for Queensland Police Service (QPS) and Queensland Ambulance Service (QAS) completed successfully on 28-07-2017, and ICEMS for the Queensland Fire and Emergency Services (QFES) completed successfully on 24-01-2018. Project closure activities have finalised. The ICEMS Project experienced significant technical and implementation issues causing multiple approved re-baselines between November 2015 and September 2017. This resulted in a revised timeframe from the original planned end date 31-08-2016 to 16-03-2018 and a revised budget from the original planned expenditure of $560K to $1,571K. Further to this, a scope change was undertaken in 2016 to extend ICEMS messaging. The Priority of this initiative has been re-assessed to Medium. The approved/planned expenditure figure has been realigned from the estimate at completion to the total project budget, resulting in a $19,860 difference. 29/8/2018, 29/8/2018,ICEMS End Project Report approved. 29/8/2018,Confirmation and approval from PSBA, QPS Project Management Office, QFES and QAS that the ICEMS Project is completed and closed. | 2018-08-17T00:00:00 | Medium | 560000 |  | Public Safety Business Agency | 100 | 1570688 |  | G | 3 | To implement the ICEMS protocol between the Queensland Police Service (QPS), Queensland Ambulance Service (QAS) and Queensland Fire and Emergency Services (QFES) computer aided dispatch systems to enable Triple Zero data sharing between agencies. | 1591000 | 2015-10-06T00:00:00 | PSBA
29/8/2018 | PSBA | QFES Office 365 Implementation Project | 2018-06-30T00:00:00 | Closed |  | 2018-06-29T00:00:00 | Project has completed. | 2018-08-17T00:00:00 | Medium | 2100000 |  | Public Safety Business Agency | 100 | 1172090 |  | G | 4 | This project will deliver the most up-to-date Office 365 suite of products to all Queensland Fire and Emergency Services (QFES) staff and enable QFES to mobilise its workforce. 29/8/2018, 29/8/2018,* Upgrade QFES technology fleet to the latest Microsoft Office version 29/8/2018,* Cloud services will enable mobility 29/8/2018,* Bridge the technology gaps between Public Safety Agencies (PSA) and allow better collaboration | 1182000 | 2017-11-01T00:00:00 | PSBA
29/8/2018 | PSBA | QPS Office 365 Implementation Project | 2018-02-28T00:00:00 | Closed |  | 2018-06-29T00:00:00 | Project Complete. 29/8/2018, 29/8/2018,The original planned end date of 28-02-2018 has been re-baselined to 30-06-2018 due to delivery of additional scope | 2018-08-17T00:00:00 | Medium | 2207000 |  | Public Safety Business Agency | 100 | 1798019 |  | G | 5 | Phase 1 - Mail Migrations 29/8/2018,The objective of the Queensland Police Service (QPS) Office 365 Implementation Project Phase 1 is to complete the following activities prior to the Frontline and Digital Services Commonwealth Games Change Freeze (mid Feb 2018): 29/8/2018, 29/8/2018,* migrate email, contacts and calendars to Office 365 online services for all QPS staff; and 29/8/2018,* enable anywhere, anytime, any device access to email, contacts and calendar via bring your own (BYO) phone, QPS Officers operational tablets (QLiTEs) and home-use for all QPS staff 29/8/2018, 29/8/2018,Phase 2 - a data migration and a pilot migration of email archives to Office 365 online | 2207000 | 2017-09-07T00:00:00 | PSBA
29/8/2018 | OSR | State Penalties Enforcement Registry (SPER) Program | 2017-12-31T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | Expenditure to date - $31.3M has been for the transformation of the SPER function, and $20.3M has been on the build phase of the ICT implementation. The broader SPER transformation program commenced in 2014, with the first stage focussed on building foundational capability. This next phase was the implementation of the new system solution (ICT SaaS) which commenced in 2016. 29/8/2018,Variation - In December 2017 the SPER Program completed a re-baselining effort which approved changes to scope, timing and costs. These changes were made to better reflect an enhanced delivery model, requiring system modifications that support improved business functionality. | 2018-07-30T00:00:00 | High | 47200000 |  | State Penalties Enforcement Registry | 79 | 51641000 |  | A | 1 | To maintain the integrity of fines as an effective sanction. 29/8/2018,To uphold confidence in the justice system. 29/8/2018,To deliver efficient and effective debt management practices which provide value for money to the State. 29/8/2018, | 62150000 | 2014-01-01T00:00:00 | QR
29/8/2018 | RI | Financial Assurance Information Registry (FAIR) | 2018-07-01T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Project cost as at end of July 2018 is $7.315.000. The FAIR project was due to be completed by 1 July 2018 to align with commencement of the Financial Provisioning Scheme (FPS). The delivery delay event is marked yes due to a deferral of the legislation to enact the FPS which would permit the scheme to commence. The FAIR project will be operational for FPS commencement. 29/8/2018,The FAIR project required for the FPS commencement is 90 percent complete. Other components of the FPS reforms will be completed in subsequent years. | 2018-07-30T00:00:00 | Medium | 15900000 |  | Insurance Commission | 90 | 7315000 |  | G | 2 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
29/8/2018 | RI | Information Security Program | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 |  | 2018-07-31T00:00:00 | Medium | 1960000 |  | Office of the Chief Information Officer | 45 | 642500 |  | G | 3 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 29/8/2018, | 1960000 | 2017-10-16T00:00:00 | QR
29/8/2018 | OSR | Office of State Revenue (OSR) Transformation Program | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | Multiple initiatives in progress focussing on machine learning, analytics, data quality, and business process improvements. Overall program is on track. | 2018-07-30T00:00:00 | High | 73548000 |  | Office of State Revenue | 22 | 13538135 |  | G | 4 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 29/8/2018, 29/8/2018,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 73548000 | 2017-08-01T00:00:00 | QR
29/8/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
29/8/2018 | Corporate Services Improvement Program | Lotus Notes Decommissioning | 2016-01-31T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project commenced in October 2015 when concept and stage 1 was approved to engage and investigate business findings around the decommission of legacy lotus notes databases. 29/8/2018,In July 2016, three additional stages aligning to three financial years from 2016/17 through to 2018/19 were further approved via a project initiation and business case. 29/8/2018,Stage 2, 2016/17, focused on analysis and stakeholder engagement to form the scope of the project and define functionality and business requirements for individual applications. 29/8/2018,Stage 3, 2017/18, focused on proof of concepts to inform and validate the plan for stage 4 in 2018/19. The project was impacted in 2017/18 by several resourcing issues, including the departure of the original project manager. 29/8/2018,The project is scheduled to complete work and close down by 30 June 2019, with the exception of the migration of files from the department's legacy Document Management System (DMS). The migration of the DMS will align with the Integrated Records and Information System (IRIS) program and should be complete by the end of 2019. | 2018-06-30T00:00:00 | High | 8150000 |  | ERP Projects Board | 52 | 2729463 |  | G | 1 | Deliver improved information platform functions for effective ICT Strategy Alignment | 8150000 | 2015-11-01T00:00:00 | TMR
29/8/2018 | Corporate Services Improvement Program | Stop Cheques - Stage 3 | 2018-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Project successfully closed on time and within budget. Project was originally proposed in February 2015 for stage 1, with project brief and project initiation documentation approved in April 2015. Stage 1 was successfully closed out in March 2016. Stage 2 was approved in April 2016, and successfully closed out 30 June 2017. Stage 3 (2017-18) commenced 1 July 2017 and successfully closed 29 June 2018. 29/8/2018,Customers are already experiencing the increased convenience and reduction of costs resulting from reduced out-bound cheques, which include deceased estate cheques, cheques to known vendors, and the expansion of products available for refund at counter such as registration refunds and concessions. | 2018-06-30T00:00:00 | Medium | 200000 |  | ERP Projects Board | 100 | 200004 |  | G | 2 | Cheques are inefficient and costly to use, process and administer for both the customer and department. A range of solutions have been developed to reduce the number of cheques that the department produces or receives including refund to card at counter, Bulk Bpay solutions and the introduction of new payment methods are being delivered to be more in line with contemporary retail offerings. The outsourcing of cheque production produced a more streamlined process. 29/8/2018,The stop cheques initiative includes 3 elements: 29/8/2018,Outsourcing/cost reduction 29/8/2018,Outbound cheques 29/8/2018,Inbound cheques | 200000 | 2017-07-01T00:00:00 | TMR
29/8/2018 | Corporate Services Improvement Program | Risk Management Solution | 2018-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Project successfully closed on time and within budget. Project was proposed in February 2016, with the project brief and budget for stage 1 (2016-17) approved in October 2016 for $350,000. Stage 1 successfully closed 30 June 2017 with an underspend of $98501. Stage 2 (2017-18) was approved in March 2017 for $710,000, and commenced 1 July 2017. Stage 2 and the project successfully closed 22 June 2018 with an underspend of $1,887. 29/8/2018,The new online enterprise risk management system (RMS) provides significant improvements in efficiency for risk recording and monitoring, and provides increased transparency on risks, risk owners and treatment responsibilities, raising the overall risk maturity at significantly lower, ongoing cost. 29/8/2018, | 2018-06-30T00:00:00 | High | 350000 |  | Corporate Services Improvement Program | 100 | 959610 |  | G | 3 | Replace the current risk management approach through the delivery of a new and contemporary enterprise Risk Management solution for TMR . | 1024435 | 2016-02-01T00:00:00 | TMR
29/8/2018 | Corporate Services Improvement Program | Integrated Records Information System (IRIS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | In response to an internal audit review of review of Transport and Main Road's (TMR) Document Management System (DMS) the Integrated Records and Information System (IRIS) project was stood up in 2015. An opportunity to further leverage functionality requirements, TMR's Executive Correspondence System (ECS) replacement was also included into scope. 29/8/2018,IRIS project was reviewed in 2017 to ensure achievability, and as a result the project budget was decreased from $7,967,972 down to $6,865,000 (plus contingency) of 10%. 29/8/2018,In April 2018, a scope change with $567,500 budget increase was approved to include the delivery of a General Correspondence System deliverable to the project, maximising return on investment and better outcomes for the customer, bringing total budget to $7,432,500 excluding contingency. | 2018-06-30T00:00:00 | High | 7967972 |  | Information Technology Branch | 35 | 5500321 |  | G | 4 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 7432500 | 2015-07-01T00:00:00 | TMR
29/8/2018 | Corporate Services Improvement Program | Safety System Replacement | 2018-07-30T00:00:00 | Delivery |  | 2018-07-30T00:00:00 | Project is on track to close on time and within budget. A new Workplace Health and Safety (WHS) solution has been procured, implemented and declared production ready 28 June 2018. It provides a contemporary workflow based approach to the recording and management of hazards and incidents, safety conversations, and claims and rehabilitation. The solution is cloud based and offers functionality to support the Departments mobile workforce. 29/8/2018, | 2018-06-30T00:00:00 | Low | 680000 |  | Corporate Services Improvement Program | 98 | 688558 |  | G | 5 | The objective of the SSR project is to replace the current Work Health and Safety ICT solution with an industry standard, cost-effective safety management solution that will enable TMR to meet its obligations under the Work Health and Safety 2011 Act, the Right to Information, Information Privacy legislation and the Workers Compensation and Rehabilitation Act 2003 (Qld). | 680000 | 2016-12-05T00:00:00 | TMR
29/8/2018 | Corporate Services Improvement Program | TSIP Enhancements - Stage 3 | 2018-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Project successfully closed on time and within budget. Project was originally proposed in February 2015 for stage 1, with project brief and project initiation documentation approved in April 2015. Stage 1 was successfully closed out in March 2016. Stage 2 was approved in April 2016, and successfully closed out 30 June 2017. Stage 3 (2017/18) commenced 1 July 2017 and successfully closed 29 June 2018. 29/8/2018,The project added real value and efficiencies through reduced overheads within the department, such as the introduction of web-based Heavy Vehicle Permits. and Improvements were also made to multiple transactional services relating to payments and receipts from customers such as the additional payment options of payWave and AMEX. | 2018-06-30T00:00:00 | Low | 200000 |  | Transactional Services Improvement Program | 100 | 199878 |  | G | 6 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. | 200000 | 2017-07-01T00:00:00 | TMR
29/8/2018 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | This commenced in July 2016 with delivery being phased in accordance with the development of the business processes. Original expenditure was 1.5M which has been revised to 1.441M on finalisation and approval of the business case. Phase 1 was completed in July 2017 and the schedule was adjusted in June 2017 to enable the delivery of the Phase 2 capability in late 2018. 29/8/2018, 29/8/2018,The project is currently on track. | 2018-06-30T00:00:00 | High | 1500000 |  | Customer Services, Safety and Regulation Division | 90 | 999274 |  | G | 7 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal services currently required. | 1441000 | 2016-01-01T00:00:00 | TMR
29/8/2018 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project commenced in mid-2015 for delivery scheduled for mid-2016. Due to the uncertainty of the solution outcome and market capability the project undertook an extensive market engagement and procurement process resulting in the schedule being extended 11 months and the budget increased from $2.5M to $4.1M in January 2017. 29/8/2018, 29/8/2018,Pending the successful completion of final testing and the formal launch of the system the project remains on track for public release from August 2018. 29/8/2018, | 2018-06-30T00:00:00 | High | 2500000 |  | Customer Services, Safety and Regulation Division | 96 | 4176989 |  | G | 8 | Implement an online learning and assessment program at the pre-learner and/or learner stage, to replace enhance learning outcomes. | 4176000 | 2015-06-12T00:00:00 | TMR
29/8/2018 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery |  | 2018-06-28T00:00:00 | This commenced in November 2016 with planned completion in mid-2017. Due to an extended procurement process, and the need to include analytical functionality, the schedule was extended 12 months and the budget increased from $300k to $894k in August 2017. The capability was delivered as scheduled in June 2018 and the project is presently finalising closure with formal closure scheduled for August 2018. | 2018-06-30T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 99 | 986706 |  | G | 9 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 894071 | 2016-11-01T00:00:00 | TMR
29/8/2018 | Customer Service, Safety and Regulation Program | Call Centre VOIP Upgrade | 2018-06-30T00:00:00 | Delivery |  | 2018-08-15T00:00:00 | This commenced in July 2017 with delivery scheduled for mid-2018. Due to vendor resourcing issues approval was provided in May 2018 for the project to deliver the capability in early FY18/19. The project is currently on track for delivery. | 2018-06-30T00:00:00 | Low | 1140000 |  | Customer Services, Safety and Regulation Division | 75 | 1072928 |  | G | 10 | The Call Centre VOIP Upgrade has commenced to upgrade the VOIP telephony platform within the department. The proposed solution will see a reduction in call costs, a shift in capability to a 29/8/2018,contemporary solution utilising an existing investment within the department. | 1140000 | 2017-04-01T00:00:00 | TMR
29/8/2018 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The RALPH project commenced in July 2016. Due to vendor software development issues, changes to the schedule and budget were approved in June 2017 with a planned completion to occur by 30 June 2018. A further extension was approved for an additional two months. The project remains on track for closure in August 2018. | 2018-06-30T00:00:00 | Medium | 500000 |  | Customer Services, Safety and Regulation Division | 81 | 693683 |  | G | 11 | TMR's current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace the existing application with a contemporary and supportable alternative to assist the department in maintaining its timely updating of fees and charges. | 734000 | 2016-07-01T00:00:00 | TMR
29/8/2018 | Customer Service, Safety and Regulation Program | Voice Comms Mgt System | 2017-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | The Voice Comms Management System project commenced in Jan 2017 for completion by mid-2018 however resource availability was impacted due to Cyclone Debbie. Delivery of the capability was completed in April 2018 with the project being formally closed on 5 July 2018. | 2018-06-30T00:00:00 | Medium | 828000 |  | Customer Services, Safety and Regulation Division | 100 | 274738 |  | G | 12 | The Voice Comms Management project consists of two replacement of existing Voice Communication and Control Systems at Townsville and Hay Point. | 828000 | 2016-01-01T00:00:00 | TMR
29/8/2018 | Customer Service, Safety and Regulation Program | Registration and CTP Certificates Online | 2017-12-31T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | The Registration and CTP Certificates Online project commenced in May 2017 as two separate initiatives - Registration Online and CTP Tax Invoice Online. Due to common system synergies the projects were merged in March 2018 resulting in the closure date being revised in accordance with the CTP component. The project is on track for closure in late 2018. | 2018-06-30T00:00:00 | Medium | 450000 |  | Customer Services, Safety and Regulation Division | 41 | 404349 |  | G | 13 | Reduce the volume of mail sent by post by developing new online services allowing CTP Tax Invoices and Registration Certificates to be generated online | 450000 | 2017-05-01T00:00:00 | TMR
29/8/2018 | Customer Service, Safety and Regulation Program | Vessel Traffic Services (VTS) | 2016-01-05T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | Pre-project work commenced in April 2014 with the initiation of the current project commencing in July 2016. The original budget of $15.2M was rebaselined to $36.2M once the post-market business case was finalised and approved to proceed in April 2017. 29/8/2018, 29/8/2018,The project is on track for delivery in mid 2019. | 2018-06-30T00:00:00 | High | 15224694 |  | Customer Services, Safety and Regulation Division | 35 | 7490606 |  | G | 14 | The purpose of the project is procure and implement a replacement decision support tool for the existing Vessel Traffic Service (VTS) used by TMR to track and monitor ship movements within Queensland ports, the Great Barrier Reef and the Torres Strait. | 36228184 | 2014-04-14T00:00:00 | TMR
29/8/2018 | Customer Service, Safety and Regulation Program | R and L Systems Software Upgrade - Stage 2 | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The R and L System Software Upgrade project commenced in July 2017. The original budget of $780K was rebaselined to $1.255M once the post-market business case was finalised and approved to proceed in September 2017. Delivery was completed as scheduled in June 2018 with the project now undergoing closure. | 2018-06-30T00:00:00 | Medium | 780000 |  | Customer Services, Safety and Regulation Division | 87 | 1115666 |  | G | 15 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
29/8/2018 | Customer Service, Safety and Regulation Program | Customer Flow Management and Reporting System - OP | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | Pre-project work commenced during FY15/16 with the initiation of the current project commencing in July 2017. The original budget of 300K was rebaselined to 3M once the post-market business case was finalised and approved to proceed in May 2018. 29/8/2018,The project is on track for delivery to occur within FY18/19. | 2018-06-30T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 52 | 367537 |  | G | 16 | The objective of this project is to replace the existing Qmatic systems throughout the entire network Customer Service sites, with a supported enterprise solution that meets TMRs current and future needs. | 3083000 | 2015-09-01T00:00:00 | TMR
29/8/2018 | Infrastructure Management and Delivery | Work Improvement Note (WIN) Replacement | 2016-12-19T00:00:00 | Closed |  | 2018-02-27T00:00:00 | The project successfully delivered a new Work Improvement Notice system using SharePoint and K2 technology and has now closed. The original project end date moved from December 2016 to February 2018 as a result of delays experienced during software development, which were identified and resolved through iterative user testing and issue rectification. The increase in project budget was a product of the schedule delay. | 2018-06-30T00:00:00 | Low | 242612 |  | Infrastructure Management 29/8/2018,and Delivery | 100 | 358229 |  | G | 17 | The Work Improvement Note (WIN) System is used to capture, track, review and report on improvements, potential problems, non-conformances, corrective actions, customer feedback and complaints. The WIN System is an essential component of the overarching business management system as it meets specific certification requirements outlined in international quality, safety and environmental standards. This project will provide a replacement to the existing Work Improvement Note (WIN) system, which is dependent on unsupported technology. | 436375 | 2016-02-15T00:00:00 | TMR
29/8/2018 | Passenger Transport Technology Program | Single Integrated Network Project (SNIP) | 2018-09-29T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | Final testing of the transport schedule system is planned to be completed this month with implementation in TransLink planned for August. | 2018-06-30T00:00:00 | High | 4992243 |  | Passenger Transport Technology Program | 30 | 690580 |  | G | 18 | Have a system in place that is consistent and integrated across service providers and TransLink. 29/8/2018,Ensure business continuity of systems. 29/8/2018,Extend the existing scheduling and network capability solution to enable it to be ready for the bus contracts (SEQBCPP). 29/8/2018,Eliminate inefficiencies and inaccuracies that occur in the current processes and dispersed data entry options. 29/8/2018,Transparency of service providers activities and performance. 29/8/2018,To improve customer experience through more accurate and reliable service information. 29/8/2018,Contributor for achieving Government objectives. 29/8/2018, | 4992243 | 2017-02-23T00:00:00 | TMR
29/8/2018 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Original project commenced in April 2016. 29/8/2018,Cost estimates were revised in November 17. 29/8/2018,In March 18 issues in gathering business data and requirements for new functionality identified. 29/8/2018,The STAS project is reporting amber as a result of unforeseen complexities associated with provisioning and transitioning of business supplied data to the new platform. The project is experiencing delays as resolution activities take place to ensure a good customer experience when the project is released to the public. 29/8/2018,An Exception Report will be considered by the PTT board to enable products to be completed and released by end of March 2019. | 2018-06-30T00:00:00 | High | 4166000 |  | TransLink | 75 | 5014390 |  | A | 19 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 5303876 | 2016-04-01T00:00:00 | TMR
29/8/2018 | Policy Planning and Investment Program | Portfolio, Program, Project and Contract Management (3PCM) - Phase 2 and 3 | 2017-03-31T00:00:00 | Closed |  | 2017-12-22T00:00:00 | The Portfolio, Program, Project and Contract Management (3PCM) project commenced in 2012 with an initial original planned expenditure of $12,757,788. The initial estimate uploaded for 3PCM intentionally included only the project initiation, market assessment and business case development. The estimate was clarified at the end of contract negotiations in the post-market business case and revised to $47,908,928. The Portfolio, Program, Project and Contract Management (3PCM) project has successfully completed its scope and the Program Board endorsed the project closure report in July 2018. The Portfolio, Program, Project and Contract Management (3PCM) project will report for one additional reporting period prior to being removed from the QG ICT Dashboard. | 2018-07-16T00:00:00 | High | 12757788 |  | Policy, Planning and Investment Division | 100 | 47794126 |  | G | 20 | Define and implement standard, consistently applied processes for planning, managing and delivering the Transport Infrastructure Portfolio across the domains of portfolio, program, project and contract management 29/8/2018,Source and implement an integrated, strategic information communication technology solution that supports the business process and rules and enables a transition away from legacy applications | 47908928 | 2012-09-01T00:00:00 | TMR
29/8/2018 | CS | Asset Assessment System | 2016-06-30T00:00:00 | Delivery |  | 2018-08-06T00:00:00 | The project is tracking to plan. | 2018-07-09T00:00:00 | High | 1688788 |  | Corporate Services | 92 | 1817346 |  | G | 1 | To improve the reliability and integrity of asset information, the ability to report on asset information by applying best practice asset management principles. | 2059995 | 2014-02-27T00:00:00 | DET
29/8/2018 | CS | Automated Website Provisioning Tool | 2017-08-18T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | The project moved into Delivery in June 2018. The project is tracking to plan. | 2018-07-09T00:00:00 | Medium | 1300000 |  | Corporate Services | 86 | 1092153 |  | G | 2 | To reduce the cost and time required to create new school and corporate websites by developing a tool that provisions new websites from a suite of reusable website templates. | 1242160 | 2017-04-03T00:00:00 | DET
29/8/2018 | PPP | Customer Complaints Management System | 2018-12-21T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | The project moved into Delivery in June 2018. The project is tracking to plan. | 2018-07-09T00:00:00 | Medium | 2753000 |  | Policy, Performance and Planning | 65 | 556465 |  | G | 3 | Improve the management and reporting of customer complaints. | 2753000 | 2017-09-11T00:00:00 | DET
29/8/2018 | SS | Early Start | 2015-07-03T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | The project is tracking to plan. The end date change to 30/11/2018 has been approved by the project board. | 2018-07-09T00:00:00 | High | 70000 |  | State Schools | 73 | 73522 |  | G | 4 | To provide schools with enhanced reporting functionality, improving their ability to analyse Prep to Year 2 student learning data. | 200992 | 2013-04-03T00:00:00 | DET
29/8/2018 | PPP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Delivery |  | 2018-09-14T00:00:00 | The project is tracking to plan. The end date change to 14/09/2018 has been approved by the project board. | 2018-07-09T00:00:00 | Medium | 700000 |  | Policy, Performance and Planning | 97 | 1472845 |  | G | 5 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
29/8/2018 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery |  | 2018-12-07T00:00:00 | The project is tracking to plan. The project is undergoing procurement/commercial activities with no financial information being published. | 2018-07-09T00:00:00 | Medium | 0 |  | Corporate Services | 71 | 0 |  | G | 6 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DET FBS SAP future state landscape for the next five years | 0 | 2017-01-16T00:00:00 | DET
29/8/2018 | CS | Injury Management System | 2017-03-27T00:00:00 | Delivery |  | 2018-10-01T00:00:00 | The project is tracking to plan. The end date change to 1/10/2018 has been approved by the project board. | 2018-07-09T00:00:00 | Medium | 1900000 |  | Corporate Services | 66 | 1418676 |  | G | 7 | To improve the management of workplace rehabilitation and claims for injured/ill staff | 1828676 | 2016-10-10T00:00:00 | DET
29/8/2018 | ODG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery |  | 2018-10-01T00:00:00 | The project is tracking to plan. | 2018-07-09T00:00:00 | Medium | 632585 |  | Office of the Director-General | 91 | 877369 |  | G | 8 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
29/8/2018 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | The project is tracking to plan. | 2018-07-09T00:00:00 | Medium | 16670000 |  | State Schools | 55 | 11683881 |  | G | 9 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 18708059 | 2015-08-03T00:00:00 | DET
29/8/2018 | PPP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery |  | 2019-05-31T00:00:00 | The project is tracking to plan.The end date change to 31/05/2019 has been approved by the project board. 29/8/2018, | 2018-07-09T00:00:00 | Medium | 1502300 |  | Policy, Performance and Planning | 97 | 1250201 |  | G | 10 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution | 1266210 | 2016-03-01T00:00:00 | DET
29/8/2018 | PPP | Redevelopment of the Policy and Procedure Register | 2018-03-30T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | The project moved into Delivery in June 2018. The project is being closely monitored for cost, quality and schedule. | 2018-07-09T00:00:00 | Medium | 1015000 |  | Policy, Performance and Planning | 69 | 820953 |  | A | 11 | The high level principles endorsed by EMB for the policy management framework which provides the foundation for this initiative include a consistent user experience for customers, regardless of who they are, where they work, and what they may be looking for; a single point of truth, providing access to all departmental policies and procedures; and publish once, with multiple links where appropriate; and that content is authoritative, relevant and meets quality standards for publication, enabling staff and stakeholders to make good decisions. 29/8/2018, | 652238 | 2016-10-13T00:00:00 | DET
29/8/2018 | SS | Trial of Platform for Virtual Academies | 2017-10-02T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | The project is tracking to plan. | 2018-07-09T00:00:00 | Medium | 151641 |  | State Schools | 81 | 236700 |  | G | 12 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage; safe and secure like-minded student virtual communities; and strategic partnerships with university, industry and business. 29/8/2018, 29/8/2018, | 141641 | 2016-06-21T00:00:00 | DET
29/8/2018 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project is tracking to plan. The end date change to 28/06/2019 has been approved by the project board. | 2018-07-09T00:00:00 | High | 41000000 |  | Corporate Services | 83 | 34998163 |  | G | 13 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
29/8/2018 | [20 empty] | INVERSTMENT INFO
29/8/2018 | ICRM | Integrated Customer and Revenue Management (ICRM) | 2021-06-30T00:00:00 | Delivery |  | 2021-06-30T00:00:00 | This project is reporting for the first time and is progressing as planned. | 2018-08-17T00:00:00 | High | 24511345 |  | DNRM Finance | 6 | 3140063 |  | G | 1 | Improvements to the way the agency handles revenue collection: 29/8/2018, 29/8/2018,* selection of a modern, enterprise-class, integrated customer and revenue management solution 29/8/2018,* implementation and deployment of the solution to at least replace the use of the current at-risk receipting systems (LAIS and MERLIN). | 24511345 | 2017-01-01T00:00:00 | DNRM
29/8/2018 | LSI | Queensland Globe improvements | 2018-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Project closed on 10 August 2018. 29/8/2018, 29/8/2018,July 2018 - All deliverables have been achieved. Project closure activities are currently under way. 29/8/2018, 29/8/2018,May 2018 - The project is continuing as planned. 29/8/2018, 29/8/2018,December 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-08-17T00:00:00 | High | 1002450 |  | Land and Spatial Information | 100 | 992226 |  | G | 2 | Enhancements to Queensland Globe to continue to evolve and improve user satisfaction and experience, such as: 29/8/2018, 29/8/2018,* create and save user-defined topics 29/8/2018,* improve query and access 29/8/2018,* provide editable 'redlining' 29/8/2018,* improve data imports. | 1002450 | 2017-10-09T00:00:00 | DNRM
29/8/2018 | QWSR | Dam Safety Regulation Solution | 2016-10-30T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | A change request has been approved altering the planned end date to enable completion of end project activities. 29/8/2018, 29/8/2018,July 2018 - All deliverables have been achieved. Project closure activities are currently under way. 29/8/2018, 29/8/2018,June 2018 - A change request has been approved altering the planned end date to remediate technical difficulties that have been experienced in the move to production. 29/8/2018, 29/8/2018,May 2018 - The project is continuing within timeframe tolerance, and is expected to close prior to the end of May 2018. 29/8/2018, 29/8/2018,March 2018 - The project is continuing as planned. 29/8/2018, 29/8/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 29/8/2018, 29/8/2018,August 2017 - Approved extension of timeframe. 29/8/2018, 29/8/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 29/8/2018, 29/8/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 29/8/2018, 29/8/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 29/8/2018, 29/8/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 29/8/2018, 29/8/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2018-08-17T00:00:00 | High | 1390000 |  | Queensland Water Supply Regulator | 98 | 1385060 |  | G | 3 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 29/8/2018, 29/8/2018,* support compliance with legislation 29/8/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 29/8/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 29/8/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. | 1390000 | 2012-04-01T00:00:00 | DNRM
29/8/2018 | Natural Resources | Land Condition Assessment Tool | 2018-04-30T00:00:00 | Delivery |  | 2018-09-26T00:00:00 | The project is continuing as planned, tracking within tolerances for time, cost and quality. 29/8/2018, 29/8/2018,June 2018 - A change request has been approved altering the planned end date and budget to allow for resolution of unforeseen complexities in deliverables. 29/8/2018, 29/8/2018,May 2018 - The project timeframe is currently being monitored, with action under way to return it to Green. 29/8/2018, 29/8/2018,April 2018 - This project is reporting for the first time and is progressing as planned. | 2018-08-17T00:00:00 | Medium | 414000 |  | Operations Support | 73 | 117960 |  | G | 4 | Implement a solution for government, industry and other stakeholders to objectively and consistently assess land conditions, including development of a pictogram-based mobile web application and a data collection tool. | 479000 | 2017-01-12T00:00:00 | DNRM
29/8/2018 | CWeHR | Coal Workers eHealth Records Project | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | This project is reporting for the first time and is progressing as planned. Note, finances reported represent Stage 0 and Stage 1. | 2018-08-17T00:00:00 | High | 3894285 |  | Occupational Health and Hygiene - Resources Safety and Health | 5 | 714000 |  | G | 5 | Improvement in data management and surveillance for coal mine worker health assessments: 29/8/2018, 29/8/2018,* new customer digital interface 29/8/2018,* improved health assessment outcomes through improved access to longitudinal health records 29/8/2018,* enable industry-wide health surveillance through electronic storage and access to health records 29/8/2018,* improved data management using appropriate health management systems and alignment with health record management requirements. | 3894285 | 2017-03-23T00:00:00 | DNRM
29/8/2018 | SO | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery |  | 2019-03-29T00:00:00 | The project is continuing as planned, tracking within tolerances for time, cost and quality. 29/8/2018, 29/8/2018,February 2018 - A change request was approved to alter the scope and associated percentage complete, time-frame and costs. 29/8/2018, 29/8/2018,December 2017 - Awaiting confirmation of project closure; project is still operating within approved time-frame tolerance. 29/8/2018, 29/8/2018,November 2017 - A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 29/8/2018, 29/8/2018,October 2017 - The project is continuing as planned. 29/8/2018, 29/8/2018,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2018-08-17T00:00:00 | High | 563000 |  | SIMTARS (Safety In Mines Testing and Research Station) | 69 | 801703 |  | G | 6 | The development and delivery of a (replacement) modern and robust Safegas solution: 29/8/2018, 29/8/2018,* risk reduction increasing capability to manage the volume of queries, transactions and data 29/8/2018,* decrease database corruption related to incidents. | 1170000 | 2017-01-25T00:00:00 | DNRM
29/8/2018 | MIRM | Mines Infrastructure Risk Mitigation Project | 2019-02-18T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | The project is continuing as planned, tracking within tolerances for time, cost and quality. 29/8/2018, 29/8/2018,April 2018 - A minor adjustment to scope has been approved; there is no impact to timeframe or cost. 29/8/2018, 29/8/2018,March 2018 - The project is continuing as planned. 29/8/2018, 29/8/2018,November 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-08-17T00:00:00 | High | 1200000 |  | Statewide Operations | 75 | 593984 |  | G | 7 | Migrate systems to supported infrastructure and software to: 29/8/2018, 29/8/2018,* provide a stable, secure, fully supported and flexible solution 29/8/2018,* eliminate the risks to which the geoscience data assets are currently exposed. | 1200000 | 2017-08-08T00:00:00 | DNRM
29/8/2018 | DPC | Performance Information Management System (PIMS) Dynamics 365 upgrade and relocation | 2018-10-30T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | The project commenced in May 2018 and is on track for delivery. The Discovery Phase has been completed and the scope of work for the upgrade project finalised. 29/8/2018,The PIMS Upgrade Oversight Group is meeting regularly to oversee implementation. Development work and initial system testing has been completed. User acceptance testing is underway | 2018-08-01T00:00:00 | High | 240494 |  | Premier and Cabinet | 70 | 78063 |  | G | 1 | To upgrade the existing PIMS solution from the current 2013 version to Microsoft Dynamics 365 and move the system to Microsoft Online. | 240494 | 2018-05-01T00:00:00 | DPC
29/8/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
29/8/2018 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 29/8/2018,* Move operational accountability and responsibility for print and imaging devices to the service provider 29/8/2018,* Reduce print and imaging costs 29/8/2018,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
29/8/2018 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
29/8/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
29/8/2018 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 29/8/2018, 29/8/2018,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
29/8/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
29/8/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 29/8/2018, 29/8/2018,* reduce operating costs 29/8/2018,* increase capacity 29/8/2018,* improve customer experience 29/8/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
29/8/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
29/8/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 29/8/2018, 29/8/2018, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
29/8/2018 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 29/8/2018, 29/8/2018,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
29/8/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
29/8/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 29/8/2018, 29/8/2018,November 2017 - Actual cost to date corrected due to input error. 29/8/2018, 29/8/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 29/8/2018, | 2017-12-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 57 | 733941 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
29/8/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | An extension to the timeframe has been approved to allow for closure activities to be finalised. 29/8/2018, 29/8/2018,July 2018 - Key deliverables have been achieved within project time-frames. Project closure activities are under way, to be finalised within the next two weeks. 29/8/2018, 29/8/2018,June 2018 - User acceptance testing is almost complete; the solution is about to move into production with project closure activities under way. 29/8/2018, 29/8/2018,May 2018 - The project is progressing as planned. 29/8/2018, 29/8/2018,November 2017 - Actual cost to date corrected due to input error. 29/8/2018, 29/8/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. | 2018-08-14T00:00:00 | Medium | 1750000 |  | Queensland Parks and Wildlife Service | 98 | 1209048 |  | G | 1 | Acquire one or more solution components to operate in conjunction with the agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | EHP
29/8/2018 | QPWS | Augmented Ranger Mobile Application | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project has been approved to commence delivery and is publishing for the first time. | 2018-08-14T00:00:00 | Low | 240000 |  | Queensland Parks and Wildlife Service | 30 | 10952 |  | G | 2 | Develop a unique, mobile, optimised solution that uses Augmented Reality to: 29/8/2018, 29/8/2018,* enrich visitors on-park engagement, experience and understanding of cultural, historical and ecological points of interests specific to the location 29/8/2018,* provide opportunities for ranger-visitor communications 29/8/2018,* aid collection of real-time visitor data. | 240000 | 2018-02-01T00:00:00 | EHP
29/8/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP
19/12/2017 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2016-08-01T00:00:00 | Delivery | G | 2018-07-30T00:00:00 | July 2017: The planned end date has been brought forward, from 31/12/2018 to 30/07/2018. This is due to a revised delivery schedule. | 2017-09-12T00:00:00 | High | 1858668 | G | Metro North | 35 | 599020 | G | G | 1 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 19/12/2017, 19/12/2017,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Women 19/12/2017,92s Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 19/12/2017, 19/12/2017,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 1858668 | 2015-06-01T00:00:00 | DH
19/12/2017 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 11180394 | G | eHealth Queensland | 4 | 32527 | G | G | 2 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 19/12/2017,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work. 19/12/2017,a0 Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 6000000 | 2017-07-03T00:00:00 | DH
19/12/2017 | CHOPD | BreastScreen Queensland Online Bookings | 2016-01-01T00:00:00 | Delivery | G | 2017-09-30T00:00:00 | August 2017: The planned end date for this initiative is 30/09/2017, which was current as at August. An updated status will be provided in the next reporting update. 19/12/2017, 19/12/2017,May 2017: Online Portal now available for women (eligible for a Breast Screening) to book their Breast Screen appointments through the Internet. Electronic GP Letters is progressing well and is on track to go live early September. 19/12/2017, 19/12/2017,April 2017: Online Portal now available for women (eligible for a Breast Screen) to book their Breast Screen appointments through the Internet. | 2017-08-31T00:00:00 | High | 3103657 | G | Chief Health Officer and Prevention | 98 | 3796330 | G | G | 3 | The BreastScreen Online Booking Project incorporates the following: 19/12/2017,Phase 1 - The Online Portal which is 90% of the Online Bookings Project went live on 5 December 2016. 19/12/2017,a0 The Online Portal enables women to register, book and reschedule their BreastScreen appointment, manage their contact details and view their BSQ notifications including invitations, reminders and results. 19/12/2017,Phase 2 - Incorporates the facility for GP's to receive patient results and reminders electronically. This initiative is scheduled to 'go live' on the 4th September 2017. | 4000000 | 2014-10-13T00:00:00 | DH
19/12/2017 | MNHHS | Business Intelligence - Enterprise Data Warehouse | 2018-06-29T00:00:00 | Initiate | G | 2018-06-28T00:00:00 | June 2017: Project reported for first time. | 2017-09-12T00:00:00 | High | 3730003 | G | Metro North | 20 | 990466 | G | G | 4 | This project will introduce Business Intelligence and Data Warehousing capabilities at MNHHS. The project will deliver BI and DW technical skills, system infrastructure, data automation tools, a pilot dataset, data governance processes and quality control framework at MNHHS. Metro North Finance and MNIT are jointly managing the project. | 2114991 | 2016-11-01T00:00:00 | DH
19/12/2017 | MNHHS | Central Patient Monitoring Equipment Replacement | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | July 2017: Project reported for first time. | 2017-09-12T00:00:00 | High | 1236416 | G | Metro North | 10 | 25133 | G | G | 5 | Metro North IT has been approached by Metro North Procurement Services (MNPS) to provide ICT advice and guidance into the Central Patient Monitoring Equipment Replacement (CPMER) Project. The Health Technology Equipment Replacement (HTER) program for central monitoring systems is providing funding in financial years 16/18 for physiological monitoring equipment requiring replacement across MNHHS hospital facilities. There is an estimated 312 pieces of equipment, primarily Physiological Monitoring devices, to be replaced under the program across MNHHS hospital facilities. MNHHS implementations are being co-ordinated by MNPS. | 1236416 | 2017-06-28T00:00:00 | DH
19/12/2017 | MNHHS | CISS (Community, Indigenous and Subacute Services) Wi-Fi | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | July 2017: Project reported for first time. | 2017-09-12T00:00:00 | High | 1280798 | G | Metro North | 17 | 675736 | G | G | 6 | The Community, Indigenous and Subacute Services (CISS) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the internal areas of the prioritised CISS sites. 19/12/2017, 19/12/2017,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1280798 | 2017-07-28T00:00:00 | DH
19/12/2017 | EHQ | Cloud First Project | 2018-06-30T00:00:00 | Initiate | G | 2018-07-09T00:00:00 | June 2017: This project was previously called ePulse Cloud First Project. | 2017-08-31T00:00:00 | High | 1750000 | G | eHealth Queensland | 22 | 1694306 | G | G | 7 | The Cloud First project will build internal capability and establish processes within Queensland Health to appropriately utilise cloud services on an ongoing basis. | 4107007 | 2017-01-01T00:00:00 | DH
19/12/2017 | HSQ | Cloud Provision to HSQ | 2016-04-11T00:00:00 | Closed | G | 2017-06-30T00:00:00 | August 2017: This project has been closed due to a review of the project by Health Support Queensland. 19/12/2017, 19/12/2017,July 2017: This project is still on hold. It is anticipated that a governance decision to determine the future of this project will be made by the next reporting period. 19/12/2017, 19/12/2017,June 2017: The latest approved end date for this project is 30 June 2017, which will change pending the continuation of the project. The project is paused due to pending recruitment activities, with no adverse impacts affecting the business while this project is on hold. | 2017-08-31T00:00:00 | Medium | 1540996 | G | Health Support Queensland | 31 | 3002706 | G | G | 8 | To consolidate HSQ applications and migrate to cloud infrastructure to improve system redundancy, system security and business continuity whilst addressing existing issues. | 3196431 | 2014-05-01T00:00:00 | DH
19/12/2017 | CED | Consumer Integrated Mental Health Application (CIMHA) Clinical Notes project (release 3.0) | 2018-02-06T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | August 2017: The project has returned to a 'Green' status, with the project's revised scope, budget and schedule being approved by the project's governance committee in late August 2017. 19/12/2017, 19/12/2017,July 2017: The overall status for this project ('Red') is unchanged from June, however, it is expected that governance approval will be obtained by the next reporting period, returning this project to 'On Track'. 19/12/2017, 19/12/2017,June 2017: This initiative is reporting 'Action required' due to resourcing issues. Project team resources have been unable to be secured within the planned timeframe, delaying the implementation of the project by 4 months. The scope of the project was extended to include additional enhancements, further impacting on project resource and schedule requirements. It is anticipated that this project will return to 'On track' once formal governance approval has been obtained for the extended implementation timeframes and additional resource requirements. | 2017-08-31T00:00:00 | Medium | 1415000 | G | Clinical Excellence | 40 | 349325 | G | G | 9 | Upgrading the CIMHA Mental Health Act module to accommodate a re-architecture of the CIMHA clinical notes module is required to deliver benefits to the clinical workforce associated with data entry efficiencies; improved data sharing across digital platforms; patient level information transfer to third parties to support service integration and data mining to support service improvement and research. | 1969365 | 2017-02-20T00:00:00 | DH
19/12/2017 | EHQ | Critical Infrastructure Upgrades 16-18 | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 | July 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 14689808 | G | eHealth Queensland | 6 | 0 | G | G | 10 | Deliver ICT infrastructure uplifts (data, voice, wireless, cabling, infrastructure design and connectivity) at Multiple Hospital and Health Services (HHS) to better support delivery of business and clinical services. | 13230525 | 2017-07-01T00:00:00 | DH
19/12/2017 | EHQ | Critical Infrastructure Upgrades 17-19 | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 11144283 | G | eHealth Queensland | 6 | 0 | G | G | 11 | The Critical Infrastructure Initiative will upgrade 19/12/2017,93like for like 19/12/2017,94 out of date network and voice asset 19/12/2017,92s within the QH network. FY17-18 will concentrate on the replacement of the end of life stand-alone Wireless LAN (WLAN) access points (AP 19/12/2017,92s) and replace these assets with new integrated WLAN AP 19/12/2017,92s connected to the centralised FLEX controllers in the core of the network. In Year 2 there are some Paging and Voice upgrades planned to remove redundant hardware. | 9180760 | 2017-07-01T00:00:00 | DH
19/12/2017 | EHQ | Critical Network Hardware | 2018-02-28T00:00:00 | Delivery | G | 2018-02-28T00:00:00 | June 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 9500000 | G | eHealth Queensland | 32 | 6930741 | G | G | 12 | The objectives of the project include: 19/12/2017,a) Mitigate the Department of Health risk that core network switches at QH facilities will no longer be supported by the manufacturer from February 2018. 19/12/2017,b) Invest in the replacement of critical ICT network hardware to maintain current capability and reliability of the data network for 120+ enterprise clinical and business applications and provide the foundation for future capability in the enterprise data centres. 19/12/2017,c) Ensure hardware replacement occurs with minimal impact to business operations in Hospital and Health Services or Corporate offices. 19/12/2017,d) Update logical and physical design and architecture documentation for ease of maintenance and management. | 8001607 | 2017-03-06T00:00:00 | DH
19/12/2017 | EHQ | Digital Collaboration Platform Program | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2017-08-31T00:00:00 | High | 11000000 | G | eHealth Queensland | 20 | 5398475 | G | G | 13 | This program will deliver digital collaboration tools for any time, any where, any device including: 19/12/2017,(a) Email and Archiving 19/12/2017,(b) Establishment and Collaboration 19/12/2017,(c) Productivity Suite Enablement | 12921837 | 2015-10-29T00:00:00 | DH
19/12/2017 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate | G | 2017-12-31T00:00:00 |  | 2017-08-31T00:00:00 | High | 1500000 | G | Queensland Ambulance Service | 40 | 423741 | G | G | 14 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 4167216 | 2015-12-01T00:00:00 | DH
19/12/2017 | QAS | e-ARF Redevelopment for iPad | 2016-12-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 |  | 2017-08-31T00:00:00 | High | 2624000 | G | Queensland Ambulance Service | 92 | 1366057 | G | G | 15 | This is an initiative to provide the electronic Ambulance Report Form (eARF) electronic patient care solution via iPads in the field. | 1910813 | 2015-09-02T00:00:00 | DH
19/12/2017 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | July 2017: Project reported for first time. | 2017-09-05T00:00:00 | High | 1283000 | G | Chief Health Officer and Prevention | 7 | 26000 | G | G | 16 | Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1283000 | 2017-03-01T00:00:00 | DH
19/12/2017 | MNHHS | Learning and Performance Management Project | 2017-06-30T00:00:00 | Initiate | G | 2018-11-26T00:00:00 |  | 2017-09-12T00:00:00 | High | 1178190 | G | Metro North | 15 | 598082 | G | G | 35 | Implement an integrated Learning Management and Performance Management system with the capability to deliver online learning and training content, facilitate performance development and maintain centralised records for reporting purposes. | 1178190 | 2016-07-11T00:00:00 | DH
19/12/2017 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery | G | 2018-11-30T00:00:00 | July 2017: Project reported for first time. | 2017-09-12T00:00:00 | High | 4827917 | G | Metro North | 30 | 1679612 | G | G | 17 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (timer) program. 19/12/2017, 19/12/2017,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 19/12/2017, 19/12/2017,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. 19/12/2017, 19/12/2017,Anticipated benefits include: improved patient health outcomes through medication safety and enhance "quality use of medicines"; staff enabled and supported in medication prescribing and administration decisions and processes; increased compliance with medication-related legal, policy and audit requirements; reduced risk (legal, financial, patient safety); improved revenue generation opportunities with PBS script generation; reduction in medication-related harm and incidents; and delivery on health service strategic intent. | 4827917 | 2016-07-01T00:00:00 | DH
19/12/2017 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 3747721 | G | eHealth Queensland | 2 | 0 | G | G | 18 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment. 19/12/2017,a0 19/12/2017,a0The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access. 19/12/2017,a0 | 2521960 | 2017-07-05T00:00:00 | DH
19/12/2017 | QAS | Enterprise Rostering System | 2018-12-31T00:00:00 | Initiate | G | 2018-12-31T00:00:00 |  | 2017-08-31T00:00:00 | High | 1000000 | G | Queensland Ambulance Service | 10 | 412987 | G | G | 19 | The initiative is to provide a centralised electronic rostering system to replace existing aging and disparate manual systems currently being utilised across the state. | 1194682 | 2016-12-01T00:00:00 | DH
19/12/2017 | EHQ | File Services Migration | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 | July 2017: The project has returned to 'On Track'. The governance committee has approved the revised project schedule and finances. The financials currently reflect the latest approved budget of the initiative. 19/12/2017, 19/12/2017,June 2017: The project was previously called File Services Migration (ePulse). 19/12/2017,The approval of the business case has been delayed. The schedule is being revised by the governance committee, with the project expecting to return to On Track in the next reporting period. | 2017-08-31T00:00:00 | High | 3400000 | G | eHealth Queensland | 15 | 2169105 | G | G | 20 | The purpose of this investment is to adopt a contemporary, simplified file management solution for Queensland Health that enables a more cohesive customer experience. | 4005164 | 2016-08-01T00:00:00 | DH
19/12/2017 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Initiate | G | 2018-12-31T00:00:00 |  | 2017-08-31T00:00:00 | High | 105000000 | G | Metro North | 36 | 29321000 | G | G | 21 | The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 19/12/2017, 19/12/2017,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 19/12/2017,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 19/12/2017, 19/12/2017,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
19/12/2017 | EHQ | Follow Me Desktop - Deployment | 2018-06-30T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 3952980 | G | eHealth Queensland | 5 | 111198 | G | G | 22 | Follow Me Desktop Deployment Project will deliver 19/12/2017,a0the Follow Me Desktop service (FMD) to HHS 19/12/2017,92 in alignment with the Infrastructure Remediation Program (IMP) and iEMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 2153980 | 2017-07-24T00:00:00 | DH
19/12/2017 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 3301500 | G | eHealth Queensland | 2 | 11386 | G | G | 23 | Project Purpose: 19/12/2017,a0To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 3301500 | 2017-07-01T00:00:00 | DH
19/12/2017 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 1120000 | G | eHealth Queensland | 5 | 0 | G | G | 24 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. 19/12/2017,The project consists of four key initiatives: 19/12/2017,QHPKI service establishment and state-wide certificate migration for wireless devices. 19/12/2017,Establishment of a Security Information and Event Management (SIEM) solution for management and prevention of security incidents. 19/12/2017,Implementation of Intrusion Prevention System (IPS) at two locations to standardise IPS management across the state. 19/12/2017,a0 19/12/2017,State-wide migration to the enhanced proxy service. 19/12/2017,a0 | 560000 | 2017-07-05T00:00:00 | DH
19/12/2017 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery | G | 2018-07-02T00:00:00 |  | 2017-08-31T00:00:00 | High | 3215000 | G | eHealth Queensland | 32 | 3019327 | G | G | 25 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 5598485 | 2015-06-22T00:00:00 | DH
19/12/2017 | EHQ | ieMR Program | 2014-12-31T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | May 2017: The following sites are in scope as part of the planned expansion of the ieMR state-wide rollout: Mackay Base Hospital, Logan Hospital, Beaudesert Hospital, Lady Cilento Children's Hospital (LCCH), Queen Elizabeth II (QEII) Hospital, Redland Hospital, and Townsville Hospital. 19/12/2017, 19/12/2017,April 2017: The Medications, Anaesthetics and Research Support (MARS) System successfully went live at the Princess Alexandra Hospital (PAH) on Sunday 19th of March 2017. Further rollouts are planned at Mackay, Logan and Beaudesert, Lady Cilento Children's Hospital, Redlands and QUII, and Townsville Hospitals by July 2018. 19/12/2017, | 2017-08-31T00:00:00 | High | 0 | G | eHealth Queensland | 80 | 0 | G | G | 26 | The integrated electronic Medical Record (ieMR) system changes the way clinicians access patient information, replacing the paper based system with a secure electronic record. The ieMR solution is focused on improving patient safety and quality of care by providing the right information, at the right place, at the right time. Paper medical records will be progressively transitioned to an electronic format. 19/12/2017,The implementation of the ieMR solution will be delivered by site teams at each of the hospitals in scope. The ieMR solution is being rolled out in a phased approach in consultation with sites to ensure effective implementation. 19/12/2017, 19/12/2017,Please note that financial information is Commercial in Confidence | 0 | 2009-10-01T00:00:00 | DH
19/12/2017 | EHQ | Infrastructure Capacity FY 17-18 | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 1000000 | G | eHealth Queensland | 5 | 4635202 | G | G | 27 | Project Purpose: 19/12/2017,a0 19/12/2017,The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified 19/12/2017,91organic growth 19/12/2017,92 requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. 19/12/2017,Each year the project will maintain a list of devices that are reaching capacity thresholds within the current financial year in the Prioritised Operations List. Prioritisation of the list will be based on the risk impact assessment for each in-scope asset to establish a most-to-least-critical replacement/upgrade ranking. The project will, based on prioritisation, implement/facilitate as many upgrades as the approved budget allows. | 5622032 | 2017-07-01T00:00:00 | DH
19/12/2017 | EHQ | Infrastructure Maintenance Program | 1900-01-01T00:00:00 | Initiate | G | 2022-06-30T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 1161415 | G | eHealth Queensland | 0 | 33340 | G | G | 28 | The Infrastructure Maintenance Program (IMP) 19/12/2017,a0will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 19/12/2017,The scope includes: 19/12/2017,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 19/12/2017,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and 19/12/2017,a0 19/12/2017,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1161414 | 2017-07-03T00:00:00 | DH
19/12/2017 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery | G | 2022-06-30T00:00:00 | July 2017: Project reported for first time. Financials currently reflect the financial year 2017-18 only. | 2017-08-31T00:00:00 | Medium | 14673739 | G | Clinical Excellence | 2 | 179067 | G | G | 29 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 19/12/2017,The ongoing program of work aims to continue and build upon existing functionality by: 19/12/2017,(a) Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 19/12/2017,(b) Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 19/12/2017,(c) Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 19/12/2017,(d) Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 19/12/2017,(e) Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
19/12/2017 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate | G | 2022-12-21T00:00:00 | June 2017: Project reported for first time. | 2017-08-31T00:00:00 | Medium | 6300000 | G | Queensland Ambulance Service | 15 | 292373 | G | G | 30 | Phased delivery of a system supporting QAS business intelligence. | 6300000 | 2017-01-03T00:00:00 | DH
19/12/2017 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | June 2017: Funding approval has been granted for this initiative in June 2017. 19/12/2017, 19/12/2017,May 2017: This project is within the project start-up phase. No funds have been expended to date on project delivery activities. Approval for funding has been granted in June, with the project planning to formally commence within the next reporting period. | 2017-09-04T00:00:00 | High | 33827000 | G | Clinical Excellence | 7 | 2500000 | G | G | 31 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 33827000 | 2017-03-01T00:00:00 | DH
19/12/2017 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 1 | 2016-11-30T00:00:00 | Delivery | G | 2018-02-28T00:00:00 |  | 2017-08-31T00:00:00 | High | 8200000 | G | Health Support Queensland | 60 | 14567743 | G | G | 32 | The IWFM project involves: 19/12/2017,(a) configuring additional functionality (currently available and licensed, but unutilised) within the existing Rostering and Payroll business solutions 19/12/2017,(b) partnering with HHSs to develop refined business models and business processes to support the roster-to-pay process 19/12/2017,(c) undertaking extensive training and change management to support the adoption and effective usage of new functionality and processes | 25060122 | 2016-02-17T00:00:00 | DH
19/12/2017 | EHQ | Interoperability Project | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | July 2017: Additional Investment has been secured from Government, once Governor in Council approval is received project will re-establish. 19/12/2017, 19/12/2017,June 2017: The project is planning to seek funding form CBRC in August 2017. 19/12/2017, 19/12/2017,April 2017: The project has completed a detailed implementation planning study and solutions design to inform scope and budget estimates. 19/12/2017, 19/12/2017,Additional funding for implementation of subsequent stages is still being sought. | 2017-08-31T00:00:00 | High | 23850000 | G | eHealth Queensland | 15 | 4702016 | G | G | 33 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 19/12/2017,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 19/12/2017,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 19/12/2017, | 39190000 | 2015-02-01T00:00:00 | DH
19/12/2017 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Initiate | G | 2019-09-30T00:00:00 |  | 2017-09-05T00:00:00 | High | 0 | G | Health Support Queensland | 48 | 0 | G | G | 34 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 19/12/2017,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. 19/12/2017, 19/12/2017,Please note that financial information is Commercial in Confidence | 0 | 2015-08-28T00:00:00 | DH
19/12/2017 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery | G | 2018-11-30T00:00:00 |  | 2017-09-12T00:00:00 | High | 4030460 | G | Metro North | 35 | 918462 | G | G | 36 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 19/12/2017, 19/12/2017,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 19/12/2017, 19/12/2017,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
19/12/2017 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery | G | 2017-12-31T00:00:00 |  | 2017-09-12T00:00:00 | High | 6299780 | G | Metro North | 75 | 4946737 | G | G | 37 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 6299780 | 2014-06-01T00:00:00 | DH
19/12/2017 | EHQ | Mobile Application System for Bring Your Own Device | 2018-06-30T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | July 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 1639698 | G | eHealth Queensland | 5 | 22260 | G | G | 38 | This project leverages the investment of the previous Bring-Your-Own-Device (BYOD) 19/12/2017,a0projects to extend the capability of device mobility by building the foundations of a Mobile Application Ecosystem - the processes, products and services to enable the managed development of low/no code applications by Health and Hospital Services (HHS). 19/12/2017,a0 This project will also complete the deployment of BYOD laptops and provide recommendations on how cost savings can be made by the organisation around Corporate devices and data plans. 19/12/2017,a0 | 1639698 | 2017-07-10T00:00:00 | DH
19/12/2017 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery | G | 2018-12-31T00:00:00 |  | 2017-08-31T00:00:00 | High | 14100000 | G | eHealth Queensland | 30 | 8889110 | G | G | 39 | This project will move Queensland Health to a modern end user workspace that is: current; delivering collaboration and productivity benefits; able to be accessed anywhere, anytime and on any device; reducing the reliance and expense of on premise infrastructure and support and not constraining the business from taking advantage of modern applications and services. | 25155173 | 2016-05-12T00:00:00 | DH
19/12/2017 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | August 2017: Project reported for first time. This project is internally known as 'M-series replacement' | 2017-08-31T00:00:00 | High | 5600000 | G | eHealth Queensland | 2 | 59572 | G | G | 40 | Project Purpose: 19/12/2017,Queensland Health is driving a huge eHealth Strategy to keep pace with the increasing demand for digital health services, to shift towards a customer-centric health system, and to enable cutting edge health service delivery. 19/12/2017,Central to the eHealth strategy is addressing issues related to ageing systems, in particular addressing the risk to health service delivery, and removing barriers to contemporary practice. 19/12/2017,Currently, eHealth Queensland is hosting a number of mission critical applications on the ageing application server platform. While this platform has provided a robust and highly available environment, it is now seven years old with increased risks to reliability and serviceability, has limited options for expansion, and is unable to provide the agile foundation required for advancing the eHealth Strategy. As such, it is an appropriate time to investigate replacement of the platform. 19/12/2017,This project aims to establish a robust, highly available and secure contemporary platform that has the 19/12/2017,93Scale Out 19/12/2017,94 capability to support the agile eHealth Strategy. | 5600000 | 2017-07-01T00:00:00 | DH
19/12/2017 | CHOPD | My Health for Life | 2020-04-30T00:00:00 | Delivery | G | 2020-04-30T00:00:00 | August 2017: The My health for life platform development schedule has experienced a brief delay to ensure the final product meets high program standards. This has no impact on the overall status of the project. 19/12/2017, 19/12/2017,July 2017: Prior reporting displayed the 'Planned end date' as 30/04/2020. The ICT component of this initiative will be delivered by 31 December 2017, and the project has now been updated to reflect this date. 19/12/2017, 19/12/2017,April 2017: Prior reporting displayed the Original Total Estimated Expenditure as $27M. The ICT component of this initiative is $2,000,000 and the project has now been updated to reflect this value. | 2017-09-04T00:00:00 | High | 27000000 | G | Chief Health Officer and Prevention | 78 | 1570586 | G | G | 41 | The My health for life (MH4L) program represents a $27.24M election commitment that will provide a statewide health risk assessment and lifestyle modification program targeting Queenslanders at high risk of developing type 2 diabetes, cardiovascular disease, obesity and some cancers. 19/12/2017,Delivery of the program will be led by Diabetes Queensland who have been contracted through an open tender process. 19/12/2017,The MH4L ICT solution will be a key enabler within the services procured under the program including internet, social media, process support and data collection/analysis. 19/12/2017,a0 No ICT is expected to be retained after the completion of the MH4L contract. | 2000000 | 2016-05-01T00:00:00 | DH
19/12/2017 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | July 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 1500000 | G | Queensland Ambulance Service | 35 | 333828 | G | G | 42 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1744000 | 2015-10-01T00:00:00 | DH
19/12/2017 | CHOPD | Notifiable Conditions System Replacement | 2018-12-31T00:00:00 | Delivery | G | 2020-02-28T00:00:00 | August 2017: The project has resumed as at 14 August 2017 with the recruitment of key project resources. The percentage complete has been updated to reflect the latest position of the project. 19/12/2017, 19/12/2017,July 2017: Formal governance approval has been provided for this project, with the project planning to recommence in August 2017. 19/12/2017, 19/12/2017,April 2017: Project is on hold as of 31 March 2017 pending formal governance approvals. | 2017-09-05T00:00:00 | High | 12000000 | G | Chief Health Officer and Prevention | 28 | 1896213 | G | G | 43 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 19/12/2017,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
19/12/2017 | EHQ | Patient Administration System (PAS) Replacement Program | 2017-06-30T00:00:00 | Initiate | G | 2017-09-30T00:00:00 | August 2017: The planned end date for this stage of the project was 30/09/2017, which was current as at August to deliver the strategic program business case. This has since been approved in October 2017 by the appropriate governance committee to progress to next stage and to seek further investment funding from Cabinet in 2018 . An updated status will be provided in the next reporting update. 19/12/2017, 19/12/2017,April 2017: This initiative was previously called "Queensland Connected Patient Care Program". | 2017-09-11T00:00:00 | High | 3850000 | G | eHealth Queensland | 79 | 2326410 | G | G | 44 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients 19/12/2017,92 journeys, and ensure that accurate information about our patients is readily available when and where required. 19/12/2017,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 19/12/2017,(a) support for patient engagement 19/12/2017,(b) integrated care 19/12/2017,(c) clinical research 19/12/2017,(d) population health (for patients using public health services) 19/12/2017,(e) performance transparency 19/12/2017,(f) resource planning. | 3850000 | 2015-11-01T00:00:00 | DH
19/12/2017 | MNHHS | Picture Archiving and Communication System (PACS) | 2017-09-29T00:00:00 | Delivery | G | 2017-12-31T00:00:00 |  | 2017-09-12T00:00:00 | High | 3114694 | G | Metro North | 74 | 2071148 | G | G | 45 | Procure and implement a contemporary Picture Archiving and Communication (PACS) system and functionality that will ensure improved service delivery for the MNHHS Medical Imaging Departments (and other PACS users) through replacement of RBWH PACS ensuring that it is scalable and able to meet the ongoing needs of Metro North Hospital and Health Service. | 3656297 | 2016-07-11T00:00:00 | DH
19/12/2017 | EHQ | Project, Program and Portfolio Management Application | 2017-12-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 |  | 2017-08-31T00:00:00 | High | 1344177 | G | eHealth Queensland | 10 | 153061 | G | G | 46 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 19/12/2017, | 157203 | 2017-05-02T00:00:00 | DH
19/12/2017 | SPPD | Queensland Health Integrated Data System initiation (QHIDSi) | 2017-09-30T00:00:00 | Delivery | G | 2017-09-30T00:00:00 | August 2017: The planned end date for this initiative is 30/09/2017, which was current as at August. An updated status will be provided in the next reporting update. 19/12/2017, 19/12/2017,July 2017: The project has experienced delays in finalising procurement which has impacted on the schedule and will return to 'On Track' in the coming months. 19/12/2017, 19/12/2017,April 2017: This initiative was previously called "Queensland Hospital Inpatient Processing System Replacement (QHIPSr) Project" | 2017-08-31T00:00:00 | High | 1800000 | G | Strategy, Policy and Planning | 96 | 890503 | A | A | 47 | This initiative will source and implement an integrated processing solution and configure it as a replacement for QHIPS which processes detailed unit record data on admitted patients from all public acute and psychiatric hospitals and licenced private hospitals and day surgery hospitals within Queensland. The technology of the current QHIPS system is at end of life and is unable to meet evolving business requirements. The project will also train existing Statistical Services Branch (SSB) staff in the use of the licensed software providing for expansion of use of the integrated processing solution as part of business-as-usual operations (e.g. to retire other end of life SSB systems). | 1800000 | 2015-09-07T00:00:00 | DH
19/12/2017 | CED | Queensland Integrated Safety Information Project (QISIP) / Risk Management | 2017-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2017-09-04T00:00:00 | Medium | 4333120 | G | Clinical Excellence | 80 | 7071893 | G | G | 48 | This initiative will source and implement an integrated processing solution and configure it as a replacement for QHIPS which processes detailed unit record data on admitted patients from all public acute and psychiatric hospitals and licensed private hospitals and day surgery hospitals within Queensland. 19/12/2017, | 16273520 | 2013-01-25T00:00:00 | DH
19/12/2017 | MNHHS | Quick Flow Project | 2019-02-01T00:00:00 | Initiate | G | 2019-06-30T00:00:00 | August 2017: This project was previously called the Ambulatory Flow Management (AFM) Project. 19/12/2017, 19/12/2017,July 20t17: The percentage complete has reduced from 10% in June to 2% in July due to revised planning activities. | 2017-09-12T00:00:00 | High | 6408600 | G | Metro North | 3 | 177494 | G | G | 49 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 19/12/2017,The key objectives of the project are to: 19/12/2017,(a) Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 19/12/2017,(b) Improve the outpatient experience across MNHSS facilities and community services 19/12/2017,(c) Improve clinic resource utilisation 19/12/2017,(d) Increase the efficiency of clinical and administrative processes 19/12/2017,(e) Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
19/12/2017 | EHQ | Regional eHealth Initiatives | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 3790000 | G | eHealth Queensland | 6 | 1898205 | G | G | 50 | The Regional eHealth Project (ReHP) is a Wireless LAN and Network Infrastructure uplift project so that sites in Far North Qld are ready to rollout their new eHealth Application. | 3489114 | 2017-07-01T00:00:00 | DH
19/12/2017 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Initiate | G | 2019-12-31T00:00:00 |  | 2017-08-31T00:00:00 | High | 34950000 | G | Cairns and Hinterland | 45 | 5958443 | G | G | 51 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patient 19/12/2017,92s home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
19/12/2017 | EHQ | Replacement of the ICT Service Management system | 2016-06-30T00:00:00 | Delivery | A | 2017-09-29T00:00:00 | August 2017: The planned end date for this initiative is 30/09/2017, which was current as at August. The system has successfully gone live at the end of September, with the project receiving governance committee approval to close at the end of October. The project is also indicating that the project will close with a 'Green' status. 19/12/2017, 19/12/2017,July: The status of this project is unchanged from June. 19/12/2017, 19/12/2017,June 2017: This initiative is still reporting amber in June. The governance committee is reviewing the scope and performance of this initiative in order to ensure the successful delivery of a complete service management solution. It is anticipated that this project will report on track in upcoming reporting periods. | 2017-08-31T00:00:00 | High | 2000000 | A | eHealth Queensland | 94 | 6472293 | A | A | 52 | This project will deliver a new cloud-based tool to improve the end-to-end management of IT support requests and incidents. The project will be delivered in two phases. The first phase has delivered a contemporary solution for IT support staff to manage requests and incidents. The second phase will deliver a new customer focused self-service portal and other system enhancements. | 7275579 | 2015-06-08T00:00:00 | DH
19/12/2017 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Initiate | G | 2020-06-30T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 10500000 | G | eHealth Queensland | 2 | 0 | G | G | 53 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 4500000 | 2017-07-03T00:00:00 | DH
19/12/2017 | EHQ | Storage and Backup Asset Replacement - FY 16/17 | 2017-06-30T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | August 2017: The planned end date for this initiative is 30/09/2017, which was current as at August. An updated status will be provided in the next reporting update. | 2017-08-31T00:00:00 | High | 1000000 | G | eHealth Queensland | 95 | 7889781 | G | G | 54 | To replace or upgrade at risk and/or aging ICT assets to enable modern healthcare delivery. | 7883138 | 2017-07-01T00:00:00 | DH
19/12/2017 | EHQ | Storage Asset Replacement | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 1671556 | G | eHealth Queensland | 8 | 6194 | G | G | 55 | The Storage Asset Replacement (SAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the SAR and Backup Asset Replacement (BAR) projects. 19/12/2017,The SAR project seeks to outline architecture for storage that will provide a cost effective, scalable and fit for purpose environment for the future of storage services within Queensland Health. 19/12/2017,a0 Utilising space saving technologies which will enable further cost savings and reduce the requirement for capacity expansion in the short to medium term. 19/12/2017,The existing storage arrays at Cairns, Townsville and Gold Coast are classed as urgent and unavoidable asset replacements. 19/12/2017,a0 These storage arrays are at capacity and will be at the end of extended vendor support in May 2018. | 1671555 | 2017-07-03T00:00:00 | DH
19/12/2017 | EHQ | Telehealth Asset Replacement FY 17-18 | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 |  | 2017-08-31T00:00:00 | High | 1960000 | G | eHealth Queensland | 4 | 9914267 | G | G | 56 | Project Purpose: 19/12/2017,a0 19/12/2017,a0 19/12/2017,Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector 19/12/2017,a0 19/12/2017,and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. 19/12/2017,The Department of Health defines Telehealth as: 19/12/2017,(a) Live, audio and/or video inter-active link for clinical consultations and educational purposes 19/12/2017,(b) Store and forward Telehealth - this model can involve digital images, video, audio and clinical data being captured ("stored") on the client computer; then at a convenient time transmitted securely ("forwarded") 19/12/2017,a0 to a clinic at another location where they are studied by relevant specialists 19/12/2017,(c) Teleradiology for remote reporting and clinical advice for diagnostic images 19/12/2017,(d) Telehealth services and equipment to monitor people 19/12/2017,92s health in their home. 19/12/2017,Benefits of Telehealth 19/12/2017,(a) Improve patient access to health care 19/12/2017,(b) Reduce travel and inconvenience for patients, families, carers and health professionals 19/12/2017,(c) Provide health professionals with access to peer support and education. 19/12/2017,The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. 19/12/2017,a0 19/12/2017,The priority is to replace those end-of-life assets which pose the greatest risk to effective health service delivery. 19/12/2017,Each year the project will prioritise and maintain the replacement scope in the Prioritised Operations List based on the risk impact assessment for each in-scope asset to establish a most-to-least critical replacement ranking. | 11613266 | 2017-07-03T00:00:00 | DH
19/12/2017 | MNHHS | The Prince Charles Hospital (TPCH) Wi-Fi | 2017-07-27T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | July 2017: Project reported for first time. | 2017-09-12T00:00:00 | High | 1408388 | G | Metro North | 17 | 742249 | G | G | 57 | The Prince Charles Hospital (TPCH) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the hospital campus for prioritised TPCH buildings. 19/12/2017, 19/12/2017,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1408388 | 2017-07-27T00:00:00 | DH
19/12/2017 | CS | Child and Family Services Information and Communication Technology (ICT) Program | 2015-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | Original planned expenditure represented approved budget from start date to 30 June 2016. This program is a multi year program and the revised total expenditure has been updated to include approved funding to 30 June 2018. | 2017-09-30T00:00:00 | Critical | 7645000 | G | Child Safety | 73 | 16109000 | G | G | 1 | This five year program will investigate, provide options and implement ICT solutions to enable Child Safety in addressing recommendations of the Queensland Child Protection Commission of Inquiry. This may include enhancements to current systems, consideration of new systems and enabling activities to address changes to policy, legislation and practice reforms resulting from the outcomes of the Inquiry. | 24181000 | 2013-12-16T00:00:00 | DCCSDS
19/12/2017 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery | A | 2017-09-30T00:00:00 | There have been delays to the project schedule from reprioritisation of resources to community recovery activities associated with Cyclone Debbie. Additionally, the vendor, SMS Management and Technology, has not delivered within the contracted timeframes and we are negotiating with the vendor to ensure completion of the solution. | 2017-09-30T00:00:00 | High | 2208000 | G | Whole of Department | 73 | 2635000 | A | A | 2 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3333000 | 2016-07-01T00:00:00 | DCCSDS
19/12/2017 | WOD | Digital Domestic and Family Violence Prevention | 2019-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | Multi year project ending June 2019. | 2017-09-30T00:00:00 | Critical | 8050000 | G | Whole of Department | 42 | 2273000 | G | G | 3 | The Digital Domestic and Family Violence Prevention Initiative is the ICT initiative to deliver the ICT components of the government response to the Bryce Report, and also progress Digital Domestic and Family Violence Prevention digital innovations. | 8050000 | 2016-07-01T00:00:00 | DCCSDS
19/12/2017 | WOD | ICT Service Transformation Program | 2016-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | Original planned expenditure represented approved budget from start date to 30 June 2016. This program is a multi year program and the revised total expenditure has been updated to include approved funding to 30 June 2018. | 2017-09-30T00:00:00 | Low | 2916000 | G | Whole of Department | 89 | 5568000 | G | G | 4 | This program includes a number of initiatives to implement service improvement opportunities and essential capital replacement activities. The program ensures that ICT systems and services are replaced in a way that supports the department's strategic direction and includes the digital vision and future ways of work roadmap. | 7555000 | 2014-12-13T00:00:00 | DCCSDS
19/12/2017 | WOD | Reporting and Business Intelligence Project | 2017-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | Original planned expenditure represented approved budget from start date to 30 June 2016. This project is a multi year project and the revised total expenditure has been updated to include approved funding to 30 June 2018 to continue reporting and business intelligence deliverables. | 2017-09-30T00:00:00 | Medium | 750000 | G | Whole of Department | 34 | 3274000 | G | G | 5 | The department has a requirement for business intelligence, data management, information presentation and multi-level reporting | 5691000 | 2015-07-01T00:00:00 | DCCSDS
19/12/2017 | WOD | Social Investment Program | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | The original expenditure includes the approved budget to 30 June 2017 only. The planned expenditure has been revised to include the approved expenditure to 30 June 2018 to complete tranche 1 and 2 of the program. | 2017-09-30T00:00:00 | Critical | 2230000 | G | Whole of Department | 26 | 1311000 | G | G | 6 | The project will implement systems and processes that support the departments social procurement spend and support interventions that are proven to work, offer good value for money and are contributing to the broader objectives of government. | 5028000 | 2016-07-01T00:00:00 | DCCSDS
19/12/2017 | CS | Adoption Client Management System | 2016-06-30T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | Planned end date has been amended to 31 October 2017 due to delays to the project schedule from reprioritisation of resources to community recovery activities associated with Cyclone Debbie, risk mitigation strategies associated with data migration, and to accommodate additional change requests during the execution of user acceptance testing. The revised expenditure and end date have been approved. | 2017-09-30T00:00:00 | Low | 523000 | G | Child Safety | 87 | 1438000 | G | G | 7 | The project will implement a contemporary and more cost effective replacement for the Adoptions Case Management System (ACMS). | 1536000 | 2016-10-01T00:00:00 | DCCSDS
19/12/2017 | WOD | Complaints Management System | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2017-09-30T00:00:00 | Low | 466000 | G | Whole of Department | 35 | 83000 | G | G | 8 | The objective of the complaints management system project which was formerly incorporated into the Technology Refresh project is to develop a complaints management system which supports the future DCCSDS business structure. The new system must also meet the recommendations made by the Queensland Ombudsman in his Management of Child Safety Complaints report in which the department has agreed that a full review of data fields for the departments complaints management database is conducted and relevant categories aligned to the departments core business practices and best practice complaints handling process. | 466000 | 2017-07-01T00:00:00 | DCCSDS
19/12/2017 | CS | ICMS Replacement | 2021-06-30T00:00:00 | Initiate | G | 2021-06-30T00:00:00 | A total estimated value will be provided once the proposal has been developed further. | 2017-09-30T00:00:00 | Critical | 0 | G | Child Safety | 6 | 1533321 | G | G | 9 | The ICMS Replacement Program will replace the current child protection and youth justice service delivery system by delivering an integrated child protection and youth justice system focused on effective customer-centric service delivery across government and Non-Government Organisations. 19/12/2017,The initiative will address the significant gaps that have developed between frontline practice and the current ICMS system. The new solution will help deliver improved effectiveness for frontline staff and therefore better outcomes for clients. It will be designed with the flexibility to be adapted over time, to respond to emerging needs and future changes. | 0 | 2017-02-01T00:00:00 | DCCSDS
19/12/2017 | CS | Our Child Project | 2019-02-28T00:00:00 | Initiate | G | 2019-02-28T00:00:00 | Project has commenced initiation activities. | 2017-09-30T00:00:00 | Critical | 4900000 | G | Child Safety | 10 | 648000 | G | G | 10 | The Our Child project will deliver a secure multi-agency information sharing platform that will enhance agencies ability to respond to instances of children missing from out-of-home care. | 4900000 | 2017-03-01T00:00:00 | DCCSDS
19/12/2017 | WOD | Destination Information | 2019-06-30T00:00:00 | Initiate | G | 2019-06-30T00:00:00 |  | 2017-09-30T00:00:00 | Critical | 8500000 | G | Whole of Department | 8 | 902000 | G | G | 11 | The Destination Information initiative will deliver smarter, simpler, better information management by improving the management of electronic information and documents, enabling the ability to file, retrieve and share information, within legislative provisions, in electronic form, removing duplication and reliance on paper based information, enabling better access to relevant information to support families and vulnerable children and enabling improved external information sharing. | 8500000 | 2017-02-01T00:00:00 | DCCSDS
19/12/2017 | Cross-Gov | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery | G | 2018-09-03T00:00:00 | The program continues to meet milestones within the set timeframes. 19/12/2017,Queensland Fire and Emergency Services Human Capital Management solution is tracking to schedule and is expected to go-live with Phase 1 in December 2017. 19/12/2017,The program is currently developing detailed business cases for Queensland Ambulance Service and Queensland Corrective Services Human Capital Management solutions. The agency review process of the final drafts will roll out in October 2017. 19/12/2017,The Queensland Ambulance Service transition to the new payroll system is keeping to set timeframes and on track for delivery in Qtr 3 FY 2017. 19/12/2017,The Program timeframe will remain amber while planning and scheduling for the QFES Payroll implementation is underway. | 2017-09-30T00:00:00 | Critical | 101500000 | G | Cross-Government program led by DSITI | 48 | 49531115 | A | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 19/12/2017, 19/12/2017,* Sustainable and supported HR and Payroll service delivery 19/12/2017,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 19/12/2017,* Strategic HR capability that supports the development, performance and safety of the departments workforce 19/12/2017,* Business Intelligence capability that provides real timely, integrated HR information 19/12/2017,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 19/12/2017,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 19/12/2017,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
19/12/2017 | QPS | Online National Police Certificate Project | 2017-06-30T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | Online National Police Certificate successfully launched on the Queensland Police website on the 13th of November 2017. | 2017-12-14T00:00:00 | High | 275000 | G | Queensland Police Service | 58 | 220000 | G | G | 1 | The Online National Police Certificate Project will implement an online service for the community to apply and pay for Name Only National Police Certificates online, rather than presenting at a police station, or using the online services of an Australian Crime Intelligence Commission accredited broker. This will provide improved customer service to the community through a more efficient and reliable QPS service, with no requirement to present at a police station, as well as provide efficiency and time savings to local police stations and the Police Information Centre. | 220000 | 2017-01-01T00:00:00 | QPS
19/12/2017 | QPS | Police Integrity and Professional Standards Project | 2020-02-17T00:00:00 | Delivery | G | 2020-02-17T00:00:00 | Partial funding for the Police Integrity and Professional Standards Project has been approved and included in the 2017-18 budget. The Invitation to Offer process has commenced and negotiation is currently being conducted with vendors to finalise the price and delivery time-frames. Additional funding is currently being sought through the QPS budget process. | 2017-12-14T00:00:00 | High | 4142000 | A | Queensland Police Service | 30 | 57500 | A | A | 2 | This initiative will deliver a new integrated Police Integrity and Professional Standards IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The Police Integrity and Professional Standards system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The Police Integrity and Professional Standards Project will also complement the Complaints Reform Project established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of the Police Integrity and Professional Standards system will place the QPS in a strong readiness position to fully implement Complaints Reform Project-generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 4142000 | 2017-03-07T00:00:00 | QPS
19/12/2017 | QPS | Advanced Data Analytics Project | 2017-07-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to deliver new capability in all streams with most capability available for use as business-as-usual during the 2018 Commonwealth Games. Current focus is on expanding the capability developed by the project in 2017-18 and the development of the business case for the next phase of QPS advanced data analytics capabilities. | 2017-12-14T00:00:00 | Low | 1730000 | G | Queensland Police Service | 83 | 1950712 | G | G | 3 | Develop the QPS Advanced Data Analytics proof-of-concept. This proof-of-concept is intended to inform a larger suite of data analytics integration and intelligence over the next four years, including the development of predictive and alert models to enhance the operational response to threats, incidents and events. | 2350000 | 2017-02-19T00:00:00 | QPS
19/12/2017 | QPS | Body Worn Cameras Project | 2018-02-28T00:00:00 | Delivery | G | 2018-02-28T00:00:00 | The Program will complete the deployment of all Stage Two body worn cameras by December 2017 and will then complete transition and closure activities by 30 June 2018. A Business Case for additional funding for a Stage Three rollout in 2018-19 has been prepared for Government consideration. A successful Stage Three rollout would see body worn cameras provided to every frontline operational police officer in Queensland. | 2017-12-14T00:00:00 | Medium Low | 6030000 | G | Queensland Police Service | 80 | 5000000 | G | G | 4 | The Queensland Police Service Body Worn Camera Project is deploying 5100 body worn cameras to frontline police officers. Body worn cameras will be deployed to 168 police stations, 16 tactical crime units, 47 road policing units, and specialist units including dog squads and the Public Safety Response Team in two stages. The cameras integrate with the QPS mobility devices, allowing officers to add metadata to videos and to review videos in the field. A system for storage and allocation of digital camera data will also be implemented as well as policy related to use of the cameras. | 6830000 | 2014-08-25T00:00:00 | QPS
19/12/2017 | PSBA | Weapons Licensing Management System Stage 2a Project | 2017-05-31T00:00:00 | Closed | G | 2017-12-29T00:00:00 | Weapons Licensing 2A Benefits Enhancement Analysis Report for the proposed benefit enhancement rule changes have now been approved by the Project Board. 19/12/2017, 19/12/2017,Weapons Licensing will implement the four rule changes as part of their business as usual schedule. The remaining project budget will also be transferred to Weapons Licensing to fund the implementation of the rules. 19/12/2017, 19/12/2017,Project now moves into Close Out phase. | 2017-12-14T00:00:00 | Medium | 2500000 | G | Public Safety Business Agency | 99 | 1888776 | G | G | 5 | Improved workflow efficiencies, reduction in work queues, less resources required to process licence renewal and weapons Permit to Acquire, etc. | 2156825 | 2015-11-11T00:00:00 | QPS
19/12/2017 | QCS | Electronic Transfer of Court Results (ETCR) Phase 3 | 2017-12-01T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is on track for completion within time and quality tolerances. It has fallen under cost tolerance as project activities were delayed between April 2017 and July 2017 to allow for other priority work affecting resource assignments. Project activities have now resumed and resource assignments confirmed as the project works towards its initial release. | 2017-10-06T00:00:00 | High | 550150 | A | Corrective Services | 23 | 303186 | G | G | 1 | * The objective of the ETCR project is to improve integration between criminal justice agencies and improve staff efficiency by reducing manual data entry effort | 1223331 | 2016-12-12T00:00:00 | DJAG
19/12/2017 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-06-30T00:00:00 | Delivery | G | 2018-12-31T00:00:00 | Original planned end date was changed from 30 June 2018 to 31 Dec 2018 due to: 19/12/2017, 19/12/2017, 19/12/2017,- initial delays in securing project resources (2016-17 Christmas/New Year shutdown) 19/12/2017, 19/12/2017, 19/12/2017,- high level of project design complexity (heterogeneous environments) 19/12/2017, 19/12/2017, 19/12/2017,- conformity with appropriate probity and procurement governance. 19/12/2017, 19/12/2017, 19/12/2017,- requirement to develop a Significant Procurement Plan (SPP). 19/12/2017, 19/12/2017, 19/12/2017, 19/12/2017,The original project estimated expenditure occurs over two years to implement Core Infrastructure DR and Oracle DR. The variance of revised cost resulting in significant savings is due to implementing a more cost effective solution proposed through the Request for Quote (RFQ) process while utilising contemporary technologies. | 2017-10-06T00:00:00 | High | 7460674 | G | Corporate Services | 10 | 3005285 | G | G | 2 | * Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 5917255 | 2016-10-01T00:00:00 | DJAG
19/12/2017 | QCS | QCS GIS Project | 2017-09-29T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | Original timeframe and expenditure were updated following contract execution to relfelect increased scope, to maximise avaialble budget, and to allow adequate timeframes for integration of third party data. | 2017-10-06T00:00:00 | Medium | 925000 | G | Corrective Services | 55 | 435513 | G | G | 3 | * Procurement and implementation of a GIS that integrates data from multiple systems to improve Business Intelligence through increased analytical capability | 1020500 | 2017-01-30T00:00:00 | DJAG
19/12/2017 | Housing | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The project has this month been focussed on providing extensive support to users across the state, with a 60-day hypercare support model in place to ensure that support requests are triaged and managed quickly and effectively. The project is now focussing on planning for a second stage Tenancy release. | 2017-11-30T00:00:00 | Critical | 56286000 | A | Housing Services | 48 | 60200000 | A | G | 1 | Replace the existing ICT housing solution with an integrated ICT system. | 70675462 | 2013-07-01T00:00:00 | HPW
19/12/2017 | PWAM | iSpace External Hosting Migration Project | 2017-01-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The User Acceptance Testing (UAT) is currently underway. Some vendor system releases had to be installed and UAT was extended as a result. The project team and the vendor are now amending the implementation plan with a new Go-live target in early 2018 (pending approval). | 2017-11-30T00:00:00 | High | 735000 | A | Queensland Government Accommodation Office | 95 | 785533 | A | A | 2 | Version upgrade and migration of the hosting of Queensland Accommodation Office core system to a hosted managed service arrangement. | 1415203 | 2016-05-01T00:00:00 | HPW
19/12/2017 | QGP | Fleet Management System Replacement Project (FMSRP - QFleet) | 2019-09-30T00:00:00 | Initiate | G | 2019-09-30T00:00:00 | Project commenced. | 2017-11-30T00:00:00 | High | 13939200 | G | QFleet | 2 | 160000 | G | G | 3 | The project will deliver for the Department of Housing and Public Works, Public Safety Business Agency and Queensland Ambulance Service a fleet management solution to replace existing aging legacy systems. | 13939200 | 2017-10-19T00:00:00 | HPW
19/12/2017 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 19/12/2017, 19/12/2017,October 2017 - The project is progressing as planned. 19/12/2017,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 19/12/2017,June 2017 - Revised Schedule approved returning the project to Green. 19/12/2017,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 19/12/2017,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 19/12/2017,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 19/12/2017,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 19/12/2017,December 2016 - The project is progressing as planned. | 2017-12-07T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 19/12/2017, 19/12/2017,* register and maintain their information 19/12/2017,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
19/12/2017 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 19/12/2017, 19/12/2017,August 2017 - Approved extension of timeframe. 19/12/2017,June 2017 - The project is progressing as planned. 19/12/2017,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 19/12/2017,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 19/12/2017,October 2016 - Progress is continuing as planned. 19/12/2017,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 19/12/2017,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 19/12/2017,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-07T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 19/12/2017, 19/12/2017,* support compliance with legislation 19/12/2017,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 19/12/2017,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 19/12/2017,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 19/12/2017, | 1390000 | 2012-04-01T00:00:00 | DEWS
19/12/2017 | BQ | Biosecurity Information Management System Program | 2017-05-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The planned end date has been extended by one month; this remains within acceptable project tolerances. 19/12/2017, 19/12/2017,March 2017 - The program is progressing as planned in line with approved change to scope, timeframe, benefits and cost. 19/12/2017,January 2017 - A small scope increase has been proposed, currently progressing through governance processes. 19/12/2017,November 2016 - Note, a scope review is currently under way. 19/12/2017,May 2016 - Program is continuing as planned. Note a small extension to planned end date. 19/12/2017,March 2016 - A re-baseline has brought all parameters back to Green. 19/12/2017,January 2016 - Timeframe, Cost, and Quality remain Amber, pending a business case update due early April 2016. 19/12/2017,November 2015 - Program is still Amber while the Timeframe is being re-baselined. 19/12/2017,September 2015 - The Exception Report has been accepted by the Program Board. Timeframe remains Amber pending a business case update. 19/12/2017,July 2015 - Resources continue to be redirected to assist with emergency response to the Panama banana disease. An Exception Report is being developed to address this. 19/12/2017,May 2015 - As anticipated, the emergency response to the Panama Banana disease outbreak has impacted both the project cost and the Timeframe. 19/12/2017,March 2015 - There is currently an outbreak of Panama banana disease which has potential to impact the schedule of this project. 19/12/2017,January 2015 - Actions are being taken to resolve some current scheduling issues. | 2017-10-17T00:00:00 | Critical | 18080000 | G | Biosecurity Queensland | 90 | 17516000 | G | G | 1 | Deliver an integrated toolkit consisting of various information management technologies and enhanced business processes to improve the management of biosecurity risks in Biosecurity Queensland's day-to-day business operations and in emergency responses. | 19409000 | 2013-07-01T00:00:00 | DAF
19/12/2017 | FQ | Coastal Surveillance Service renewal and enhancement | 2016-07-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | All deliverables have been achieved. The project closed on 31 October 2017. 19/12/2017, 19/12/2017,October 2017 - The project is progressing as planned. 19/12/2017,July 2017 - A further extension to the planned end date was approved with no impact on costs. 19/12/2017,March 2017 - A further extension to the planned end date was approved with no impact on costs as work has slowed, aligning with the vendor+S4's capacity to deliver. 19/12/2017,January 2017 - An extension to the planned end date was approved due to ongoing data verification trials between old and new processes. 19/12/2017,November 2016 - An extension to the planned end date was approved. Note the actual cost to date adjustment due to previously included recurrent operational costs by mistake. 19/12/2017,September 2016 - The planned end date was extended due to upgrades of software and network connectivity taking longer than expected. 19/12/2017,July 2016 - An extension to the planned end date was approved. Note the previous estimated expenditure included recurrent operational costs by mistake. 19/12/2017,March 2016 - The project is continuing as planned. | 2017-11-01T00:00:00 | High | 115782 | G | Fisheries Queensland | 100 | 103187 | G | G | 2 | The primary objectives will be: 19/12/2017, 19/12/2017,* reduction of manual data entry tasks and automation of administration and reporting processes 19/12/2017,* improvement in ability to respond to entanglements and recover equipment in a more timely way 19/12/2017,* a single location for all data 19/12/2017,* direct integration with EHP's StrandNet application. 19/12/2017, | 115782 | 2015-08-01T00:00:00 | DAF
19/12/2017 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery | G | 2018-01-31T00:00:00 | The project is continuing as planned. 19/12/2017, 19/12/2017,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2017-11-20T00:00:00 | Medium | 608146 | G | Forestry Queensland | 75 | 607646 | G | G | 3 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 19/12/2017, 19/12/2017,* the capture, management and integration of data 19/12/2017,* value-adding opportunities for business improvement 19/12/2017,management of risk associated with ongoing use and maintenance of disparate systems. | 706063 | 2016-06-15T00:00:00 | DAF
19/12/2017 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
19/12/2017 | PSBA | Emergency Services Computer Aided Dispatch (ESCAD) Upgrade Program | 2016-09-30T00:00:00 | Delivery | G | 2018-07-03T00:00:00 | Queensland Ambulance Service (QAS) and Queensland Fire and Emergency Services (QFES) successfully completed the User Acceptance Testing (UAT) of Pre-Production and Training environments of the upgraded ESCAD system and the Operator Trainings are proceeding in October 2017. Meanwhile, the Detailed Cut Over Planning is progressing and targets the Cut Over Period in January 2018, subject to any latent technical issues and any unforeseen significant events. The Assurance Gate Review is currently underway to assess the readiness for the upgraded ESCAD system. The Planned expenditure on the Whole of Government ICT Dashboard reflects the total approved budgets funded by QAS and QFES. | 2017-10-16T00:00:00 | Critical | 6774820 | G | Public Safety Business Agency | 72 | 8348933 | G | G | 1 | A program of work for Queensland Ambulance Service and Queensland Fire and Emergency Services to upgrade the Emergency Services Computer Aided Dispatch System, including infrastructure, operating system and application software. | 10289600 | 2015-01-15T00:00:00 | PSBA
19/12/2017 | PSBA | Emergency Vehicle Priority (EVP) Project | 2016-06-30T00:00:00 | Delivery | G | 2017-12-15T00:00:00 | EVP request for further extension to June 2018 pending funding availability. EVP rollout to Cairns has completed and will continue to work with Transport and Main Roads in undertaking further rollouts across Queensland, including Ipswich, Rockhampton and Gladstone. Procurement contract near finalised and Project continuing with procurement of system support managed service with anticipation of a contract in place late October 2017. | 2017-10-16T00:00:00 | High | 3370000 | G | Public Safety Business Agency | 86 | 3794740 | G | G | 2 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 19/12/2017, 19/12/2017,* Responsive vehicle movements 19/12/2017,* Improve road safety 19/12/2017,* Congestion management 19/12/2017,* Community safety | 3794740 | 2013-01-01T00:00:00 | PSBA
19/12/2017 | PSBA | Inter-CAD Electronic Messaging System (ICEMS) | 2017-12-01T00:00:00 | Delivery | G | 2017-12-01T00:00:00 | Stage 3 has been extended to 1/12/17 and delivery is being closely monitored for completion on this date. Please note: The original planned end date has been updated to correct an error that was previously published. | 2017-10-16T00:00:00 | Critical | 560000 | G | Public Safety Business Agency | 92 | 1507030 | G | G | 3 | To implement the ICEMS protocol between the Queensland Police Service (QPS), Queensland Ambulance Service (QAS) and Queensland Fire and Emergency Services (QFES) computer aided dispatch systems to enable Triple Zero data sharing between agencies. | 1674541 | 2015-10-06T00:00:00 | PSBA
19/12/2017 | PSBA | QAS Office 365 Implementation Project | 2017-06-30T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The Queensland Ambulance Service Office 365 Implementation Project is responsible for migrating all Queensland Ambulance Service email mailboxes and archive mailboxes to Office 365. Project is tracking to schedule, budget and has no major issues blocking it from being delivered by 31 October 2017. $400,000 was deferred from FY16/17 to continue the migrations and an additional $400,000 has been allocated. | 2017-10-16T00:00:00 | Medium | 1544817 | G | Public Safety Business Agency | 69 | 1134887 | G | G | 4 | The project will deliver digital transformation for Queensland Ambulance Service (QAS) through the implementation of the Office 365 suite of products to augment the below enhancements to their current business processes. 19/12/2017, 19/12/2017,1. Undertaking smarter meetings; 19/12/2017,2. Facilitating better administration; 19/12/2017,3. Accessing information anywhere, any time; 19/12/2017,4. Engaging and communicating better; 19/12/2017,5. Supporting capability development; 19/12/2017,6. Facilitating business intelligence; and 19/12/2017,7. Enabling efficient workflow and approvals. | 1402889 | 2017-01-23T00:00:00 | PSBA
19/12/2017 | PSBA | QPS Office 365 Pilot and Office Client Upgrade Project | 2017-06-30T00:00:00 | Closed | G | 2017-08-31T00:00:00 | Project complete. | 2017-10-16T00:00:00 | Critical | 1030000 | G | Public Safety Business Agency | 100 | 965484 | G | G | 5 | The project will enable Queensland Police Service (QPS) to evaluate the suitability of the Office 365 services for potential wider rollout across the agency and upgrade all QPS installations of Office 2013 to Office Pro Plus 2016. | 1029692 | 2017-01-30T00:00:00 | PSBA
19/12/2017 | OSR | SPER Program | 2017-12-31T00:00:00 | Delivery | A | 2018-03-30T00:00:00 | * 15/05/2017 - The State Penalties Enforcement Amendment Bill 2017 features Work and Development Orders (WDO), offering Queenslanders experiencing genuine hardship with alternative ways to reduce or pay off their debt was passed in Parliament on the 10th May 2017. The Bill will simplify the fee arrangements, making it easier for our customers to understand their obligations, and facilitate a case management approach to people with SPER debts. The implementation of the ICT system solution (Stage 2) is continuing, and in parallel, SPER are initiating a re-baselining exercise of the implementation scope, approach and schedule. 19/12/2017,* 08/06/2017 - A re-baselining exercise of the implementation scope, approach and schedule is progressing and is anticipated to be completed by 30 June 2017. 19/12/2017,* 17/07/2017 - Expenditure to date: $22.5M has been for the transformation of the SPER function; and $8.7M has been on the build phase of the ICT Implementation (Software as a Service - SaaS). 19/12/2017,Original Planned Expenditure and Cost to date has been updated to include the ICT Implementation Solution. The remaining components of the Program includes further functional design and build of the replacement ICT solution. A revised delivery date is targeted for Quarter 1, 2018. 19/12/2017,* 04/10/2017 - Revised and detailed delivery schedule is being finalised. The SPER Program has completed the implemention of the new governance arrangements focussing on ICT delivery and the management and control of risks, designed to safeguard the new implementation approach. | 2017-10-06T00:00:00 | High | 47200000 | G | State Penalties Enforcement Registry | 46 | 38378000 | A | A | 1 | To maintain the integrity of fines as an effective sanction. To uphold confidence in the justice system. To deliver efficient and effective debt management practices which provide value for money to the State. 19/12/2017, | 47200000 | 2014-01-01T00:00:00 | QR
19/12/2017 | OSR | Contact Centre | 2017-09-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | * 06/04/2017 - Design activities have commenced and are on track for completion by the end of April. Business deployment schedule has been confirmed. Network and infrastructure activities have commenced. 19/12/2017,* 05/05/2017 - Design has been finalised and build activities have commenced. Project on track for delivery by end of September 2017. 19/12/2017,* 06/06/2017 - Project remains on track. Build and unit testing is on schedule for completion on 19th June 2017. Commissioning of a new communications link is planned for the week commencing 12th June. Change Impact Assessment work is in progress. 19/12/2017,* 10/07/2017 - Due to a network freeze in Queensland Treasury the project has been unavoidably delayed, impacting the implementation schedule and the project budget. The project has been re-baselined with the planned end date October 2017 and there is sufficient funds allocated to the 2017/18 budget. 19/12/2017,* 11/08/2017 - Project on track for first deployment scheduled 25th September 2017. System Integration Testing complete and User Acceptance Testing scheduled for commencement 21st August, 2017. 19/12/2017,* 04/10/2017 - First Contact Centre go live completed, with the second deployment scheduled for 9th October. On track to complete all rollouts by end of October 2017. | 2017-10-04T00:00:00 | Medium | 1020000 | G | Office of State Revenue | 95 | 974214 | G | G | 2 | The Office of State Revenue's existing contact centre solution has reached its end of life. As a result, the Office of State Revenue is implementing a new comprehensive call centre solution designed to improve productivity and the client experience across all taxes and the Queensland First Home Owners' Grant administered by the office. | 1080300 | 2017-02-27T00:00:00 | QR
19/12/2017 | OIR | Renewal and Photographic Licensing System (RAPS) Assessor Portal | 2018-07-13T00:00:00 | Delivery | G | 2018-05-10T00:00:00 | * 27/03/2017 - The project has been initiated. Recruitment is now complete and development work has commenced. 19/12/2017,* 02/05/2017 - Resources commencing to undertake the first Development phase. Business requirements analysis is progressing. 19/12/2017,* 02/06/2017 - Contract Lead Developer engaged undertaking prepartion works for first development phase. Business requirements analysis continues to progress. 19/12/2017,* 11/07/2017 - Project scope reviewed to deliver the business and stakeholders critical functionality. Project resources continuing to be recruited during July. 19/12/2017,* 11/08/2017 - Revised project scope, which includes the changes to the schedule, costs and benefits, has been approved. The project has now commenced into the development phase, with business analysis continuing in parallel with early development. 19/12/2017,* 04/10/2017 - Development phase and business analysis continued to progress. Business requirements to be completed by end of October. | 2017-10-04T00:00:00 | High | 766467 | G | Office of Industrial Relations | 20 | 220999 | G | G | 3 | The RAPS Assessor Portal project commenced as an initiative to target improving services for high risk work licensing accredited assessors, registered training organisations and licensing and advisory services. Currently accredited assessors must use a combination of cumbersome paper based processes, smart forms, and an online service that is difficult to use. This project will improve and integrate the external and internal applications and reduce duplicated processes for high-risk work licensing stakeholders whilst meeting legislative requirements. One simplified online service will be delivered for assessors that will save them time and make compliance easier. | 769103 | 2016-12-14T00:00:00 | QR
19/12/2017 | RI | Financial Assurance Information Registry (FAIR) | 2018-07-01T00:00:00 | Initiate | G | 2018-07-01T00:00:00 | * 23/06/2017 - Project continuing in planning phase, appropriate governance mechanisms have been established. 19/12/2017,* 10/07/2017 - Awaiting outcome of public consultation before refining system design and scope. Adjustments made to the project expenditure and planned end date to cater for rounding up and actual go-live date of the ICT solution. 19/12/2017,* 11/08/17 - Preparing for Investment Review, after the review the project will move to the build phase. 19/12/2017,* 04/10/2017 - Project passed Investment Review. Project Manager has commenced and the engagement of the development team is being finalised. | 2017-10-04T00:00:00 | Medium | 15900000 | G | Insurance Commission | 12 | 301107 | G | G | 4 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
19/12/2017 | RI | Information Security Program | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | * 06/10/2017 - Project is in initiation phase, undertaking planning, procurement and recruitment activities. | 2017-10-06T00:00:00 | Medium | 0 | G | Office of the Chief Information Officer | 0 | 0 | G | G | 5 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 19/12/2017, | 0 | 2017-10-16T00:00:00 | QR
19/12/2017 | OSR | OSR Transformation Program | 2020-06-30T00:00:00 | Delivery | G | 2020-06-30T00:00:00 | * 04/10/2017 - Undertaking a series of Process Re-design Sprints to allow for the rapid exploration of opportunities that exist within a process, and developing recommedations for a future version of the process. Initial series of sprints will continue through to November 2017. Deployment of the first data stream related initiative, Single Customer View for Individuals ( Phase 1) is on track for go live End October 2017. Commenced project to deliver a pilot for the Virtual Assistant initiative, the pilot is planned for end of November 2017. | 2017-10-04T00:00:00 | High | 66918000 | G | Office of State Revenue | 1 | 122972 | G | G | 6 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 19/12/2017, 19/12/2017,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 66918000 | 2017-08-01T00:00:00 | QR
19/12/2017 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
19/12/2017 | Corporate Services Improvement Systems Board | Human Resource Management Improvement | 2016-06-30T00:00:00 | Closed | G | 2017-09-15T00:00:00 | The Human Resource Management Improvement project closure report was approved by the Project Board in September 2017. This project will no longer report on the ICT Dashboard. | 2017-10-31T00:00:00 | High | 2500000 | G | Information Technology Branch | 100 | 3732726 | G | G | 1 | To improve people management processes, provide greater workforce reporting and support better workforce decisions by implementing a range of system improvements to the TMR HR data platform. | 4234000 | 2015-01-05T00:00:00 | TMR
19/12/2017 | Corporate Services Improvement Systems Board | Learnzone Improvement Project | 2017-06-30T00:00:00 | Delivery | G | 2017-09-30T00:00:00 | The LearnZone Improvement project is on track. | 2017-10-31T00:00:00 | High | 796000 | G | Transactional Services Improvement Program | 95 | 418782 | G | G | 2 | Innovate, develop and deliver an improved and centralised digital learning service and management function. 19/12/2017, 19/12/2017, | 801000 | 2016-02-01T00:00:00 | TMR
19/12/2017 | Corporate Services Improvement Systems Board | Lotus Notes Decommissioning | 2016-01-31T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project is on track. | 2017-10-31T00:00:00 | High | 8150000 | G | ERP Projects Board | 63 | 1541945 | G | G | 3 | Deliver improved information platform functions for effective ICT Strategy Alignment | 8150000 | 2015-11-01T00:00:00 | TMR
19/12/2017 | Corporate Services Improvement Systems Board | Stop Cheques - Stage 3 | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Stop Cheques Stage 3 project is on track. | 2017-10-31T00:00:00 | Medium | 200000 | G | ERP Projects Board | 20 | 101255 | G | G | 4 | Cheques are inefficient and costly to use, process and administer for both the customer and department. A range of solutions have been developed to reduce the number of cheques that the department produces or receives including refund to card at counter | 200000 | 2017-07-01T00:00:00 | TMR
19/12/2017 | Corporate Services Improvement Systems Board | Risk Management Solution | 2018-07-01T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Risk Management Solution project is on track. | 2017-10-31T00:00:00 | High | 350000 | G | Corporate Services Improvement Systems Board | 20 | 472873 | G | G | 5 | Replace the current risk management approach through the delivery of a new and contemporary enterprise Risk Management solution for TMR . | 710000 | 2017-07-02T00:00:00 | TMR
19/12/2017 | Corporate Services Improvement Systems Board | Integrated Records Information System (IRIS) | 2018-07-01T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The IRIS project is on track. | 2017-10-31T00:00:00 | High | 7967972 | G | Information Technology Branch | 25 | 1638111 | G | G | 6 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 7967972 | 2017-07-02T00:00:00 | TMR
19/12/2017 | Corporate Services Improvement Systems Board | Transactional Services Improvement Program Enhancements | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Transactional Services Improvement Program Enhancements Stage 3 is on track. | 2017-10-31T00:00:00 | Low | 200000 | G | Transactional Services Improvement Program | 20 | 103953 | G | G | 7 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolid | 200000 | 2017-07-01T00:00:00 | TMR
19/12/2017 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery | G | 2018-09-30T00:00:00 | The CDOP Online Portal project is on track. | 2017-10-31T00:00:00 | High | 1500000 | G | Customer Services, Safety and Regulation Division | 86 | 699513 | G | G | 8 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal | 1441000 | 2016-01-01T00:00:00 | TMR
19/12/2017 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The eLearner project is currently on track. | 2017-10-31T00:00:00 | High | 2500000 | G | Customer Services, Safety and Regulation Division | 94 | 3992296 | G | G | 9 | Implement an online learning and assessment program at the pre-learner and/or learner stage, to replace enhance learning outcomes. | 4176000 | 2015-06-12T00:00:00 | TMR
19/12/2017 | Customer Service, Safety and Regulation Program | Facial Recognition Replacement | 2017-03-31T00:00:00 | Delivery | G | 2017-08-31T00:00:00 | The Facial Recognition project has successfully completed its scope and a project closure report will be submitted to the Program Board for consideration in November 2017 | 2017-10-31T00:00:00 | High | 531250 | G | Customer Services, Safety and Regulation Division | 99 | 600675 | G | G | 10 | To provide Queensland integration with the National Driver Licence Facial Recognition System (NDLFRS) as part of the National Facial Recognition Matching Capability. This project will see the sharing of and upload of TMR facial image holdings to a nationa | 631250 | 2015-07-13T00:00:00 | TMR
19/12/2017 | Customer Service, Safety and Regulation Program | Hardware Security Modules (HSM) | 2016-07-29T00:00:00 | Delivery | G | 2017-08-31T00:00:00 | The HSM project has successfully completed its scope and a project closure report will be submitted to the Program Board for consideration in November 2017 | 2017-10-31T00:00:00 | High | 500000 | G | Customer Services, Safety and Regulation Division | 99 | 394206 | G | G | 11 | The Hardware Security Modules (HSMs) form part of the Queensland Driver Licence smartcard product set introduced in 2010 and generate keys for smartcard authentication and validation by TMR-authorised card readers at TMR Customer Service Centres, QGAP and | 500000 | 2015-08-01T00:00:00 | TMR
19/12/2017 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The Mobile Compliance Information System project is on track. | 2017-10-31T00:00:00 | High | 300000 | G | Customer Services, Safety and Regulation Division | 77 | 563964 | G | G | 12 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 630000 | 2016-11-01T00:00:00 | TMR
19/12/2017 | Customer Service, Safety and Regulation Program | Online Customer Experience Phase 3 | 2017-06-30T00:00:00 | Closed | G | 2017-06-30T00:00:00 | The Online Customer Experience Phase 3 project closure report was approved by the Project Board in September 2017. This project will no longer report on the ICT Dashboard. | 2017-10-31T00:00:00 | Low | 1265000 | G | Customer Services, Safety and Regulation Division | 100 | 1077498 | G | G | 13 | Within the Online Customer Experience Phase 3 Program the following initiatives will be completed: 19/12/2017, eNotices Expansion eReminder 19/12/2017, Re-architecture Authentication 19/12/2017, Disability Parking Permits 19/12/2017, OnlineWeb Chat | 1059481 | 2016-07-01T00:00:00 | TMR
19/12/2017 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery | G | 2017-12-24T00:00:00 | The Ralph Replacement project is on track. | 2017-10-31T00:00:00 | Medium | 500000 | G | Customer Services, Safety and Regulation Division | 58 | 561535 | G | G | 14 | TMR's current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace | 674000 | 2016-07-01T00:00:00 | TMR
19/12/2017 | Customer Service, Safety and Regulation Program | Voice Comms Mgt System | 2017-06-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | The Voice Comms Management System project is on track. | 2017-10-31T00:00:00 | Medium | 828000 | G | Customer Services, Safety and Regulation Division | 75 | 274738 | G | G | 15 | The Voice Comms Management project consists of two replacement of existing Voice Communication and Control Systems at Townsville and Hay Point. | 828000 | 2016-01-01T00:00:00 | TMR
19/12/2017 | Customer Service, Safety and Regulation Program | CTP Tax Invoice Online | 2017-12-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The CTP Tax Invoice Online project is on track. | 2017-10-31T00:00:00 | Medium | 300000 | G | Customer Services, Safety and Regulation Division | 10 | 49603 | G | G | 16 | The Compulsory Third Party Tax Invoice Online project will deliver a new online service which will enable Customers to self-serve and print an electronic version of the CTP Invoice, removing the need for TMR to process paper based invoices, avoiding produ | 300000 | 2017-05-01T00:00:00 | TMR
19/12/2017 | Customer Service, Safety and Regulation Program | MSQ iBase Project | 2017-06-30T00:00:00 | Delivery | G | 2017-07-28T00:00:00 | The MSQ iBase project has successfully completed its scope and a project closure report will be submitted to the Program Board for consideration in November 2017. | 2017-10-31T00:00:00 | Low | 450000 | G | Customer Services, Safety and Regulation Division | 99 | 227589 | G | G | 17 | The Maritime Safety Queensland ibase Project has commenced as the current incident register platform has been identified as requiring replacement. The future platform will work in collaboration with current field input and smart devices. | 292000 | 2017-01-01T00:00:00 | TMR
19/12/2017 | Customer Service, Safety and Regulation Program | R and L Systems Software Upgrade | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The R and L Systems Software Upgrade project is on track. | 2017-10-31T00:00:00 | Medium | 780000 | G | Customer Services, Safety and Regulation Division | 20 | 34459 | G | G | 18 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
19/12/2017 | Infrastructure Management and Delivery | Access Management System (AMS) - formerly Heavy Vehicle Permit Management System | 2015-10-31T00:00:00 | Paused | A | 2017-06-30T00:00:00 | TMR is taking steps to conclude the Access Management System project, in light of significant changes in the operating environment since it was commenced, including the way permits are issued and the role of the National Heavy Vehicle Regulator with its A | 2017-10-31T00:00:00 | High | 4281564 | A | Infrastructure Management 19/12/2017,and Delivery | 83 | 8307429 | A | A | 19 | Improve heavy vehicle and load movement safety through effective schemes, guidelines and conditions management 19/12/2017, Allow coordinated road operations such that an increase in activity will not result in economic detriment or a loss of safety and public ame | 9001258 | 2013-06-01T00:00:00 | TMR
19/12/2017 | Infrastructure Management and Delivery | Work Improvement Note (WIN) Replacement | 2016-12-19T00:00:00 | Delivery | G | 2017-10-11T00:00:00 | The WIN Replacement project project is on track. | 2017-10-31T00:00:00 | Low | 242612 | G | Infrastructure Management 19/12/2017,and Delivery | 89 | 232264 | G | G | 20 | The Work Improvement Note (WIN) System is used to capture, track, review and report on improvements, potential problems, non-conformances, corrective actions, customer feedback and complaints. The WIN System is an essential component of the overarching bu | 409763 | 2016-02-15T00:00:00 | TMR
19/12/2017 | Infrastructure Management and Delivery | 2018 Commonwealth Games Journey Planner (GJP) | 2017-10-13T00:00:00 | Delivery | G | 2018-04-27T00:00:00 | The 2018 Commonwealth GJP project is on track. | 2017-10-31T00:00:00 | High | 450000 | G | Infrastructure Management 19/12/2017,and Delivery | 65 | 477851 | G | G | 21 | A dedicated Journey Planner application supports this need by providing a single source of truth for all transport information related to the Games, and also allows for rapid changes to routes, schedules, and stops, if any are required, in order to drive | 973899 | 2016-10-16T00:00:00 | TMR
19/12/2017 | Passenger Transport Technology Program | Customer Contact Management Solution (CCMS) | 2017-06-30T00:00:00 | Delivery | G | 2017-11-10T00:00:00 | The CCMS project is on track. | 2017-10-31T00:00:00 | High | 1279000 | G | TransLink | 85 | 1406139 | G | G | 22 | To implement an industry standard, robust and extensible solution to replace the existing Commentline solution. To achieve better performance of the customer contact management functions. To provide the base platform to support the future implementation | 1279000 | 2016-04-01T00:00:00 | TMR
19/12/2017 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The STAS Auto Forms project is on track. | 2017-10-31T00:00:00 | High | 4166000 | G | TransLink | 59 | 2856066 | G | G | 23 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 5043876 | 2016-04-01T00:00:00 | TMR
19/12/2017 | Policy Planning and Investment Program | Portfolio, Program, Project and Contract Management (3PCM) - Phase 2 and 3 | 2017-03-31T00:00:00 | Delivery | A | 2017-12-22T00:00:00 | The 3PCM project is currently reporting amber for quality as there is a small number of defects from a recent data migration activity that is currently being investigated and resolved. | 2017-10-31T00:00:00 | High | 12757788 | G | Policy, Planning and Investment Division | 98 | 47629762 | G | A | 24 | Define and implement standard, consistently applied processes for planning, managing and delivering the Transport Infrastructure Portfolio across the domains of portfolio, program, project and contract management 19/12/2017, Source and implement an integrated, s | 47670648 | 2012-09-01T00:00:00 | TMR
19/12/2017 | CS | Bandwidth Upgrade Project | 2017-07-31T00:00:00 | Closed | G | 2017-08-02T00:00:00 | The project completed closure on 30 June 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | High | 5551767 | G | Corporate Services | 98 | 4575357 | G | G | 1 | To upgrade internet connectivity for Queensland State Schools, uplifting data speeds to 25kbps per student, improving access to online educational and community resources. 19/12/2017, | 4575357 | 2015-01-12T00:00:00 | DET
19/12/2017 | SS | Early Start | 2015-07-03T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Medium | 70000 | G | State Schools | 74 | 73522 | G | G | 2 | To provide schools with enhanced reporting functionality, improving their ability to analyse Prep to Year 2 student learning data. | 200992 | 2013-04-03T00:00:00 | DET
19/12/2017 | CS | eDRMS Upgrade Project | 2016-06-30T00:00:00 | Closed | G | 2017-07-04T00:00:00 | The project completed closure on 4 July 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | Critical | 2203000 | G | Corporate Services | 92 | 1734511 | G | G | 3 | To upgrade the key operational system so that it meets current and future demands and aligns with electronic information management practices. | 1680000 | 2015-01-12T00:00:00 | DET
19/12/2017 | PP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Delivery | G | 2018-02-27T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 700000 | G | Policy, Performance and Planning | 74 | 1125550 | G | G | 4 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
19/12/2017 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery | G | 2018-08-10T00:00:00 | The project is tracking to plan. The project is currently subject to procurement activities. | 2017-09-08T00:00:00 | High | 0 | G | Corporate Services | 37 | 0 | G | G | 5 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DET FBS SAP future state landscape for the next five years | 0 | 2017-01-16T00:00:00 | DET
19/12/2017 | SS | Global Learning Environment | 2018-12-30T00:00:00 | Closed | G | 2017-06-02T00:00:00 | The project completed closure on 13 July 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | Critical | 800000 | G | State Schools | 100 | 2552704 | G | G | 6 | To provide an online global learning solution which focuses on the 2018 Commonwealth Games, encouraging learning and collaboration in Queensland, nationally and internationally. | 2492000 | 2014-10-29T00:00:00 | DET
19/12/2017 | DG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery | G | 2018-01-01T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Low | 632585 | G | DG | 79 | 755722 | G | G | 7 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
19/12/2017 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery | G | 2019-12-18T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Critical | 16670000 | G | State Schools | 44 | 7426976 | G | G | 8 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 23470000 | 2015-08-03T00:00:00 | DET
19/12/2017 | PP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | The project is tracking to the revised plan. The project is currently subject to procurement activities. | 2017-09-08T00:00:00 | High | 0 | G | Policy, Performance and Planning | 54 | 0 | G | G | 9 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution | 0 | 2016-03-01T00:00:00 | DET
19/12/2017 | CS | Purchase IT Replacement Project | 2015-09-30T00:00:00 | Closed | G | 2017-09-18T00:00:00 | The project completed closure on 31 July 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | Medium | 248800 | G | Corporate Services | 99 | 905348 | G | G | 10 | To replace the existing system with a solution that meets current and future demands, provides enhanced analytics and improvements to reporting. | 1100000 | 2015-06-29T00:00:00 | DET
19/12/2017 | PP | Research Services 2.0 | 2016-09-30T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Low | 230000 | G | Policy, Performance and Planning | 85 | 404745 | G | G | 11 | To develop a solution that assists in the management of the Department of Education and Training commissioned research proposals and projects, improving resourcing and information dissemination. | 431157 | 2015-11-02T00:00:00 | DET
19/12/2017 | SS | School Budget Solution | 2017-03-31T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 2030000 | G | State Schools | 95 | 6295520 | G | G | 12 | To develop a solution that assists schools with resource management, improving their ability to support students in achieving better educational outcomes. | 6641785 | 2014-12-15T00:00:00 | DET
19/12/2017 | TS | Study Tours Support System Upgrade | 2016-06-30T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Medium | 680000 | G | Training and Skills | 96 | 772580 | G | G | 13 | To replace or upgrade the existing Study Tours system with an online solution that has enhanced functionality, improving processes, data quality and tour management. | 779894 | 2015-08-31T00:00:00 | DET
19/12/2017 | TS | Training Management System | 2016-12-31T00:00:00 | Delivery | A | 2018-04-30T00:00:00 | The project is being monitored for cost, schedule and quality. The project is currently subject to procurement activities. | 2017-09-08T00:00:00 | Critical | 0 | A | Training and Skills | 62 | 0 | A | A | 14 | To replace multiple systems with a solution that meets current and future demands, reduces costs and improves the management of vocational and educational training. | 0 | 2013-04-01T00:00:00 | DET
19/12/2017 | SS | Trial of platform for virtual academies | 2017-10-02T00:00:00 | Delivery | G | 2018-12-31T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 151641 | G | State Schools | 40 | 101875 | G | G | 15 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage; safe and secure like-minded student virtual communities; and strategic partnerships with university, industry and business. 19/12/2017, 19/12/2017, | 151641 | 2016-06-21T00:00:00 | DET
19/12/2017 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery | G | 2019-06-28T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 41000000 | G | Corporate Services | 48 | 25998875 | G | G | 16 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
19/12/2017 | [20 empty] | INVERSTMENT INFO
19/12/2017 | CSG | Coal Seam Gas Groundwater Monitoring Arrangements | 2017-12-31T00:00:00 | Paused | G | 2018-06-30T00:00:00 | Change to the planned end date approved, there is no impact to cost. Initiative now paused until early 2018. 19/12/2017, 19/12/2017,August 2017 - Revised total expenditure (budget) updated to include all operating costs not previously reported. 19/12/2017,June 2017 - Progress is continuing as planned. Still on schedule to complete December 2017. 19/12/2017,December 2016 - Much of the project has been completed and a significant amount of the procurement expenditure for capital equipment has occurred. 19/12/2017,October 2016 - Progress is continuing as planned. 19/12/2017,August 2016 - Cost returned to Green after a review of costs associated with activities remaining, and a correction in actual cost to date adjustment. 19/12/2017,June 2016 - Cost is Amber with a resource review under way. 19/12/2017,February 2016 - Progress is continuing as planned. 19/12/2017, | 2017-11-07T00:00:00 | High | 2380568 | G | Coal Seam Gas Compliance | 95 | 2548371 | G | G | 1 | Enhance availability of groundwater data through improvements to network monitoring of bores for clients and landholders. | 2598256 | 2014-01-13T00:00:00 | DNRM
19/12/2017 | SIMTARS | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery | G | 2017-11-10T00:00:00 | A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 19/12/2017, 19/12/2017,October 2017 - The project is continuing as planned. 19/12/2017,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2017-11-06T00:00:00 | High | 563000 | G | SIMTARS (Safety In Mines Testing and Research Station) | 98 | 589135 | G | G | 2 | The development and delivery of a (replacement) modern and robust Safegas solution: 19/12/2017, 19/12/2017,* risk reduction increasing capability to manage the volume of queries, transactions and data 19/12/2017,* decrease database corruption related to incidents. 19/12/2017, | 619000 | 2017-01-25T00:00:00 | DNRM
19/12/2017 | SO | Mines Infrastructure Risk Mitigation Project | 2019-02-18T00:00:00 | Delivery | G | 2019-02-18T00:00:00 | The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2017-11-14T00:00:00 | High | 1200000 | G | Statewide Operations | 5 | 56000 | G | G | 3 | Migrate systems to supported infrastructure and software to: 19/12/2017, 19/12/2017,* provide a stable, secure, fully supported and flexible solution 19/12/2017,* eliminate the risks to which the geoscience data assets are currently exposed. 19/12/2017, | 1200000 | 2017-08-08T00:00:00 | DNRM
19/12/2017 | GSQ | MinesOnlineMaps - Spatial Presentation Replacement | 2017-06-30T00:00:00 | Paused | G | 2018-04-30T00:00:00 | Project is paused awaiting review of a possible change in direction. Cost remains green while investigation is undertaken to identify if deferral request was processed. | 2017-11-16T00:00:00 | Medium | 531030 | G | Geological Survey of Queensland | 60 | 98271 | G | G | 4 | Provide a web-based mapping solution for the ongoing provision of MinesOnlineMaps (MOMaps) into the future. 19/12/2017, | 531030 | 2016-08-01T00:00:00 | DNRM
19/12/2017 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DPC
19/12/2017 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
19/12/2017 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 19/12/2017,* Move operational accountability and responsibility for print and imaging devices to the service provider 19/12/2017,* Reduce print and imaging costs 19/12/2017,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
19/12/2017 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
19/12/2017 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
19/12/2017 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 19/12/2017, 19/12/2017,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
19/12/2017 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
19/12/2017 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 19/12/2017, 19/12/2017,* reduce operating costs 19/12/2017,* increase capacity 19/12/2017,* improve customer experience 19/12/2017,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
19/12/2017 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
19/12/2017 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 19/12/2017, 19/12/2017, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
19/12/2017 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 19/12/2017, 19/12/2017,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
19/12/2017 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
19/12/2017 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | Actual cost to date corrected due to input error. 19/12/2017, 19/12/2017,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 19/12/2017, | 2017-11-21T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 49 | 584449 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
19/12/2017 | ESR | Environmental Management Register/Contaminated Land Register - replacement | 2017-06-30T00:00:00 | Paused | G | 2017-06-30T00:00:00 | August 2017 - The project is paused awaiting the outcome of a change request for additional scope - this will return the project to a Green state. 19/12/2017,April 2017 - A minor correction has been made to the revised total estimated expenditure to include $20,000 operating prior years. 19/12/2017,February 2017 - A change request has been approved moving the initiative cost back to Green. 19/12/2017,December 2016 - Project is continuing as planned, with a change request under way to return cost to Green. 19/12/2017,October 2016 - Project delivery activities formally commenced on 2 October 2016. 19/12/2017,August 2016 - The initiative was paused for some time but has now recommenced and moved into delivery. It is progressing as planned. | 2017-11-23T00:00:00 | High | 981680 | A | Environmental Services and Regulation | 78 | 718000 | A | A | 1 | The current system no longer supports efficient delivery of the department's responsibilities. The replacement will: 19/12/2017, 19/12/2017,* mitigate the risks associated with a system that is beyond its useful life 19/12/2017,* improve access to information by individuals, business and industry conducting searches (property lot plan) of the registers 19/12/2017,* support the creation of notices to stakeholders 19/12/2017,* reduce manual tasks through the introduction of automated workflows and customer self-serve and self-correct. 19/12/2017, | 1111680 | 2016-07-01T00:00:00 | EHP
19/12/2017 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP
30/12/2018 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-10-31T00:00:00 | High | 5600000 |  | eHealth Queensland | 51 | 4134115 |  | G | 1 | This project aims to establish a robust, highly available and secure contemporary platform that has the capability to support the agile eHealth Strategy. | 5492863 | 2017-07-03T00:00:00 | DH
30/12/2018 | HSQ | Pathology and Forensic Laboratory System Rehosting Project | 2018-06-30T00:00:00 | Delivery |  | 2018-12-13T00:00:00 | August 2018: This project has returned to 'green'. Approval was granted in August to extend the project's schedule to December 2018. 30/12/2018, 30/12/2018,July 2018: This project is now reporting 'red' due to delays to the infrastructure component of the project. Options are being prepared to minimise the impact to the overall schedule and cost of the project, to be approved in August 2018. 30/12/2018, 30/12/2018,Reason for variance: Latest approved budget includes both operational and capital costs and delays where experienced with the provisioning of required technical infrastructure. | 2018-11-12T00:00:00 | High | 1691324 |  | Health Support Queensland | 90 | 2582135 |  | G | 2 | Delivery of a replacement hardware and visualisation solution for the AUSLAB and AUSCARE systems that will achieve improved resiliency of the architecture, updated operating system and inclusion of virtualisation. AUSLAB and AUSCARE are critical to support laboratories and patient clinical care. | 3246769 | 2017-08-28T00:00:00 | DH
30/12/2018 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2018-09-30T00:00:00 | Delivery |  | 2018-11-30T00:00:00 |  | 2018-11-12T00:00:00 | High | 3692973 |  | Metro North | 95 | 1912261 |  | G | 3 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 30/12/2018, 30/12/2018,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Women's Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 30/12/2018, 30/12/2018,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 3692973 | 2015-06-01T00:00:00 | DH
30/12/2018 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 11180394 |  | eHealth Queensland | 35 | 815399 |  | G | 4 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 30/12/2018,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work.? Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 10915391 | 2017-07-03T00:00:00 | DH
30/12/2018 | EHQ | Digital Collaboration Platform Program | 2018-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | May 2018: This project has now returned to 'green' with the project's revised schedule being approved. 30/12/2018, 30/12/2018,March 2018: Project activities have continued to be delayed, resulting in this project reporting 'Red'. A project change request has been submitted to the project's governance committee. Successful deployment was recently achieved in Townsville. 30/12/2018, 30/12/2018,January 2018: This project is experiencing delays in pre-migration activities. 30/12/2018, 30/12/2018,Reason for variance: Original budget was reflective of an original estimate based on high level planning. Detailed planning has since refined the estimated budget (including vendor licensing arrangements) which received approval for budget increase in June 2017. | 2018-10-31T00:00:00 | High | 11000000 |  | eHealth Queensland | 40 | 18853354 |  | G | 5 | This program will deliver digital collaboration tools for any time, any where, any device including: 30/12/2018,? Email and Archiving 30/12/2018,? Establishment and Collaboration 30/12/2018,? Productivity Suite Enablement | 22664506 | 2015-10-29T00:00:00 | DH
30/12/2018 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate |  | 2017-12-31T00:00:00 | June 2018: The current proposed date of completion is the 31 December 2019, which is subject to project board approval. 30/12/2018, 30/12/2018,Reason for variance: The original estimated expenditure was projected prior to the Request for Information (RFI) to the open market. Consequently, the planned expenditure was revised based on the market responses following the RFI. | 2018-11-09T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 40 | 715063 |  | G | 6 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 5697000 | 2015-12-01T00:00:00 | DH
30/12/2018 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | October 2018: The project successfully went live in late September 2018, and is currently undergoing final project closure activities. 30/12/2018, 30/12/2018,May 2018: The project has completed a solution evaluation process, with the project requiring additional schedule and financials as originally approved. The project is expecting to return to 'green' upon receiving change request approval. 30/12/2018, 30/12/2018,Reason for variance: The evaluation process further revised the original budget and implementation was delayed to facilitate extended procurement processes. | 2018-11-08T00:00:00 | High | 1166363 |  | Chief Health Officer and Prevention | 98 | 389642 |  | G | 7 | Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1384239 | 2017-07-24T00:00:00 | DH
30/12/2018 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery |  | 2019-03-01T00:00:00 | October 2018: The budget has yet to be allocated for the Financial Year 18/19. The project's governance committee is monitoring budget expenditure. 30/12/2018, 30/12/2018,September 2018: Technical issues have impacted the current implementation schedule, with the project prioritising the correction of these issues. 30/12/2018, 30/12/2018,Reason for variance: Following a change in project scope and dependent implementations, the project was slightly extended to March 2019. | 2018-11-14T00:00:00 | High | 4827917 |  | Metro North | 68 | 4571072 |  | G | 8 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (ieMR) program. 30/12/2018, 30/12/2018,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 30/12/2018, 30/12/2018,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. | 4827917 | 2016-07-01T00:00:00 | DH
30/12/2018 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | April 2018: This initiative is now 'in delivery'. | 2018-10-31T00:00:00 | High | 3792744 |  | eHealth Queensland | 30 | 887425 |  | G | 9 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment.??The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access.? | 3723476 | 2017-07-05T00:00:00 | DH
30/12/2018 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | October 2018: The project continues to work with implementation partners to finalise the schedule and cost of go-live. System integration and change management activities are continuing to be a primary focus of the project. Schedule and cost details will be updated upon approval of a change request. 30/12/2018, 30/12/2018,August 2018: The project is reporting red due to schedule delays and an anticipated funding shortfall associated with integration complexities and change management activities required. A change request is progressing to address these concerns. | 2018-11-13T00:00:00 | High | 105000000 |  | Metro North | 66 | 100020900 |  | R | 10 | The current Queensland Health Finance, Asset and Materials Maintenance Information System (FAMMIS) system is based on a heavily customised solution which is almost 20 years old and no longer supported. 30/12/2018,The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 30/12/2018, 30/12/2018,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 30/12/2018,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 30/12/2018, 30/12/2018,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
30/12/2018 | EHQ | Follow Me Desktop - Deployment | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 3952980 |  | eHealth Queensland | 71 | 2016512 |  | G | 11 | Follow Me Desktop Deployment Project will deliver: the Follow Me Desktop service (FMD) to HHS' in alignment with the Infrastructure Remediation Program (IMP) and ieMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 3621306 | 2017-07-03T00:00:00 | DH
30/12/2018 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 3301500 |  | eHealth Queensland | 41 | 1328776 |  | G | 12 | Project Purpose:?To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 2345263 | 2017-07-01T00:00:00 | DH
30/12/2018 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 1120000 |  | eHealth Queensland | 65 | 731336 |  | G | 13 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. | 1072242 | 2017-07-05T00:00:00 | DH
30/12/2018 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery |  | 2020-06-26T00:00:00 | Reason for variance: The scope and schedule for IAMP has been extended due to revised timelines to accommodate for extended development, integration, and deployment activities. | 2018-10-31T00:00:00 | High | 3215000 |  | eHealth Queensland | 40 | 6201355 |  | G | 14 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 12206443 | 2015-06-22T00:00:00 | DH
30/12/2018 | EHQ | ieMR Program (Funding Packages 3 and 4) | 2019-04-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | August 2018: The SurgiNet component of ieMR went live at The Townsville Hospital in August 2018. This builds on existing ieMR capability, providing pre and post operative documents directly into the patient chart module, to better support patient care. 30/12/2018, 30/12/2018,July 2018: The Enterprise Schedule Management (ESM) component of ieMR went live at The Townsville Hospital in July 2018. This updated patient scheduling tool will improve inpatient and outpatient scheduling processes. 30/12/2018, 30/12/2018,June 2018: The advanced version of the ieMR system has gone live at the Queen Elizabeth II (QEII) Hospital in June, which includes enhancements to the interface between ieMR and the XRay Radiology Information System. 30/12/2018, 30/12/2018,May: The advanced version of the ieMR system has gone live at the Redland Hospital. Additional clinical reporting was also enabled by ieMR in May. | 2018-10-31T00:00:00 | High | 0 |  | eHealth Queensland | 33 | 0 |  | G | 15 | ieMR will enable improved patient care through the development of a state-wide, authoritative single source of the patient records. 30/12/2018, 30/12/2018,The ieMR will provide clinicians with the ability to: 30/12/2018,* access data that is integrated, accurate and clinically relevant 30/12/2018,* support decision making and better use of information 30/12/2018,* optimise management of patients, resources and provision of services 30/12/2018,* support interaction across a network of providers by making it easier to find providers, transfer information and collaborate with multidisciplinary providers. 30/12/2018,The Program scope (all tranches) is to roll out the ieMR system to 24 hospitals across Queensland. 30/12/2018, 30/12/2018,Please note that financial information for ieMR is Commercial in Confidence | 0 | 2016-11-17T00:00:00 | DH
30/12/2018 | EHQ | Infrastructure Maintenance Program Establishment | 2018-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | March 2018: This initiative has been refocused to the establishment phase of the Infrastructure Maintenance Program, and as such the % complete and original end date have been updated to reflect this phase of the program. The latest approved end date will be updated in a following reporting month. | 2018-10-31T00:00:00 | High | 1161414 |  | eHealth Queensland | 95 | 1330542 |  | G | 16 | The Infrastructure Maintenance Program (IMP)?will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 30/12/2018,The scope includes: 30/12/2018,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 30/12/2018,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and? 30/12/2018,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1922376 | 2017-07-03T00:00:00 | DH
30/12/2018 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery |  | 2022-06-30T00:00:00 |  | 2018-11-02T00:00:00 | High | 14673739 |  | Clinical Excellence | 22 | 2596831 |  | G | 17 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 30/12/2018,The ongoing program of work aims to continue and build upon existing functionality by: 30/12/2018,? Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 30/12/2018,? Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 30/12/2018,? Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 30/12/2018,? Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 30/12/2018,? Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
30/12/2018 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate |  | 2022-12-21T00:00:00 | Reason for variance: Budget was revised following market evaluation. | 2018-11-09T00:00:00 | High | 6300000 |  | Queensland Ambulance Service | 30 | 2275278 |  | G | 18 | Phased delivery of a system supporting QAS business intelligence. | 9240000 | 2017-01-03T00:00:00 | DH
30/12/2018 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | Reason for variance: Budget has been revised as a result of reallocation of funding provided under the Specialist Outpatient Strategy to support additional statewide Smart Referrals functionality. 30/12/2018,Schedule has been impacted by only 6months yet still falls within the commitment timeframe. | 2018-11-07T00:00:00 | High | 33827000 |  | Clinical Excellence | 37 | 17931615 |  | G | 19 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 39408218 | 2017-03-01T00:00:00 | DH
30/12/2018 | EHQ | Interoperability Project | 2016-04-29T00:00:00 | Delivery |  | 2019-09-29T00:00:00 | Reason for variance: Original funding was reflective of committed funding made available to commence planning activities (including business case development) and implementation of risk mitigation activities of the existing interoperability solution, until such time (late 2017) approval for the implementation of the new solution was granted. | 2018-11-14T00:00:00 | High | 39189509 |  | eHealth Queensland | 35 | 20201276 |  | G | 20 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 30/12/2018,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 30/12/2018,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 30/12/2018, | 39189509 | 2015-02-01T00:00:00 | DH
30/12/2018 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Delivery |  | 2020-12-21T00:00:00 | Reason for variance: The latest budget was revised based on the latest governance approval. The schedule has been revised to accommodate for extended procurement timeframes and additional prototyping activities being added to the scope of the program. | 2018-11-12T00:00:00 | High | 64000000 |  | Health Support Queensland | 59 | 24872155 |  | G | 21 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 30/12/2018,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. | 63558771 | 2015-08-28T00:00:00 | DH
30/12/2018 | GCHHS | Medical Imaging Informatics Solution (MIIS) Risk Mitigation | 2018-12-31T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | October 2018: The project is continuing to report amber, with the project adjusting scope to ensure the solution aligns with the current budget. In addition, recruitment delays have impacted the project's schedule. 30/12/2018, 30/12/2018,Reason for variance: Revised project delivery costs were approved in March 2018, as part the Stage Gate 3 Business Case. 30/12/2018,Schedule was revised to align with the Digital Healthcare Program (ieMR) on the Gold Coast. | 2018-11-12T00:00:00 | High | 5000000 |  | Gold Coast | 33 | 3055548 |  | A | 22 | The Medical Imaging Informatics Solution (MIIS) Risk Mitigation project has identified an Imaging solution which will address the risks and opportunities described in the Case for Change including the mitigation of patient safety risks, increased efficiency and productivity, improvi.ng medical imaging billing revenue collection and cash flow. The solution has user endorsement from radiologists and clinicians and will be specifically configured to meet GCHHS?s needs. | 12800000 | 2017-04-03T00:00:00 | DH
30/12/2018 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Reason for variance: The end date of the project was extended to accommodate additional go-live finalisation activities. | 2018-11-12T00:00:00 | High | 4030460 |  | Metro North | 85 | 4290772 |  | G | 23 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 30/12/2018, 30/12/2018,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 30/12/2018, 30/12/2018,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
30/12/2018 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | May 2018: This project has returned to 'green', with the project's schedule and budget being monitored by the project's governance committee. 30/12/2018, 30/12/2018,April 2018: The project is continuing to report 'Red' due to continued delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. 30/12/2018, 30/12/2018,Reason for variance: The budget was extended to accommodate additional implementation scope. | 2018-11-12T00:00:00 | High | 6340000 |  | Metro North | 5 | 6925962 |  | G | 24 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 8161556 | 2014-06-01T00:00:00 | DH
30/12/2018 | EHQ | Metro South and East Queensland ICT Infrastructure Replacement Initiative | 2018-06-29T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | October 2018: The project is currently reporting red, with the project requesting additional budget to successfully complete project deliverables. A request to extend the budget has been submitted to the project's governance committee for approval. | 2018-10-31T00:00:00 | High | 4160449 |  | eHealth Queensland | 72 | 2278250 |  | R | 25 | Will replace or uplift out of date end of life ICT assets. | 3583313 | 2017-07-01T00:00:00 | DH
30/12/2018 | EHQ | Metro South East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-04-29T00:00:00 |  | 2018-10-31T00:00:00 | High | 2182844 |  | eHealth Queensland | 85 | 1170603 |  | G | 26 | Will replace or uplift out of date end of life ICT assets. | 2154311 | 2017-07-01T00:00:00 | DH
30/12/2018 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | August 2018: The project has returned to 'green'. Activities to improve project team resourcing and increase key deployment rates are continuing into September. The project will continue to monitor the performance of migration and upgrade activities. 30/12/2018, 30/12/2018,July 2018: The project is now reporting 'amber' due to a lack of technical and deployment resource availability, impacting on the project's schedule. Mitigation actions are in place to reduce the schedule and resourcing impact. 30/12/2018, 30/12/2018,May 2018: This project has now returned to 'green' with the project's revised schedule being approved. 30/12/2018, 30/12/2018,Reason for variance: Original budget was reflective of an original estimate based on high level planning. Detailed planning has since refined the estimated budget (including vendor licensing arrangements) which received approval for budget increase in June 2017. | 2018-10-31T00:00:00 | High | 14100000 |  | eHealth Queensland | 80 | 26839391 |  | G | 27 | A managed operating environment means that everyone within the organisation is running a clean, basic operating system with centralised update management. This includes upgrades of all PC operating systems, preparing QH applications for running on recent operating system environments, and Infrastructure remediation activities to ensure the deployment tools are sufficient and ready for production. | 38741697 | 2016-05-12T00:00:00 | DH
30/12/2018 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | October 2018: A technical implementation freeze and testing delays have resulted in an implementation delay of this initiative. The project's governance committee is currently reviewing the end date of this initiative. 30/12/2018, 30/12/2018,July 2018: The latest approved end date has been updated. 30/12/2018, 30/12/2018,June 2018: The latest approved end date of this project remains at 30 June 2018, pending the approval of a revised implementation date. 30/12/2018, 30/12/2018,Reason for variance: Budget and schedule were revised following a tender process as per responses from the market. | 2018-11-09T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 90 | 1104145 |  | G | 28 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1510000 | 2015-10-01T00:00:00 | DH
30/12/2018 | CHOPD | Notifiable Conditions System Replacement | 2019-06-29T00:00:00 | Delivery |  | 2020-02-28T00:00:00 | Reason for variance: Approval to extend project timelines was received November 2014. Business Case was updated and approved in November 2016, including extending the schedule to February 2020. | 2018-11-09T00:00:00 | High | 11590000 |  | Chief Health Officer and Prevention | 46 | 3159688 |  | G | 29 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 30/12/2018,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
30/12/2018 | EHQ | Patient Administration System (PAS) Replacement - Business Case Development Project | 2017-06-30T00:00:00 | Initiate |  | 2019-03-29T00:00:00 | Reason for variance: Further funding was provided in 2017-18 and 2018-19 to finalise the start-up activities, including the delivery of a detailed business case and early procurement activities. | 2018-10-31T00:00:00 | High | 3850000 |  | eHealth Queensland | 81 | 6743035 |  | G | 30 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients? journeys, and ensure that accurate information about our patients is readily available when and where required. 30/12/2018, 30/12/2018,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 30/12/2018,? support for patient engagement 30/12/2018,? integrated care 30/12/2018,? clinical research 30/12/2018,? population health (for patients using public health services) 30/12/2018,? performance transparency 30/12/2018,? resource planning. | 11890760 | 2015-11-01T00:00:00 | DH
30/12/2018 | CSD | Practice Management Enterprise Solution | 2018-11-30T00:00:00 | Delivery |  | 2019-01-31T00:00:00 | October 2018: This project is now reporting amber, with the project approving an updated project schedule and budget. This is as a result of placing the implementation of the project on hold while technical system issues are resolved. 30/12/2018, 30/12/2018,September 2018: The project is now reporting red, with the project placing the implementation on hold while technical system issues are resolved. The project's schedule and budget will be adjusted following the approval of a change request to extend the end date of the project. 30/12/2018, 30/12/2018,Reason for variance: The latest approved budget was revised to reflect additional project establishment costs and development, testing and piloting activities. The schedule was also revised following procurement outcomes. | 2018-11-08T00:00:00 | High | 1470000 |  | Corporate Services | 82 | 2351941 |  | A | 31 | The main practice management software used by HHSs to conduct private practice services and billing activities is being replaced. The initiative will procure and implement "like for like" functionality enterprise solution for participating HHSs (15 in total). | 2961432 | 2017-08-01T00:00:00 | DH
30/12/2018 | EHQ | Project, Program and Portfolio Management Application | 2018-03-31T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | May 2018: This project has now returned to 'green' with the project's revised schedule being approved. 30/12/2018, 30/12/2018,April 2018: This project is now reporting 'amber' due to re-aligning the project's schedule and finances to meet changing organisational requirements. The project has submitted | 2018-10-31T00:00:00 | High | 1344177 |  | eHealth Queensland | 60 | 802775 |  | G | 32 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 30/12/2018, | 1531491 | 2017-05-02T00:00:00 | DH
30/12/2018 | EHQ | Queensland State-wide ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 3246247 |  | eHealth Queensland | 73 | 2562355 |  | G | 33 | Will replace or uplift out of date end of life ICT assets. | 3183491 | 2017-07-01T00:00:00 | DH
30/12/2018 | EHQ | Queensland State-wide ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-10-31T00:00:00 | High | 3283431 |  | eHealth Queensland | 80 | 3469051 |  | G | 34 | Will replace or uplift out of date end of life ICT assets. | 3273746 | 2017-07-01T00:00:00 | DH
30/12/2018 | MNHHS | Quick Flow Project | 2019-06-30T00:00:00 | Initiate |  | 2019-06-30T00:00:00 |  | 2018-11-12T00:00:00 | High | 6408600 |  | Metro North | 47 | 2140216 |  | G | 35 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 30/12/2018,The key objectives of the project are to: 30/12/2018,? Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 30/12/2018,? Improve the outpatient experience across MNHSS facilities and community services 30/12/2018,? Improve clinic resource utilisation 30/12/2018,? Increase the efficiency of clinical and administrative processes 30/12/2018,? Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
30/12/2018 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Delivery |  | 2019-09-30T00:00:00 | October 2018: While the project continues to report red in October, the project has reviewed and revised upcoming milestone dates, with the full project schedule expecting to be approved in Nov/Dec 2018. 30/12/2018, 30/12/2018,September 2018: The project continues to report red due to additional functional, technical and integration requirements being added to the scope and as a result, is likely to impact the schedule. 30/12/2018, 30/12/2018,August 2018: The design and development phase of the project has been delayed to accommodate additional business and technical requirements. 30/12/2018, 30/12/2018,Reason for variance: The schedule has changed to ensure issues in project implementation are addressed. | 2018-11-09T00:00:00 | High | 34950000 |  | Cairns and Hinterland | 65 | 16445497 |  | R | 36 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patients home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
30/12/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-02-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 4260336 |  | eHealth Queensland | 80 | 2575151 |  | G | 37 | Will replace or uplift out of date end of life ICT assets. | 4213118 | 2017-07-01T00:00:00 | DH
30/12/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 2150147 |  | eHealth Queensland | 73 | 1674696 |  | G | 38 | Will replace or uplift out of date end of life ICT assets. | 2593463 | 2017-07-01T00:00:00 | DH
30/12/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-10-31T00:00:00 | High | 1651750 |  | eHealth Queensland | 85 | 1386231 |  | G | 39 | Will replace or uplift out of date end of life ICT assets. | 1643098 | 2017-07-01T00:00:00 | DH
30/12/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 4245973 |  | eHealth Queensland | 83 | 3248346 |  | G | 40 | Will replace or uplift out of date end of life ICT assets. | 4216631 | 2017-07-01T00:00:00 | DH
30/12/2018 | EHQ | Service Delivery Excellence Project (SDEP) | 2018-02-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | March 2018: The latest approved end date and percentage complete has been updated. 30/12/2018, 30/12/2018,February 2018: The latest approved end date for this initiative will be updated pending advise from the project. | 2018-10-31T00:00:00 | High | 4822000 |  | eHealth Queensland | 40 | 2404342 |  | G | 41 | The Service Delivery Excellence Project (SDEP) aims to improve the service delivery functions of eHealth Queensland to help the organisation achieve its Customers and services Foundation and Shared Goal: 30/12/2018,Enhance value for customers by streamlining end to end services, processes and delivery models so that we can provide an exceptional customer experience. 30/12/2018,Stage 1 has the primary objective of delivering the Project Initiation Document (PID) for the Service Delivery Excellence Project (SDEP) Stage 2. | 4736721 | 2017-10-03T00:00:00 | DH
30/12/2018 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Delivery |  | 2020-09-30T00:00:00 |  | 2018-10-31T00:00:00 | High | 10500000 |  | eHealth Queensland | 28 | 3589457 |  | G | 42 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 10494349 | 2017-07-03T00:00:00 | DH
30/12/2018 | MNHHS | Royal Brisbane and Women's Hospital Wi-Fi | 2019-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-11-12T00:00:00 | High | 6000000 |  | Metro North | 40 | 3743502 |  | G | 43 | The RBWH Wi-Fi Project will provide an uplift and renewal to the latest Queensland Health (QH) standard for wireless local area network (WLAN) coverage within the internal areas of prioritised RBWH buildings in order to support digital healthcare. 30/12/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for the RBWH in the near future. | 6000000 | 2017-10-22T00:00:00 | DH
30/12/2018 | EHQ | Sunshine Coast University Hospital (SCUH) Stage 2 ICT Expansion | 2018-06-30T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | February 2018: This project has been reported for the first time. | 2018-10-31T00:00:00 | High | 3180000 |  | eHealth Queensland | 92 | 4012107 |  | G | 44 | Sunshine Coast University Hospital (SCUH) ICT Stage 1 delivered the ICT required to achieve the successful commissioning of SCUH in March 2017. The SCUH Stage 2 ICT Expansion covers the investment period from 1 July 2017 to 31 December 2018 and is intended to support the planned expansion of SCUH to increase capacity and establish new services. | 4012107 | 2017-07-03T00:00:00 | DH
30/12/2018 | CHQ | Information Sharing Project Phase 2 | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | August 2018: The project is now reporting 'green'. The updated procurement approach was approved by the project's governance committee in August. 30/12/2018, 30/12/2018,July 2018: This project is now reporting 'amber' due to a change in procurement approach, which has impacted on the project's financials and schedule. The project's governance committee is reviewing the updated approach, returning the project to 'green' upon approval (expected to be in September). 30/12/2018, 30/12/2018,Reason for variance: Project budget was returned to support the implementation of another project. | 2018-11-05T00:00:00 | High | 4455455 |  | Children's Health Queensland | 37 | 1465673 |  | G | 45 | Department of Health, eHealth Queensland, Children's Health Queensland and Mater Health share a common vision for the seamless integration of care across organisational boundaries, in the interests of patient safety, quality, efficiency and improved access to care. This vision of integrated care processes is enabled through seamless access, at the point of care, to necessary health information and efficient transactional capabilities that support the care continuum. | 3568598 | 2018-01-10T00:00:00 | DH
30/12/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Alcohol and Other Drugs (AODS) Consumer Technical Refresh | 2019-06-28T00:00:00 | Ended |  | 2019-06-28T00:00:00 | October 2018: This project has now closed. A governance decision has been made to merge the outcomes and deliverables of this project into the new Consumer Integrated Mental Health Application (CIMHA) Secure Transfer and Technical Refresh Project. 30/12/2018, 30/12/2018,May 2018: This project has been reported for the first time. | 2018-11-02T00:00:00 | High | 1248860 |  | Clinical Excellence | 35 | 364660 |  | G | 46 | This project is refreshing the technical implementation of the CIMHA Consumer module, in preparation for the introduction of new Alcohol and Other Drugs (AODS) system functionality. | 1248860 | 2018-04-16T00:00:00 | DH
30/12/2018 | SPP | Queensland Health Integrated Processing System establishment (QHIDSe) | 2019-10-15T00:00:00 | Delivery |  | 2019-10-15T00:00:00 | May 2018: This project has been reported for the first time. | 2018-11-02T00:00:00 | High | 3257000 |  | Strategy, Policy and Planning | 31 | 1448604 |  | G | 47 | The QHIDSe project will develop in-house the foundation of an integrated processing system (i.e. QHIDS (Queensland Health Integrated Data System) using agile techniques and software development tools enabling QHIDS to be used as a replacement for the Queensland Hospital Inpatient Processing System (QHIPS, which processes the Queensland Hospital Admitted Patient Data Collection) and extended through future initiatives to provide new functionality. | 3257000 | 2018-05-25T00:00:00 | DH
30/12/2018 | HSQ | Modernised Managed Operating Environment (MOE) and Digital Collaboration Platform for HSQ | 2018-12-31T00:00:00 | Delivery |  | 2019-03-31T00:00:00 | September 2018: The project is continuing to report amber, with the project's schedule being impacted by a dependant project implementation schedule. 30/12/2018, 30/12/2018,July 2018: The project is now reporting 'red' due to project team resourcing issues, as well as technical and scheduling delays of a dependent project impacting on the overall schedule. The project's governance committee is reviewing the project's schedule, with the project expecting to return to 'green' upon approval of an updated delivery approach. 30/12/2018, 30/12/2018,Reason for variance: The original budget reflected the 2017/18 FY spend only. | 2018-11-12T00:00:00 | High | 1057000 |  | Health Support Queensland | 41 | 1600218 |  | G | 48 | Delivery of a fully functional, production managed operating environment and digital collaboration platform packaged to all desktops, laptops and some smart devices within the Health Support Queensland environment. | 3414000 | 2018-01-01T00:00:00 | DH
30/12/2018 | CHOPD | Mosquito-borne Disease Program: Spatial Database Project | 2019-06-21T00:00:00 | Initiate |  | 2019-06-21T00:00:00 | June 2018: This project has been reported for the first time. 30/12/2018, 30/12/2018,Reason for variance: The budget was revised following market scan activities. | 2018-11-09T00:00:00 | High | 940000 |  | Chief Health Officer and Prevention | 61 | 229133 |  | G | 49 | The vector surveillance and control program requires a state-wide surveillance and control solution to assist with the response to the risk of Dengue, Zika and Chikungunya virus outbreaks in vulnerable North Queensland and the mitigation of emerging risks across Central and Southern Queensland. | 1540000 | 2017-07-31T00:00:00 | DH
30/12/2018 | EHQ | Telehealth Asset Replacement | 2019-06-28T00:00:00 | Delivery |  | 2019-06-27T00:00:00 | July 2018: This project has commenced reporting for the first time. | 2018-10-31T00:00:00 | High | 1950000 |  | eHealth Queensland | 29 | 234325 |  | G | 50 | Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. | 1950000 | 2018-07-02T00:00:00 | DH
30/12/2018 | MNHHS | Connecting Care information Program (CCI) | 2022-06-30T00:00:00 | Initiate |  | 2022-06-30T00:00:00 | July 2018: This project has commenced reporting for the first time. 30/12/2018, 30/12/2018,Reason for variance: The budget was revised to include an additional financial year. | 2018-11-12T00:00:00 | High | 760455 |  | Metro North | 25 | 1009208 |  | G | 51 | The Connecting Care Information Program - CCI -will support streamlining and improvement of clinical and administrative workflows through delivery of key Information Technology (IT) enablers. | 1140000 | 2017-03-21T00:00:00 | DH
30/12/2018 | MNHHS | Metro North Health and Hospital Service Contemporary Workspace Phase 1 | 2019-01-01T00:00:00 | Delivery |  | 2019-01-01T00:00:00 | July 2018: This project has commenced reporting for the first time. 30/12/2018, 30/12/2018,Reason for variance: The latest approved budget includes additional implementation costs and funding for the 18-19 financial year. | 2018-11-12T00:00:00 | High | 233000 |  | Metro North | 50 | 717031 |  | G | 52 | This project is focusing on preparing the Metro North Hospital and Health Service (MNHHS) applications to be ready for contemporary operating system deployment. | 1665831 | 2017-08-01T00:00:00 | DH
30/12/2018 | MNHHS | Metro North Picture Archiving and Communication (PACS) Replacement for The Prince Charles Hospital | 2018-12-03T00:00:00 | Delivery |  | 2018-12-03T00:00:00 | July 2018: This project has commenced reporting for the first time. 30/12/2018, 30/12/2018,Reason for variance: The latest approved budget includes additional funding approved for the 18-19 financial year. | 2018-11-12T00:00:00 | High | 2301451 |  | Metro North | 24 | 897927 |  | G | 53 | Procure and implement a contemporary Picture Archiving and Communication (PACS) System and functionality that will ensure improved Service delivery for the MNHHS Medical Imaging Departments at The Prince Charles Hospital (TPCH). | 2301451 | 2017-12-01T00:00:00 | DH
30/12/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Secure Transfer Project | 2019-01-28T00:00:00 | Ended |  | 2019-01-28T00:00:00 | October 2018: This project has now closed. A governance decision has been made to merge the outcomes and deliverables of this project into the new Consumer Integrated Mental Health Application (CIMHA) Secure Transfer and Technical Refresh Project. 30/12/2018, 30/12/2018,July 2018: This project has commenced reporting for the first time. 30/12/2018, 30/12/2018,Reason for variance: The budget was refined after the solution design stage with extended approvals required, impacting the project schedule. | 2018-11-02T00:00:00 | High | 610000 |  | Clinical Excellence | 10 | 125001 |  | G | 54 | The purpose of this initiative is to upgrade the CIMHA application with functionality to automate the sending of selected clinical notes and data securely. This will improve the efficiency and timeliness of information sharing. | 1109521 | 2017-10-16T00:00:00 | DH
30/12/2018 | CED | Patient Online Portal (POP) | 2019-12-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | July 2018: This project has commenced reporting for the first time. | 2018-11-07T00:00:00 | High | 15500000 |  | Clinical Excellence | 8 | 2432981 |  | G | 55 | The Patient Online Portal (POP) aims to improve a patients outpatient journey through greater visibility and enhanced communication capability across specialist services. Additionally, the solution seeks to provide greater flexibility in the provision of outpatient services, allowing patients to better manage their care. | 15500000 | 2018-03-05T00:00:00 | DH
30/12/2018 | MNHHS | Digital Transformation Readiness | 2018-12-27T00:00:00 | Initiate |  | 2018-12-27T00:00:00 | July 2018: This project has commenced reporting for the first time. | 2018-11-14T00:00:00 | High | 2771674 |  | Metro North | 28 | 1005588 |  | G | 56 | The key objectives of Digital Transformation Readiness are to perform activities in preparation for Metro North Hospital and Health Service (MNHHS) Digital Transformation with a focus on the integrated electronic Medical Record (ieMR) readiness. | 2771674 | 2018-06-29T00:00:00 | DH
30/12/2018 | MNHHS | Referral Lodgement and Tracking (RLaT) | 2019-01-23T00:00:00 | Delivery |  | 2019-01-23T00:00:00 | October 2018: The project is now reporting red due to additional implementation complexities which has resulted in a 6 month schedule delay extending the planned end date to June 2019. 30/12/2018, 30/12/2018,July 2018: This project has commenced reporting for the first time. | 2018-11-12T00:00:00 | High | 3184098 |  | Metro North | 70 | 2384360 |  | R | 57 | This project will deliver a state-wide capability for referrers to lodge patient referrals electronically with Queensland Health. The referral will be automatically routed to the appropriate Hospital and Health Service (HHS). | 3184098 | 2018-02-09T00:00:00 | DH
30/12/2018 | EHQ | Infrastructure Capacity Expansion FY 18-19 | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 1192426 |  | eHealth Queensland | 30 | 33901 |  | G | 58 | The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified organic growth requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. | 1192425 | 2018-07-02T00:00:00 | DH
30/12/2018 | EHQ | Storage Asset Replacement FY 18-19 | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 4446000 |  | eHealth Queensland | 7 | 59045 |  | G | 59 | The Server Asset Replacement Project is responsible for replacing prioritised, highly utilised and critical server assets which are coming to, or have reached, end-of-financial-life. | 4446000 | 2018-07-02T00:00:00 | DH
30/12/2018 | MNHHS | Digital Dictation Upgrade Project | 2017-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | October 2018: This project is now reporting red. The implementation date is expecting to be delayed, with additional budget also required to complete the extended implementation of the solution. 30/12/2018, 30/12/2018,Reason for variance: The latest approved budget includes funding for 2018/19 financial year. The go-live date and, therefore, the project end date, has been revised in line with customer expectations. | 2018-11-12T00:00:00 | High | 828522 |  | Metro North | 90 | 1024021 |  | R | 60 | To replace the current versions of the Digital Dictation Systems in use at MNHHS facilities with the newest release of the product. The new release introduces efficiencies in the workflow process and contributes to patient care improvement through reduction in timeframe to complete patient letters. | 1048522 | 2016-07-25T00:00:00 | DH
30/12/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Secure Transfer and Technical Refresh Project | 2019-10-14T00:00:00 | Delivery |  | 2019-10-14T00:00:00 | October 2018: This initiative has been reported for the first time. | 2018-11-08T00:00:00 | High | 2828381 |  | Clinical Excellence | 17 | 479532 |  | G | 61 | Upgrade the CIMHA application with functionality to automate the sending of selected clinical notes and data to external entities. This will improve to efficiency and timeliness of information sharing with external clinicians at assist them to make better decisions at the point of care. | 2828381 | 2018-04-16T00:00:00 | DH
30/12/2018 | HSQ | iPharmacy Upgrade Project | 2019-07-29T00:00:00 | Initiate |  | 2019-07-29T00:00:00 | October 2018: This initiative has been reported for the first time. | 2018-11-12T00:00:00 | High | 1861600 |  | Health Support Queensland | 5 | 0 |  | G | 62 | Upgrade of the statewide i.Pharmacy application, infrastructure and hardware to ensure the availability and future sustainability of the Pharmacy services across the State. | 1861600 | 2018-10-01T00:00:00 | DH
30/12/2018 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 2 | 2019-09-30T00:00:00 | Delivery |  | 2019-09-30T00:00:00 | October 2018: This initiative has been reported for the first time. | 2018-11-12T00:00:00 | High | 27243224 |  | Health Support Queensland | 2 | 897164 |  | G | 63 | Stage 2 of the IWFM Project will provide direct access to managing Queensland Health employee details, provide the capability of the submission of online forms, as well as enabling manager and employee self-service. This implementation will remove duplication, reduce paperwork and return the control and accountability of workforce establishment management to the business, thereby improving visibility of information, transparency of form tracking, increasing productivity and accuracy and reducing the time and inconvenience of returned forms. | 27243224 | 2018-09-13T00:00:00 | DH
30/12/2018 | QAS | Mobile Data State-wide | 2020-06-30T00:00:00 | Initiate |  | 2020-06-30T00:00:00 | October 2018: This initiative has been reported for the first time. | 2018-11-09T00:00:00 | High | 21672000 |  | Queensland Ambulance Service | 3 | 71798 |  | G | 64 | This initiative will expand mobile data and automatic vehicle location capability statewide, and establish remote configuration, monitoring and updates to in-vehicle mobile units. | 21672000 | 2018-05-01T00:00:00 | DH
30/12/2018 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Project planned expenditure and end date have been revised due to a number of factors: 30/12/2018, 30/12/2018,- The original planned expenditure of $2.2M was a high level estimate and has been refined with the complexity of the processes and system being uncovered as the project was stood up. 30/12/2018, 30/12/2018,- An increased scope and associated effort to ensure maximum benefit is gained from the investment, so that Queenslanders are better supported during natural disasters. 30/12/2018, 30/12/2018,- Delays to project schedule and associated additional resourcing costs as a result of: 30/12/2018, 30/12/2018, - Staff diverted to priority community recovery support roles during activations over the last 12 months, including TC Debbie, TC Nora and the North Queensland floods and most recently to NQ Bushfires. During natural disasters, our agency resources are focused on providing critical support to communities and Queenslanders in need. 30/12/2018, 30/12/2018, - Extended vendor delivery times. | 2018-11-30T00:00:00 | High | 2208000 |  | Department of Communities, Disabilty Services and Seniors | 89 | 3705000 |  | G | 1 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3780000 | 2016-07-01T00:00:00 | DCCSDS
30/12/2018 | DTS_ICTSPC | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | Feedback from the Queensland Fire and Emergency Management (QFES) Human Capital Management (HCM) Project Closure Report has been received. There are activities identified through the closure report review process which need to be addressed before the closure report can be approved. A plan is being developed to finalise these activities. 30/12/2018, 30/12/2018,The Queensland Corrective Services (QCS) HCM Project has commenced implementation with an expected completion timeframe of late 2019. 30/12/2018, 30/12/2018,The QFES payroll project transitioning to Aurion is progressing to schedule. 30/12/2018, 30/12/2018,Queensland Ambulance Services (QAS) Payroll has achieved successful results from the first Parallel Pay Run Test. To provide further rigour and assurance for a successful transition, an additional Parallel Pay Run Test for the QAS payroll project has been included with a revised implementation schedule of March 2019 being approved by the Executive Steering Committee. 30/12/2018, 30/12/2018,The QAS Payroll technical integration solution has been successfully developed, tested and released into production as scheduled. 30/12/2018, 30/12/2018,At the direction of the Executive Steering Committee (3/07/18) the program scope was increased to include the procurement of a Time and Attendance solution for QFES, QAS and QCS. An Invitation to Officer (ITO) process has been undertaken to determine market suitability to agency requirements with vendor demonstrations and agency evaluation in their final stages. 30/12/2018, 30/12/2018,The Human Resource Information Solution (HRIS) Program is continuing as Amber due to the revision of scheduling for Queensland Fire and Emergency Services (QFES) and QAS Payroll. | 2018-09-30T00:00:00 | Critical | 101500000 |  | ICT Strategic Project Coordination | 68 | 62987631 |  | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 30/12/2018, 30/12/2018,* Sustainable and supported HR and Payroll service delivery 30/12/2018,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 30/12/2018,* Strategic HR capability that supports the development, performance and safety of the departments workforce 30/12/2018,* Business Intelligence capability that provides real timely, integrated HR information 30/12/2018,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 30/12/2018,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 30/12/2018,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
30/12/2018 | QPS | GPS Tracking (Bail) | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | Legislation provisioning for GPS monitoring of court bailed offenders commenced on 31/3/18. QPS established interim GPS tracking capability leveraging existing contract held by Queensland Corrective Services. 30/12/2018,QPS is now undertaking a WoG open ITO to establish a longer term contract for GPS tracking devices and monitoring of offenders. 30/12/2018,Note: The project is currently undergoing procurement/commercial activity and is therefore not publishing any financial data. | 2018-10-08T00:00:00 | High | 0 |  | Queensland Police Service | 40 | 0 |  | G | 1 | As per the Commencement of the Bail (Domestic Violence) and Another Act Amendment Act 2017 (the Amending Act) on 30 March 2018, Magistrates will be empowered to impose a tracking condition on a defendant granted bail as a condition of their bail undertaking. 30/12/2018,As such the QPS intends to progressively implement an electronic monitoring capability on a State Wide basis. 30/12/2018,An implementation project has commenced to create an electronic monitoring capability for geographically locating and monitoring a defendant on bail for QPS to meet requirements of the Amended Act. 30/12/2018,The GPS Tracking Project is an initial proposal to validate the utility of the technology prior to seeking a longer term solution. | 0 | 2018-03-30T00:00:00 | QPS
30/12/2018 | QPS | Police Integrity and Professional Standards | 2018-08-24T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | Full funding has now been approved for the Police Integrity and Professional Standards (PIPS) IT system. 30/12/2018, 30/12/2018,The Project has received a green assessment for the Gate 3 Quality Assurance Review. 30/12/2018, 30/12/2018,Feb 18: Note: original planned end date amended as previously published information was incorrect. | 2018-10-15T00:00:00 | High | 4142000 |  | Queensland Police Service | 35 | 337200 |  | G | 2 | This initiative will deliver a new integrated Police Integrity and Professional Standards IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The Police Integrity and Professional Standards system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The Police Integrity and Professional Standards Project will also complement the Complaints Reform Project established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of thePolice Integrity and Professional Standards system will place the QPS in a strong readiness position to fully implement Complaints Reform Project-generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 6792000 | 2017-03-07T00:00:00 | QPS
30/12/2018 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Objectives 30/12/2018, 30/12/2018, 30/12/2018,This project will deliver a secondary DR site and hyper-converged system to provide resilience for all departmental business applications in the event of a disaster. 30/12/2018, 30/12/2018,Project Updates 30/12/2018, 30/12/2018, 30/12/2018,Core infrastructure DR implementation 80% complete. All migrated production systems successfully replicating to secondary DR site. 30/12/2018,Oracle system DR implementation is 100% complete. 30/12/2018,Oracle applications DR testing successfully completed. 30/12/2018,Legacy applications that are incompatible with Core infrastructure platform will be migrated to a new DR-capable environment by end of Nov 2018. 30/12/2018,Security DR implementation in progress. Dependency on provisioning of network connectivity has caused delays. 30/12/2018,All end-of-life ICT infrastructure will be decommissioned by Dec 2018. 30/12/2018,The newly implemented DR infrastructure will provide improved stability and life extension to existing business-critical applications. 30/12/2018,DR recovery procedure development, testing strategy and ICT DR Plan updates almost complete. Awaiting endorsement. 30/12/2018,DJAG DR failover testing has been completed and QCS DR testing scheduled to be completed by end of Nov 2018. 30/12/2018, 30/12/2018,Some issues have impacted YTD position however it is anticipated the original completion date will be met. | 2018-10-30T00:00:00 | High | 7314596 |  | Corporate Services | 90 | 5449744 |  | G | 1 | *Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 6512596 | 2016-10-01T00:00:00 | DJAG
30/12/2018 | BCS | Blue Card Services Recommendation 28.1 Project - Blue Card Home Based Care Register | 2018-12-21T00:00:00 | Delivery |  | 2019-01-31T00:00:00 | In July 2016, the Queensland Family and Child Commission QFCC released the When a child is missing Remembering Tiahleigh - A report into Queensland's children missing from out-of-home care report making 29 recommendations. Recommendation 28 required the QFCC to undertake a further review of legislation, policies and practices relating to information sharing between relevant agencies responsible for children in regulated service environments. 30/12/2018,The Recommendation 28 Supplementary Review, A report on information sharing to enhance the safety of children in regulated home based services (Supplementary Review) is the QFCC response to Recommendation 28 and makes 17 recommendations in relation to information sharing between agencies responsible for regulating and monitoring regulated services provided from the home, namely foster and kinship care, family day care and stand alone care services. 30/12/2018,Implementation of the register will require legislative amendment. | 2018-10-30T00:00:00 | High | 1573000 |  | Blue Card Services | 60 | 860628 |  | G | 2 | The objective of this project is to establish a register for recording and reporting on regulated child-related services provided from the home, specifically limited to foster/kinship care, family day care and stand-alone care. As recommended by the Queensland Family and Child Commission (QFCC) within the Recommendation 28 Supplementary Review Report (A report on information sharing to enhance the safety of children in regulated home-based services) this register will: 30/12/2018,a) identify co-located home-based services 30/12/2018,b) enable the Queensland Police Service to have line of sight to the register to access up-to-date information when Police attend a residential address to identify potential risks to children, and 30/12/2018,c) make information available to agencies, including Department of Child Safety, Youth and Women, Department of Education and the Office of the Public Guardian to assist with regulating and/or monitoring specific home-based services. | 1573000 | 2017-04-01T00:00:00 | DJAG
30/12/2018 | HHS_HH | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery |  | 2019-03-31T00:00:00 | The FOPATS Program undertook a significant re-baseline in late 2016 to inform and approve changes to its strategic direction, scope, delivery methodology, timing and costs, including strengthening program governance and revising the Business Case to complete against a two staged implementation, Property and then Tenancy. 30/12/2018, 30/12/2018,Following this review, the Property Release, the first of two stages, was delivered successfully on time on 1 November 2017 and delivered benefits including efficiencies in property management and reporting. 30/12/2018, 30/12/2018,The Program has completed more detailed planning for the second stage Tenancy Release, which will remove the operational dependency on the existing ICT housing solution entirely. Tenancy design activities are now well progressed, with a view to determining a feasible Program end date. 30/12/2018, 30/12/2018,The FOPATS Program has been updated to Amber status while the final review of design documents and system configurations against the Queensland Housing Strategy service delivery operating model reforms is completed. | 2018-09-30T00:00:00 | Critical | 56286000 |  | Housing and Homelessness | 65 | 79622498 |  | A | 1 | Replace the existing ICT housing solution with an integrated ICT system. | 121597695 | 2013-07-01T00:00:00 | HPW
30/12/2018 | BPAM_QF | Fleet Management System Replacement Project (FMSRP - QFleet) | 2019-09-30T00:00:00 | Initiate |  | 2019-09-30T00:00:00 | Delays in implementation have resulted from the onboarding of appropriate project resourcing. A senior project manager for the partner agencies has been appointed. Project stakeholder resourcing delays have been addressed and project is returning to schedule. 30/12/2018, | 2018-09-30T00:00:00 | High | 13939200 |  | QFleet | 25 | 954562 |  | A | 2 | The objective of the FMSRP is the procurement and implementation of a new common Fleet Management System that meets QFleet, QPS, QFES and QAS core business requirements and provides best value for money. It will provide a contemporary, sustainable common Fleet Management System that delivers effective and efficient business services for the agencies now and into the future. | 13937796 | 2017-10-19T00:00:00 | HPW
30/12/2018 | BPAM_QF | QFleet Car Sharing Model Implementation Project (CSMIP) | 2018-08-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Procurement activity has concluded. Contract drafting is complex and has taken longer than anticipated, resulting in delays in timing and an amber status. 30/12/2018, 30/12/2018,Implementation planning, including system testing, is continuing in parallel with the contract drafting. Once the contract is finalised, a revised timeline will be considered by the project board. 30/12/2018, | 2018-09-30T00:00:00 | High | 454735 |  | QFleet | 70 | 99458 |  | A | 3 | The objective of the Car Sharing Model Implementation Project (CSMIP) is the procurement and implementation of a fully automated, innovative and sustainable multi-agency car sharing solution delivering effective and efficient short-term motor vehicle hire services for government, now and in the future. | 454735 | 2017-11-20T00:00:00 | HPW
30/12/2018 | DTS_SSQ | Pay Safe Project | 2018-07-31T00:00:00 | Initiate |  | 2019-03-28T00:00:00 | A preferred vendor has been selected with contract negotiations to commence mid-October 2018. | 2018-09-30T00:00:00 | Critical | 1500000 |  | Smart Service Queensland | 29 | 175832 |  | G | 4 | The project will implement an improved capability for offering secure payment card transactions via the telephone. To meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS) when the new VOIP telephony solution is introduced. | 1500000 | 2018-01-29T00:00:00 | HPW
30/12/2018 | DTS_SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery |  | 2018-12-22T00:00:00 | The Smart Service Telephony Replacement Project Board is monitoring the project closely to ensure current go live dates are met. 30/12/2018, 30/12/2018,User Acceptance Testing has commenced with few critical defects identified. The defects are being investigated and root causes have been identified and are being managed. 30/12/2018, 30/12/2018,The project is currently reporting Amber due to unavoidable project delays caused by the high complexity of the technology and business configuration needed to meet requirements and ensuring adequate testing of the new system is undertaken prior to going live. | 2018-09-30T00:00:00 | Critical | 4490634 |  | Smart Service Queensland | 70 | 4051553 |  | A | 5 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 30/12/2018, 30/12/2018,* reduce operating costs 30/12/2018,* increase capacity 30/12/2018,* improve customer experience 30/12/2018,* provide new functionality. | 4566079 | 2015-04-02T00:00:00 | HPW
30/12/2018 | DTS_SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The Technology Platform Project is currently awaiting readiness of some Telephony Replacement Project deliverables before progressing the final Technology Platform Project deliverables which will result in a re-baselined end date. 30/12/2018, 30/12/2018,Discussion has commenced with vendors for revised quotes and timeframes. This information will form the basis of a re-baseline of the project with new end dates and final budget. | 2018-09-30T00:00:00 | Critical | 3390861 |  | Smart Service Queensland | 85 | 2573385 |  | A | 6 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution and the call recording solution. | 3390862 | 2017-05-15T00:00:00 | HPW
30/12/2018 | DTS_DAP | Digital Archiving Program Tranche 1 Transition-In | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | Since the execution of the Digital Archiving as-a-Service Contract on 6/08/2018, implementation is progressing well with the Initiation Stage completed. Supplier performance is good and all required Deliverables have been received on time. Service Design for archival management and control has commenced. Qld State Archives staff remain positive and have contributed strongly to the initial round of Service Design workshops. | 2018-09-30T00:00:00 | Medium | 8186387 |  | Digital Archiving Program | 10 | 555839 |  | G | 7 | Deliver archival management and control capability with access, search and discovery for use by QSA, Public Authorities and the Public | 8186387 | 2018-08-07T00:00:00 | HPW
30/12/2018 | DTS_SSQ | Customer Identity and Details Enhancements FY17-18 | 2018-10-30T00:00:00 | Delivery |  | 2019-03-01T00:00:00 | Penetration testing for the Customer Identity and Details Enhancements project has been completed and re-testing will occur once all identified penetration testing defects are resolved. 30/12/2018, 30/12/2018,Load testing for the Content Delivery Solution Project (CDS) was successfully delivered and is complete. 30/12/2018, 30/12/2018,The additional costs associated with the remediation activity has resulted in an amber status. A revised budget will be considered by the project board in due course. | 2018-09-30T00:00:00 | High | 1200000 |  | Smart Service Queensland | 75 | 1505563 |  | A | 8 | Improved technology and functionality to meet agency requirements in customer identity and details to enable agency adoption and uptake driving further value for customers. 30/12/2018, 30/12/2018,* CDM Blueprint 30/12/2018,* Transition to new platform 30/12/2018,* Auth pilot 30/12/2018,* CDM release 2 pilot | 1200000 | 2017-07-01T00:00:00 | HPW
30/12/2018 | CS_CIO | ICT Infrastructure Refresh Project | 2018-06-30T00:00:00 | Closed |  | 2018-09-30T00:00:00 | Project closed 30 September 2018. 30/12/2018, 30/12/2018,The refresh activities have increased the departments security profile in terms of managed software installations, up-to-date security patching and monitoring. 30/12/2018, 30/12/2018,The Windows 10 phase was extremely successful having deployed to over 4,000 devices across approximately 100 sites across the state. | 2018-09-30T00:00:00 | Medium | 1173338 |  | Chief Information Office | 100 | 936537 |  | G | 9 | To upgrade ICT infrastructure to maintain a fully supported and secure environment and leverage and take advantage of offerings from current DHPW licencing agreements. | 1173338 | 2017-02-13T00:00:00 | HPW
30/12/2018 | DTS_ICTSS | Government Wireless Network Contract and Administration Billing System | 2018-06-30T00:00:00 | Initiate |  | 2019-06-30T00:00:00 | The Contract and Administration Billing System (CABS) project documentation has progressed with the Business Case, Project Plan and Project Initiation Document (PID) created. The procurement phase has commenced. | 2018-09-30T00:00:00 | High | 0 |  | ICT Strategic Sourcing | 19 | 0 |  | G | 10 | The GWN Contract Directorate seeks a fully managed software-as-a-service solution to replace existing excel spreadsheets and macros that have organically grown in complexity, improve record keeping compliance, and alleviate current single points of failure and reliance. This project is to procure a purposely designed software system that is fully functional, customisable, redundant, reliable, will meet the current and future requirements of the GWN Contract, and replace current Contract Modification and Contractor Performance processes. | 0 | 2017-11-01T00:00:00 | HPW
30/12/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 30/12/2018, 30/12/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 30/12/2018,October 2017 - The project is progressing as planned. 30/12/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 30/12/2018,June 2017 - Revised Schedule approved returning the project to Green. 30/12/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 30/12/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 30/12/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 30/12/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 30/12/2018,December 2016 - The project is progressing as planned. | 2017-12-21T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 30/12/2018, 30/12/2018,* register and maintain their information 30/12/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
30/12/2018 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 30/12/2018, 30/12/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 30/12/2018,August 2017 - Approved extension of timeframe. 30/12/2018,June 2017 - The project is progressing as planned. 30/12/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 30/12/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 30/12/2018,October 2016 - Progress is continuing as planned. 30/12/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 30/12/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 30/12/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-21T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 30/12/2018, 30/12/2018,* support compliance with legislation 30/12/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 30/12/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 30/12/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 30/12/2018, | 1390000 | 2012-04-01T00:00:00 | DEWS
30/12/2018 | BQCC | Communication and Stakeholder Engagement Solution | 2018-04-27T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Deliverables have been achieved and project closure documentation is being finalised. 30/12/2018, 30/12/2018,November 2018 - The project has returned to Green status. 30/12/2018,October 2018 - Timeframe will be exceeded due to resourcing issues. This has affected key capability to perform testing and the finalisation of procedures and supporting documentation. A review of timeframe and associated costs is under way. 30/12/2018,September 2018 - Timeframe is being monitored closely due to business demands impacting testing and completion of documentation. Project closure is now planned by 30 September 2018. 30/12/2018,August 2018 - The project is progressing as planned and is on schedule. 30/12/2018,July 2018 - An extension to the planned end date and additional budget has been approved by the governance committee. 30/12/2018,June 2018 - Hidden complexities around integration with other solutions has affected the timing of user acceptance testing and training schedules. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 30/12/2018,May 2018 - A change to the planned end date and cost has been approved. 30/12/2018,March 2018 - Note adjustment to planned end date corrected due to typographical error. 30/12/2018,February 2018 - The project is progressing as planned. 30/12/2018,December 2017 - The project was approved to move into delivery in October 2017 and is being published for the first time. | 2018-12-10T00:00:00 | Medium | 694000 |  | Biosecurity Queensland Control Centre | 100 | 1011823 |  | G | 1 | To implement a simple, easy to use system that will facilitate the collection of information associated with the National Red Imported Fire Ant Eradication Program and the National Electric Ant Eradication Program. This will include contact management, complaints management, history of interactions, event management, training management, social media interactions, marketing campaign and reporting. | 1048849 | 2017-06-01T00:00:00 | DAF
30/12/2018 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The project has been rebaselined and approved to encompass additional scope. Accordingly, there has been an adjustment to the percentage of deliverables achieved, the schedule, and cost. 30/12/2018, 30/12/2018,November 2018 - Stage 2 has been endorsed and is going ahead. 30/12/2018,July 2018 - The project has re-commenced. Approval has been granted for an extension to the planned end date, and an increase in associated costs. 30/12/2018,June 2018 - Field testing has identified unexpected issues that will impact on the planned end date. Effort is underway with Microsoft to apply a technical fix (patch) to resolve errors. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 30/12/2018,April 2018 - An extension to the planned end date has been approved, returning the project status to Green. 30/12/2018,March 2018 - A minor scope increase has been proposed, affecting both timeframe and cost, which is progressing through the governance process. 30/12/2018,March 2018 - The project is progressing as planned. 30/12/2018,December 2017 - A variation to scope was approved, resulting in a change to the planned end date and total estimated expenditure. 30/12/2018,November 2017 - The project is continuing as planned. 30/12/2018,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2018-12-18T00:00:00 | Medium | 608146 |  | Forestry Queensland | 70 | 1144127 |  | G | 2 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 30/12/2018, 30/12/2018,* the capture, management and integration of data 30/12/2018,* value-adding opportunities for business improvement 30/12/2018,management of risk associated with ongoing use and maintenance of disparate systems. | 1696431 | 2016-06-15T00:00:00 | DAF
30/12/2018 | FQ | Novel Commercial and Recreational Fishing Apps | 2018-09-30T00:00:00 | Delivery |  | 2019-01-31T00:00:00 | The project is Amber due to a delay with implementation of the commercial app. A review of scope is currently under way, affecting the schedule and cost. 30/12/2018, 30/12/2018,October 2018 - The project is progressing as planned and is on schedule. Note: the approved end date has been updated in accordance with the approved business case. 30/12/2018,September 2018 - Contract documentation has been finalised and the first two development cycles are under way. 30/12/2018,August 2018 - The project was approved to move to delivery in July 2018 and is publishing for the first time. | 2018-12-11T00:00:00 | High | 571000 |  | Fisheries Queensland | 40 | 459864 |  | A | 3 | * Provide up-to-date information on the rules and regulations about fishing and marine park zoning in Queensland 30/12/2018,* Achieve better compliance through access to information 30/12/2018,* More uptake of the App by providing regulations from other marine agencies 30/12/2018,* Resolve issues with offline access to information. 30/12/2018, 30/12/2018, | 571000 | 2018-02-01T00:00:00 | DAF
30/12/2018 | ASQ | Portfolio Activity Reporting Information System | 2018-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The project is progressing as planned and is on schedule. 30/12/2018, 30/12/2018,September 2018 - Extensive stakeholder consultation has been undertaken and included in documentation. 30/12/2018,August 2018 - The project is progressing as planned and is on schedule. 30/12/2018,July 2018 - Project is continuing as planned. 30/12/2018,June 2018 - Refreshed business case approved, the project has been re-baselined returning it to a Green status. 30/12/2018,May 2018 - Funding has been approved to fully implement the project and it is now in delivery. 30/12/2018,February 2018 - The project is paused until a funding source is identified. 30/12/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-12-04T00:00:00 | High | 978000 |  | Agri-Science Queensland | 10 | 386509 |  | G | 4 | Review and consolidate the variety of processes and technologies currently being used to manage the department's research, development and extension, and other projects. | 978000 | 2015-08-13T00:00:00 | DAF
30/12/2018 | BQ | RBE (Registered Biosecurity Entity) Renewal Project | 2019-08-30T00:00:00 | Delivery |  | 2019-08-30T00:00:00 | The project is progressing as planned and is on schedule. 30/12/2018, 30/12/2018,August 2018 - The project was approved to move to delivery in July 2018 and is publishing for the first time. | 2018-12-05T00:00:00 | High | 2867000 |  | Biosecurity Queensland | 25 | 701272 |  | G | 5 | * Develop an efficient end-to-end registration renewal process to allow effective management of renewals 30/12/2018,* Ensure stakeholders are aware of renewal requirements and the importance of maintaining up-to-date information 30/12/2018,* Provide the ability to efficiently communicate with customers about registered biosecurity entity processes and renewals 30/12/2018,* Provide data integration between the online customer portal and the underlying technology solution 30/12/2018,* Minimise administrative overhead. | 2821000 | 2017-11-10T00:00:00 | DAF
30/12/2018 | Ag | Risk Reduction for Customer Service Centre | 2019-04-19T00:00:00 | Delivery |  | 2019-04-19T00:00:00 | The project is progressing as planned and is on schedule. 30/12/2018, 30/12/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-12-17T00:00:00 | High | 1767000 |  | Customer and Business Services | 76 | 1137865 |  | G | 6 | Implement a solution to mitigate risk of end of life for the agency's call centre logging application. | 1767000 | 2015-01-30T00:00:00 | DAF
30/12/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
30/12/2018 | PSBA | Emergency Vehicle Priority (EVP) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | Project delivery completed. Approved scope of EVP rollouts have been completed with vehicle fitouts finished in Rockhampton, Maryborough, Hervey Bay and Gladstone for both Queensland Ambulance Service and Queensland Fire and Emergency Services. The EVP Inter-Departmental Steering Committee approved the EVP Project to close on 31 October 2018. The project is reporting 99% completion while awaiting finalisation of financial information and Project Closure Report. Project scope was expanded to include procurement of a managed service for operational support and maintenance and increasing vehicle deployments to a total of 730 emergency vehicles, resulting in a revised timeframe from the original planned end date of 30-06-2017 to 31-10-2018, and a revised total expenditure from $3.37 million to $4.25 million. Revised total expenditure is pending approval to reduce by $96k to align to actual cost to date of $4.25M. | 2018-12-17T00:00:00 | High | 3370000 |  | Public Safety Business Agency | 99 | 4252940 |  | G | 1 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 30/12/2018, 30/12/2018,* Responsive vehicle movements 30/12/2018,* Improve road safety 30/12/2018,* Congestion management 30/12/2018,* Community safety | 4348696 | 2013-01-01T00:00:00 | PSBA
30/12/2018 | OSR | State Penalties Enforcement Registry (SPER) Program |  | Delivery |  | 2019-06-30T00:00:00 | The project completion timeframe has been extended by 6 months, from the end of 2018 to 30 June 2019, with a target go-live date for the new SPER ICT system by May 2019. 30/12/2018,The cost to deliver the new system will be met within the original budget. 30/12/2018,The design and build phase of the new system was completed on time in mid-2018. Vendor system testing and system integration testing with key partner agencies has now been completed. 30/12/2018,User testing for the new system began in November 2018. 30/12/2018,The extension of time will allow for extensive user testing with a broad range of fine issuing and referring agencies to ensure the system is reliable and has the highest standard of data integrity and security. 30/12/2018,A significant change management and training program is in progress for both staff and external stakeholders who refer their debts to SPER. | 2018-11-16T00:00:00 | High | 47200000 |  | State Penalties Enforcement Registry | 79 | 58700000 |  | A | 1 | To maintain the integrity of fines as an effective sanction. 30/12/2018,To uphold confidence in the justice system. 30/12/2018,To deliver efficient and effective debt management practices which provide value for money to the State. 30/12/2018, | 62150000 | 2014-01-01T00:00:00 | QR
30/12/2018 | RI | Financial Assurance Information Registry (FAIR) |  | Delivery |  | 2019-03-01T00:00:00 | The FAIR project is aligned with commencement of the Financial Provisioning Scheme (FPS). A deferral of the passage of the legislation to enact the FPS, which would permit the scheme to commence, has led the delivery delay event to be marked yes. Consistent with the November passage of the FPS legislation stakeholders have been informed that the FPS is expected to commence in the first half of 2019. 30/12/2018, 30/12/2018,The FAIR project required for the FPS commencement remains unchanged at 90 percent complete. Other components of the FPS reforms will be completed in subsequent years. 30/12/2018,Consistent with the expected rollout of the FPS in the first half of 2019 the IT system is currently in a final development, testing and maintenance phase preparing for scheme commencement. Given the project is reaching its conclusion, it requires close monitoring by management regarding on time delivery 30/12/2018, | 2018-11-27T00:00:00 | Medium | 15900000 |  | Insurance Commission | 90 | 9630651 |  | A | 2 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
30/12/2018 | RI | Information Security Program |  | Delivery |  | 2019-06-30T00:00:00 | The program is on track according to schedule and budget. | 2018-11-16T00:00:00 | Medium | 1960000 |  | Office of the Chief Information Officer | 60 | 710705 |  | G | 3 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 30/12/2018, | 1960000 | 2017-10-16T00:00:00 | QR
30/12/2018 | OSR | Office of State Revenue (OSR) Transformation Program |  | Delivery |  | 2020-06-30T00:00:00 | Commenced Phase 2 of Program with focus on implementing a new secure online portal for all taxpayers, extending machine learning and analytics capability, enhancing data quality, and introducing system capability to improve business processes, and intelligent process automation. 30/12/2018,In total 14 digital initiatives/products have been successfully delivered that incorporate machine learning, the establishment of an enterprise data warehouse, and implementation of an intelligent virtual assistant. 30/12/2018,Overall program is on track. | 2018-11-16T00:00:00 | High | 73548000 |  | Office of State Revenue | 35 | 20468627 |  | G | 4 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 30/12/2018, 30/12/2018,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 73548000 | 2017-08-01T00:00:00 | QR
30/12/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
30/12/2018 | Corporate Services Improvement Program | Integrated Records Information System (IRIS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | In response to an internal audit review of Transport and Main Road's (TMR) Document Management System (DMS) the Integrated Records and Information System (IRIS) project was stood up in 2015. 30/12/2018,IRIS project was reviewed in 2017, and as a result the project budget was decreased from $7,967,972 down to $6,865,000 (plus contingency) of 10%. 30/12/2018, The project leveraged additional functionality requirements by including TMR's Executive Correspondence System (ECS) replacement into scope. Due to recent risks eventuating, the project has had to absorb additional costs originally scheduled to be offset. | 2018-09-30T00:00:00 | High | 7967972 |  | Corporate Division | 45 | 6404800 |  | A | 1 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 6865000 | 2015-07-01T00:00:00 | TMR
30/12/2018 | Corporate Services Improvement Program | Lotus Notes Decommissioning (OP) | 2016-01-31T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project commenced in October 2015 when concept and stage 1 was approved to engage and investigate business findings around the decommission of legacy lotus notes databases. 30/12/2018,In July 2016, three additional stages aligning to three financial years from 2016/17 through to 2018/19 were further approved via a project initiation and business case. 30/12/2018,Stage 2, 2016/17, focused on analysis and stakeholder engagement to form the scope of the project and define functionality and business requirements for individual applications. 30/12/2018,Stage 3, 2017/18, focused on proof of concepts to inform and validate the plan for stage 4 in 2018/19. The project was impacted in 2017/18 by several resourcing issues, including the departure of the original project manager. 30/12/2018,The project is scheduled to complete work and close down by 30 June 2019, with the exception of the migration of files from the departments legacy Document Management System (DMS). The migration of the DMS will align with the Integrated Records and Information System (IRIS) program and should be complete by the end of 2019. | 2018-09-30T00:00:00 | High | 8150000 |  | Corporate Division | 60 | 3490918 |  | A | 2 | Deliver improved information platform functions for effective ICT Strategy Alignment | 8150000 | 2015-11-01T00:00:00 | TMR
30/12/2018 | Corporate Services Improvement Program | Transactional Services Improvement Program 2018-19 | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | Project successfully commenced 1 July 2018. | 2018-09-30T00:00:00 | High | 400000 |  | Corporate Division | 10 | 89604 |  | G | 3 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. | 400000 | 2018-07-01T00:00:00 | TMR
30/12/2018 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | This commenced in July 2016 with delivery being phased in accordance with the development of the business processes. Original expenditure was 1.5M which has been revised to $1.441M on finalisation and approval of the business case. Phase 1 was completed in July 2017 and the schedule was adjusted in June 2017 to enable the delivery of the Phase 2 capability in mid 2019. 30/12/2018, 30/12/2018,The project is currently on track. | 2018-09-30T00:00:00 | High | 1500000 |  | Customer Services, Safety and Regulation Division | 90 | 1018266 |  | G | 4 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal services currently required. | 1441000 | 2016-01-01T00:00:00 | TMR
30/12/2018 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | The project commenced in mid 2015 with an initial exploratory phase, initially scheduled for delivery in mid 2016. Due to the uncertainty of the solution outcome and market capability the project undertook a multi stage market engagement and procurement process. Once the solution had been fully defined, the schedule was extended by 11 months and the budget increased from $2.5M to $4.1M in January 2017. 30/12/2018, 30/12/2018,Development is now complete. A pilot phase has been successfully completed. The project is now conducting final testing and preparing for a full launch. An Exception Report was approved to extend the end date to 31 October 2018 and an addtional $98k which was approved by the CSSR PB on 29 August 2018. The project is on track to be closed by October 2018. 30/12/2018, 30/12/2018, | 2018-09-30T00:00:00 | High | 2500000 |  | Customer Services, Safety and Regulation Division | 96 | 4191537 |  | G | 5 | Implement an online learning and assessment program at the prelearner and/or learner stage, to enhance learning and outcomes for new drivers. | 4274000 | 2015-06-12T00:00:00 | TMR
30/12/2018 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery |  | 2018-06-28T00:00:00 | This commenced in November 2016 with planned completion in mid 2017. Due to an extended procurement process, and the need to include analytical functionality, the schedule was extended 12 months and the budget increased from $300k to $894k in August 2017. The capability was delivered as scheduled in June 2018 and the project is presently finalising closure with formal closure scheduled for August 2018. However, this is taken longer than expected and may require a re-baseline on schedule in the closure report. 30/12/2018,Project will be closed in October 2018. 30/12/2018, | 2018-09-30T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 99 | 1016536 |  | G | 6 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 989237 | 2016-11-01T00:00:00 | TMR
30/12/2018 | Customer Service, Safety and Regulation Program | Customer Flow Mgmt and Reporting System | 2018-06-30T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | Preproject work commenced during FY15/16 with the initiation of the current project commencing in July 2017. The original budget of 300K was rebaselined to 3M once the post-market business case was finalised and approved to proceed in May 2018. 30/12/2018,The project is on track for delivery to occur within FY18/19. | 2018-09-30T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 75 | 1972536 |  | G | 7 | Replacement of the existing statewide network of customer flow management and reporting systems which is currently supplied by QMatic Australia and will be unsupported in 2017. CSB currently have 43 CSCs around the state that use QMatic systems. Replacement of the existing statewide customer flow management and reporting system which is currently supplied by QMatic Australia and will be unsupported in 2017. | 3083000 | 2015-09-01T00:00:00 | TMR
30/12/2018 | Customer Service, Safety and Regulation Program | Call Centre VOIP Upgrade | 2018-06-30T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Project commenced in July 2017. Due to a resourcing issue. Approval was given to amend the implementation date from June 2018 to August 2018. | 2018-09-30T00:00:00 | High | 1140000 |  | Customer Services, Safety and Regulation Division | 99 | 1073628 |  | G | 8 | The Call Centre VOIP Upgrade has commenced to upgrade the VOIP telephony platform within the department. The proposed solution will see a reduction in call costs, a shift in capability to a contemporary solution utilising an existing investment within the department. | 1140000 | 2017-04-01T00:00:00 | TMR
30/12/2018 | Customer Service, Safety and Regulation Program | Smart Licence Card | 2018-08-21T00:00:00 | Delivery |  | 2019-03-31T00:00:00 | Gate 3 investment decision was approved by 24 May ISC. End of contract has been signed. Project are working on delivery. | 2018-09-30T00:00:00 | High | 723000 |  | Customer Services, Safety and Regulation Division | 82 | 1501154 |  | G | 9 | The project is responsible for managing business analysis and requirements specification activities, developing relevant procurement documentation, overseeing the identification and selection of a suitably qualified vendor, facilitating the transfer of contract management responsibilities from Information Technology Branch (ITB) to Transport Regulation Branch (TRB), and managing the complete transition to a new solution before the extended contract expiry date. The estimated cost for the project is $1.68M over three (3) financial years. | 2717000 | 2016-07-01T00:00:00 | TMR
30/12/2018 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The RALPH project commenced in July 2016. Due to vendor software development issues, changes to the schedule and budget were approved in June 2017. The project is currently over schedule and reporting red. The project is working on rebaselining which is expected to be finalised by November 2018. | 2018-09-30T00:00:00 | Medium | 500000 |  | Customer Services, Safety and Regulation Division | 87 | 756494 |  | R | 10 | TMRs current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace the existing application with a contemporary and supportable alternative to assist the department in maintaining its timely updating of fees and charges. | 734000 | 2016-07-01T00:00:00 | TMR
30/12/2018 | Customer Service, Safety and Regulation Program | Vessel Traffic Services (VTS) | 2016-01-05T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | Preproject work commenced in April 2014 with the initiation of the current project commencing in July 2016. The original budget of $15.2M was rebaselined to $36.2M once the post-market business case was finalised and approved to proceed in April 2017. 30/12/2018, 30/12/2018,The project is on track for delivery in mid 2019. | 2018-09-30T00:00:00 | High | 15224694 |  | Customer Services, Safety and Regulation Division | 55 | 6209775 |  | G | 11 | Replacement of TIM and surface picture software for Reef VTS Phase 1 for the replacement of TIM and surface picture software for Reef VTS. | 36228184 | 2014-04-14T00:00:00 | TMR
30/12/2018 | Customer Service, Safety and Regulation Program | Registration and CTP Certificates Online | 2017-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | The Registration and CTP Certificates Online project commenced in May 2017 as two separate initiatives Registration Online and CTP Tax Invoice Online. Due to common system synergies the projects were merged in March 2018 resulting in the closure date being revised in accordance with the CTP component. An Exception Report was approved to extend the end date to 31 December 2018 and an addtional $233k which was approved by the CSSR PB on 29 August 2018. The project is on track for delivery and closure in late 2018. | 2018-09-30T00:00:00 | Medium | 0 |  | Customer Services, Safety and Regulation Division | 67 | 483728 |  | G | 12 | Create an online service for customers to email or print their registration certificate and CTP tax invoices, to provide customers with more convenience, and reduce reliance on paper and post. | 637000 | 2017-05-01T00:00:00 | TMR
30/12/2018 | Customer Service, Safety and Regulation Program | R and L Systems Software Upgrade - Stage 2 | 2018-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | The R and L System Software Upgrade project commenced in July 2017. The original budget of $780K was rebaselined to $1.255M once the post-market business case was finalised and approved to proceed in September 2017. Delivery was completed as scheduled in June 2018. Project was officially closed on 3 September 2018. | 2018-09-30T00:00:00 | Medium | 780000 |  | Customer Services, Safety and Regulation Division | 100 | 1115450 |  | G | 13 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
30/12/2018 | Passenger Transport Technology Program | Single Integrated Network Project (SNIP) | 2018-09-29T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | Software upgrade for TransLink users planned to complete in September. Rollout of the system to SEQ bus service providers to commence in November. Delays in vendor negotations and reduction in scope has triggered an exception report and rebaselining of the project scope, schedule and budget. An updated project plan has been approved by the governance board. | 2018-09-30T00:00:00 | High | 4992243 |  | TransLink Division | 32 | 858604 |  | G | 14 | Enable implementation of performance based contracts for SEQ buses 30/12/2018,Have a system in place that is consistent and integrated across service providers and TransLink 30/12/2018,Reduce or remove inefficiencies and data inaccuracies that occur in the current processes 30/12/2018,Improve transparency of SEQ bus service providers activities and performance 30/12/2018,Improved customer experience through more accurate and reliable SEQ bus service information 30/12/2018,To improve customer experience through more accurate and reliable service information. 30/12/2018,Contributor for achieving Government objectives. | 3637240 | 2017-02-23T00:00:00 | TMR
30/12/2018 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery |  | 2019-08-30T00:00:00 | Original project commenced in April 2016. 30/12/2018,Budget shortfall identified in November 17. 30/12/2018,In March 18 issues in gathering business data and requirements for new functionality identified. 30/12/2018,The STAS project is reporting amber as a result of unforeseen complexities associated with provisioning and transitioning of business supplied data to the new platform. The project is experiencing delays as resolution activities take place to ensure a good customer experience when the project is released to the public. 30/12/2018,The Project Board approved an exception plan in September which will enable products to be completed and released by the end of March 2019. | 2018-09-30T00:00:00 | High | 4166000 |  | TransLink Division | 68 | 5399590 |  | G | 15 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 6459560 | 2016-04-01T00:00:00 | TMR
30/12/2018 | CS | Asset Assessment System | 2016-06-30T00:00:00 | Delivery |  | 2019-02-15T00:00:00 | The project is reviewing requirements and schedule before commencing next stage. | 2018-11-09T00:00:00 | Medium | 1688788 |  | Corporate Services | 82 | 1890702 |  | G | 1 | To improve the reliability and integrity of asset information, the ability to report on asset information by applying best practice asset management principles. | 2179995 | 2014-02-27T00:00:00 | DET
30/12/2018 | CS | Automated Website Provisioning Tool | 2018-12-21T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | The project is tracking to plan. | 2018-11-09T00:00:00 | Medium | 1300000 |  | Corporate Services | 98 | 1109027 |  | G | 2 | To reduce the cost and time required to create new school and corporate websites by developing a tool that provisions new websites from a suite of reusable website templates. | 1242160 | 2017-04-03T00:00:00 | DET
30/12/2018 | CS | Copper Disconnection Management | 2021-06-30T00:00:00 | Delivery |  | 2021-06-30T00:00:00 | The project is tracking to plan. | 2018-11-09T00:00:00 | Low | 2155000 |  | Corporate Services | 25 | 1175273 |  | G | 3 | The project will migrate all copper based services mandated for disconnection to an appropriate replacement technology within the required timeframes specified by nbnTM and Telstra ensuring services are not incorrectly disconnected. | 3071000 | 2017-07-03T00:00:00 | DET
30/12/2018 | PPP | Customer Complaints Management System | 2018-12-21T00:00:00 | Delivery |  | 2018-01-31T00:00:00 | The project is tracking to the revised plan approved by the project board. | 2018-11-09T00:00:00 | Medium | 2753000 |  | Policy, Performance and Planning | 76 | 879995 |  | G | 4 | Improve the management and reporting of customer complaints. | 2753000 | 2017-09-11T00:00:00 | DET
30/12/2018 | PPP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Delivery |  | 2018-11-26T00:00:00 | The project is tracking to the revised plan approved by the project board. | 2018-11-09T00:00:00 | High | 700000 |  | Policy, Performance and Planning | 99 | 1498286 |  | G | 5 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
30/12/2018 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery |  | 2018-12-13T00:00:00 | The project is tracking to plan. | 2018-11-09T00:00:00 | High | 659131 |  | Corporate Services | 82 | 471353 |  | G | 6 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DoE FBS SAP future state landscape for the next five years. | 619866 | 2017-01-16T00:00:00 | DET
30/12/2018 | ODG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | The project is tracking to plan. | 2018-11-09T00:00:00 | Low | 632585 |  | Office of the Director-General | 91 | 877369 |  | G | 7 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
30/12/2018 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | The project is tracking to plan. | 2018-11-09T00:00:00 | Critical | 16670000 |  | State Schools | 55 | 12661082 |  | G | 8 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 18115935 | 2015-08-03T00:00:00 | DET
30/12/2018 | ECCE | National Quality Standard Assessment and Rating Data Tool | 2018-12-13T00:00:00 | Delivery |  | 2018-12-17T00:00:00 | The project is tracking to plan. | 2018-11-09T00:00:00 | High | 467900 |  | Early Childhood and Community Engagement | 50 | 280020 |  | G | 9 | To improve the security and functionality of the tool used for the assessment and quality improvement of early childhood education and care centres. | 467900 | 2018-02-22T00:00:00 | DET
30/12/2018 | PPP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project is tracking to plan. | 2018-11-09T00:00:00 | High | 1502300 |  | Policy, Performance and Planning | 97 | 1311495 |  | G | 10 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution. | 1407880 | 2016-03-01T00:00:00 | DET
30/12/2018 | PPP | Online School Data Profile | 2018-06-30T00:00:00 | Delivery |  | 2020-02-28T00:00:00 | The project is tracking to plan. | 2018-11-09T00:00:00 | Low | 1872000 |  | Policy, Performance and Planning | 16 | 717912 |  | G | 11 | Improved data interaction capabilities for stakeholders accessing school data profiles. Improved efficiency in production and distribution of information contained in school data profiles. | 1700000 | 2017-10-02T00:00:00 | DET
30/12/2018 | SS | Pre-Departure Orientation Information Mobile Application | 2017-12-31T00:00:00 | Delivery |  | 2019-08-13T00:00:00 | The project is tracking to the revised plan approved by the project board. The project is undergoing procurement/commercial activities. | 2018-11-09T00:00:00 | Medium | 0 |  | State Schools | 56 | 0 |  | G | 12 | Improved service offerings and improved user experience in provision of information to support international students. | 0 | 2016-02-11T00:00:00 | DET
30/12/2018 | PPP | Redevelopment of the Policy and Procedure Register | 2018-03-30T00:00:00 | Delivery |  | 2018-12-14T00:00:00 | The project is being closely monitored for cost, quality and schedule. | 2018-11-09T00:00:00 | Medium | 1015000 |  | Policy, Performance and Planning | 76 | 1088070 |  | A | 13 | The project will deliver a contemporary online repository of departmental policies and procedures for access by staff, students and the general public. The objectives of the project are to deliver a consistent user experience for customers, regardless of who they are, where they work, and what they may be looking for; a single point of truth, providing access to departmental policies and procedures; and platform to publish policy and procedures once, with multiple links to additional information where appropriate; and authoritative content that meets quality standards for publication, enabling staff and stakeholders to make good decisions. | 935765 | 2016-10-13T00:00:00 | DET
30/12/2018 | CS | SABA Platform Upgrade | 2017-11-09T00:00:00 | Delivery |  | 2019-02-12T00:00:00 | The project is tracking to plan. | 2018-11-09T00:00:00 | Medium | 1791556 |  | Corporate Services | 88 | 2010025 |  | G | 14 | The objective of the project is to replace the existing system, currently hosted on obsolete technology, which is at end-of-service-life. In its current state, the system represents a significant business risk, due to the likelihood of increased system failures, further leading to ongoing business outages and increased maintenance and support costs. | 2303846 | 2017-08-01T00:00:00 | DET
30/12/2018 | SS | Trial of Platform for Virtual Academies | 2017-10-02T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | The project is tracking to plan. | 2018-11-09T00:00:00 | High | 151641 |  | State Schools | 95 | 160135 |  | G | 15 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage; safe and secure like-minded student virtual communities; and strategic partnerships with university, industry and business. 30/12/2018, 30/12/2018, | 227850 | 2016-06-21T00:00:00 | DET
30/12/2018 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project is tracking to plan. | 2018-11-09T00:00:00 | High | 41000000 |  | Corporate Services | 93 | 35156526 |  | G | 16 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
30/12/2018 | OIR | Investigations Management System | 2018-12-14T00:00:00 | Delivery |  | 2018-12-14T00:00:00 | The project is tracking to plan. | 2018-09-28T00:00:00 | Critical | 461742 |  | Office Of Industrial Relations | 35 | 286857 |  | G | 17 | This project will deliver a case management solution for the OIR Investigations unit. | 644711 | 2017-01-07T00:00:00 | DET
30/12/2018 | OIR | Renewal and Photographic Licensing System (RAPS) Assessor Portal | 2018-07-13T00:00:00 | Delivery |  | 2018-11-06T00:00:00 | The project is tracking to plan. | 2018-11-06T00:00:00 | High | 766467 |  | Office Of Industrial Relations | 99 | 737480 |  | G | 18 | The Assessor Portal project will deliver an improved online services for high risk work licensing accredited assessors, registered training organisations and licensing and advisory services. Currently accredited assessors must use a combination of cumbersome paper based processes, smart forms, and an online service that is difficult to use. | 997011 | 2016-12-14T00:00:00 | DET
30/12/2018 | [20 empty] | INVERSTMENT INFO
30/12/2018 | ICRM | Integrated Customer and Revenue Management (ICRM) | 2021-03-30T00:00:00 | Delivery |  | 2021-03-30T00:00:00 | Progress is on track and within project tolerances. 30/12/2018, 30/12/2018,November 2018 - The project is continuing as planned and is on schedule. Update to the planned end date made to match approved business case not previously reported. 30/12/2018,October 2018 - The project is continuing as planned and is on schedule. 30/12/2018,August 2018 - This project is reporting for the first time and is progressing as planned. | 2018-12-10T00:00:00 | High | 24511345 |  | DNRM Finance | 12 | 5102418 |  | G | 1 | Improvements to the way the agency handles revenue collection: 30/12/2018, 30/12/2018,* selection of a modern, enterprise-class, integrated customer and revenue management solution 30/12/2018,* implementation and deployment of the solution to replace the use of the current at-risk receipting systems. | 24511345 | 2017-01-01T00:00:00 | DNRM
30/12/2018 | QWSR | Dam Safety Regulation Solution | 2016-10-30T00:00:00 | Closed |  | 2019-02-28T00:00:00 | Deliverables have been achieved and project closure activities are complete. 30/12/2018, 30/12/2018,November 2018 - The project is continuing as planned and remains on schedule. 30/12/2018,October 2018 - An extension to the approved end date has been endorsed, with no affect on cost. 30/12/2018,September 2018 - Documentation is being finalised; the project remains within accepted tolerances. 30/12/2018,August 2018 - A change request has been approved altering the planned end date to enable completion of end project activities. 30/12/2018,July 2018 - All deliverables have been achieved. Project closure activities are currently under way. 30/12/2018,June 2018 - A change request has been approved altering the planned end date to remediate technical difficulties that have been experienced in the move to production. 30/12/2018,May 2018 - The project is continuing within timeframe tolerance, and is expected to close prior to the end of May 2018. 30/12/2018,March 2018 - The project is continuing as planned. 30/12/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 30/12/2018,August 2017 - Approved extension of timeframe. 30/12/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 30/12/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 30/12/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 30/12/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 30/12/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2018-12-14T00:00:00 | High | 1390000 |  | Queensland Water Supply Regulator | 100 | 1385060 |  | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 30/12/2018, 30/12/2018,* support compliance with legislation 30/12/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 30/12/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 30/12/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. | 1390000 | 2012-04-01T00:00:00 | DNRM
30/12/2018 | Natural Resources | Land Condition Assessment Tool | 2018-04-30T00:00:00 | Paused |  | 2019-01-25T00:00:00 | The project has paused following advice of a change in the vendor's capacity to provide all of the services specified under the contract arrangements. 30/12/2018, 30/12/2018,November 2018 - The project is currently Amber due to some features being incomplete. 30/12/2018,October 2018 - An extension to the approved end date has been endorsed, with no impact on costs. Note the change to the percentage complete, aligning with deliverable achieved thus far. 30/12/2018,September 2018 - An extension to the project end date has been approved to accommodate vendor resource constraints. There is no impact to cost. Discussions are under way with the vendor to ensure resourcing constraints will not impact quality, or further delay delivery. 30/12/2018,August 2018 - The project is continuing as planned, tracking within tolerances for time, cost and quality. 30/12/2018,June 2018 - A change request has been approved altering the planned end date and budget to allow for resolution of unforeseen complexities in deliverables. 30/12/2018,May 2018 - The project timeframe is currently being monitored, with action under way to return it to Green. 30/12/2018,April 2018 - This project is reporting for the first time and is progressing as planned. | 2018-12-20T00:00:00 | Medium | 414000 |  | Operations Support | 70 | 161671 |  | A | 3 | Implement a solution for government, industry and other stakeholders to objectively and consistently assess land conditions, including development of a pictogram-based mobile web application and a data collection tool. | 479000 | 2017-01-12T00:00:00 | DNRM
30/12/2018 | CWeHR | Coal Workers eHealth Records Project | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | A review of scope is currently under way. 30/12/2018, 30/12/2018,November 2018 - The project is progressing with a small adjustment to the expenditure due to timing of accruals. 30/12/2018,October 2018 - The project is continuing as planned, tracking within project tolerances. 30/12/2018,August 2018 - This project is reporting for the first time and is progressing as planned. Note finances reported represent Stage 0 and Stage 1. 30/12/2018, | 2018-12-07T00:00:00 | High | 3894285 |  | Occupational Health and Hygiene - Resources Safety and Health | 5 | 1296193 |  | A | 4 | Improvement in data management and surveillance for coal mine worker health assessments: 30/12/2018, 30/12/2018,* new customer digital interface 30/12/2018,* improved health assessment outcomes through improved access to longitudinal health records 30/12/2018,* enabled industry-wide health surveillance through electronic storage and access to health records 30/12/2018,* improved data management using appropriate health management systems and alignment with health record management requirements. | 3894285 | 2017-03-23T00:00:00 | DNRM
30/12/2018 | SO | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery |  | 2019-03-29T00:00:00 | The project is progressing well and is tracking within tolerances. 30/12/2018, 30/12/2018,November 2018 - The project is progressing as planned. 30/12/2018,August 2018 - The project is continuing as planned, tracking within tolerances for time, cost and quality. 30/12/2018,February 2018 - A change request was approved to alter the scope and associated percentage complete, time-frame and costs. 30/12/2018,December 2017 - Awaiting confirmation of project closure; project is still operating within approved time-frame tolerance. 30/12/2018,November 2017 - A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 30/12/2018,October 2017 - The project is continuing as planned. 30/12/2018,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2018-12-07T00:00:00 | High | 563000 |  | SIMTARS (Safety In Mines Testing and Research Station) | 84 | 935190 |  | G | 5 | The development and delivery of a (replacement) modern and robust Safegas solution: 30/12/2018, 30/12/2018,* risk reduction increasing capability to manage the volume of queries, transactions and data 30/12/2018,* decrease database corruption related to incidents. | 1170000 | 2017-01-25T00:00:00 | DNRM
30/12/2018 | DPC | Performance Information Management System (PIMS) Dynamics 365 upgrade and relocation | 2018-10-30T00:00:00 | Closed |  | 2018-10-30T00:00:00 | The project has now been delivered. The new system is live and has been rolled out across departments. | 2018-12-06T00:00:00 | High | 240494 |  | Premier and Cabinet | 100 | 240494 |  | G | 1 | To upgrade the existing PIMS solution from the current 2013 version to Microsoft Dynamics 365 and move the system to Microsoft Online. | 240494 | 2018-05-01T00:00:00 | DPC
30/12/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
30/12/2018 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 30/12/2018,* Move operational accountability and responsibility for print and imaging devices to the service provider 30/12/2018,* Reduce print and imaging costs 30/12/2018,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
30/12/2018 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
30/12/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
30/12/2018 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 30/12/2018, 30/12/2018,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
30/12/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
30/12/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 30/12/2018, 30/12/2018,* reduce operating costs 30/12/2018,* increase capacity 30/12/2018,* improve customer experience 30/12/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
30/12/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
30/12/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 30/12/2018, 30/12/2018, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
30/12/2018 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 30/12/2018, 30/12/2018,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
30/12/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
30/12/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 30/12/2018, 30/12/2018,November 2017 - Actual cost to date corrected due to input error. 30/12/2018, 30/12/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 30/12/2018, | 2017-12-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 57 | 733941 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
30/12/2018 | CSS | Wildlife Platform | 2018-07-31T00:00:00 | Delivery |  | 2019-07-31T00:00:00 | The project is progressing as planned. 30/12/2018, 30/12/2018,November 2018 - Project has been moved into delivery and is reporting for the first time. | 2018-11-26T00:00:00 | Medium | 395000 |  | Conservation and Sustainability Services | 4 | 14616 |  | G | 1 | Implement a platform that will increase the quality and availability of information related to wildlife sightings, in particular crocodiles. This will allow transparency and support for the public to better manage their own safety, whilst providing a central analytics and reporting resource to improve strategic analysis, planning and management. | 395000 | 2018-07-31T00:00:00 | EHP
30/12/2018 | EPP | Queensland Waste Disposal Levy System | 2018-07-10T00:00:00 | Delivery |  | 2019-08-01T00:00:00 | A small extension to the planned end date has been approved to allow for integration with the financial management system. 30/12/2018, 30/12/2018,November 2018 - The project is progressing as planned. 30/12/2018,September 2018 - The project has been approved to commence delivery and is publishing for the first time. | 2018-12-19T00:00:00 | Critical | 2248000 |  | Environmental Policy and Planning | 70 | 710361 |  | G | 2 | Implement a solution to meet new legislative arrangements for a waste disposal levy, to effectively and efficiently enable: 30/12/2018, 30/12/2018,* site operators to accurately record data 30/12/2018,* reconciliation of waste data and levy liabilities 30/12/2018,* timely access to, and interrogation of, large datasets. | 2248000 | 2018-07-10T00:00:00 | EHP
30/12/2018 | ESR | Connect Workflow Remediation | 2018-10-24T00:00:00 | Initiate |  | 2019-01-31T00:00:00 | The project is investigating options and is reporting for the first time. | 2018-12-20T00:00:00 | Medium | 0 |  | Environmental Services and Regulation | 0 | 0 |  | G | 3 | Undertake system enhancements, improvements to workflow and implementation of prioritised support backlog as identified by the Connect Taskforce Report. | 0 | 2018-10-24T00:00:00 | EHP
30/12/2018 | ESR | User Experience Improvement and Rebranding | 2018-10-30T00:00:00 | Initiate |  | 2019-05-31T00:00:00 | The project is investigating options and is reporting for the first time. | 2018-12-20T00:00:00 | Medium | 0 |  | Environmental Services and Regulation | 0 | 0 |  | G | 4 | Improve usability of the Connect system through redesign of the user interface and delivery via an enterprise platform. | 0 | 2018-10-30T00:00:00 | EHP
30/12/2018 | QPWS | Augmented Ranger Mobile Application | 2018-02-01T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | Project milestones are on target to be met. 30/12/2018, 30/12/2018,November 2018 - The project is progressing as planned. 30/12/2018,August 2018 - The project has been approved to commence delivery and is publishing for the first time. | 2018-12-03T00:00:00 | Low | 240000 |  | Queensland Parks and Wildlife Service | 30 | 125660 |  | G | 5 | Develop a mobile, optimised solution that uses Augmented Reality to: 30/12/2018, 30/12/2018,* enrich visitors? on-park engagement, experiences and understanding of cultural, historical and ecological points of interests specific to the location 30/12/2018,* provide opportunities for ranger-visitor communications 30/12/2018,* aid collection of real-time visitor data. | 240000 | 2018-02-01T00:00:00 | EHP
30/12/2018 | QPWS | Integrated Permitting System Project | 2019-02-28T00:00:00 | Initiate |  | 2020-04-03T00:00:00 | The project is investigating options and is reporting for the first time. | 2018-12-19T00:00:00 | High | 0 |  | Queensland Parks and Wildlife Service | 15 | 0 |  | G | 6 | Leverage and implement a solution to manage the lifecycle of permit and agreement applications from lodgement, assessment and approval through to completion, return of operations, and reporting for compliance monitoring. | 0 | 2017-07-03T00:00:00 | EHP
30/12/2018 | CSS | Native Animal Licensing Framework System | 2020-01-01T00:00:00 | Initiate |  | 2020-01-01T00:00:00 | The project is investigating options and is reporting for the first time. | 2018-12-19T00:00:00 | Low | 0 |  | Conservation and Sustainability Services | 0 | 0 |  | G | 7 | An enterprise solution is required for the management of Native Animal Licencing. This solution will: 30/12/2018, 30/12/2018,* streamline the issuing and management of wildlife licences 30/12/2018,* enable licence holders to digitally share information about their animals 30/12/2018,* improve data availability 30/12/2018,* enable proactive administrative support 30/12/2018,* facilitate compliance and enforcement practices. | 0 | 2018-10-05T00:00:00 | EHP
30/12/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP
28/2/2018 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Initiate | G | 2018-12-31T00:00:00 |  | 2018-01-31T00:00:00 | High | 5600000 | G | eHealth Queensland | 10 | 412698 | G | G | 1 | This project aims to establish a robust, highly available and secure contemporary platform that has the capability to support the agile eHealth Strategy. | 5600000 | 2017-07-03T00:00:00 | DH
28/2/2018 | HSQ | AUSLAB Re-hosting project | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-01-31T00:00:00 | High | 1691324 | G | Health Support Queensland | 20 | 215663 | G | G | 2 | Delivery of a replacement hardware and visualisation solution for the AUSLAB and AUSCARE systems that will achieve improved resiliency of the architecture, updated operating system and inclusion of virtualisation. AUSLAB and AUSCARE are critical to support laboratories and patient clinical care. | 1691324 | 2017-08-28T00:00:00 | DH
28/2/2018 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2016-08-01T00:00:00 | Delivery | G | 2018-07-30T00:00:00 |  | 2018-02-13T00:00:00 | High | 1858668 | G | Metro North | 35 | 974181 | G | G | 3 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 28/2/2018, 28/2/2018,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Women 28/2/2018,92s Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 28/2/2018, 28/2/2018,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 2482431 | 2015-06-01T00:00:00 | DH
28/2/2018 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 11180394 | G | eHealth Queensland | 11 | 244358 | G | G | 4 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 28/2/2018,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work. 28/2/2018,a0 Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 11180394 | 2017-07-03T00:00:00 | DH
28/2/2018 | MNHHS | Business Intelligence - Enterprise Data Warehouse | 2018-06-29T00:00:00 | Delivery | G | 2018-06-28T00:00:00 |  | 2018-02-13T00:00:00 | High | 2114991 | G | Metro North | 72 | 1470224 | G | G | 5 | This project will introduce Business Intelligence and Data Warehousing capabilities at MNHHS. The project will deliver BI & DW technical skills, system infrastructure, data automation tools, a pilot dataset, data governance processes and quality control framework at MNHHS. Metro North Finance and MNIT are jointly managing the project. | 2114991 | 2016-11-01T00:00:00 | DH
28/2/2018 | MNHHS | Central Patient Monitoring Equipment Replacement | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-02-13T00:00:00 | High | 1236416 | G | Metro North | 40 | 374088 | G | G | 6 | Metro North IT has been approached by Metro North Procurement Services (MNPS) to provide ICT advice and guidance into the Central Patient Monitoring Equipment Replacement (CPMER) Project. The Health Technology Equipment Replacement (HTER) program for central monitoring systems is providing funding in financial years 16/18 for physiological monitoring equipment requiring replacement across MNHHS hospital facilities. There is an estimated 312 pieces of equipment, primarily Physiological Monitoring devices, to be replaced under the program across MNHHS hospital facilities. MNHHS implementations are being co-ordinated by MNPS. | 1236416 | 2017-06-28T00:00:00 | DH
28/2/2018 | MNHHS | CISS (Community, Indigenous and Subacute Services) Wi-Fi | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-02-13T00:00:00 | Medium | 1280798 | G | Metro North | 51 | 777860 | G | G | 7 | The Community, Indigenous and Subacute Services (CISS) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the internal areas of the prioritised CISS sites. 28/2/2018, 28/2/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1280798 | 2017-07-28T00:00:00 | DH
28/2/2018 | EHQ | Cloud First Project | 2018-06-30T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-01-31T00:00:00 | High | 4250000 | G | eHealth Queensland | 45 | 2304030 | G | G | 8 | The Cloud First project will build internal capability and establish processes within Queensland Health to appropriately utilise cloud services on an ongoing basis. | 4107007 | 2017-01-01T00:00:00 | DH
28/2/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Clinical Notes project (release 3.0) | 2018-02-06T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-02-05T00:00:00 | High | 1415000 | G | Clinical Excellence | 75 | 1434705 | G | G | 9 | Upgrading the CIMHA Mental Health Act module to accommodate a re-architecture of the CIMHA clinical notes module is required to deliver benefits to the clinical workforce associated with data entry efficiencies; improved data sharing across digital platforms; patient level information transfer to third parties to support service integration and data mining to support service improvement and research. | 1969365 | 2017-02-20T00:00:00 | DH
28/2/2018 | EHQ | Critical Network Hardware | 2018-02-28T00:00:00 | Delivery | G | 2018-05-31T00:00:00 | January: The project is reporting 'Amber' due to limited resource availability and additional technical requirements, impacting the schedule of the project. | 2018-01-31T00:00:00 | High | 8636364 | A | eHealth Queensland | 60 | 7352201 | A | A | 10 | The objectives of the project include: 28/2/2018,a) Mitigate the Department of Health risk that core network switches at QH facilities will no longer be supported by the manufacturer from February 2018. 28/2/2018,b) Invest in the replacement of critical ICT network hardware to maintain current capability and reliability of the data network for 120+ enterprise clinical and business applications and provide the foundation for future capability in the enterprise data centres. 28/2/2018,c) Ensure hardware replacement occurs with minimal impact to business operations in Hospital and Health Services or Corporate offices. 28/2/2018,d) Update logical and physical design and architecture documentation for ease of maintenance and management. | 8001607 | 2017-03-06T00:00:00 | DH
28/2/2018 | EHQ | Digital Collaboration Platform Program | 2018-06-30T00:00:00 | Delivery | G | 2019-02-28T00:00:00 | January: This project is experiencing delays in pre-migration activities. | 2018-01-31T00:00:00 | High | 11000000 | A | eHealth Queensland | 32 | 8151262 | R | R | 11 | This program will deliver digital collaboration tools for any time, any where, any device including: 28/2/2018, 28/2/2018,95 Email and Archiving 28/2/2018, 28/2/2018,95 Establishment and Collaboration 28/2/2018, 28/2/2018,95 Productivity Suite Enablement | 18467291 | 2015-10-29T00:00:00 | DH
28/2/2018 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate | G | 2017-12-31T00:00:00 | January: The planned end date will be updated within following reporting periods to reflect the project's updated schedule. | 2018-01-31T00:00:00 | High | 1500000 | G | Queensland Ambulance Service | 40 | 517744 | G | G | 12 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 4167216 | 2015-12-01T00:00:00 | DH
28/2/2018 | QAS | e-ARF Redevelopment for iPad | 2016-12-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | January: The system was implemented in late November, and the project is currently within the project closure stage. | 2018-01-31T00:00:00 | High | 2624000 | G | Queensland Ambulance Service | 99 | 1762732 | G | G | 13 | This is an initiative to provide the electronic Ambulance Report Form (eARF) electronic patient care solution via iPads in the field. | 1910813 | 2015-09-02T00:00:00 | DH
28/2/2018 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | January: Further solution clarification is required, which has impacted on the delivery timeframe of this project. | 2018-01-31T00:00:00 | High | 1283000 | G | Chief Health Officer and Prevention | 49 | 59500 | A | A | 14 | ?Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1283000 | 2017-03-01T00:00:00 | DH
28/2/2018 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery | G | 2018-11-30T00:00:00 |  | 2018-02-13T00:00:00 | High | 4827917 | G | Metro North | 55 | 2360602 | G | G | 15 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (ieMR) program. 28/2/2018, 28/2/2018,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 28/2/2018, 28/2/2018,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. | 4827917 | 2016-07-01T00:00:00 | DH
28/2/2018 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 3792744 | G | eHealth Queensland | 6 | 157529 | G | G | 16 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment. 28/2/2018,a0 28/2/2018,a0The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access. 28/2/2018,a0 | 3792744 | 2017-07-05T00:00:00 | DH
28/2/2018 | QAS | Enterprise Rostering System | 2018-12-31T00:00:00 | Paused | G | 2018-12-31T00:00:00 |  | 2018-01-31T00:00:00 | High | 1000000 | G | Queensland Ambulance Service | 10 | 505297 | G | G | 17 | The initiative is to provide a centralised electronic rostering system to replace existing aging and disparate manual systems currently being utilised across the state. | 1194682 | 2016-12-01T00:00:00 | DH
28/2/2018 | EHQ | File Services Migration | 2017-06-30T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 3400000 | G | eHealth Queensland | 25 | 2676132 | G | G | 18 | The purpose of this investment is to adopt a contemporary, simplified file management solution for Queensland Health that enables a more cohesive customer experience. | 9907925 | 2016-08-01T00:00:00 | DH
28/2/2018 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 |  | 2018-02-02T00:00:00 | High | 33827000 | G | Clinical Excellence | 17 | 8169763 | G | G | 30 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 33827000 | 2017-03-01T00:00:00 | DH
28/2/2018 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Delivery | G | 2018-12-31T00:00:00 |  | 2018-01-31T00:00:00 | High | 105000000 | G | Metro North | 52 | 47469241 | G | G | 19 | The current Queensland Health Finance, Asset and Materials Maintenance Information System (FAMMIS) system is based on a heavily customised solution which is almost 20 years old and no longer supported. 28/2/2018,The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 28/2/2018, 28/2/2018,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 28/2/2018,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 28/2/2018, 28/2/2018,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
28/2/2018 | EHQ | Follow Me Desktop - Deployment | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 3952980 | G | eHealth Queensland | 35 | 809182 | G | G | 20 | Follow Me Desktop Deployment Project will deliver 28/2/2018,a0the Follow Me Desktop service (FMD) to HHS 28/2/2018,92 in alignment with the Infrastructure Remediation Program (IMP) and ieMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 3952980 | 2017-07-03T00:00:00 | DH
28/2/2018 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-01-31T00:00:00 | High | 3301500 | G | eHealth Queensland | 13 | 117505 | G | G | 21 | Project Purpose: 28/2/2018,a0To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 2490769 | 2017-07-01T00:00:00 | DH
28/2/2018 | EHQ | ICT Regional Wireless Infrastructure Initiatives | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-01-31T00:00:00 | High | 4170000 | G | eHealth Queensland | 35 | 2435249 | G | G | 22 | The Regional eHealth Project (ReHP) is a Wireless LAN and Network Infrastructure uplift project so that sites in Far North Qld are ready to rollout their new eHealth Application. | 3489114 | 2017-07-01T00:00:00 | DH
28/2/2018 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | Critical | 1120000 | G | eHealth Queensland | 20 | 342946 | G | G | 23 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. | 1120000 | 2017-07-05T00:00:00 | DH
28/2/2018 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 3215000 | G | eHealth Queensland | 36 | 4323547 | G | G | 24 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 12318334 | 2015-06-22T00:00:00 | DH
28/2/2018 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-01-31T00:00:00 | High | 1500000 | G | Queensland Ambulance Service | 80 | 591017 | G | G | 42 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1744000 | 2015-10-01T00:00:00 | DH
28/2/2018 | EHQ | ieMR Program (Funding Packages 3 and 4) | 2019-04-30T00:00:00 | Delivery | G | 2019-04-30T00:00:00 |  | 2018-01-31T00:00:00 | High | 0 | G | eHealth Queensland | 25 | 0 | G | G | 25 | ieMR will enable improved patient care through the development of a state-wide, authoritative single source of the patient records. 28/2/2018, 28/2/2018,The ieMR will provide clinicians with the ability to: 28/2/2018,* access data that is integrated, accurate and clinically relevant 28/2/2018,* support decision making and better use of information 28/2/2018,* optimise management of patients, resources and provision of services 28/2/2018,* support interaction across a network of providers by making it easier to find providers, transfer information and collaborate with multidisciplinary providers. 28/2/2018,The Program scope (all tranches) is to roll out the ieMR system to 24 hospitals across Queensland. 28/2/2018, 28/2/2018,Please note that financial information for ieMR is Commercial in Confidence | 0 | 2016-11-17T00:00:00 | DH
28/2/2018 | EHQ | Infrastructure Capacity FY 17-18 | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-01-31T00:00:00 | Medium | 1000000 | G | eHealth Queensland | 35 | 351452 | G | G | 26 | Project Purpose: 28/2/2018,a0 28/2/2018,The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified 28/2/2018,91organic growth 28/2/2018,92 requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. | 2000000 | 2017-07-01T00:00:00 | DH
28/2/2018 | EHQ | Infrastructure Maintenance Program | 2022-06-30T00:00:00 | Initiate | G | 2022-06-30T00:00:00 |  | 2018-01-31T00:00:00 | Medium | 1161415 | G | eHealth Queensland | 1 | 289325 | G | G | 27 | The Infrastructure Maintenance Program (IMP) 28/2/2018,a0will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 28/2/2018,The scope includes: 28/2/2018,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 28/2/2018,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and 28/2/2018,a0 28/2/2018,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1161414 | 2017-07-03T00:00:00 | DH
28/2/2018 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery | G | 2022-06-30T00:00:00 |  | 2018-02-05T00:00:00 | High | 14673739 | G | Clinical Excellence | 10 | 1336461 | G | G | 28 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 28/2/2018,The ongoing program of work aims to continue and build upon existing functionality by: 28/2/2018, 28/2/2018,95 Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 28/2/2018, 28/2/2018,95 Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 28/2/2018, 28/2/2018,95 Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 28/2/2018, 28/2/2018,95 Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 28/2/2018, 28/2/2018,95 Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
28/2/2018 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate | G | 2022-12-21T00:00:00 |  | 2018-01-31T00:00:00 | High | 6300000 | G | Queensland Ambulance Service | 18 | 424267 | G | G | 29 | Phased delivery of a system supporting QAS business intelligence. | 6300000 | 2017-01-03T00:00:00 | DH
28/2/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 4245973 | G | eHealth Queensland | 59 | 1103433 | G | G | 56 | Will replace or uplift out of date end of life ICT assets. | 4245973 | 2017-07-01T00:00:00 | DH
28/2/2018 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 1 | 2016-11-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | January: Additional scope requirements have caused the project to extend the schedule and request additional finances, which is progressing through the project 28/2/2018,92s governance committee. | 2018-01-31T00:00:00 | High | 8200000 | A | Health Support Queensland | 87 | 20502185 | A | A | 31 | The IWFM project involves: 28/2/2018,- configuring additional functionality (currently available and licensed, but unutilised) within the existing Rostering and Payroll business solutions 28/2/2018,- partnering with HHSs to develop refined business models and business processes to support the roster-to-pay process 28/2/2018,- undertaking extensive training and change management to support the adoption and effective usage of new functionality and processes | 25060122 | 2016-02-17T00:00:00 | DH
28/2/2018 | EHQ | Interoperability Project | 2016-04-29T00:00:00 | Delivery | G | 2019-09-29T00:00:00 |  | 2018-01-31T00:00:00 | High | 23850000 | G | eHealth Queensland | 15 | 9787999 | G | G | 32 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 28/2/2018,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 28/2/2018,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 28/2/2018, | 39189509 | 2015-02-01T00:00:00 | DH
28/2/2018 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Delivery | G | 2020-10-30T00:00:00 |  | 2018-01-31T00:00:00 | High | 64000000 | G | Health Support Queensland | 44 | 16183025 | G | G | 33 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 28/2/2018,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. | 64000000 | 2015-08-28T00:00:00 | DH
28/2/2018 | MNHHS | Learning and Performance Management Project | 2017-06-30T00:00:00 | Initiate | G | 2018-11-26T00:00:00 |  | 2018-02-13T00:00:00 | High | 1178190 | G | Metro North | 70 | 1027734 | G | G | 34 | Implement an integrated Learning Management and Performance Management system with the capability to deliver online learning and training content, facilitate performance development and maintain centralised records for reporting purposes. | 1178190 | 2016-07-11T00:00:00 | DH
28/2/2018 | GCHHS | Medical Imaging Informatics Solution (MIIS) Risk Mitigation | 2018-12-31T00:00:00 | Delivery | G | 2018-12-31T00:00:00 |  | 2018-02-07T00:00:00 | High | 5000000 | G | Gold Coast | 18 | 643136 | G | G | 35 | The Medical Imaging Informatics Solution (MIIS) Risk Mitigation project has identified an Imaging solution which will address the risks and opportunities described in the Case for Change including the mitigation of patient safety risks, increased efficiency and productivity, improvi.ng medical imaging billing revenue collection and cash flow. The solution has user endorsement from radiologists and clinicians and will be specifically configured to meet GCHHS 28/2/2018,92s needs. | 5000000 | 2017-04-03T00:00:00 | DH
28/2/2018 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery | G | 2018-11-30T00:00:00 |  | 2018-02-13T00:00:00 | High | 4030460 | G | Metro North | 35 | 1430660 | G | G | 36 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 28/2/2018, 28/2/2018,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 28/2/2018, 28/2/2018,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
28/2/2018 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | January: The project is now reporting 'Red' due to delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-02-16T00:00:00 | High | 6299780 | R | Metro North | 75 | 5583203 | R | R | 37 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 6299780 | 2014-06-01T00:00:00 | DH
28/2/2018 | EHQ | Metro South and East Queensland ICT Infrastructure Replacement Initiative | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-01-31T00:00:00 | High | 4160449 | G | eHealth Queensland | 58 | 546719 | G | G | 38 | Will replace or uplift out of date end of life ICT assets. | 4160448 | 2017-07-01T00:00:00 | DH
28/2/2018 | EHQ | Metro South East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 2182844 | G | eHealth Queensland | 35 | 153318 | G | G | 39 | Will replace or uplift out of date end of life ICT assets. | 2182843 | 2017-07-01T00:00:00 | DH
28/2/2018 | EHQ | Mobile Application System for Bring Your Own Device | 2018-06-30T00:00:00 | Delivery | G | 2018-07-06T00:00:00 |  | 2018-01-31T00:00:00 | High | 1639698 | G | eHealth Queensland | 50 | 758156 | G | G | 40 | This project leverages the investment of the previous Bring-Your-Own-Device (BYOD) 28/2/2018,a0projects to extend the capability of device mobility by building the foundations of a Mobile Application Ecosystem - the processes, products and services to enable the managed development of low/no code applications by Health and Hospital Services (HHS). 28/2/2018,a0 This project will also complete the deployment of BYOD laptops and provide recommendations on how cost savings can be made by the organisation around Corporate devices and data plans. 28/2/2018,a0 | 1639698 | 2017-07-01T00:00:00 | DH
28/2/2018 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery | G | 2018-12-19T00:00:00 | January: This project is experiencing delays in pre-migration activities and delays experienced in another dependent project. | 2018-01-31T00:00:00 | High | 14100000 | G | eHealth Queensland | 40 | 13879589 | R | R | 41 | This project will move Queensland Health to a modern end user workspace that is: current; delivering collaboration and productivity benefits; able to be accessed anywhere, anytime and on any device; reducing the reliance and expense of on premise infrastructure and support and not constraining the business from taking advantage of modern applications and services. | 27427900 | 2016-05-12T00:00:00 | DH
28/2/2018 | CHOPD | Notifiable Conditions System Replacement | 2019-06-29T00:00:00 | Delivery | G | 2020-02-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 12000000 | G | Chief Health Officer and Prevention | 35 | 2232472 | G | G | 43 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 28/2/2018,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
28/2/2018 | EHQ | Patient Administration System (PAS) Replacement Program | 2017-06-30T00:00:00 | Initiate | G | 2019-03-29T00:00:00 |  | 2018-01-31T00:00:00 | Medium | 3850000 | G | eHealth Queensland | 51 | 3468054 | G | G | 44 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients 28/2/2018,92 journeys, and ensure that accurate information about our patients is readily available when and where required. 28/2/2018, 28/2/2018,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 28/2/2018, 28/2/2018,95 support for patient engagement 28/2/2018, 28/2/2018,95 integrated care 28/2/2018, 28/2/2018,95 clinical research 28/2/2018, 28/2/2018,95 population health (for patients using public health services) 28/2/2018, 28/2/2018,95 performance transparency 28/2/2018, 28/2/2018,95 resource planning. | 11890865 | 2015-11-01T00:00:00 | DH
28/2/2018 | MNHHS | Picture Archiving and Communication System (PACS) | 2017-09-29T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | January: The project is now reporting 'Red' due to delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-02-16T00:00:00 | High | 3114694 | R | Metro North | 75 | 3300756 | R | R | 45 | Procure and implement a contemporary Picture Archiving and Communication (PACS) system and functionality that will ensure improved service delivery for the MNHHS Medical Imaging Departments (and other PACS users) through replacement of RBWH PACS ensuring that it is scalable and able to meet the ongoing needs of Metro North Hospital and Health Service. | 3656297 | 2016-07-11T00:00:00 | DH
28/2/2018 | CSD | Practice Management Enterprise Solution | 2018-11-01T00:00:00 | Initiate | G | 2018-11-01T00:00:00 |  | 2017-12-31T00:00:00 | High | 1470000 | G | Corporate Services | 35 | 341000 | G | G | 46 | The main practice management software used by HHSs to conduct private practice services and billing activities is being replaced. The initiative will procure and implement "like for like" functionality enterprise solution for participating HHSs (15 in total). | 1470000 | 2017-08-01T00:00:00 | DH
28/2/2018 | EHQ | Project, Program and Portfolio Management Application | 2018-03-31T00:00:00 | Initiate | G | 2018-06-29T00:00:00 |  | 2018-01-31T00:00:00 | Medium | 1344177 | G | eHealth Queensland | 25 | 427305 | G | G | 47 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 28/2/2018, | 1473632 | 2017-05-02T00:00:00 | DH
28/2/2018 | CED | Queensland Integrated Safety Information Project (QISIP) / Risk Management | 2017-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-02-01T00:00:00 | High | 4333120 | G | Clinical Excellence | 89 | 7526725 | G | G | 48 | This initiative will source a state wide system to replace existing enterprise risk management systems to support patient and staff incident reporting, feedback, case management and risk management processes. | 16273520 | 2013-01-25T00:00:00 | DH
28/2/2018 | EHQ | Queensland State-wide ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 3246247 | G | eHealth Queensland | 30 | 375571 | G | G | 49 | Will replace or uplift out of date end of life ICT assets. | 3246247 | 2017-07-01T00:00:00 | DH
28/2/2018 | EHQ | Queensland State-wide ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 3283431 | G | eHealth Queensland | 63 | 1488343 | G | G | 50 | Will replace or uplift out of date end of life ICT assets. | 3282431 | 2017-07-01T00:00:00 | DH
28/2/2018 | MNHHS | Quick Flow Project | 2019-02-01T00:00:00 | Initiate | G | 2019-06-30T00:00:00 |  | 2018-02-13T00:00:00 | High | 6408600 | G | Metro North | 35 | 818106 | G | G | 51 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 28/2/2018,The key objectives of the project are to: 28/2/2018, 28/2/2018,95 Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 28/2/2018, 28/2/2018,95 Improve the outpatient experience across MNHSS facilities and community services 28/2/2018, 28/2/2018,95 Improve clinic resource utilisation 28/2/2018, 28/2/2018,95 Increase the efficiency of clinical and administrative processes 28/2/2018, 28/2/2018,95 Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
28/2/2018 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Initiate | G | 2019-12-31T00:00:00 |  | 2018-02-08T00:00:00 | High | 34950000 | G | Cairns and Hinterland | 0 | 8544386 | G | G | 52 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patient 28/2/2018,92s home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
28/2/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 4260336 | G | eHealth Queensland | 35 | 259921 | G | G | 53 | Will replace or uplift out of date end of life ICT assets. | 4260336 | 2017-07-01T00:00:00 | DH
28/2/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 2150147 | G | eHealth Queensland | 55 | 531979 | G | G | 54 | Will replace or uplift out of date end of life ICT assets. | 2150147 | 2017-07-01T00:00:00 | DH
28/2/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 1651750 | G | eHealth Queensland | 35 | 249954 | G | G | 55 | Will replace or uplift out of date end of life ICT assets. | 1651750 | 2017-07-01T00:00:00 | DH
28/2/2018 | EHQ | Service Delivery Excellence Project (SDEP) Stage 1 | 2018-02-28T00:00:00 | Delivery | G | 2018-03-29T00:00:00 |  | 2018-01-31T00:00:00 | High | 713000 | G | eHealth Queensland | 18 | 248836 | G | G | 57 | The Service Delivery Excellence Project (SDEP) aims to improve the service delivery functions of eHealth Queensland to help the organisation achieve its Customers and services Foundation and Shared Goal: 28/2/2018,Enhance value for customers by streamlining end to end services, processes and delivery models so that we can provide an exceptional customer experience. 28/2/2018,Stage 1 has the primary objective of delivering the Project Initiation Document (PID) for the Service Delivery Excellence Project (SDEP) Stage 2. | 7136880 | 2017-10-04T00:00:00 | DH
28/2/2018 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Initiate | G | 2020-09-30T00:00:00 |  | 2018-01-31T00:00:00 | High | 10500000 | G | eHealth Queensland | 9 | 386161 | G | G | 58 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 10500000 | 2017-07-03T00:00:00 | DH
28/2/2018 | MNHHS | Royal Brisbane and Women's Hospital Wi-Fi | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 |  | 2018-02-13T00:00:00 | High | 5000000 | G | Metro North | 12 | 1980023 | G | G | 59 | The RBWH Wi-Fi Project will provide an uplift and renewal to the latest Queensland Health (QH) standard for wireless local area network (WLAN) coverage within the internal areas of prioritised RBWH buildings in order to support digital healthcare. 28/2/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for the RBWH in the near future. | 5000000 | 2017-10-22T00:00:00 | DH
28/2/2018 | EHQ | Storage Asset Replacement | 2018-06-29T00:00:00 | Delivery | G | 2018-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 1671556 | G | eHealth Queensland | 22 | 140609 | G | G | 60 | The Storage Asset Replacement (SAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the SAR and Backup Asset Replacement (BAR) projects. 28/2/2018,The SAR project seeks to outline architecture for storage that will provide a cost effective, scalable and fit for purpose environment for the future of storage services within Queensland Health. 28/2/2018,a0 Utilising space saving technologies which will enable further cost savings and reduce the requirement for capacity expansion in the short to medium term. | 1671555 | 2017-07-03T00:00:00 | DH
28/2/2018 | EHQ | Telehealth Asset Replacement FY 17-18 | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-01-31T00:00:00 | High | 1960000 | G | eHealth Queensland | 55 | 731742 | G | G | 61 | Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector 28/2/2018,a0 28/2/2018,and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. 28/2/2018,The Department of Health defines Telehealth as: 28/2/2018, 28/2/2018,95Live, audio and/or video inter-active link for clinical consultations and educational purposes 28/2/2018, 28/2/2018,95Store and forward Telehealth - this model can involve digital images, video, audio and clinical data being captured ("stored") on the client computer; then at a convenient time transmitted securely ("forwarded") 28/2/2018,a0 to a clinic at another location where they are studied by relevant specialists 28/2/2018, 28/2/2018,95Teleradiology for remote reporting and clinical advice for diagnostic images 28/2/2018, 28/2/2018,95Telehealth services and equipment to monitor people 28/2/2018,92s health in their home. 28/2/2018,Benefits of Telehealth 28/2/2018, 28/2/2018,95Improve patient access to health care 28/2/2018, 28/2/2018,95Reduce travel and inconvenience for patients, families, carers and health professionals 28/2/2018, 28/2/2018,95Provide health professionals with access to peer support and education. 28/2/2018,The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. 28/2/2018,a0 28/2/2018,The priority is to replace those end-of-life assets which pose the greatest risk to effective health service delivery. | 1960000 | 2017-07-03T00:00:00 | DH
28/2/2018 | MNHHS | The Prince Charles Hospital (TPCH) Wi-Fi | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 |  | 2018-02-13T00:00:00 | High | 1408388 | G | Metro North | 30 | 952844 | G | G | 62 | The Prince Charles Hospital (TPCH) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the hospital campus for prioritised TPCH buildings. 28/2/2018, 28/2/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1408388 | 2017-07-27T00:00:00 | DH
28/2/2018 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery | G | 2018-03-31T00:00:00 | There have been delays to the project schedule from reprioritisation of resources to community recovery activities associated with Cyclone Debbie. Additionally, the vendor, SMS Management and Technology, has not delivered within the contracted timeframes and we are negotiating with the vendor to ensure completion of the solution. | 2018-01-31T00:00:00 | High | 2208000 | G | Whole of Department | 83 | 3072000 | G | G | 1 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3483000 | 2016-07-01T00:00:00 | DCCSDS
28/2/2018 | WOD | ICT Service Transformation Program | 2016-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | Original planned expenditure represented approved budget from start date to 30 June 2016. This program is a multi year program and the revised total expenditure has been updated to include approved funding to 30 June 2018. | 2018-01-31T00:00:00 | Low | 2916000 | G | Whole of Department | 93 | 6605000 | G | G | 2 | This program includes a number of initiatives to implement service improvement opportunities and essential capital replacement activities. The program ensures that ICT systems and services are replaced in a way that supports the department's strategic direction and includes the digital vision and future ways of work roadmap. | 7555000 | 2014-12-13T00:00:00 | DCCSDS
28/2/2018 | WOD | Reporting and Business Intelligence Project | 2017-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | Original planned expenditure represented approved budget from start date to 30 June 2016. This project is a multi year project and the revised total expenditure has been updated to include approved funding to 30 June 2018 to continue reporting and business intelligence deliverables. | 2018-01-31T00:00:00 | Medium | 750000 | G | Whole of Department | 45 | 4026000 | G | G | 3 | The department has a requirement for business intelligence, data management, information presentation and multi-level reporting. | 5541000 | 2015-07-01T00:00:00 | DCCSDS
28/2/2018 | WOD | Social Investment Program | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | The original expenditure includes the approved budget to 30 June 2017 only. The planned expenditure has been revised to include the approved expenditure to 30 June 2018 to complete tranche 1 and 2 of the program. | 2018-01-31T00:00:00 | Critical | 2230000 | G | Whole of Department | 30 | 1762000 | G | G | 4 | The project will implement systems and processes that support the departments social procurement spend and support interventions that are proven to work, offer good value for money and are contributing to the broader objectives of government. | 5028000 | 2016-07-01T00:00:00 | DCCSDS
28/2/2018 | WOD | Complaints Management System | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-01-31T00:00:00 | Low | 466000 | G | Whole of Department | 60 | 339000 | G | G | 5 | The objective of the complaints management system project which was formerly incorporated into the Technology Refresh project is to develop a complaints management system which supports the future DCCSDS business structure. The new system must also meet the recommendations made by the Queensland Ombudsman in his Management of Child Safety Complaints report in which the department has agreed that a full review of data fields for the departments complaints management database is conducted and relevant categories aligned to the departments core business practices and best practice complaints handling process. | 466000 | 2017-07-01T00:00:00 | DCCSDS
28/2/2018 | Cross-Gov | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery | G | 2018-09-03T00:00:00 | Queensland Fire and Emergency Services Human Capital Management solution achieved Stage 1 go-live as planned in December 2017. The Business Case for Queensland Corrective Services Human Capital Management solution is awaiting final review with commencement of the approved approach planned for late Quarter 1 2018. Queensland Ambulance Service Human Capital Management Business Case is progressing through a three phase review stage. 28/2/2018, 28/2/2018,The approach to transition for the Queensland Ambulance Service payroll to Aurion has been reviewed with a proposed change to the implementation timeframe from March 2018 to November 2018. In accordance with proper program governance, the overall program status will now indicate red pending formal approval of the Change Request by the Executive Steering Committee expected in February 2018. 28/2/2018, 28/2/2018,* Note 1. - Planned End Date. 28/2/2018,The introduction of an additional project into the program for the implementation of a time and attendance solution will require a change to the end date of the Program. In addition, planning for Queensland Fire and Emergency Services Payroll transition to Aurion is still being completed. Once schedules for these projects have been completed, the end date of the program will be revised and signed off by the Executive Steering Committee. 28/2/2018, | 2017-12-31T00:00:00 | Critical | 101500000 | G | Cross-Government program led by DSITI | 55 | 52653982 | A | R | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 28/2/2018, 28/2/2018,* Sustainable and supported HR and Payroll service delivery 28/2/2018,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 28/2/2018,* Strategic HR capability that supports the development, performance and safety of the departments workforce 28/2/2018,* Business Intelligence capability that provides real timely, integrated HR information 28/2/2018,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 28/2/2018,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 28/2/2018,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
28/2/2018 | QPS | Online National Police Certificate Project | 2017-06-30T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | Since the successful launch of Online National Police Certificates 72% of all applications have been submitted online. The overall number of applications submitted online, has doubled from December 2017 to January 2018. 28/2/2018, 28/2/2018,National Police Certificate campaign material is currently being distributed to all Police Districts for display in all Stations and Police Beats. External marketing via social media will commence in February-March 2018. 28/2/2018, 28/2/2018,The revised project budget has been amended from previously published figures to reflect the increased investment in promotional products. | 2018-02-19T00:00:00 | High | 275000 | G | Queensland Police Service | 85 | 230000 | G | G | 1 | The Online National Police Certificate Project will implement an online service for the community to apply and pay for Name Only National Police Certificates online, rather than presenting at a police station, or using the online services of an Australian Crime Intelligence Commission accredited broker. This will provide improved customer service to the community through a more efficient and reliable QPS service, with no requirement to present at a police station, as well as provide efficiency and time savings to local police stations and the Police Information Centre. | 250000 | 2017-01-01T00:00:00 | QPS
28/2/2018 | QPS | Police Integrity and Professional Standards Project | 2020-02-17T00:00:00 | Delivery | G | 2020-02-17T00:00:00 | Previous Invitation to Offer considered and not proceeded with as it was deemed financially un-viable. Project asked to re-scope the market and conduct new Invitation to Offer to establish if vendors for a more affordable and innovative solution are available. Meeting with relevant stakeholders to be organised to discuss way forward. | 2018-02-19T00:00:00 | High | 4142000 | A | Queensland Police Service | 30 | 99000 | A | A | 2 | This initiative will deliver a new integrated Police Integrity and Professional Standards IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The Police Integrity and Professional Standards system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The Police Integrity and Professional Standards Project will also complement the Complaints Reform Project established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of the Police Integrity and Professional Standards system will place the QPS in a strong readiness position to fully implement Complaints Reform Project-generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 4142000 | 2017-03-07T00:00:00 | QPS
28/2/2018 | QPS | Advanced Data Analytics Project | 2017-07-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to deliver new capability in all streams with most capability available for use during the 2018 Commonwealth Games. Current focus is on expanding the capability developed by the project into 2017-18 as business-as-usual capability and positioning the outputs/products of the project for developing the next phase of QPS advanced analytics capabilities. | 2018-02-19T00:00:00 | Low | 1730000 | G | Queensland Police Service | 87 | 2050602 | G | G | 3 | Develop the QPS Advanced Data Analytics proof-of-concept. This proof-of-concept is intended to inform a larger suite of data analytics integration and intelligence over the next four years, including the development of predictive and alert models to enhance the operational response to threats, incidents and events. | 2350000 | 2017-02-19T00:00:00 | QPS
28/2/2018 | QPS | Body Worn Cameras Project | 2018-02-28T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Project completed the deployment of all Stage Two body worn cameras in December 2017 and is now preparing closure activities and transition to business as usual by 30 June 2018. 28/2/2018, 28/2/2018,The original approved budget was $6.03M. In May 2017 the QPS Demand and Resource Committee approved an additional $0.860M, making the total approved budget $6.890M. | 2018-02-19T00:00:00 | Medium Low | 6030000 | G | Queensland Police Service | 80 | 5400000 | G | G | 4 | The Queensland Police Service Body Worn Camera Project is deploying 5100 body worn cameras to frontline police officers. Body worn cameras will be deployed to 168 police stations, 16 tactical crime units, 47 road policing units, and specialist units including dog squads and the Public Safety Response Team in two stages. The cameras integrate with the QPS mobility devices, allowing officers to add metadata to videos and to review videos in the field. A system for storage and allocation of digital camera data will also be implemented as well as policy related to use of the cameras. | 6890000 | 2014-08-25T00:00:00 | QPS
28/2/2018 | PSBA | Weapons Licensing Management System Stage 2a Project | 2017-05-31T00:00:00 | Closed | G | 2017-12-29T00:00:00 | Weapons Licensing 2A Benefits Enhancement Analysis Report for the proposed benefit enhancement rule changes has now been approved by the Project Board. The project has been handed over to Weapons Licensing. Weapons Licensing will implement the four rule changes as part of their business as usual schedule. The remaining project budget has been transferred to Weapons Licensing to fund the implementation of the rule changes. The Project is now going through approval for formal closure. | 2018-02-19T00:00:00 | Medium | 2500000 | G | Public Safety Business Agency | 100 | 1888776 | G | G | 5 | Improved workflow efficiencies, reduction in work queues, less resources required to process licence renewal and weapons Permit to Acquire, etc. | 2156825 | 2015-11-11T00:00:00 | QPS
28/2/2018 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-06-30T00:00:00 | Delivery | G | 2018-12-31T00:00:00 | Original planned end date was changed from 30 June 2018 to 31 Dec 2018 due to: 28/2/2018, 28/2/2018, 28/2/2018,- initial delays in securing project resources (2016-17 Christmas/New Year shutdown) 28/2/2018, 28/2/2018, 28/2/2018,- high level of project design complexity (heterogeneous environments) 28/2/2018, 28/2/2018, 28/2/2018,- conformity with appropriate probity and procurement governance. 28/2/2018, 28/2/2018, 28/2/2018,- requirement to develop a Significant Procurement Plan (SPP). 28/2/2018, 28/2/2018, 28/2/2018, 28/2/2018,The original project estimated expenditure occurs over two years to implement Core Infrastructure DR and Oracle DR. The variance of revised cost resulting in significant savings is due to implementing a more cost effective solution proposed through the Request for Quote (RFQ) process while utilising contemporary technologies. | 2018-01-18T00:00:00 | High | 7460674 | G | Corporate Services | 25 | 3086714 | G | G | 1 | * Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 5917255 | 2016-10-01T00:00:00 | DJAG
28/2/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | All staff relocations are complete with minor works being carried out on some floors with expected completion by 30 January 2018. | 2017-12-31T00:00:00 | Medium | 800000 | G | Chief Information Office | 99 | 909875 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | HPW
28/2/2018 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitoring. | 2017-12-31T00:00:00 | High | 144000 | A | Chief Information Office | 87 | 196000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 28/2/2018,* Move operational accountability and responsibility for print and imaging devices to the service provider 28/2/2018,* Reduce print and imaging costs 28/2/2018,* Leverage innovative technologies. | 206000 | 2016-01-01T00:00:00 | HPW
28/2/2018 | QSS | Legacy Finance Archiving Project | 2018-03-29T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-12-31T00:00:00 | High | 845949 | G | Queensland Shared Services | 84 | 467325 | G | G | 3 | This project will archive finance data for legacy finance solution into a standard archive/enquiry solution. | 845949 | 2016-09-01T00:00:00 | HPW
28/2/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2018-03-16T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-12-31T00:00:00 | High | 1800000 | G | Queensland Shared Services | 83 | 1488137 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | HPW
28/2/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The automated payment solution is in the procurement phase. The overall status is amber due to dependencies on the Content Delivery System Project which is progressing slower than expected. | 2017-12-31T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 85 | 972682 | A | A | 5 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | HPW
28/2/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The Project Board continues to closely monitor the dependencies with the Content Delivery Solution Project. All other aspects of the project remain on track. | 2017-12-31T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 70 | 2856456 | A | A | 6 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 28/2/2018, 28/2/2018,* reduce operating costs 28/2/2018,* increase capacity 28/2/2018,* improve customer experience 28/2/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | HPW
28/2/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The CDS Project continues to progress through Testing activities to ensure a quality solution is implemented. The Project Board are working closely with the vendor to assess any impacts to the timeframes as a result of an extended Testing phase | 2017-12-31T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 70 | 1540194 | A | A | 7 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | HPW
28/2/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. | 2017-12-31T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 70 | 1816019 | G | G | 8 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | HPW
28/2/2018 | QSA | Digital Archiving Program - Tranche 1 | 2019-12-31T00:00:00 | Delivery | G | 2019-12-31T00:00:00 | Procurement stage is progressing to planned timeframes and milestones. | 2017-12-31T00:00:00 | Critical | 12701000 | G | Queensland State Archives | 45 | 587415 | G | G | 9 | To ensure the delivery of an as-a-Service eco-system to effectively archive, manage and enable search and discovery of Queensland's permanent high value records. The new digital services will support the Queensland Government's blueprint for innovation and collaboration, providing better outcomes for Queenslanders. | 12701000 | 2017-07-01T00:00:00 | HPW
28/2/2018 | CITEC ICT | z14 Mainframe Upgrade | 2018-07-31T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-12-31T00:00:00 | High | 4720752 | G | CITEC ICT | 2 | 4440879 | G | G | 10 | The project will replace the two existing z12 Mainframes (Production and Disaster Recovery) with upgraded z14 Mainframes and migrate the existing data from the old to the new. 28/2/2018, 28/2/2018,The current z12 platform is unable to be upgraded and cannot provide sufficient capability for increasing client requirements. The continued use of the z12 platform represents significant risk to business continuity. 28/2/2018, 28/2/2018,The upgrade will reduce ongoing operating costs, enable improved services to clients and provide for clients' future capacity requirements. 28/2/2018, | 4720752 | 2017-12-18T00:00:00 | HPW
28/2/2018 | Housing | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery | G | 2019-03-31T00:00:00 | Over the last month, the project has remained focussed on embedding the successful first release, Property, in support of end users across the State. 28/2/2018, 28/2/2018,The Program remains focused on planning for the second of the two releases, Tenancy, which will remove the operational dependency on the existing ICT housing solution entirely. 28/2/2018, 28/2/2018,The Program also secured approval of the revised business case and expenditure in December 2017. 28/2/2018, | 2017-12-31T00:00:00 | Critical | 56286000 | G | Housing Services | 51 | 63000000 | G | G | 11 | Replace the existing ICT housing solution with an integrated ICT system. | 121600000 | 2013-07-01T00:00:00 | HPW
28/2/2018 | PWAM | iSpace External Hosting Migration Project | 2017-01-31T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The user testing is completed. 28/2/2018,A dry run is being undertaken as a rehearsal for the Go_Live weekend to ensure the delivery of a stable quality product. 28/2/2018,A revised Go_Live target for February 2018 has been approved. 28/2/2018, | 2017-12-31T00:00:00 | High | 735000 | A | Queensland Government Accommodation Office | 87 | 810146 | A | A | 12 | Version upgrade and migration of the hosting of Queensland Accommodation Office core system to a hosted managed service arrangement. | 1415203 | 2016-05-01T00:00:00 | HPW
28/2/2018 | QGP | Fleet Management System Replacement Project (FMSRP - QFleet) | 2019-09-30T00:00:00 | Initiate | G | 2019-09-30T00:00:00 | The project is tracking to plan. The project is currently subject to procurement activities. | 2017-12-31T00:00:00 | High | 13939200 | G | QFleet | 2 | 238000 | G | G | 13 | The project will deliver for the Department of Housing and Public Works, Public Safety Business Agency and Queensland Ambulance Service a fleet management solution to replace existing aging legacy systems. | 13939200 | 2017-10-19T00:00:00 | HPW
28/2/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 28/2/2018, 28/2/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 28/2/2018,October 2017 - The project is progressing as planned. 28/2/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 28/2/2018,June 2017 - Revised Schedule approved returning the project to Green. 28/2/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 28/2/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 28/2/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 28/2/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 28/2/2018,December 2016 - The project is progressing as planned. | 2017-12-21T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 28/2/2018, 28/2/2018,* register and maintain their information 28/2/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
28/2/2018 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 28/2/2018, 28/2/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 28/2/2018,August 2017 - Approved extension of timeframe. 28/2/2018,June 2017 - The project is progressing as planned. 28/2/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 28/2/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 28/2/2018,October 2016 - Progress is continuing as planned. 28/2/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 28/2/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 28/2/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-21T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 28/2/2018, 28/2/2018,* support compliance with legislation 28/2/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 28/2/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 28/2/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 28/2/2018, | 1390000 | 2012-04-01T00:00:00 | DEWS
28/2/2018 | BQ | Biosecurity Information Management System Program | 2017-05-31T00:00:00 | Delivery | G | 2018-02-28T00:00:00 | The program is progressing as planned. 28/2/2018, 28/2/2018,December 2017 - Program delivery is complete, however, the final end date has been extended by three months to allow for full transition to business as usual, project and program closure activities and final assurance reviews. 28/2/2018,November 2017 - The planned end date has been extended by one month; this remains within acceptable program tolerances. 28/2/2018,March 2017 - The program is progressing as planned in line with approved change to scope, timeframe, benefits and cost. 28/2/2018,January 2017 - A small scope increase has been proposed, currently progressing through governance processes. 28/2/2018,November 2016 - Note, a scope review is currently under way. 28/2/2018,May 2016 - Program is continuing as planned. Note a small extension to planned end date. 28/2/2018,March 2016 - A re-baseline has brought all parameters back to Green. 28/2/2018,January 2016 - Timeframe, Cost, and Quality remain Amber, pending a business case update due early April 2016. 28/2/2018,November 2015 - Program is still Amber while the Timeframe is being re-baselined. 28/2/2018,September 2015 - The Exception Report has been accepted by the Program Board. Timeframe remains Amber pending a business case update. 28/2/2018,July 2015 - Resources continue to be redirected to assist with emergency response to the Panama banana disease. An Exception Report is being developed to address this. 28/2/2018,May 2015 - As anticipated, the emergency response to the Panama Banana disease outbreak has impacted both the project cost and the Timeframe. 28/2/2018,March 2015 - There is currently an outbreak of Panama banana disease which has potential to impact the schedule of this project. 28/2/2018,January 2015 - Actions are being taken to resolve some current scheduling issues. | 2018-02-12T00:00:00 | Critical | 18080000 | G | Biosecurity Queensland | 98 | 18230000 | G | G | 1 | Deliver an integrated toolkit consisting of various information management technologies and enhanced business processes to improve the management of biosecurity risks in Biosecurity Queensland's day-to-day business operations and in emergency responses. | 19409000 | 2013-07-01T00:00:00 | DAF
28/2/2018 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery | G | 2018-03-31T00:00:00 | The project is progressing as planned. 28/2/2018, 28/2/2018,December 2017 - A variation to scope was approved, resulting in a change to the planned end date and total estimated expenditure. 28/2/2018, 28/2/2018,November 2017 - The project is continuing as planned. 28/2/2018, 28/2/2018,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2018-02-12T00:00:00 | Medium | 608146 | G | Forestry Queensland | 80 | 726225 | G | G | 2 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 28/2/2018, 28/2/2018,* the capture, management and integration of data 28/2/2018,* value-adding opportunities for business improvement 28/2/2018,* management of risk associated with ongoing use and maintenance of disparate systems. | 976431 | 2016-06-15T00:00:00 | DAF
28/2/2018 | BQCC | Communication and Stakeholder Engagement Solution | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | The project is progressing as planned. 28/2/2018, 28/2/2018,December 2017 - The project was approved to move into delivery in October 2017 and is being published for the first time. | 2018-02-12T00:00:00 | Medium | 694000 | G | Biosecurity Queensland Control Centre | 25 | 293745 | G | G | 3 | Implement a simple, easy to use system that will facilitate the collection of information associated with the National Red Imported Fire Ant Eradication Program and the National Electric Ant Eradication Program. This will include contact management, complaints management, history of interactions, event management, training management, social media interactions, marketing campaign and reporting. | 694000 | 2017-06-01T00:00:00 | DAF
28/2/2018 | ASQ | Portfolio Activity Reporting Information System | 2018-06-30T00:00:00 | Paused | G | 2018-06-30T00:00:00 | The project is paused until a funding source is identified. 28/2/2018, 28/2/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-02-12T00:00:00 | High | 500000 | G | Agri-Science Queensland | 10 | 231622 | G | G | 4 | Review and consolidate the variety of processes and technologies currently being used to manage the department's research, development and extension, and other projects. | 500000 | 2015-08-13T00:00:00 | DAF
28/2/2018 | Ag | Risk Reduction for Customer Service Centre | 2019-04-19T00:00:00 | Delivery | G | 2019-04-19T00:00:00 | The project is continuing as planned. 28/2/2018, 28/2/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-02-12T00:00:00 | High | 1767000 | G | Agriculture | 10 | 143997 | G | G | 5 | Implement a solution to mitigate risk of end of life for the agency's call centre logging application. | 1767000 | 2015-01-30T00:00:00 | DAF
28/2/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
28/2/2018 | PSBA | Emergency Services Computer Aided Dispatch (ESCAD) Upgrade Program | 2016-09-30T00:00:00 | Delivery | G | 2018-07-03T00:00:00 | The updated ESCAD system cut over for Queensland Ambulance Service (QAS) completed successfully on 17 January 2018, and the Queensland Fire and Emergency Services (QFES) also completed successfully on 24 January 2018. | 2018-02-20T00:00:00 | Critical | 6774820 | G | Public Safety Business Agency | 86 | 8812255 | G | G | 1 | A program of work for Queensland Ambulance Service and Queensland Fire and Emergency Services to upgrade the Emergency Services Computer Aided Dispatch System,including infrastructure, operating system and application software. | 10289600 | 2015-01-15T00:00:00 | PSBA
28/2/2018 | PSBA | Emergency Vehicle Priority (EVP) Project | 2017-06-30T00:00:00 | Delivery | G | 2018-10-31T00:00:00 | EVP rollouts continuing across Queensland, including Ipswich, Rockhampton and Gladstone. EVP rollout is currently due for completion April 2018, which will be ahead of scheduled completion date of end of 2018. More vehicles are proposed to be fitted beyond the scope of the project subject to approval. Budget figure now reflects $515k increase to support approved project extension to October 2018. | 2018-02-20T00:00:00 | High | 3370000 | G | Public Safety Business Agency | 80 | 3920604 | G | G | 2 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 28/2/2018, 28/2/2018,* Responsive vehicle movements 28/2/2018,* Improve road safety 28/2/2018,* Congestion management 28/2/2018,* Community safety | 4370331 | 2013-01-01T00:00:00 | PSBA
28/2/2018 | PSBA | Inter-CAD Electronic Messaging System (ICEMS) | 2017-12-01T00:00:00 | Delivery | G | 2018-02-23T00:00:00 | Project delivery completed 1 December 2017. End date has been extended to 23 February 2018 to allow for project closure activities to be completed. % complete revised to reflect extended duration. | 2018-02-20T00:00:00 | Critical | 560000 | G | Public Safety Business Agency | 91 | 1548783 | G | G | 3 | To implement the ICEMS protocol between the Queensland Police Service (QPS), Queensland Ambulance Service (QAS) and Queensland Fire and Emergency Services (QFES) computer aided dispatch systems to enable Triple Zero data sharing between agencies. | 1545139 | 2015-10-06T00:00:00 | PSBA
28/2/2018 | PSBA | QPS Office 365 Implementation Project | 2018-02-28T00:00:00 | Delivery | G | 2018-02-28T00:00:00 | QPS Office 365 Implementation Project has completed the migration of all employee and business accounts to Office 365 online services. | 2018-02-14T00:00:00 | Critical | 2207000 | G | Public Safety Business Agency | 75 | 675267 | G | G | 4 | The objective of the Queensland Police Service (QPS) Office 365 Implementation Project is to complete the following activities prior to the FDS Commonwealth Games Change Freeze (mid Feb 2018). 28/2/2018, 28/2/2018,* Migrate email, contacts and calendars to Office 365 online services for all QPS staff 28/2/2018,* Enable anywhere, anytime, any device access to email, contacts and calendar via bring your own (BYO) phone, QPS Officers operational tablets (QLiTEs) and home use for all QPS staff | 2207000 | 2017-09-07T00:00:00 | PSBA
28/2/2018 | OSR | State Penalties Enforcement Registry (SPER) Program | 2017-12-31T00:00:00 | Delivery | G | 2018-10-31T00:00:00 | Revised Expenditure and cost to date has been updated to account for an elongated ICT delivery and provision for a contingency. A contract variation has been negotiated and executed. The remaining components of the Program include build, system integration testing, user acceptance testing of the replacement ICT solution. A revised delivery date is targeted for October, 2018. | 2017-12-31T00:00:00 | High | 47200000 | G | State Penalties Enforcement Registry | 55 | 43176000 | A | A | 1 | To maintain the integrity of fines as an effective sanction. To uphold confidence in the justice system. To deliver efficient and effective debt management practices which provide value for money to the State. 28/2/2018, | 62150000 | 2014-01-01T00:00:00 | QR
28/2/2018 | RI | Financial Assurance Information Registry (FAIR) | 2018-07-01T00:00:00 | Delivery | G | 2018-07-01T00:00:00 | Some functionality has been developed and undergoing testing. Project is on track with system being operational by 1 July 2018. | 2018-02-09T00:00:00 | Medium | 15900000 | G | Insurance Commission | 50 | 1691000 | G | G | 2 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
28/2/2018 | RI | Information Security Program | 2019-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The program is on track according to schedule and budget. | 2018-02-09T00:00:00 | Medium | 1960000 | G | Office of the Chief Information Officer | 25 | 175365 | G | G | 3 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 28/2/2018, | 1960000 | 2017-10-16T00:00:00 | QR
28/2/2018 | OSR | Office of State Revenue (OSR) Transformation Program | 2020-06-30T00:00:00 | Delivery | G | 2020-06-30T00:00:00 | Commenced machine learning initiative for tax insights. Program is on track. | 2018-02-09T00:00:00 | High | 73548000 | G | Office of State Revenue | 6 | 8918965 | G | G | 4 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 28/2/2018, 28/2/2018,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 73548000 | 2017-08-01T00:00:00 | QR
28/2/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
28/2/2018 | Corporate Services Improvement Systems Board | Learnzone Improvement Project | 2017-06-30T00:00:00 | Delivery | G | 2017-09-30T00:00:00 | The LearnZone Improvement project is reporting red due to remediation actions on project deliverables impacting the project's timeframe. These remediation actions have now been completed. A Project End Report has been drafted for Program Board approval. Once the Project End Report is approved, the project will be marked as closed on the QG ICT Dashboard. | 2017-12-31T00:00:00 | High | 796000 | G | Transactional Services Improvement Program | 95 | 360150 | R | R | 1 | Innovate, develop and deliver an improved and centralised digital learning service and management function. | 801000 | 2016-02-01T00:00:00 | TMR
28/2/2018 | Corporate Services Improvement Systems Board | Lotus Notes Decommissioning | 2016-01-31T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project is on track. | 2017-12-31T00:00:00 | High | 8150000 | G | ERP Projects Board | 63 | 1819953 | G | G | 2 | Deliver improved information platform functions for effective ICT Strategy Alignment. | 8150000 | 2015-11-01T00:00:00 | TMR
28/2/2018 | Corporate Services Improvement Systems Board | Stop Cheques - Stage 3 | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Stop Cheques Stage 3 project is on track. | 2017-12-31T00:00:00 | Medium | 200000 | G | ERP Projects Board | 20 | 149613 | G | G | 3 | Cheques are inefficient and costly to use, process and administer for both the customer and department. A range of solutions have been developed to reduce the number of cheques that the department produces or receives including refund to card at counter, Bulk Bpay solutions and the introduction of new payment methods are being delivered to be more in line with contemporary retail offerings. The outsourcing of cheque production produced a more streamlined process. 28/2/2018,The stop cheques initiative includes 3 elements; Outsourcing, cost reduction, outbound cheques and inbound cheques. | 200000 | 2017-07-01T00:00:00 | TMR
28/2/2018 | Corporate Services Improvement Systems Board | Risk Management Solution | 2018-07-01T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Risk Management Solution project is on track. | 2017-12-31T00:00:00 | High | 350000 | G | Corporate Governance | 20 | 581326 | G | G | 4 | Replace the current risk management approach through the delivery of a new and contemporary enterprise Risk Management solution for TMR. | 710000 | 2017-07-02T00:00:00 | TMR
28/2/2018 | Corporate Services Improvement Systems Board | Integrated Records Information System (IRIS) | 2018-07-01T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The IRIS project is on track. | 2017-12-31T00:00:00 | High | 7967972 | G | Information Technology Branch | 25 | 1754750 | G | G | 5 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 7967972 | 2017-07-02T00:00:00 | TMR
28/2/2018 | Corporate Services Improvement Systems Board | Transactional Services Improvement Program Enhancements | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Transactional Services Improvement Program Enhancements Stage 3 is on track. | 2017-12-31T00:00:00 | Low | 200000 | G | Transactional Services Improvement Program | 20 | 140098 | G | G | 6 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. | 200000 | 2017-07-01T00:00:00 | TMR
28/2/2018 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery | G | 2018-09-30T00:00:00 | The CDOP Online Portal project is on track. | 2017-12-31T00:00:00 | High | 1500000 | G | Customer Services, Safety and Regulation Division | 87 | 768248 | G | G | 7 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal services currently required. | 1441000 | 2016-01-01T00:00:00 | TMR
28/2/2018 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The eLearner project is currently on track. | 2017-12-31T00:00:00 | High | 2500000 | G | Customer Services, Safety and Regulation Division | 93 | 4082698 | G | G | 8 | Implement an online learning and assessment program at the pre-learner and/or learner stage, to replace enhance learning outcomes. | 4176000 | 2015-06-12T00:00:00 | TMR
28/2/2018 | Customer Service, Safety and Regulation Program | Facial Recognition Replacement | 2017-03-31T00:00:00 | Closed | G | 2017-08-31T00:00:00 | The Facial Recognition project closure report was approved by the Project Board in December 2017. The Facial Recognition project will report for one more reporting period before being removed from the ICT Dashboard. | 2017-12-31T00:00:00 | High | 531250 | G | Customer Services, Safety and Regulation Division | 100 | 183076 | G | G | 9 | To provide Queensland integration with the National Driver Licence Facial Recognition System (NDLFRS) as part of the National Facial Recognition Matching Capability. This project will see the sharing of and upload of TMR facial image holdings to a national solution that will conduct facial recognition services and sharing with Australian Government, road agencies and law enforcement agencies. | 631250 | 2015-07-13T00:00:00 | TMR
28/2/2018 | Customer Service, Safety and Regulation Program | Hardware Security Modules (HSM) | 2016-07-29T00:00:00 | Closed | G | 2017-08-31T00:00:00 | The HSM project closure report was approved by the Project Board in December 2017. The HSM project will report for one more reporting period before being removed from the ICT Dashboard. | 2017-12-31T00:00:00 | High | 500000 | G | Customer Services, Safety and Regulation Division | 100 | 395016 | G | G | 10 | The Hardware Security Modules (HSMs) form part of the Queensland Driver Licence smartcard product set introduced in 2010 and generate keys for smartcard authentication and validation by TMR-authorised card readers at TMR Customer Service Centres, QGAP and Queensland Police Service locations throughout Queensland. These HSMs are coming to 'pend of life and will be required to be replaced to continue the protection of smartcard authenticity and key validation for the TMR products. | 500000 | 2015-08-01T00:00:00 | TMR
28/2/2018 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The Mobile Compliance Information System project is on track. | 2017-12-31T00:00:00 | High | 300000 | G | Customer Services, Safety and Regulation Division | 80 | 632056 | G | G | 11 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 630000 | 2016-11-01T00:00:00 | TMR
28/2/2018 | Customer Service, Safety and Regulation Program | Call Centre VOIP Upgrade | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Call Centre VOIP Upgrade project is on track. | 2017-12-31T00:00:00 | Low | 1140000 | G | Customer Services, Safety and Regulation Division | 25 | 611572 | G | G | 12 | The Call Centre VOIP Upgrade has commenced to upgrade the VOIP telephony platform within the department. The proposed solution will see a reduction in call costs, a shift in capability to a 28/2/2018,contemporary solution utilising an existing investment within the department. | 1140000 | 2017-04-01T00:00:00 | TMR
28/2/2018 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery | G | 2017-12-24T00:00:00 | The Ralph Replacement project is on track. | 2017-12-31T00:00:00 | Medium | 500000 | G | Customer Services, Safety and Regulation Division | 59 | 568136 | G | G | 13 | TMR's current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace the existing application with a contemporary and supportable alternative to assist the department in maintaining its timely updating of fees and charges. | 674000 | 2016-07-01T00:00:00 | TMR
28/2/2018 | Customer Service, Safety and Regulation Program | The Voice Communications Management System | 2017-06-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | The Voice Comms Management System project is on track. | 2017-12-31T00:00:00 | Medium | 828000 | G | Customer Services, Safety and Regulation Division | 75 | 274738 | G | G | 14 | The Voice Communications Management System project consists of two replacement of existing Voice Communication and Control Systems at Townsville and Hay Point. | 828000 | 2016-01-01T00:00:00 | TMR
28/2/2018 | Customer Service, Safety and Regulation Program | Compulsory Third Party Tax Invoice Online | 2017-12-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The CTP Tax Invoice Online project is on track. | 2017-12-31T00:00:00 | Medium | 300000 | G | Customer Services, Safety and Regulation Division | 12 | 17281 | G | G | 15 | The Compulsory Third Party Tax Invoice Online project will deliver a new online service which will enable Customers to self-serve and print an electronic version of the CTP Invoice, removing the need for TMR to process paper based invoices, avoiding production and postage charges. | 300000 | 2017-05-01T00:00:00 | TMR
28/2/2018 | Customer Service, Safety and Regulation Program | The Maritime Safety Queensland (MSQ) iBase Project | 2017-06-30T00:00:00 | Closed | G | 2017-07-28T00:00:00 | The MSQ iBase project closure report was approved by the Project Board in November 2017. This project will no longer report on the ICT Dashboard. | 2017-12-31T00:00:00 | Low | 450000 | G | Customer Services, Safety and Regulation Division | 100 | 227589 | G | G | 16 | The Maritime Safety Queensland ibase Project has commenced as the current incident register platform has been identified as requiring replacement. The future platform will work in collaboration with current field input and smart devices. | 292000 | 2017-01-01T00:00:00 | TMR
28/2/2018 | Customer Service, Safety and Regulation Program | Vessel Traffic Services (VTS) | 2016-01-05T00:00:00 | Delivery | G | 2018-11-30T00:00:00 | The Vessel Traffic Services (VTS) project has not previously reported on the ICT Dashboard. The project is on track. | 2017-12-31T00:00:00 | High | 15224694 | G | Customer Services, Safety and Regulation Division | 25 | 5535297 | G | G | 17 | The purpose of the project is procure and implement a replacement decision support tool for the existing Vessel Traffic Service (VTS) used by TMR to track and monitor ship movements within Queensland ports, the Great Barrier Reef and the Torres Strait. | 25569044 | 2014-04-14T00:00:00 | TMR
28/2/2018 | Customer Service, Safety and Regulation Program | Registration and Licensing (R and L) Systems Software Upgrade | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The R and L Systems Software Upgrade project is on track. | 2017-12-31T00:00:00 | Medium | 780000 | G | Customer Services, Safety and Regulation Division | 20 | 21799 | G | G | 18 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
28/2/2018 | Infrastructure Management and Delivery | Access Management System (AMS) - formerly Heavy Vehicle Permit Management System | 2015-10-31T00:00:00 | Paused | A | 2017-06-30T00:00:00 | TMR is taking steps to conclude the Access Management System project, in light of significant changes in the operating environment since it was commenced, including the way permits are issued and the role of the National Heavy Vehicle Regulator with its AccessCONNECT system. | 2017-12-31T00:00:00 | High | 4281564 | A | Infrastructure Management 28/2/2018,and Delivery | 83 | 8307429 | A | A | 19 | Improve heavy vehicle and load movement safety through effective schemes, guidelines and conditions management. Allow coordinated road operations such that an increase in activity will not result in economic detriment or a loss of safety and public amenity. | 9001258 | 2013-06-01T00:00:00 | TMR
28/2/2018 | Infrastructure Management and Delivery | Work Improvement Note (WIN) Replacement | 2016-12-19T00:00:00 | Delivery | G | 2018-02-27T00:00:00 | The WIN Replacement project is on track. An exception report to extend the projects end date to February 2018 and additional budget to cover additional expenses was approved by the Program Board in December 2017. | 2017-12-31T00:00:00 | Low | 242612 | G | Infrastructure Management 28/2/2018,and Delivery | 89 | 254384 | G | G | 20 | The Work Improvement Note (WIN) System is used to capture, track, review and report on improvements, potential problems, non-conformances, corrective actions, customer feedback and complaints. The WIN System is an essential component of the overarching business management system as it meets specific certification requirements outlined in international quality, safety and environmental standards. This project will provide a replacement to the existing Work Improvement Note (WIN) system, which is dependent on unsupported technology. | 436375 | 2016-02-15T00:00:00 | TMR
28/2/2018 | Infrastructure Management and Delivery | 2018 Commonwealth Games Journey Planner (GJP) | 2017-10-13T00:00:00 | Delivery | G | 2018-04-27T00:00:00 | The 2018 Commonwealth GJP project is on track. | 2017-12-31T00:00:00 | High | 450000 | G | Infrastructure Management 28/2/2018,and Delivery | 67 | 477851 | G | G | 21 | A dedicated Journey Planner application supports this need by providing a single source of truth for all transport information related to the Games, and also allows for rapid changes to routes, schedules, and stops, if any are required, in order to drive transport behaviour and maintain network efficiency. | 973899 | 2016-10-16T00:00:00 | TMR
28/2/2018 | Passenger Transport Technology Program | Customer Contact Management Solution (CCMS) | 2017-06-30T00:00:00 | Delivery | G | 2017-11-10T00:00:00 | The CCMS project has successfully completed its scope and a project closure report will be submitted to the Program Board for consideration in January 2018. It should be noted the reported planned expenditure versus the actual cost to date variance will be rectified once the departments internal budgeting processes are completed for the current quarter. Once the approved budget is loaded, the variance will be greatly reduced and will be reflected in the next reporting period. | 2017-12-31T00:00:00 | High | 1279000 | G | TransLink | 99 | 1534791 | G | G | 22 | To implement an industry standard, robust and extensible solution to replace the existing Commentline solution. To achieve better performance of the customer contact management functions. To provide the base platform to support the future implementation of an xRM roadmap. 28/2/2018, | 1279000 | 2016-04-01T00:00:00 | TMR
28/2/2018 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery | G | 2018-08-31T00:00:00 | The STAS Auto Forms project is on track. | 2017-12-31T00:00:00 | High | 4166000 | G | TransLink | 59 | 3389218 | G | G | 23 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 5043876 | 2016-04-01T00:00:00 | TMR
28/2/2018 | Policy Planning and Investment Program | Portfolio, Program, Project and Contract Management (3PCM) - Phase 2 and 3 | 2017-03-31T00:00:00 | Delivery | G | 2017-12-22T00:00:00 | The 3PCM project has returned to green (reporting amber last reporting period) and is on track. The small number of defects identified in data migration activities have been resolved and are no longer impacting quality tolerances. | 2017-12-31T00:00:00 | High | 12757788 | G | Policy, Planning and Investment Division | 99 | 47767820 | G | G | 24 | Define and implement standard, consistently applied processes for planning, managing and delivering the Transport Infrastructure Portfolio across the domains of portfolio, program, project and contract management. Source and implement an integrated, strategic information communication technology solution that supports the business process and rules and enables a transition away from legacy applications. | 47908928 | 2012-09-01T00:00:00 | TMR
28/2/2018 | CS | Bandwidth Upgrade Project | 2017-07-31T00:00:00 | Closed | G | 2017-08-02T00:00:00 | The project completed closure on 30 June 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | High | 5551767 | G | Corporate Services | 98 | 4575357 | G | G | 1 | To upgrade internet connectivity for Queensland State Schools, uplifting data speeds to 25kbps per student, improving access to online educational and community resources. 28/2/2018, | 4575357 | 2015-01-12T00:00:00 | DET
28/2/2018 | SS | Early Start | 2015-07-03T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Medium | 70000 | G | State Schools | 74 | 73522 | G | G | 2 | To provide schools with enhanced reporting functionality, improving their ability to analyse Prep to Year 2 student learning data. | 200992 | 2013-04-03T00:00:00 | DET
28/2/2018 | CS | eDRMS Upgrade Project | 2016-06-30T00:00:00 | Closed | G | 2017-07-04T00:00:00 | The project completed closure on 4 July 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | Critical | 2203000 | G | Corporate Services | 92 | 1734511 | G | G | 3 | To upgrade the key operational system so that it meets current and future demands and aligns with electronic information management practices. | 1680000 | 2015-01-12T00:00:00 | DET
28/2/2018 | PP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Delivery | G | 2018-02-27T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 700000 | G | Policy, Performance and Planning | 74 | 1125550 | G | G | 4 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
28/2/2018 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery | G | 2018-08-10T00:00:00 | The project is tracking to plan. The project is currently subject to procurement activities. | 2017-09-08T00:00:00 | High | 0 | G | Corporate Services | 37 | 0 | G | G | 5 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DET FBS SAP future state landscape for the next five years | 0 | 2017-01-16T00:00:00 | DET
28/2/2018 | SS | Global Learning Environment | 2018-12-30T00:00:00 | Closed | G | 2017-06-02T00:00:00 | The project completed closure on 13 July 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | Critical | 800000 | G | State Schools | 100 | 2552704 | G | G | 6 | To provide an online global learning solution which focuses on the 2018 Commonwealth Games, encouraging learning and collaboration in Queensland, nationally and internationally. | 2492000 | 2014-10-29T00:00:00 | DET
28/2/2018 | DG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery | G | 2018-01-01T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Low | 632585 | G | DG | 79 | 755722 | G | G | 7 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
28/2/2018 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery | G | 2019-12-18T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Critical | 16670000 | G | State Schools | 44 | 7426976 | G | G | 8 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 23470000 | 2015-08-03T00:00:00 | DET
28/2/2018 | PP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | The project is tracking to the revised plan. The project is currently subject to procurement activities. | 2017-09-08T00:00:00 | High | 0 | G | Policy, Performance and Planning | 54 | 0 | G | G | 9 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution | 0 | 2016-03-01T00:00:00 | DET
28/2/2018 | CS | Purchase IT Replacement Project | 2015-09-30T00:00:00 | Closed | G | 2017-09-18T00:00:00 | The project completed closure on 31 July 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | Medium | 248800 | G | Corporate Services | 99 | 905348 | G | G | 10 | To replace the existing system with a solution that meets current and future demands, provides enhanced analytics and improvements to reporting. | 1100000 | 2015-06-29T00:00:00 | DET
28/2/2018 | PP | Research Services 2.0 | 2016-09-30T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Low | 230000 | G | Policy, Performance and Planning | 85 | 404745 | G | G | 11 | To develop a solution that assists in the management of the Department of Education and Training commissioned research proposals and projects, improving resourcing and information dissemination. | 431157 | 2015-11-02T00:00:00 | DET
28/2/2018 | SS | School Budget Solution | 2017-03-31T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 2030000 | G | State Schools | 95 | 6295520 | G | G | 12 | To develop a solution that assists schools with resource management, improving their ability to support students in achieving better educational outcomes. | 6641785 | 2014-12-15T00:00:00 | DET
28/2/2018 | SS | Trial of platform for virtual academies | 2017-10-02T00:00:00 | Delivery | G | 2018-12-31T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 151641 | G | State Schools | 40 | 101875 | G | G | 13 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage; safe and secure like-minded student virtual communities; and strategic partnerships with university, industry and business. 28/2/2018, 28/2/2018, | 151641 | 2016-06-21T00:00:00 | DET
28/2/2018 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery | G | 2019-06-28T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 41000000 | G | Corporate Services | 48 | 25998875 | G | G | 14 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
28/2/2018 | OIR | Renewal and Photographic Licensing System (RAPS) Assessor Portal | 2018-07-13T00:00:00 | Delivery | G | 2018-05-10T00:00:00 | Development phase and business analysis continued to progress. Business requirements to be completed by end of October. | 2017-10-04T00:00:00 | High | 766467 | G | Office of Industrial Relations | 20 | 220999 | G | G | 15 | The RAPS Assessor Portal project commenced as an initiative to target improving services for high risk work licensing accredited assessors, registered training organisations and licensing and advisory services. Currently accredited assessors must use a combination of cumbersome paper based processes, smart forms, and an online service that is difficult to use. This project will improve and integrate the external and internal applications and reduce duplicated processes for high-risk work licensing stakeholders whilst meeting legislative requirements. One simplified online service will be delivered for assessors that will save them time and make compliance easier. | 769103 | 2016-12-14T00:00:00 | DET
28/2/2018 | TS | Study Tours Support System Upgrade | 2016-06-30T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Medium | 680000 | G | Training and Skills | 96 | 772580 | G | G | 16 | To replace or upgrade the existing Study Tours system with an online solution that has enhanced functionality, improving processes, data quality and tour management. | 779894 | 2015-08-31T00:00:00 | DET
28/2/2018 | [20 empty] | INVERSTMENT INFO
28/2/2018 | CSG | Coal Seam Gas Groundwater Monitoring Arrangements | 2017-12-31T00:00:00 | Paused | G | 2018-06-30T00:00:00 | A change to the planned end date has been approved; there is no impact to cost. Initiative now paused until early 2018. 28/2/2018, 28/2/2018,August 2017 - Revised total expenditure (budget) updated to include all operating costs not previously reported. 28/2/2018, 28/2/2018,June 2017 - Progress is continuing as planned. Still on schedule to complete December 2017. 28/2/2018, 28/2/2018,December 2016 - Much of the project has been completed and a significant amount of the procurement expenditure for capital equipment has occurred. 28/2/2018, 28/2/2018,October 2016 - Progress is continuing as planned. 28/2/2018, 28/2/2018,August 2016 - Cost returned to Green after a review of costs associated with activities remaining, and a correction in actual cost to date adjustment. 28/2/2018, 28/2/2018,June 2016 - Cost is Amber with a resource review under way. 28/2/2018, 28/2/2018,February 2016 - Progress is continuing as planned. | 2018-02-12T00:00:00 | High | 2380568 | G | Coal Seam Gas Compliance | 95 | 2548371 | G | G | 1 | Enhance availability of groundwater data through improvements to network monitoring of bores for clients and landholders. | 2598256 | 2014-01-13T00:00:00 | DNRM
28/2/2018 | SIMTARS | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery | G | 2019-03-01T00:00:00 | A change request was approved to alter the scope and associated percentage complete, time-frame and costs. 28/2/2018, 28/2/2018,December 2017 - Awaiting confirmation of project closure; project is still operating within approved time-frame tolerance. 28/2/2018, 28/2/2018,November 2017 - A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 28/2/2018, 28/2/2018,October 2017 - The project is continuing as planned. 28/2/2018, 28/2/2018,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2018-02-12T00:00:00 | High | 563000 | G | SIMTARS (Safety In Mines Testing and Research Station) | 60 | 612819 | G | G | 2 | The development and delivery of a (replacement) modern and robust Safegas solution: 28/2/2018, 28/2/2018,* risk reduction increasing capability to manage the volume of queries, transactions and data 28/2/2018,* decrease database corruption related to incidents. | 1170000 | 2017-01-25T00:00:00 | DNRM
28/2/2018 | SO | Mines Infrastructure Risk Mitigation Project | 2019-02-18T00:00:00 | Delivery | G | 2019-02-28T00:00:00 | The project is continuing as planned. 28/2/2018, 28/2/2018,November 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-02-12T00:00:00 | High | 1200000 | G | Statewide Operations | 17 | 185000 | G | G | 3 | Migrate systems to supported infrastructure and software to: 28/2/2018, 28/2/2018,* provide a stable, secure, fully supported and flexible solution 28/2/2018,* eliminate the risks to which the geoscience data assets are currently exposed. | 1200000 | 2017-08-08T00:00:00 | DNRM
28/2/2018 | GSQ | MinesOnlineMaps - Spatial Presentation Replacement | 2017-06-30T00:00:00 | Paused | G | 2018-04-30T00:00:00 | Project is paused awaiting review of a possible change in direction. Cost remains Green while investigation is undertaken to identify if deferral request was processed. | 2018-02-12T00:00:00 | Medium | 531030 | G | Geological Survey of Queensland | 60 | 98271 | G | G | 4 | Provide a web-based mapping solution for the ongoing provision of MinesOnlineMaps (MOMaps) into the future. | 531030 | 2016-08-01T00:00:00 | DNRM
28/2/2018 | LSI | Queensland Globe Improvements | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is continuing as planned. 28/2/2018, 28/2/2018,December 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-02-12T00:00:00 | High | 1002450 | G | Land and Spatial Information | 40 | 388837 | G | G | 5 | Enhancements to Queensland Globe to continue to evolve and improve user satisfaction and experience, such as: 28/2/2018, 28/2/2018,* create and save user-defined topics 28/2/2018,* improve query and access 28/2/2018,* provide editable 'redlining' 28/2/2018,* improve data imports. | 1002450 | 2017-10-09T00:00:00 | DNRM
28/2/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 28/2/2018, 28/2/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 28/2/2018,October 2017 - The project is progressing as planned. 28/2/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 28/2/2018,June 2017 - Revised Schedule approved returning the project to Green. 28/2/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 28/2/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 28/2/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 28/2/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 28/2/2018,December 2016 - The project is progressing as planned. | 2018-02-12T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 95 | 712717 | G | G | 6 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 28/2/2018, 28/2/2018,* register and maintain their information 28/2/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DNRM
28/2/2018 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 28/2/2018, 28/2/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 28/2/2018,August 2017 - Approved extension of timeframe. 28/2/2018,June 2017 - The project is progressing as planned. 28/2/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 28/2/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 28/2/2018,October 2016 - Progress is continuing as planned. 28/2/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 28/2/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 28/2/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2018-02-12T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 93 | 1363080 | G | G | 7 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 28/2/2018, 28/2/2018,* support compliance with legislation 28/2/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 28/2/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 28/2/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 28/2/2018, | 1390000 | 2012-04-01T00:00:00 | DNRM
28/2/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DPC
28/2/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
28/2/2018 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 28/2/2018,* Move operational accountability and responsibility for print and imaging devices to the service provider 28/2/2018,* Reduce print and imaging costs 28/2/2018,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
28/2/2018 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
28/2/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
28/2/2018 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 28/2/2018, 28/2/2018,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
28/2/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
28/2/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 28/2/2018, 28/2/2018,* reduce operating costs 28/2/2018,* increase capacity 28/2/2018,* improve customer experience 28/2/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
28/2/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
28/2/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 28/2/2018, 28/2/2018, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
28/2/2018 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 28/2/2018, 28/2/2018,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
28/2/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
28/2/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 28/2/2018, 28/2/2018,November 2017 - Actual cost to date corrected due to input error. 28/2/2018, 28/2/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 28/2/2018, | 2017-12-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 57 | 733941 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
28/2/2018 | ESR | Environmental Management Register/Contaminated Land Register - replacement | 2017-06-30T00:00:00 | Paused | G | 2017-06-30T00:00:00 | August 2017 - The project is paused awaiting the outcome of a change request for additional scope; this will return the project to a Green state. 28/2/2018, 28/2/2018,April 2017 - A minor correction has been made to the revised total estimated expenditure to include $20,000 operating prior years. 28/2/2018, 28/2/2018,February 2017 - A change request has been approved moving the initiative cost back to Green. 28/2/2018, 28/2/2018,December 2016 - Project is continuing as planned, with a change request under way to return cost to Green. 28/2/2018, 28/2/2018,October 2016 - Project delivery activities formally commenced on 2 October 2016. 28/2/2018, 28/2/2018,August 2016 - The initiative was paused for some time but has now recommenced and moved into delivery. It is progressing as planned. | 2018-02-12T00:00:00 | High | 981680 | A | Environmental Services and Regulation | 78 | 718000 | A | A | 1 | The current system no longer supports efficient delivery of the department's responsibilities. The replacement will: 28/2/2018, 28/2/2018,* mitigate the risks associated with a system that is beyond its useful life 28/2/2018,* improve access to information by individuals, business and industry conducting searches (property lot plan) of the registers 28/2/2018,* support the creation of notices to stakeholders 28/2/2018,* reduce manual tasks through the introduction of automated workflows and customer self-serve and self-correct. 28/2/2018, | 1111680 | 2016-07-01T00:00:00 | EHP
28/2/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 28/2/2018, 28/2/2018,November 2017 - Actual cost to date corrected due to input error. 28/2/2018, 28/2/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 28/2/2018, | 2018-02-12T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 65 | 925706 | G | G | 2 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | EHP
28/2/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP
20/2/2019 | EHQ | Application Server Replacement |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 42 | 4345060 |  | G | 1 | This project aims to establish a robust, highly available and secure contemporary platform that has the capability to support the agile eHealth Strategy. |  | 2017-07-03T00:00:00 | DH
20/2/2019 | HSQ | Pathology and Forensic Laboratory System Rehosting Project |  | Delivery |  |  |  | 2018-12-12T00:00:00 | High |  |  | Health Support Queensland | 96 | 2700084 |  | G | 2 | Delivery of a replacement hardware and visualisation solution for the AUSLAB and AUSCARE systems that will achieve improved resiliency of the architecture, updated operating system and inclusion of virtualisation. AUSLAB and AUSCARE are critical to support laboratories and patient clinical care. |  | 2017-08-28T00:00:00 | DH
20/2/2019 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 |  | Delivery |  |  |  | 2018-12-13T00:00:00 | High |  |  | Metro North | 40 | 2011047 |  | G | 3 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 20/2/2019, 20/2/2019,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Women's Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 20/2/2019, 20/2/2019,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. |  | 2015-06-01T00:00:00 | DH
20/2/2019 | EHQ | Backup Asset Replacement |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 37 | 904466 |  | G | 4 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 20/2/2019,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work. Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. |  | 2017-07-03T00:00:00 | DH
20/2/2019 | EHQ | Digital Collaboration Platform Program |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 80 | 19453017 |  | G | 5 | This program will deliver digital collaboration tools for any time, any where, any device including: 20/2/2019,Email and Archiving 20/2/2019,Establishment and Collaboration 20/2/2019,Productivity Suite Enablement |  | 2015-10-29T00:00:00 | DH
20/2/2019 | QAS | Dynamic Deployment and Service Delivery Modelling |  | Initiate |  |  |  | 2018-12-11T00:00:00 | High |  |  | Queensland Ambulance Service | 40 | 777894 |  | G | 6 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. |  | 2015-12-01T00:00:00 | DH
20/2/2019 | CHOPD | Electronic List of Approved Medicines |  | Delivery |  |  |  | 2018-12-04T00:00:00 | High |  |  | Chief Health Officer and Prevention | 98 | 389642 |  | G | 7 | Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. |  | 2017-07-24T00:00:00 | DH
20/2/2019 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) |  | Delivery |  |  |  | 2018-12-13T00:00:00 | High |  |  | Metro North | 68 | 4781761 |  | G | 8 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (ieMR) program. 20/2/2019, 20/2/2019,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 20/2/2019, 20/2/2019,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. |  | 2016-07-01T00:00:00 | DH
20/2/2019 | EHQ | Enterprise Firewall Service (EFS) |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 33 | 1050131 |  | G | 9 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment.??The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access.? |  | 2017-07-05T00:00:00 | DH
20/2/2019 | MNHHS | Financial System Renewal (FSR) Project |  | Delivery |  |  |  | 2018-12-11T00:00:00 | High |  |  | Metro North | 69 | 102508717 |  | R | 10 | The current Queensland Health Finance, Asset and Materials Maintenance Information System (FAMMIS) system is based on a heavily customised solution which is almost 20 years old and no longer supported. 20/2/2019,The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 20/2/2019, 20/2/2019,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 20/2/2019,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 20/2/2019, 20/2/2019,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. |  | 2016-12-07T00:00:00 | DH
20/2/2019 | EHQ | Follow Me Desktop - Deployment |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 73 | 2162144 |  | G | 11 | Follow Me Desktop Deployment Project will deliver the Follow Me Desktop service (FMD) to HHS' in alignment with the Infrastructure Remediation Program (IMP) and ieMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. |  | 2017-07-03T00:00:00 | DH
20/2/2019 | EHQ | Regional North and West Queensland ICT Infrastructure Replacement Initiative |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 77 | 1985328 |  | G | 38 | Will replace or uplift out of date end of life ICT assets. |  | 2017-07-01T00:00:00 | DH
20/2/2019 | EHQ | HBCIS Hardware Refresh |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 45 | 1424741 |  | G | 12 | Project Purpose: To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. |  | 2017-07-01T00:00:00 | DH
20/2/2019 | EHQ | ICT Security Enhancements (ISE) |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 65 | 736698 |  | G | 13 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. |  | 2017-07-05T00:00:00 | DH
20/2/2019 | EHQ | Identity Access Management Project |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 42 | 6366359 |  | G | 14 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. |  | 2015-06-22T00:00:00 | DH
20/2/2019 | EHQ | ieMR Program (Funding Packages 3 and 4) |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 37 | 176540137 |  | G | 15 | ieMR will enable improved patient care through the development of a state-wide, authoritative single source of the patient records. 20/2/2019, 20/2/2019,The ieMR will provide clinicians with the ability to: 20/2/2019,* access data that is integrated, accurate and clinically relevant 20/2/2019,* support decision making and better use of information 20/2/2019,* optimise management of patients, resources and provision of services 20/2/2019,* support interaction across a network of providers by making it easier to find providers, transfer information and collaborate with multidisciplinary providers. 20/2/2019,The Program scope (all tranches) is to roll out the ieMR system to 24 hospitals across Queensland. |  | 2016-11-17T00:00:00 | DH
20/2/2019 | EHQ | Infrastructure Maintenance Program Establishment |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 96 | 1431232 |  | G | 16 | The Infrastructure Maintenance Program (IMP)?will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 20/2/2019,The scope includes: 20/2/2019,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 20/2/2019,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and? 20/2/2019,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. |  | 2017-07-03T00:00:00 | DH
20/2/2019 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program |  | Delivery |  |  |  | 2018-12-11T00:00:00 | High |  |  | Clinical Excellence | 22 | 3603483 |  | G | 17 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 20/2/2019,The ongoing program of work aims to continue and build upon existing functionality by: 20/2/2019,- Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 20/2/2019,- Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 20/2/2019,- Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 20/2/2019,- Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 20/2/2019,- Supporting utilisation of clinical quality information by HHS and the Department of Health. |  | 2017-07-01T00:00:00 | DH
20/2/2019 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) |  | Initiate |  |  |  | 2018-12-11T00:00:00 | High |  |  | Queensland Ambulance Service | 30 | 2608621 |  | G | 18 | Phased delivery of a system supporting QAS business intelligence. |  | 2017-01-03T00:00:00 | DH
20/2/2019 | CED | integrated Referral Management Solution (iRMS) |  | Delivery |  |  |  | 2018-12-11T00:00:00 | High |  |  | Clinical Excellence | 37 | 21078289 |  | G | 19 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. |  | 2017-03-01T00:00:00 | DH
20/2/2019 | EHQ | Interoperability Project |  | Delivery |  |  |  | 2018-12-11T00:00:00 | High |  |  | eHealth Queensland | 37 | 21338466 |  | G | 20 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 20/2/2019,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 20/2/2019,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 20/2/2019, |  | 2015-02-01T00:00:00 | DH
20/2/2019 | HSQ | Laboratory Information System Program (LIS Program) |  | Delivery |  |  |  | 2018-12-12T00:00:00 | High |  |  | Health Support Queensland | 59 | 25717412 |  | A | 21 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 20/2/2019,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. |  | 2015-08-28T00:00:00 | DH
20/2/2019 | GCHHS | Medical Imaging Informatics Solution (MIIS) Risk Mitigation |  | Delivery |  |  |  | 2018-12-13T00:00:00 | High |  |  | Gold Coast | 33 | 3286185 |  | A | 22 | The Medical Imaging Informatics Solution (MIIS) Risk Mitigation project has identified an Imaging solution which will address the risks and opportunities described in the Case for Change including the mitigation of patient safety risks, increased efficiency and productivity, improvi.ng medical imaging billing revenue collection and cash flow. The solution has user endorsement from radiologists and clinicians and will be specifically configured to meet GCHHS?s needs. |  | 2017-04-03T00:00:00 | DH
20/2/2019 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) |  | Delivery |  |  |  | 2018-12-13T00:00:00 | High |  |  | Metro North | 85 | 4341246 |  | G | 23 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 20/2/2019, 20/2/2019,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 20/2/2019, 20/2/2019,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. |  | 2016-07-01T00:00:00 | DH
20/2/2019 | MNHHS | Metro North Radiology Information System (MRIS) Project |  | Delivery |  |  |  | 2018-12-13T00:00:00 | High |  |  | Metro North | 95 | 7001277 |  | G | 24 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. |  | 2014-06-01T00:00:00 | DH
20/2/2019 | EHQ | Metro South and East Queensland ICT Infrastructure Replacement Initiative |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 74 | 2314640 |  | R | 25 | Will replace or uplift out of date end of life ICT assets. |  | 2017-07-01T00:00:00 | DH
20/2/2019 | EHQ | Metro South East Queensland ICT Infrastructure Critical Uplift Initiative |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 95 | 1179267 |  | G | 26 | Will replace or uplift out of date end of life ICT assets. |  | 2017-07-01T00:00:00 | DH
20/2/2019 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 84 | 29264362 |  | G | 27 | A managed operating environment means that everyone within the organisation is running a clean, basic operating system with centralised update management. This includes upgrades of all PC operating systems, preparing QH applications for running on recent operating system environments, and Infrastructure remediation activities to ensure the deployment tools are sufficient and ready for production. |  | 2016-05-12T00:00:00 | DH
20/2/2019 | QAS | Non-Urgent Patient Transport |  | Delivery |  |  |  | 2018-12-11T00:00:00 | High |  |  | Queensland Ambulance Service | 90 | 1104145 |  | G | 28 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. |  | 2015-10-01T00:00:00 | DH
20/2/2019 | CHOPD | Notifiable Conditions System Replacement |  | Delivery |  |  |  | 2018-12-10T00:00:00 | High |  |  | Chief Health Officer and Prevention | 46 | 3257412 |  | G | 29 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 20/2/2019,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. |  | 2014-11-01T00:00:00 | DH
20/2/2019 | EHQ | Patient Administration System (PAS) Replacement - Business Case Development Project |  | Initiate |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 81 | 7339694 |  | G | 30 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients' journeys, and ensure that accurate information about our patients is readily available when and where required. 20/2/2019, 20/2/2019,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 20/2/2019,- support for patient engagement 20/2/2019,- integrated care 20/2/2019,- clinical research 20/2/2019,- population health (for patients using public health services) 20/2/2019,- performance transparency 20/2/2019,- resource planning. |  | 2015-11-01T00:00:00 | DH
20/2/2019 | CSD | Practice Management Enterprise Solution |  | Delivery |  |  |  | 2018-12-07T00:00:00 | High |  |  | Corporate Services | 83 | 2524461 |  | A | 31 | The main practice management software used by HHSs to conduct private practice services and billing activities is being replaced. The initiative will procure and implement "like for like" functionality enterprise solution for participating HHSs (15 in total). |  | 2017-08-01T00:00:00 | DH
20/2/2019 | EHQ | Project, Program and Portfolio Management Application |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 63 | 899098 |  | R | 32 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 20/2/2019, |  | 2017-05-02T00:00:00 | DH
20/2/2019 | EHQ | Queensland State-wide ICT Infrastructure Critical Uplift Initiative |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 80 | 2787750 |  | G | 33 | Will replace or uplift out of date end of life ICT assets. |  | 2017-07-01T00:00:00 | DH
20/2/2019 | EHQ | Queensland State-wide ICT Infrastructure Replacement Initiative |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 90 | 3554151 |  | G | 34 | Will replace or uplift out of date end of life ICT assets. |  | 2017-07-01T00:00:00 | DH
20/2/2019 | MNHHS | Quick Flow Project |  | Initiate |  |  |  | 2018-12-13T00:00:00 | High |  |  | Metro North | 47 | 2254786 |  | G | 35 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 20/2/2019,The key objectives of the project are to: 20/2/2019,- Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 20/2/2019,- Improve the outpatient experience across MNHSS facilities and community services 20/2/2019,- Improve clinic resource utilisation 20/2/2019,- Increase the efficiency of clinical and administrative processes 20/2/2019,- Ensure appropriate billing for outpatient services provided |  | 2016-12-05T00:00:00 | DH
20/2/2019 | CHHHS | Regional eHealth Project |  | Delivery |  |  |  | 2018-12-11T00:00:00 | High |  |  | Cairns and Hinterland | 75 | 17536062 |  | G | 36 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patient's home as possible. |  | 2015-10-05T00:00:00 | DH
20/2/2019 | EHQ | Regional North and West Queensland ICT Infrastructure Critical Uplift Initiative |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 85 | 2852961 |  | G | 37 | Will replace or uplift out of date end of life ICT assets. |  | 2017-07-01T00:00:00 | DH
20/2/2019 | EHQ | Regional South and East Queensland ICT Infrastructure Critical Uplift Initiative |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 95 | 1400613 |  | G | 39 | Will replace or uplift out of date end of life ICT assets. |  | 2017-07-01T00:00:00 | DH
20/2/2019 | EHQ | Regional South and East Queensland ICT Infrastructure Replacement Initiative |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 85 | 3257610 |  | G | 40 | Will replace or uplift out of date end of life ICT assets. |  | 2017-07-01T00:00:00 | DH
20/2/2019 | EHQ | Service Delivery Excellence Project (SDEP) |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 50 | 2835955 |  | G | 41 | The Service Delivery Excellence Project (SDEP) aims to improve the service delivery functions of eHealth Queensland to help the organisation achieve its Customers and services Foundation and Shared Goal: 20/2/2019,Enhance value for customers by streamlining end to end services, processes and delivery models so that we can provide an exceptional customer experience. 20/2/2019,Stage 1 has the primary objective of delivering the Project Initiation Document (PID) for the Service Delivery Excellence Project (SDEP) Stage 2. |  | 2017-10-03T00:00:00 | DH
20/2/2019 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 31 | 3722167 |  | G | 42 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access |  | 2017-07-03T00:00:00 | DH
20/2/2019 | MNHHS | Royal Brisbane and Women's Hospital Wi-Fi |  | Delivery |  |  |  | 2018-12-13T00:00:00 | High |  |  | Metro North | 80 | 4041050 |  | G | 43 | The RBWH Wi-Fi Project will provide an uplift and renewal to the latest Queensland Health (QH) standard for wireless local area network (WLAN) coverage within the internal areas of prioritised RBWH buildings in order to support digital healthcare. 20/2/2019,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for the RBWH in the near future. |  | 2017-10-22T00:00:00 | DH
20/2/2019 | EHQ | Sunshine Coast University Hospital (SCUH) Stage 2 ICT Expansion |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 83 | 4124839 |  | G | 44 | Sunshine Coast University Hospital (SCUH) ICT Stage 1 delivered the ICT required to achieve the successful commissioning of SCUH in March 2017. The SCUH Stage 2 ICT Expansion covers the investment period from 1 July 2017 to 31 December 2018 and is intended to support the planned expansion of SCUH to increase capacity and establish new services. |  | 2017-07-03T00:00:00 | DH
20/2/2019 | CHQ | Information Sharing Project Phase 2 |  | Delivery |  |  |  | 2018-12-06T00:00:00 | High |  |  | Children's Health Queensland | 50 | 1640000 |  | G | 45 | Department of Health, eHealth Queensland, Children's Health Queensland and Mater Health share a common vision for the seamless integration of care across organisational boundaries, in the interests of patient safety, quality, efficiency and improved access to care. This vision of integrated care processes is enabled through seamless access, at the point of care, to necessary health information and efficient transactional capabilities that support the care continuum. |  | 2018-01-10T00:00:00 | DH
20/2/2019 | SPP | Queensland Health Integrated Processing System establishment (QHIDSe) |  | Delivery |  |  |  | 2018-12-11T00:00:00 | High |  |  | Strategy, Policy and Planning | 36 | 1606721 |  | G | 46 | The QHIDSe project will develop in-house the foundation of an integrated processing system (i.e. QHIDS (Queensland Health Integrated Data System) using agile techniques and software development tools enabling QHIDS to be used as a replacement for the Queensland Hospital Inpatient Processing System (QHIPS, which processes the Queensland Hospital Admitted Patient Data Collection) and extended through future initiatives to provide new functionality. |  | 2018-05-25T00:00:00 | DH
20/2/2019 | HSQ | Modernised Managed Operating Environment (MOE) and Digital Collaboration Platform for HSQ |  | Delivery |  |  |  | 2018-12-12T00:00:00 | High |  |  | Health Support Queensland | 60 | 1873675 |  | G | 47 | Delivery of a fully functional, production managed operating environment and digital collaboration platform packaged to all desktops, laptops and some smart devices within the Health Support Queensland environment. |  | 2018-01-01T00:00:00 | DH
20/2/2019 | CHOPD | Mosquito-borne Disease Program: Spatial Database Project |  | Initiate |  |  |  | 2018-12-10T00:00:00 | High |  |  | Chief Health Officer and Prevention | 65 | 316402 |  | G | 48 | The vector surveillance and control program requires a state-wide surveillance and control solution to assist with the response to the risk of Dengue, Zika and Chikungunya virus outbreaks in vulnerable North Queensland and the mitigation of emerging risks across Central and Southern Queensland. |  | 2017-07-31T00:00:00 | DH
20/2/2019 | EHQ | Telehealth Asset Replacement |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 41 | 269630 |  | G | 49 | Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. |  | 2018-07-02T00:00:00 | DH
20/2/2019 | MNHHS | Connecting Care information Program (CCI) |  | Initiate |  |  |  | 2018-12-13T00:00:00 | High |  |  | Metro North | 25 | 984803 |  | G | 50 | The Connecting Care Information Program - CCI -will support streamlining and improvement of clinical and administrative workflows through delivery of key Information Technology (IT) enablers. |  | 2017-03-21T00:00:00 | DH
20/2/2019 | MNHHS | Metro North Health and Hospital Service Contemporary Workspace Phase 1 |  | Delivery |  |  |  | 2018-12-13T00:00:00 | High |  |  | Metro North | 55 | 834392 |  | G | 51 | This project is focusing on preparing the Metro North Hospital and Health Service (MNHHS) applications to be ready for contemporary operating system deployment. |  | 2017-08-01T00:00:00 | DH
20/2/2019 | MNHHS | Metro North Picture Archiving and Communication (PACS) Replacement for The Prince Charles Hospital |  | Delivery |  |  |  | 2018-12-13T00:00:00 | High |  |  | Metro North | 95 | 1318226 |  | G | 52 | Procure and implement a contemporary Picture Archiving and Communication (PACS) System and functionality that will ensure improved Service delivery for the MNHHS Medical Imaging Departments at The Prince Charles Hospital (TPCH). |  | 2017-12-01T00:00:00 | DH
20/2/2019 | CED | Patient Online Portal (POP) |  | Delivery |  |  |  | 2018-12-11T00:00:00 | High |  |  | Clinical Excellence | 8 | 2954347 |  | G | 53 | The Patient Online Portal (POP) aims to improve a patient's outpatient journey through greater visibility and enhanced communication capability across specialist services. Additionally, the solution seeks to provide greater flexibility in the provision of outpatient services, allowing patients to better manage their care. |  | 2018-03-05T00:00:00 | DH
20/2/2019 | MNHHS | Digital Transformation Readiness |  | Initiate |  |  |  | 2018-11-14T00:00:00 | High |  |  | Metro North | 28 | 1005588 |  | G | 54 | The key objectives of Digital Transformation Readiness are to perform activities in preparation for Metro North Hospital and Health Service (MNHHS) Digital Transformation with a focus on the integrated electronic Medical Record (ieMR) readiness. |  | 2018-06-29T00:00:00 | DH
20/2/2019 | MNHHS | Referral Lodgement and Tracking (RLaT) |  | Delivery |  |  |  | 2018-12-13T00:00:00 | High |  |  | Metro North | 73 | 2702381 |  | R | 55 | This project will deliver a state-wide capability for referrers to lodge patient referrals electronically with Queensland Health. The referral will be automatically routed to the appropriate Hospital and Health Service (HHS). |  | 2018-02-09T00:00:00 | DH
20/2/2019 | EHQ | Infrastructure Capacity Expansion FY 18-19 |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 35 | 226315 |  | G | 56 | The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified organic growth requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. |  | 2018-07-02T00:00:00 | DH
20/2/2019 | EHQ | Storage Asset Replacement FY 18-19 |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 10 | 101651 |  | G | 57 | The Server Asset Replacement Project is responsible for replacing prioritised, highly utilised and critical server assets which are coming to, or have reached, end-of-financial-life. |  | 2018-07-02T00:00:00 | DH
20/2/2019 | MNHHS | Digital Dictation Upgrade Project |  | Delivery |  |  |  | 2018-12-13T00:00:00 | High |  |  | Metro North | 90 | 1077760 |  | R | 58 | To replace the current versions of the Digital Dictation Systems in use at MNHHS facilities with the newest release of the product. The new release introduces efficiencies in the workflow process and contributes to patient care improvement through reduction in timeframe to complete patient letters. |  | 2016-07-25T00:00:00 | DH
20/2/2019 | CED | Consumer Integrated Mental Health Application (CIMHA) Secure Transfer and Technical Refresh Project |  | Delivery |  |  |  | 2018-12-11T00:00:00 | High |  |  | Clinical Excellence | 20 | 571089 |  | G | 59 | Upgrade the CIMHA application with functionality to automate the sending of selected clinical notes and data to external entities. This will improve to efficiency and timeliness of information sharing with external clinicians at assist them to make better decisions at the point of care. |  | 2018-04-16T00:00:00 | DH
20/2/2019 | HSQ | iPharmacy Upgrade Project |  | Initiate |  |  |  | 2018-12-05T00:00:00 | High |  |  | Health Support Queensland | 3 | 13860 |  | G | 60 | Remediate the functionality issues introduced with the i.Pharmacy v8.1 build 17 implementation including a reduction of BAU costs / time associated with manual interventions and workarounds. 20/2/2019,Ensure i.Pharmacy version issues are identified and remediated for future upgrades. 20/2/2019,Minimise costs associated with the Windows 7 support and deployment fee-for-service. 20/2/2019,Ensure i.Pharmacy application viability post Windows 7 end of extended support period (12 January 2020). 20/2/2019,Stabilise supporting infrastructure and hardware for ongoing operational viability. 20/2/2019,Ensure early issue identification and management through the establishment of ongoing vendor engagement forums to review requirements. |  | 2018-10-01T00:00:00 | DH
20/2/2019 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 2 |  | Delivery |  |  |  | 2018-12-12T00:00:00 | High |  |  | Health Support Queensland | 4 | 1996825 |  | G | 61 | Stage 2 of the IWFM Project will provide direct access to managing Queensland Health employee details, provide the capability of the submission of online forms, as well as enabling manager and employee self-service. This implementation will remove duplication, reduce paperwork and return the control and accountability of workforce establishment management to the business, thereby improving visibility of information, transparency of form tracking, increasing productivity and accuracy and reducing the time and inconvenience of returned forms. |  | 2018-09-13T00:00:00 | DH
20/2/2019 | QAS | Mobile Data State-wide |  | Initiate |  |  |  | 2018-12-11T00:00:00 | High |  |  | Queensland Ambulance Service | 3 | 130751 |  | G | 62 | This initiative will expand mobile data and automatic vehicle location capability statewide, and establish remote configuration, monitoring and updates to in-vehicle mobile units. |  | 2018-05-01T00:00:00 | DH
20/2/2019 | EHQ | Clinical and Business Intelligence Foundation Project |  | Initiate |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 5 | 71103 |  | G | 63 | The Clinical and Business Intelligence Foundation (CBIF) Project will - 20/2/2019,1. Implement a scalable, shared and trusted foundational platform to accelerate collaborative Department of Health (DoH) and Health and Hospital Service (HHS) data warehousing and intelligence development. 20/2/2019,2. Establish standard development, operational, security, metadata and governance architectures, patterns and procedures to accelerate future projects on the platform. 20/2/2019,3. Deliver reusable scheduling, emergency and surgery data vault structures, upon which views, data marts and reports/dashboards can be delivered to customers. |  | 2018-09-03T00:00:00 | DH
20/2/2019 | EHQ | Telephony, Paging and Messaging Remediation and Development Project |  | Initiate |  |  |  | 2018-11-30T00:00:00 | High |  |  | eHealth Queensland | 2 | 0 |  | G | 64 | Deliver ICT infrastructure uplifts at Multiple Hospital and Health Services (HHS) to address gaps in the Telephony, Paging and Messaging service, to bring the Telephony, Paging and Messaging service and the associated infrastructure up to a bench-marked state and develop a roadmap / strategy and associated architectures and standards to facilitate an incremental progression to a defined and agreed target-state. |  | 2018-09-03T00:00:00 | DH
20/2/2019 | [12 empty] | 0 | 0 |  |  | 1 |  |  |  | DCCSDS
20/2/2019 | DTS_ICTSPC | Human Resource Information Solution (HRIS) Program |  | Delivery |  |  |  | 2018-10-31T00:00:00 | Critical |  |  | ICT Strategic Project Coordination | 68 | 64324631 |  | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 20/2/2019, 20/2/2019,* Sustainable and supported HR and Payroll service delivery 20/2/2019,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 20/2/2019,* Strategic HR capability that supports the development, performance and safety of the departments workforce 20/2/2019,* Business Intelligence capability that provides real timely, integrated HR information 20/2/2019,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 20/2/2019,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 20/2/2019,* Align with the Commission of Audit Recommendations |  | 2012-09-03T00:00:00 | CROSS GOV
20/2/2019 | QPS | GPS Tracking (Bail) |  | Delivery |  |  |  | 2018-12-19T00:00:00 | High |  |  | Queensland Police Service | 40 | 0 |  | G | 1 | As per the Commencement of the Bail (Domestic Violence) and Another Act Amendment Act 2017 (the Amending Act) on 30 March 2018, Magistrates will be empowered to impose a tracking condition on a defendant granted bail as a condition of their bail undertaking. 20/2/2019,As such the QPS intends to progressively implement an electronic monitoring capability on a State Wide basis. 20/2/2019,An implementation project has commenced to create an electronic monitoring capability for geographically locating and monitoring a defendant on bail for QPS to meet requirements of the Amended Act. 20/2/2019,The GPS Tracking Project is an initial proposal to validate the utility of the technology prior to seeking a longer term solution. |  | 2018-03-30T00:00:00 | QPS
20/2/2019 | QPS | Police Integrity and Professional Standards |  | Delivery |  |  |  | 2018-12-19T00:00:00 | High |  |  | Queensland Police Service | 35 | 492654 |  | G | 2 | This initiative will deliver a new integrated Police Integrity and Professional Standards (PIPS) IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The PIPS system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The PIPS Project will also complement the Complaints Reform Project (CRP) established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of the PIPS system will place the QPS in a strong readiness position to fully implement CRP-generated changes to disciplinary processes and immediately deliver the benefits of these changes. |  | 2017-03-07T00:00:00 | QPS
20/2/2019 | QPS | eWarrants |  | Delivery |  |  |  | 2018-12-19T00:00:00 | Medium |  |  | Queensland Police Service | 3 | 850000 |  | G | 3 | Develop and introduce new and enhanced business processes and information exchange capabilities (requiring modifications to applications and technology) to enable the electronic creation, and management of Warrants issued by the Magistrates Courts for the duration of the Warrant. 20/2/2019, 20/2/2019,This is an inter-agency initiative involving QPS, Integrated Criminal Justice (ICJ), Department of Justice and Attorney General (DJAG), Communities and Corrections. It is anticipated that overall Program/Project Management will be the responsibility of ICJ and follow a similar model to that established for eDV (Domestic Violence). 20/2/2019, 20/2/2019,Legislative changes will need to occur with both QPS and DJAG, in regard to the current requirements regarding the receiving, processing and validity of hard copy warrants. |  | 2017-06-16T00:00:00 | QPS
20/2/2019 | CS | ICT Disaster Recovery Model Project (IDRP) |  | Closed |  |  |  | 2019-02-18T00:00:00 | High |  |  | Corporate Services | 100 | 6164631 |  | G | 1 | *Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. |  | 2016-10-01T00:00:00 | DJAG
20/2/2019 | BCS | Blue Card Services Recommendation 28.1 Project - Blue Card Home Based Care Register |  | Delivery |  |  |  | 2018-10-30T00:00:00 | High |  |  | Blue Card Services | 60 | 860628 |  | G | 2 | The objective of this project is to establish a register for recording and reporting on regulated child-related services provided from the home, specifically limited to foster/kinship care, family day care and stand-alone care. As recommended by the Queensland Family and Child Commission (QFCC) within the Recommendation 28 Supplementary Review Report (A report on information sharing to enhance the safety of children in regulated home-based services) this register will: 20/2/2019,a) identify co-located home-based services 20/2/2019,b) enable the Queensland Police Service to have line of sight to the register to access up-to-date information when Police attend a residential address to identify potential risks to children, and 20/2/2019,c) make information available to agencies, including Department of Child Safety, Youth and Women, Department of Education and the Office of the Public Guardian to assist with regulating and/or monitoring specific home-based services. |  | 2017-04-01T00:00:00 | DJAG
20/2/2019 | HHS_HH | Future of Property and Tenancy Systems |  | Delivery |  |  |  | 2018-10-31T00:00:00 | Critical |  |  | Housing and Homelessness | 67 | 81871542 |  | G | 1 | Replace the existing ICT housing solution with an integrated ICT system. |  | 2013-07-01T00:00:00 | HPW
20/2/2019 | BPAM_QF | Fleet Management System Replacement Project (FMSRP - QFleet) |  | Initiate |  |  |  | 2018-10-31T00:00:00 | High |  |  | QFleet | 25 | 1120176 |  | A | 2 | The objective of the FMSRP is the procurement and implementation of a new common Fleet Management System that meets QFleet, QPS, QFES and QAS core business requirements and provides best value for money. It will provide a contemporary, sustainable common Fleet Management System that delivers effective and efficient business services for the agencies now and into the future. |  | 2017-10-19T00:00:00 | HPW
20/2/2019 | BPAM_QF | QFleet Car Sharing Model Implementation Project (CSMIP) |  | Delivery |  |  |  | 2018-10-31T00:00:00 | High |  |  | QFleet | 80 | 109980 |  | A | 3 | The objective of the Car Sharing Model Implementation Project (CSMIP) is the procurement and implementation of a fully automated, innovative and sustainable multi-agency car sharing solution delivering effective and efficient short-term motor vehicle hire services for government, now and in the future. |  | 2017-11-20T00:00:00 | HPW
20/2/2019 | DTS_SSQ | Pay Safe Project |  | Initiate |  |  |  | 2018-10-31T00:00:00 | Critical |  |  | Smart Service Queensland | 29 | 204690 |  | G | 4 | The Pay Safe project will implement an improved capability for offering secure payment card transactions via the telephone. To meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS) when the new VOIP telephony solution is introduced. |  | 2018-01-29T00:00:00 | HPW
20/2/2019 | DTS_SSQ | Smart Service Telephony Replacement Project |  | Delivery |  |  |  | 2018-10-31T00:00:00 | Critical |  |  | Smart Service Queensland | 80 | 4154771 |  | A | 5 | Smart Service Queensland seeks to transition the current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 20/2/2019, 20/2/2019,* reduce operating costs 20/2/2019,* increase capacity 20/2/2019,* improve customer experience 20/2/2019,* provide new functionality. |  | 2015-04-02T00:00:00 | HPW
20/2/2019 | DTS_SSQ | Technology Platform Project (TPP) |  | Delivery |  |  |  | 2018-10-31T00:00:00 | Critical |  |  | Smart Service Queensland | 90 | 2448606 |  | A | 6 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution and the call recording solution. |  | 2017-05-15T00:00:00 | HPW
20/2/2019 | DTS_DAP | Digital Archiving Program Tranche 1 Transition-In |  | Delivery |  |  |  | 2018-10-31T00:00:00 | Medium |  |  | Digital Archiving Program | 13 | 754509 |  | G | 7 | The Digital Archiving Program is seeking to deliver archival management and control capability with access, search and discovery for use by Queensland State Archives (QSA), Public Authorities and the Public. |  | 2018-08-07T00:00:00 | HPW
20/2/2019 | DTS_SSQ | Customer Identity and Details Enhancements FY17-18 |  | Delivery |  |  |  | 2018-10-31T00:00:00 | High |  |  | Smart Service Queensland | 75 | 1593131 |  | A | 8 | The Customer Identity and Details Enhancements FY17-18 project seeks to improve technology and functionality to meet agency requirements in Customer Identity and Details and enable agency adoption and uptake driving allowing further value for customers. 20/2/2019, 20/2/2019,* CDM Blueprint 20/2/2019,* Transition to new platform 20/2/2019,* Auth pilot 20/2/2019,* CDM release 2 pilot |  | 2017-07-01T00:00:00 | HPW
20/2/2019 | DTS_ICTSS | Government Wireless Network Contract and Administration Billing System |  | Initiate |  |  |  | 2018-10-31T00:00:00 | High |  |  | ICT Strategic Sourcing | 25 | 0 |  | G | 9 | The Government Wireless Network (GWN) Contract Directorate seeks a fully managed software-as-a-service solution to replace existing excel spreadsheets and macros that have organically grown in complexity, improve record keeping compliance, and alleviate current single points of failure and reliance. This project is to procure a purposely designed software system that is fully functional, customisable, redundant, reliable, will meet the current and future requirements of the GWN Contract, and replace current Contract Modification and Contractor Performance processes. |  | 2017-11-01T00:00:00 | HPW
20/2/2019 | DTS_QSS | Single Touch Payroll Project |  | Initiate |  |  |  | 2018-10-31T00:00:00 | High |  |  | Queensland Shared Services | 3 | 18033 |  | G | 10 | Queensland Shared Services (QSS) is seeking to implement Single Touch Payroll reporting for QSS customer agencies from 1 July 2019 to ensure legislative compliance. 20/2/2019,Single Touch Payroll is a federally legislated requirement for employers (with over 20 employees) to report payments and withholdings to the Australian Taxation Office in conjunction with the regular payment cycle. Single Touch Payroll law was legislated on 16 September 2016 forming part of the Budget Savings (Omnibus) Act 2016. 20/2/2019, |  | 2018-10-11T00:00:00 | HPW
20/2/2019 | CS_CIO | eDRMS Foundation Project |  | Initiate |  |  |  | 2018-10-31T00:00:00 | High |  |  | Chief Information Office | 1 | 18239 |  | G | 11 | The eDRMS Foundation project will investigate the department's current state and determine the appropriate environment for implementation of electronic document and records management functionality. |  | 2018-10-16T00:00:00 | HPW
20/2/2019 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 20/2/2019, 20/2/2019,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 20/2/2019,October 2017 - The project is progressing as planned. 20/2/2019,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 20/2/2019,June 2017 - Revised Schedule approved returning the project to Green. 20/2/2019,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 20/2/2019,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 20/2/2019,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 20/2/2019,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 20/2/2019,December 2016 - The project is progressing as planned. | 2017-12-21T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 20/2/2019, 20/2/2019,* register and maintain their information 20/2/2019,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
20/2/2019 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 20/2/2019, 20/2/2019,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 20/2/2019,August 2017 - Approved extension of timeframe. 20/2/2019,June 2017 - The project is progressing as planned. 20/2/2019,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 20/2/2019,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 20/2/2019,October 2016 - Progress is continuing as planned. 20/2/2019,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 20/2/2019,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 20/2/2019,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-21T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 20/2/2019, 20/2/2019,* support compliance with legislation 20/2/2019,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 20/2/2019,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 20/2/2019,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 20/2/2019, | 1390000 | 2012-04-01T00:00:00 | DEWS
20/2/2019 | BQ | Biosecurity Remote Sensing Research and Development Project |  | Delivery |  |  |  | 2019-02-08T00:00:00 | Critical |  |  | Biosecurity Queensland | 20 | 698285 |  | G | 1 | Investigate and deploy contemporary remote sensing technologies to enable improved surveillance activities for the National Red Imported Fire Ant Eradication Program. |  | 2015-07-01T00:00:00 | DAF
20/2/2019 | Ag | Economic Decision Support Tools Upgrade |  | Delivery |  |  |  | 2019-02-08T00:00:00 | High |  |  | Rural Economic Development | 10 | 127601 |  | G | 2 | Transition existing economic decision support tools to an online platform to inform decision making by growers and graziers on environmentally-sustainable management practices. |  | 2017-09-01T00:00:00 | DAF
20/2/2019 | BQ | Communication and Stakeholder Engagement Solution |  | Closed |  |  |  | 2019-02-08T00:00:00 | Medium |  |  | Biosecurity Queensland | 100 | 1011823 |  | G | 3 | To implement a simple, easy to use system that will facilitate the collection of information associated with the National Red Imported Fire Ant Eradication Program and the National Electric Ant Eradication Program. This will include contact management, complaints management, history of interactions, event management, training management, social media interactions, marketing campaign and reporting. |  | 2017-06-01T00:00:00 | DAF
20/2/2019 | Forestry | Forestry Mobility Project |  | Delivery |  |  |  | 2019-02-08T00:00:00 | Medium |  |  | Forestry Queensland | 75 | 1283898 |  | G | 4 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 20/2/2019, 20/2/2019,* the capture, management and integration of data 20/2/2019,* value-adding opportunities for business improvement 20/2/2019,management of risk associated with ongoing use and maintenance of disparate systems. |  | 2016-06-15T00:00:00 | DAF
20/2/2019 | Fisheries | Novel Commercial and Recreational Fishing Apps |  | Delivery |  |  |  | 2019-02-08T00:00:00 | High |  |  | Fisheries Queensland | 40 | 464214 |  | A | 5 | * Provide up-to-date information on the rules and regulations about fishing and marine park zoning in Queensland 20/2/2019,* Achieve better compliance through access to information 20/2/2019,* More uptake of the App by providing regulations from other marine agencies 20/2/2019,* Resolve issues with offline access to information. 20/2/2019, 20/2/2019, |  | 2018-02-01T00:00:00 | DAF
20/2/2019 | ASQ | Portfolio Activity Reporting Information System |  | Delivery |  |  |  | 2019-02-08T00:00:00 | High |  |  | Agri-Science Queensland | 10 | 492122 |  | G | 6 | Review and consolidate the variety of processes and technologies currently being used to manage the department's research, development and extension, and other projects. |  | 2015-08-13T00:00:00 | DAF
20/2/2019 | BQ | RBE (Registered Biosecurity Entity) Renewal Project |  | Delivery |  |  |  | 2019-02-08T00:00:00 | High |  |  | Biosecurity Queensland | 25 | 795175 |  | G | 7 | * Develop an efficient end-to-end registration renewal process to allow effective management of renewals 20/2/2019,* Ensure stakeholders are aware of renewal requirements and the importance of maintaining up-to-date information 20/2/2019,* Provide the ability to efficiently communicate with customers about registered biosecurity entity processes and renewals 20/2/2019,* Provide data integration between the online customer portal and the underlying technology solution 20/2/2019,* Minimise administrative overhead. |  | 2017-11-10T00:00:00 | DAF
20/2/2019 | Ag | Risk reduction for Customer Service Centre |  | Delivery |  |  |  | 2019-02-08T00:00:00 | High |  |  | Customer and Business Services | 90 | 1216487 |  | G | 8 | Implement a solution to mitigate risk of end of life for the agency's call centre logging application. |  | 2015-01-30T00:00:00 | DAF
20/2/2019 | [12 empty] | 0 | 0 |  |  | 1 |  |  |  | DSD
20/2/2019 | PSBA | Emergency Vehicle Priority (EVP) Project |  | Delivery |  |  |  | 2019-01-16T00:00:00 | High |  |  | Public Safety Business Agency | 99 | 4253094 |  | G | 1 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 20/2/2019, 20/2/2019,* Responsive vehicle movements 20/2/2019,* Improve road safety 20/2/2019,* Congestion management 20/2/2019,* Community safety |  | 2013-01-01T00:00:00 | PSBA
20/2/2019 | OSR | State Penalties Enforcement Registry (SPER) Program |  | Delivery |  |  |  | 2018-11-16T00:00:00 | High |  |  | State Penalties Enforcement Registry | 79 | 58700000 |  | A | 1 | To maintain the integrity of fines as an effective sanction. 20/2/2019,To uphold confidence in the justice system. 20/2/2019,To deliver efficient and effective debt management practices which provide value for money to the State. 20/2/2019, |  | 2014-01-01T00:00:00 | QR
20/2/2019 | RI | Financial Assurance Information Registry (FAIR) |  | Delivery |  |  |  | 2018-11-27T00:00:00 | Medium |  |  | Insurance Commission | 90 | 9630651 |  | A | 2 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. |  | 2017-05-01T00:00:00 | QR
20/2/2019 | RI | Information Security Program |  | Delivery |  |  |  | 2018-11-16T00:00:00 | Medium |  |  | Office of the Chief Information Officer | 60 | 710705 |  | G | 3 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 20/2/2019, |  | 2017-10-16T00:00:00 | QR
20/2/2019 | OSR | Office of State Revenue (OSR) Transformation Program |  | Delivery |  |  |  | 2018-11-16T00:00:00 | High |  |  | Office of State Revenue | 35 | 20468627 |  | G | 4 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 20/2/2019, 20/2/2019,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. |  | 2017-08-01T00:00:00 | QR
20/2/2019 | [12 empty] | 0 | 0 |  |  | 1 |  |  |  | DATSIP
20/2/2019 | Corporate Services Improvement Program | Integrated Records Information System (IRIS) |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | Corporate Division | 52 | 5497306 |  | A | 1 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. |  | 2015-07-01T00:00:00 | TMR
20/2/2019 | Corporate Services Improvement Program | Lotus Notes Decommissioning |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | Corporate Division | 67 | 4022549 |  | A | 2 | Deliver improved information platform functions for effective ICT Strategy Alignment |  | 2015-11-01T00:00:00 | TMR
20/2/2019 | Corporate Services Improvement Program | Office 365 |  | Initiate |  |  |  | 2018-11-30T00:00:00 | High |  |  | Corporate Division | 65 | 1473598 |  | G | 3 | Establish a TMR digital workspace by implementing an extended suite of digital tools, services and capabilities for employees to adopt and use. The program will define a digital workspace strategy and roadmap, based on workforce profiles and supporting TMR use cases. It will implement a digital toolbox centred on cloud adoption, enterprise mobility, and the new generation of personal productivity tools, such as Office365. The program, and its constituent projects, will impact all business units within TMR, touching almost all staff. The program will adopt a holistic approach, integrating and aligning people. |  | 2017-07-01T00:00:00 | TMR
20/2/2019 | Corporate Services Improvement Program | Transactional Services Improvement Program 2018/19 (TSIP) |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | Corporate Division | 10 | 161829 |  | G | 4 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. |  | 2018-07-01T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | Customer Services, Safety and Regulation Division | 90 | 1066439 |  | G | 5 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal services currently required. |  | 2016-01-01T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Vessel Traffic Services (VTS) |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | Customer Services, Safety and Regulation Division | 58 | 7333697 |  | G | 11 | To identify, procure and implement a modern, integrated Vessel Traffic Service (VTS) system that combines the latest in ship tracking and monitoring technology with shipping movement information to ensure safe and efficient ship movements and the protection of the marine environment. |  | 2014-04-14T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | eLearner Driver |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | Customer Services, Safety and Regulation Division | 98 | 4199808 |  | G | 6 | Implement an online learning and assessment program at the prelearner and/or learner stage, to enhance learning and outcomes for new drivers. |  | 2015-06-12T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System |  | Closed |  |  |  | 2018-11-30T00:00:00 | High |  |  | Customer Services, Safety and Regulation Division | 100 | 1034065 |  | G | 7 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. |  | 2016-11-01T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Customer Flow Mgmt and Reporting System |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | Customer Services, Safety and Regulation Division | 96 | 2976632 |  | G | 8 | Replacement of the existing statewide network of customer flow management and reporting systems which is currently supplied by QMatic Australia and will be unsupported in 2017. CSB currently have 43 CSCs around the state that use QMatic systems. Replacement of the existing state-wide customer flow management and reporting system which is currently supplied by QMatic Australia and will be unsupported in 2017. |  | 2015-09-01T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Smart Licence Card |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | Customer Services, Safety and Regulation Division | 85 | 1642632 |  | G | 9 | The project is responsible for managing business analysis and requirements specification activities, developing relevant procurement documentation, overseeing the identification and selection of a suitably qualified vendor, facilitating the transfer of contract management responsibilities from Information Technology Branch to Transport Regulation Branch, and managing the complete transition to a new solution before the extended contract expiry date. The estimated cost for the project is $1.68M over three (3) financial years. |  | 2016-07-01T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Registration and Licensing Price Host Replacement (RALPH) |  | Delivery |  |  |  | 2018-11-30T00:00:00 | Medium |  |  | Customer Services, Safety and Regulation Division | 90 | 739144 |  | G | 10 | TMR's current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace the existing application with a contemporary and supportable alternative to assist the department in maintaining its timely updating of fees and charges. |  | 2016-07-01T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Facial and Signature Image Processing Project (FSIP) |  | Initiate |  |  |  | 2018-11-30T00:00:00 | High |  |  | Customer Services, Safety and Regulation Division | 50 | 1872882 |  | G | 17 | To identify procure and implement a solution for facial signature image capture facial recognition and case management. These functions are delivered through 3 separate contract extensions have been exercised. |  | 2017-07-01T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Registration and CTP Certificates Online |  | Delivery |  |  |  | 2018-11-30T00:00:00 | Medium |  |  | Customer Services, Safety and Regulation Division | 98 | 583403 |  | G | 12 | Create an online service for customers to email or print their registration certificate and CTP tax invoices, to provide customers with more convenience, and reduce reliance on paper and post. |  | 2017-05-01T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Workflow Management Pilot |  | Initiate |  |  |  | 2018-11-30T00:00:00 | Low |  |  | Customer Services, Safety and Regulation Division | 2 | 0 |  | G | 13 | Using a Pilot this initiative seeks to capitalise on the capability being provided by TMRs Genesys Platform Replacement project (completed August 2018) to investigate the implementation of an integrated workflow distribution (IWD) system. The Pilot will trial the use of the new Genesys platform with the compatible Intelligent Workflow Distribution (iWD) system. This will offer new capability to electronically distribute processing work to remote system users across the state. The Pilot will examine the existing manual processes and through testing determine how TMR can use an integrated workflow management system. |  | 2018-07-01T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Tidal Application Upgrades |  | Initiate |  |  |  | 2018-11-30T00:00:00 | Low |  |  | Customer Services, Safety and Regulation Division | 58 | 62007 |  | G | 14 | Develop tidal analysis software and systems operating on sustainable technology with full user documentation. |  | 2017-03-01T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Improved Online Authentication |  | Initiate |  |  |  | 2018-11-30T00:00:00 | Medium |  |  | Customer Services, Safety and Regulation Division | 1 | 9990 |  | G | 15 | Simplify the current authentication process by providing a gateway for customers. Customers could then proceed to business authentication or individual authentication and DVS allowing for a simpler and customer friendly way to access TMRs online services. |  | 2018-09-01T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Online Booking System |  | Initiate |  |  |  | 2018-11-30T00:00:00 | High |  |  | Customer Services, Safety and Regulation Division | 18 | 35703 |  | G | 16 | The Online Booking System works with desktops, tables and mobile phones. It allows any number of appointment types to be created and handles a wide range of times and locations. The system can integrate with payment gateways and sends tailored confirmation emails or SMS to customers. Customers can securely amend or cancel their appointments. |  | 2018-07-02T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Online Services User Experience Remediat |  | Initiate |  |  |  | 2018-11-30T00:00:00 | Low |  |  | Customer Services, Safety and Regulation Division | 6 | 13160 |  | G | 18 | Review all online services to provide a consistent and improved customer experience across TMR online services. |  | 2018-07-02T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Intelligent Access Program (South Australia) |  | Delivery |  |  |  | 2018-11-30T00:00:00 | Medium |  |  | Customer Services, Safety and Regulation Division | 98 | 0 |  | G | 19 | Integration of South Australia Data in the Transport and Main Roads Intelligent Access Program. |  | 2017-05-08T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Hazard Perception(TMR Integration) |  | Initiate |  |  |  | 2018-11-30T00:00:00 | Medium |  |  | Customer Services, Safety and Regulation Division | 5 | 55190 |  | G | 20 | Migrate TMR from the current inhouse created Hazard Perception Test (HPT) to the recognised AustRoads NHPT platform. |  | 2017-10-01T00:00:00 | TMR
20/2/2019 | Customer Service, Safety and Regulation Program | Flexible Registration Payments |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | Customer Services, Safety and Regulation Division | 47 | 663364 |  | G | 21 | Implement an ICT solution that is capable of supporting proposed changes to current registration payment terms to enable customers to pay registration fees on a monthly basis. |  | 2017-12-15T00:00:00 | TMR
20/2/2019 | Infrastructure Management and Delivery | GECO Asbestos Management Enhancements (GAME) |  | Delivery |  |  |  | 2018-11-30T00:00:00 | Low |  |  | Infrastructure Management and Delivery | 45 | 60127 |  | G | 22 | The objective of this project is to enhance the existing GECO mobile and desktop applications to provide additional capabilities to assist in effective longer-term management of asbestos for transport infrastructure assets. These capabilities will primarily allow for; Enhanced segregation and control of asbestos-related data and users 20/2/2019,Persistence of asbestos information that can be accessed and added to over time 20/2/2019,Management of attachments and documents (e.g. certificates of testing) 20/2/2019,Development of a timeline for asbestos records (i.e. record of all activities over time) 20/2/2019,Generation of printed asbestos registers for sharing information with field workers and contractors |  | 2018-06-01T00:00:00 | TMR
20/2/2019 | Infrastructure Management and Delivery | Permit for Access to Road Corridor (PARC) |  | Initiate |  |  |  | 2018-11-30T00:00:00 | Low |  |  | Infrastructure Management and Delivery | 57 | 877623 |  | G | 23 | The overall objective of the Permit for Access to Road and Corridor (PARC) project is to develop and implement a resilient system, supported by ITB, integrated with TMR back end systems, that supports the state wide needs for Queensland permit applications. 20/2/2019,Key benefits of this project include: saving of an estimated 10,000 hours per annum in operation costs, improved customer service, improved network visibility, state-wide consistency of the processes involved, improved productivity to the transport network, robust reporting analytics capability and the ability to track permit status. 20/2/2019, 20/2/2019, |  | 2017-05-03T00:00:00 | TMR
20/2/2019 | Passenger Transport Technology Program | Single Integrated Network Project (SNIP) |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | TransLink Division | 55 | 1139570 |  | G | 24 | Enable implementation of performance based contracts for SEQ buses 20/2/2019,Have a system in place that is consistent and integrated across service providers and TransLink 20/2/2019,Reduce or remove inefficiencies and data inaccuracies that occur in the current processes 20/2/2019,Improve transparency of SEQ bus service providers activities and performance 20/2/2019,Improved customer experience through more accurate and reliable SEQ bus service information 20/2/2019,To improve customer experience through more accurate and reliable service information. 20/2/2019,Contributor for achieving Government objectives. |  | 2017-02-23T00:00:00 | TMR
20/2/2019 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms |  | Delivery |  |  |  | 2018-11-30T00:00:00 | High |  |  | TransLink Division | 70 | 5624289 |  | A | 25 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. |  | 2016-04-01T00:00:00 | TMR
20/2/2019 | CS | Asset Assessment System |  | Delivery |  |  |  | 2019-01-10T00:00:00 | Medium |  |  | Corporate Services | 82 | 1890702 |  | G | 1 | To improve the reliability and integrity of asset information, the ability to report on asset information by applying best practice asset management principles. |  | 2014-02-27T00:00:00 | DET
20/2/2019 | CS | Automated Website Provisioning Tool |  | Closed |  |  |  | 2019-01-10T00:00:00 | Medium |  |  | Corporate Services | 100 | 1240212 |  | G | 2 | To reduce the cost and time required to create new school and corporate websites by developing a tool that provisions new websites from a suite of reusable website templates. |  | 2017-04-03T00:00:00 | DET
20/2/2019 | CS | Copper Disconnection Management |  | Delivery |  |  |  | 2019-01-10T00:00:00 | Low |  |  | Corporate Services | 25 | 1438334 |  | G | 3 | The project will migrate all copper based services mandated for disconnection to an appropriate replacement technology within the required timeframes specified by nbntm and Telstra ensuring services are not incorrectly disconnected. |  | 2017-07-03T00:00:00 | DET
20/2/2019 | PPP | Customer Complaints Management System |  | Delivery |  |  |  | 2019-01-10T00:00:00 | Medium |  |  | Policy, Performance and Planning | 98 | 1546818 |  | G | 4 | Improve the management and reporting of customer complaints. |  | 2017-09-11T00:00:00 | DET
20/2/2019 | CS | Finance Infrastructure and Managed Services Renewal Project |  | Delivery |  |  |  | 2019-01-10T00:00:00 | High |  |  | Corporate Services | 100 | 583771 |  | G | 5 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DoE FBS SAP future state landscape for the next five years. |  | 2017-01-16T00:00:00 | DET
20/2/2019 | ODG | Legal Case Management System |  | Closed |  |  |  | 2019-01-10T00:00:00 | Low |  |  | Office of the Director-General | 91 | 877369 |  | G | 6 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. |  | 2015-12-10T00:00:00 | DET
20/2/2019 | State Schools | NAPLAN Online Program |  | Delivery |  |  |  | 2019-01-10T00:00:00 | Critical |  |  | State Schools | 55 | 13107424 |  | G | 7 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. |  | 2015-08-03T00:00:00 | DET
20/2/2019 | ECCE | National Quality Standard Assessment and Rating Data Tool |  | Delivery |  |  |  | 2019-01-10T00:00:00 | High |  |  | Early Childhood and Community Engagement | 45 | 403140 |  | G | 8 | To improve the security and functionality of the tool used for the assessment and quality improvement of early childhood education and care centres. |  | 2018-02-22T00:00:00 | DET
20/2/2019 | PPP | Online Collection and Survey Solution |  | Delivery |  |  |  | 2019-01-10T00:00:00 | High |  |  | Policy, Performance and Planning | 100 | 1418095 |  | G | 9 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution. |  | 2016-03-01T00:00:00 | DET
20/2/2019 | PPP | School Online Reporting Dashboard |  | Delivery |  |  |  | 2019-01-10T00:00:00 | Low |  |  | Policy, Performance and Planning | 19 | 859683 |  | G | 10 | Improved data interaction capabilities for stakeholders accessing school data profiles. Improved efficiency in production and distribution of information contained in school data profiles. |  | 2017-10-02T00:00:00 | DET
20/2/2019 | SS | Pre-Departure Orientation Information Mobile Application |  | Delivery |  |  |  | 2019-01-10T00:00:00 | Medium |  |  | State Schools | 56 | 211784 |  | G | 11 | Improved service offerings and improved user experience in provision of information to support international students. |  | 2016-02-11T00:00:00 | DET
20/2/2019 | PPP | Redevelopment of the Policy and Procedure Register |  | Delivery |  |  |  | 2019-01-10T00:00:00 | Medium |  |  | Policy, Performance and Planning | 79 | 1266012 |  | A | 12 | The project will deliver a contemporary online repository of departmental policies and procedures for access by staff, students and the general public. The objectives of the project are to deliver a consistent user experience for customers, regardless of who they are, where they work, and what they may be looking for; a single point of truth, providing access to departmental policies and procedures; and platform to publish policy and procedures once, with multiple links to additional information where appropriate; and authoritative content that meets quality standards for publication, enabling staff and stakeholders to make good decisions. |  | 2016-10-13T00:00:00 | DET
20/2/2019 | CS | SABA Platform Upgrade |  | Delivery |  |  |  | 2019-01-10T00:00:00 | Medium |  |  | Corporate Services | 89 | 2138215 |  | G | 13 | The objective of the project is to replace the existing system, currently hosted on obsolete technology, which is at end-of-service-life. In its current state, the system represents a significant business risk, due to the likelihood of increased system failures, further leading to ongoing business outages and increased maintenance and support costs. |  | 2017-08-01T00:00:00 | DET
20/2/2019 | SS | Trial of Platform for Virtual Academies |  | Closed |  |  |  | 2019-01-10T00:00:00 | High |  |  | State Schools | 100 | 176114 |  | G | 14 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage; safe and secure like-minded student virtual communities; and strategic partnerships with university, industry and business. 20/2/2019, 20/2/2019, |  | 2016-06-21T00:00:00 | DET
20/2/2019 | CS | Wireless Upgrade Project |  | Delivery |  |  |  | 2019-01-10T00:00:00 | High |  |  | Corporate Services | 95 | 36719790 |  | G | 15 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. |  | 2014-09-01T00:00:00 | DET
20/2/2019 | OIR | Investigations Management System |  | Delivery |  |  |  | 2019-01-11T00:00:00 | Critical |  |  | Office of Industrial Relations | 38 | 0 |  | A | 16 | This project will deliver a case management solution for the OIR Investigations unit. |  | 2017-01-07T00:00:00 | DET
20/2/2019 | [20 empty] | INVERSTMENT INFO
20/2/2019 | FCO | Integrated Customer and Revenue Management (ICRM) |  | Delivery |  |  |  | 2019-02-08T00:00:00 | High |  |  | Finance and Corporate Operations | 15 | 6097755 |  | G | 1 | Improvements to the way the agency handles revenue collection: 20/2/2019, 20/2/2019,* selection of a modern, enterprise-class, integrated customer and revenue management solution 20/2/2019,* implementation and deployment of the solution to replace the use of the current at-risk receipting systems. |  | 2017-01-01T00:00:00 | DNRM
20/2/2019 | NR | Land Condition Assessment Tool |  | Paused |  |  |  | 2019-02-08T00:00:00 | Medium |  |  | Natural Resources | 70 | 161671 |  | A | 2 | Implement a solution for government, industry and other stakeholders to objectively and consistently assess land conditions, including development of a pictogram-based mobile web application and a data collection tool. |  | 2017-01-12T00:00:00 | DNRM
20/2/2019 | RSH | Coal Workers eHealth Records Project |  | Delivery |  |  |  | 2019-02-08T00:00:00 | High |  |  | Resources Safety and Health | 5 | 1437663 |  | A | 3 | Improvement in data management and surveillance for coal mine worker health assessments: 20/2/2019, 20/2/2019,* new customer digital interface 20/2/2019,* improved health assessment outcomes through improved access to longitudinal health records 20/2/2019,* enabled industry-wide health surveillance through electronic storage and access to health records 20/2/2019,* improved data management using appropriate health management systems and alignment with health record management requirements. |  | 2017-03-23T00:00:00 | DNRM
20/2/2019 | SIMTARS | Mines Gas Monitoring Solution Replacement (Phase 1) |  | Delivery |  |  |  | 2019-02-08T00:00:00 | High |  |  | Safety In Mines Testing and Research Station | 85 | 968197 |  | G | 4 | The development and delivery of a (replacement) modern and robust Safegas solution: 20/2/2019, 20/2/2019,* risk reduction increasing capability to manage the volume of queries, transactions and data 20/2/2019,* decrease database corruption related to incidents. |  | 2017-01-25T00:00:00 | DNRM
20/2/2019 | [12 empty] | 0 | 0 |  |  | 1 |  |  |  | DPC
20/2/2019 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
20/2/2019 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 20/2/2019,* Move operational accountability and responsibility for print and imaging devices to the service provider 20/2/2019,* Reduce print and imaging costs 20/2/2019,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
20/2/2019 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
20/2/2019 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
20/2/2019 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 20/2/2019, 20/2/2019,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
20/2/2019 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
20/2/2019 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 20/2/2019, 20/2/2019,* reduce operating costs 20/2/2019,* increase capacity 20/2/2019,* improve customer experience 20/2/2019,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
20/2/2019 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
20/2/2019 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 20/2/2019, 20/2/2019, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
20/2/2019 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 20/2/2019, 20/2/2019,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
20/2/2019 | [12 empty] | 0 | 0 |  |  | 1 |  |  |  | DTESB
20/2/2019 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 20/2/2019, 20/2/2019,November 2017 - Actual cost to date corrected due to input error. 20/2/2019, 20/2/2019,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 20/2/2019, | 2017-12-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 57 | 733941 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
20/2/2019 | QPWS | Augmented Ranger Mobile Application |  | Delivery |  |  |  | 2019-02-08T00:00:00 | Low |  |  | Queensland Parks and Wildlife Service | 75 | 198060 |  | G | 1 | Develop a mobile, optimised solution that uses Augmented Reality to: 20/2/2019, 20/2/2019,* enrich visitors' on-park engagement, experiences and understanding of cultural, historical and ecological points of interests specific to the location 20/2/2019,* provide opportunities for ranger-visitor communications 20/2/2019,* aid collection of real-time visitor data. |  | 2018-02-01T00:00:00 | EHP
20/2/2019 | ESR | Connect Workflow Remediation |  | Delivery |  |  |  | 2019-02-08T00:00:00 | Medium |  |  | Environmental Services and Regulation | 20 | 50382 |  | G | 2 | Undertake system enhancements, improvements to workflow and implementation of prioritised support backlog as identified by the Connect Taskforce Report. |  | 2018-10-24T00:00:00 | EHP
20/2/2019 | QPWS | Integrated Permitting System Project |  | Initiate |  |  |  | 2019-02-08T00:00:00 | High |  |  | Queensland Parks and Wildlife Service | 15 | 0 |  | G | 3 | Leverage and implement a solution to manage the lifecycle of permit and agreement applications from lodgement, assessment and approval through to completion, return of operations, and reporting for compliance monitoring. |  | 2017-07-03T00:00:00 | EHP
20/2/2019 | ESR | User Experience Improvement and Rebranding |  | Delivery |  |  |  | 2019-02-08T00:00:00 | Medium |  |  | Environmental Services and Regulation | 5 | 69924 |  | G | 4 | Improve usability of the Connect system through redesign of the user interface and delivery via an enterprise platform. |  | 2018-10-30T00:00:00 | EHP
20/2/2019 | CSS | Wildlife Platform |  | Delivery |  |  |  | 2019-02-08T00:00:00 | Medium |  |  | Conservation and Sustainability Services | 20 | 89832 |  | G | 5 | Implement a platform that will increase the quality and availability of information related to wildlife sightings, in particular crocodiles. This will allow transparency and support for the public to better manage their own safety, whilst providing a central analytics and reporting resource to improve strategic analysis, planning and management. |  | 2018-07-31T00:00:00 | EHP
20/2/2019 | CSS | Native Animal Licensing Framework System |  | Paused |  |  |  | 2019-02-08T00:00:00 | Low |  |  | Conservation and Sustainability Services | 17 | 20000 |  | G | 6 | An enterprise solution is required for the management of Native Animal Licencing. This solution will: 20/2/2019, 20/2/2019,* streamline the issuing and management of wildlife licences 20/2/2019,* enable licence holders to digitally share information about their animals 20/2/2019,* improve data availability 20/2/2019,* enable proactive administrative support 20/2/2019,* facilitate compliance and enforcement practices. |  | 2018-10-05T00:00:00 | EHP
20/2/2019 | EPP | Queensland Waste Disposal Levy System |  | Delivery |  |  |  | 2019-02-08T00:00:00 | Critical |  |  | Environmental Policy and Planning | 70 | 777070 |  | G | 7 | Implement a solution to meet new legislative arrangements for a waste disposal levy, to effectively and efficiently enable: 20/2/2019, 20/2/2019,* site operators to accurately record data 20/2/2019,* reconciliation of waste data and levy liabilities 20/2/2019,* timely access to, and interrogation of, large datasets. |  | 2018-07-10T00:00:00 | EHP
20/2/2019 | QPWS | Nature Refuges Business System Replacement |  | Delivery |  |  |  | 2019-02-08T00:00:00 | Low |  |  | Queensland Parks and Wildlife Service | 0 | 0 |  | G | 8 | A data management system to replace the Nature Refuge Business Centre System improving administration, tracking and reporting on information relating to the prospective, declared and active nature refuges. |  | 2018-10-09T00:00:00 | EHP
20/2/2019 | [12 empty] | 0 | 0 |  |  | 1 |  |  |  | DILGP
23/1/2018 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Initiate | G | 2018-12-31T00:00:00 | August 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 5600000 | G | eHealth Queensland | 7 | 279747 | G | G | 1 | Queensland Health is driving a huge eHealth Strategy to keep pace with the increasing demand for digital health services, to shift towards a customer-centric health system, and to enable cutting edge health service delivery. 23/1/2018,Central to the eHealth strategy is addressing issues related to ageing systems, in particular addressing the risk to health service delivery, and removing barriers to contemporary practice. 23/1/2018,Currently, eHealth Queensland is hosting a number of mission critical applications on the ageing application server platform. While this platform has provided a robust and highly available environment, it is now seven years old with increased risks to reliability and serviceability, has limited options for expansion, and is unable to provide the agile foundation required for advancing the eHealth Strategy. As such, it is an appropriate time to investigate replacement of the platform. 23/1/2018,This project aims to establish a robust, highly available and secure contemporary platform that has the 23/1/2018,93Scale Out 23/1/2018,94 capability to support the agile eHealth Strategy. | 5600000 | 2017-07-03T00:00:00 | DH
23/1/2018 | HSQ | AUSLAB Re-hosting project | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | November: Project reported for the first time. | 2017-12-06T00:00:00 | High | 2800000 | G | Health Support Queensland | 11 | 185153 | G | G | 2 | Delivery of a replacement hardware and visualisation solution for the AUSLAB and AUSCARE systems that will achieve improved resiliency of the architecture, updated operating system and inclusion of virtualisation. AUSLAB and AUSCARE are critical to support laboratories and patient clinical care. | 1691324 | 2017-08-28T00:00:00 | DH
23/1/2018 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2016-08-01T00:00:00 | Delivery | G | 2018-07-30T00:00:00 | July 2017: The planned end date has been brought forward, from 31/12/2018 to 30/07/2018. This is due to a revised delivery schedule. | 2017-12-12T00:00:00 | High | 1858668 | G | Metro North | 35 | 777625 | G | G | 3 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 23/1/2018, 23/1/2018,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Women 23/1/2018,92s Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 23/1/2018, 23/1/2018,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 1858668 | 2015-06-01T00:00:00 | DH
23/1/2018 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 | August 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 11180394 | G | eHealth Queensland | 9 | 184272 | G | G | 4 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 23/1/2018,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work. 23/1/2018,a0 Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 11180394 | 2017-07-03T00:00:00 | DH
23/1/2018 | CHOPD | BreastScreen Queensland Online Bookings | 2016-01-01T00:00:00 | Closed | G | 2017-09-30T00:00:00 | November 2017: This project is now complete. Online portal now available for women (eligible for a BreastScreening) to book their BreastScreen appointments through the internet. Electronic GP letters was implemented on 4 September 2017. 23/1/2018, 23/1/2018,August 2017: The planned end date for this initiative is 30/09/2017, which was current as at August. An updated status will be provided in the next reporting update. 23/1/2018, 23/1/2018,May 2017: Online Portal now available for women (eligible for a Breast Screening) to book their Breast Screen appointments through the Internet. Electronic GP Letters is progressing well and is on track to go live early September. | 2017-11-30T00:00:00 | High | 3103657 | G | Chief Health Officer and Prevention | 100 | 3890921 | G | G | 5 | ?The BreastScreen Online Booking Project incorporates the following: 23/1/2018,Phase 1 - The Online Portal which is 90% of the Online Bookings Project went live on 5 December 2016. 23/1/2018,a0 The Online Portal enables women to register, book and reschedule their BreastScreen appointment, manage their contact details and view their BSQ notifications including invitations, reminders and results. 23/1/2018,Phase 2 - Incorporates the facility for GP's to receive patient results and reminders electronically. This initiative is scheduled to 'go live' on the 4th September 2017. | 4000000 | 2014-10-13T00:00:00 | DH
23/1/2018 | MNHHS | Business Intelligence - Enterprise Data Warehouse | 2018-06-29T00:00:00 | Delivery | G | 2018-06-28T00:00:00 | June 2017: Project reported for first time. | 2017-12-12T00:00:00 | High | 2114991 | G | Metro North | 72 | 1269385 | G | G | 6 | This project will introduce Business Intelligence and Data Warehousing capabilities at MNHHS. The project will deliver BI & DW technical skills, system infrastructure, data automation tools, a pilot dataset, data governance processes and quality control framework at MNHHS. Metro North Finance and MNIT are jointly managing the project. | 2114991 | 2016-11-01T00:00:00 | DH
23/1/2018 | MNHHS | Central Patient Monitoring Equipment Replacement | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | July 2017: Project reported for first time. | 2017-12-12T00:00:00 | High | 1236416 | G | Metro North | 39 | 141071 | G | G | 7 | Metro North IT has been approached by Metro North Procurement Services (MNPS) to provide ICT advice and guidance into the Central Patient Monitoring Equipment Replacement (CPMER) Project. The Health Technology Equipment Replacement (HTER) program for central monitoring systems is providing funding in financial years 16/18 for physiological monitoring equipment requiring replacement across MNHHS hospital facilities. There is an estimated 312 pieces of equipment, primarily Physiological Monitoring devices, to be replaced under the program across MNHHS hospital facilities. MNHHS implementations are being co-ordinated by MNPS. | 1236416 | 2017-06-28T00:00:00 | DH
23/1/2018 | MNHHS | CISS (Community, Indigenous and Subacute Services) Wi-Fi | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | July 2017: Project reported for first time. | 2017-12-12T00:00:00 | High | 1280798 | G | Metro North | 22 | 725229 | G | G | 8 | The Community, Indigenous and Subacute Services (CISS) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the internal areas of the prioritised CISS sites. 23/1/2018, 23/1/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1280798 | 2017-07-28T00:00:00 | DH
23/1/2018 | EHQ | Cloud First Project | 2018-06-30T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | June 2017: This project was previously called ePulse Cloud First Project. | 2017-11-30T00:00:00 | High | 4250000 | G | eHealth Queensland | 30 | 2093301 | G | G | 9 | The Cloud First project will build internal capability and establish processes within Queensland Health to appropriately utilise cloud services on an ongoing basis. | 4107007 | 2017-01-01T00:00:00 | DH
23/1/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Clinical Notes project (release 3.0) | 2018-02-06T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | August 2017: The project has returned to a 'Green' status, with the project's revised scope, budget and schedule being approved by the project's governance committee in late August 2017. 23/1/2018, 23/1/2018,July 2017: The overall status for this project ('Red') is unchanged from June, however, it is expected that governance approval will be obtained by the next reporting period, returning this project to 'On Track'. 23/1/2018, 23/1/2018,June 2017: This initiative is reporting 'Action required' due to resourcing issues. Project team resources have been unable to be secured within the planned timeframe, delaying the implementation of the project by 4 months. The scope of the project was extended to include additional enhancements, further impacting on project resource and schedule requirements. It is anticipated that this project will return to 'On track' once formal governance approval has been obtained for the extended implementation timeframes and additional resource requirements. | 2017-11-30T00:00:00 | Medium | 1415000 | G | Clinical Excellence | 65 | 1275656 | G | G | 10 | Upgrading the CIMHA Mental Health Act module to accommodate a re-architecture of the CIMHA clinical notes module is required to deliver benefits to the clinical workforce associated with data entry efficiencies; improved data sharing across digital platforms; patient level information transfer to third parties to support service integration and data mining to support service improvement and research. | 1969365 | 2017-02-20T00:00:00 | DH
23/1/2018 | EHQ | Critical Network Hardware | 2018-02-28T00:00:00 | Delivery | G | 2018-02-28T00:00:00 | November: The project is reporting amber due to resource availability and added site deployment complexities. The project is seeking approval for additional funding, and is rebaselining the schedule. 23/1/2018, 23/1/2018,June 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 8636364 | A | eHealth Queensland | 55 | 7216622 | A | A | 11 | The objectives of the project include: 23/1/2018,a) Mitigate the Department of Health risk that core network switches at QH facilities will no longer be supported by the manufacturer from February 2018. 23/1/2018,b) Invest in the replacement of critical ICT network hardware to maintain current capability and reliability of the data network for 120+ enterprise clinical and business applications and provide the foundation for future capability in the enterprise data centres. 23/1/2018,c) Ensure hardware replacement occurs with minimal impact to business operations in Hospital and Health Services or Corporate offices. 23/1/2018,d) Update logical and physical design and architecture documentation for ease of maintenance and management. | 8001607 | 2017-03-06T00:00:00 | DH
23/1/2018 | EHQ | Digital Collaboration Platform Program | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2017-11-30T00:00:00 | High | 11000000 | G | eHealth Queensland | 25 | 6561800 | G | G | 12 | This program will deliver digital collaboration tools for any time, any where, any device including: 23/1/2018, 23/1/2018,95 Email and Archiving 23/1/2018, 23/1/2018,95 Establishment and Collaboration 23/1/2018, 23/1/2018,95 Productivity Suite Enablement | 18467291 | 2015-10-29T00:00:00 | DH
23/1/2018 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate | G | 2017-12-31T00:00:00 |  | 2017-11-30T00:00:00 | High | 1500000 | G | Queensland Ambulance Service | 40 | 489580 | G | G | 13 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 4167216 | 2015-12-01T00:00:00 | DH
23/1/2018 | QAS | e-ARF Redevelopment for iPad | 2016-12-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 |  | 2017-11-30T00:00:00 | High | 2624000 | G | Queensland Ambulance Service | 98 | 1526038 | G | G | 14 | This is an initiative to provide the electronic Ambulance Report Form (eARF) electronic patient care solution via iPads in the field. | 1910813 | 2015-09-02T00:00:00 | DH
23/1/2018 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | July 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 1283000 | G | Chief Health Officer and Prevention | 43 | 16500 | G | G | 15 | ?Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1283000 | 2017-03-01T00:00:00 | DH
23/1/2018 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery | G | 2018-11-30T00:00:00 | July 2017: Project reported for first time. | 2017-12-12T00:00:00 | High | 4827917 | G | Metro North | 30 | 1902595 | G | G | 16 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (timer) program. 23/1/2018, 23/1/2018,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 23/1/2018, 23/1/2018,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. | 4827917 | 2016-07-01T00:00:00 | DH
23/1/2018 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 | August 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 3792744 | G | eHealth Queensland | 4 | 103752 | G | G | 17 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment. 23/1/2018,a0 23/1/2018,a0The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access. 23/1/2018,a0 | 3792744 | 2017-07-05T00:00:00 | DH
23/1/2018 | QAS | Enterprise Rostering System | 2018-12-31T00:00:00 | Paused | G | 2018-12-31T00:00:00 |  | 2017-11-30T00:00:00 | High | 1000000 | G | Queensland Ambulance Service | 10 | 479876 | G | G | 18 | The initiative is to provide a centralised electronic rostering system to replace existing aging and disparate manual systems currently being utilised across the state. | 1194682 | 2016-12-01T00:00:00 | DH
23/1/2018 | MNHHS | Learning and Performance Management Project | 2017-06-30T00:00:00 | Initiate | G | 2018-11-26T00:00:00 |  | 2017-12-12T00:00:00 | High | 1178190 | G | Metro North | 20 | 820001 | G | G | 36 | Implement an integrated Learning Management and Performance Management system with the capability to deliver online learning and training content, facilitate performance development and maintain centralised records for reporting purposes. | 1178190 | 2016-07-11T00:00:00 | DH
23/1/2018 | EHQ | File Services Migration | 2017-06-30T00:00:00 | Delivery | G | 2019-06-28T00:00:00 | July 2017: The project has returned to 'On Track'. The governance committee has approved the revised project schedule and finances. The financials currently reflect the latest approved budget of the initiative. 23/1/2018, 23/1/2018,June 2017: The project was previously called File Services Migration (ePulse). 23/1/2018,The approval of the business case has been delayed. The schedule is being revised by the governance committee, with the project expecting to return to On Track in the next reporting period. | 2017-11-30T00:00:00 | High | 3400000 | G | eHealth Queensland | 19 | 2464407 | G | G | 19 | The purpose of this investment is to adopt a contemporary, simplified file management solution for Queensland Health that enables a more cohesive customer experience. | 9907925 | 2016-08-01T00:00:00 | DH
23/1/2018 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Delivery | G | 2018-12-31T00:00:00 |  | 2017-11-30T00:00:00 | High | 105000000 | G | Metro North | 47 | 37311235 | G | G | 20 | The current Queensland Health Finance, Asset and Materials Maintenance Information System (FAMMIS) system is based on a heavily customised solution which is almost 20 years old and no longer supported. 23/1/2018,The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 23/1/2018, 23/1/2018,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 23/1/2018,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 23/1/2018, 23/1/2018,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
23/1/2018 | EHQ | Follow Me Desktop - Deployment | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 | August 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 3952980 | G | eHealth Queensland | 25 | 626701 | G | G | 21 | Follow Me Desktop Deployment Project will deliver 23/1/2018,a0the Follow Me Desktop service (FMD) to HHS 23/1/2018,92 in alignment with the Infrastructure Remediation Program (IMP) and ieMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 3952980 | 2017-07-03T00:00:00 | DH
23/1/2018 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | August 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 3301500 | G | eHealth Queensland | 5 | 87257 | G | G | 22 | Project Purpose: 23/1/2018,a0To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 3301500 | 2017-07-01T00:00:00 | DH
23/1/2018 | EHQ | ICT Regional Wireless Infrastructure Initiatives | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 | September 2017: The initiatives name has been changed from Regional eHealth Initiatives. 23/1/2018, 23/1/2018,August 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 1590909 | G | eHealth Queensland | 15 | 1898240 | G | G | 23 | The Regional eHealth Project (ReHP) is a Wireless LAN and Network Infrastructure uplift project so that sites in Far North Qld are ready to rollout their new eHealth Application. | 3489114 | 2017-07-01T00:00:00 | DH
23/1/2018 | EHQ | Interoperability Project | 2016-04-29T00:00:00 | Delivery | G | 2019-09-29T00:00:00 | July 2017: Additional Investment has been secured from Government, once Governor in Council approval is received project will re-establish. 23/1/2018, 23/1/2018,June 2017: The project is planning to seek funding form CBRC in August 2017. 23/1/2018, 23/1/2018,April 2017: The project has completed a detailed implementation planning study and solutions design to inform scope and budget estimates. 23/1/2018, 23/1/2018,Additional funding for implementation of subsequent stages is still being sought. | 2017-11-30T00:00:00 | High | 23850000 | G | eHealth Queensland | 15 | 8721757 | G | G | 34 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 23/1/2018,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 23/1/2018,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 23/1/2018, | 39189509 | 2015-02-01T00:00:00 | DH
23/1/2018 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 | August 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 1120000 | G | eHealth Queensland | 10 | 116229 | G | G | 24 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. 23/1/2018,The project consists of four key initiatives: 23/1/2018,QHPKI service establishment and state-wide certificate migration for wireless devices. 23/1/2018,Establishment of a Security Information and Event Management (SIEM) solution for management and prevention of security incidents. 23/1/2018,Implementation of Intrusion Prevention System (IPS) at two locations to standardise IPS management across the state. 23/1/2018,a0 23/1/2018,State-wide migration to the enhanced proxy service. 23/1/2018,a0 | 1120000 | 2017-07-05T00:00:00 | DH
23/1/2018 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery | G | 2018-07-02T00:00:00 |  | 2017-11-30T00:00:00 | High | 3215000 | G | eHealth Queensland | 35 | 3817306 | G | G | 25 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 12318334 | 2015-06-22T00:00:00 | DH
23/1/2018 | EHQ | ieMR Program (Trances 1 and 2) | 2014-12-31T00:00:00 | Delivery | G | 2017-06-29T00:00:00 | November: The ieMR Program has revised its reporting to separate Tranches 1 and 2 from Funding Package 3 and 4. 23/1/2018, 23/1/2018,September: Enterprise Schedule Management (ESM) is the solution used in Queensland Health digital hospitals to manage patient appointments and referrals, and has successfully gone live at the Mackay Base Hospital on 25 September. ESM will be used by outpatient and perioperative administration staff for a number of surgical activities. The Program is reporting Amber due to a projected overspend. 23/1/2018, 23/1/2018,May 2017: The following sites are in scope as part of the planned expansion of the ieMR state-wide rollout: Mackay Base Hospital, Logan Hospital, Beaudesert Hospital, Lady Cilento Children's Hospital (LCCH), Queen Elizabeth II (QEII) Hospital, Redland Hospital, and Townsville Hospital. | 2017-11-30T00:00:00 | High | 0 | G | eHealth Queensland | 99 | 0 | G | G | 26 | The integrated electronic Medical Record (ieMR) system changes the way clinicians access patient information, replacing the paper based system with a secure electronic record. The ieMR solution is focused on improving patient safety and quality of care by providing the right information, at the right place, at the right time. Paper medical records will be progressively transitioned to an electronic format. 23/1/2018,The implementation of the ieMR solution will be delivered by site teams at each of the hospitals in scope. The ieMR solution is being rolled out in a phased approach in consultation with sites to ensure effective implementation. 23/1/2018, 23/1/2018,Please note that financial information is Commercial in Confidence | 0 | 2009-10-01T00:00:00 | DH
23/1/2018 | EHQ | ieMR Program (Funding Package 3 and 4) | 2019-04-30T00:00:00 | Delivery | G | 2019-04-30T00:00:00 | November: Project reported for the first time. 23/1/2018,The ieMR Program has revised its reporting to separate Tranches 1 and 2 from Funding Package 3 and 4. | 2017-11-30T00:00:00 | High | 0 | G | eHealth Queensland | 7 | 0 | G | G | 27 | ieMR will enable improved patient care through the development of a state-wide, authoritative single source of the patient records. 23/1/2018, 23/1/2018,The ieMR will provide clinicians with the ability to: 23/1/2018,* access data that is integrated, accurate and clinically relevant 23/1/2018,* support decision making and better use of information 23/1/2018,* optimise management of patients, resources and provision of services 23/1/2018,* support interaction across a network of providers by making it easier to find providers, transfer information and collaborate with multidisciplinary providers. 23/1/2018,The Program scope (all tranches) is to roll out the ieMR system to 24 hospitals across Queensland. 23/1/2018, 23/1/2018,Please note that financial information for ieMR is Commercial in Confidence | 0 | 2016-11-17T00:00:00 | DH
23/1/2018 | EHQ | Infrastructure Capacity FY 17-18 | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | August 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 1000000 | G | eHealth Queensland | 20 | 43574 | G | G | 28 | Project Purpose: 23/1/2018,a0 23/1/2018,The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified 23/1/2018,91organic growth 23/1/2018,92 requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. 23/1/2018,Each year the project will maintain a list of devices that are reaching capacity thresholds within the current financial year in the Prioritised Operations List. Prioritisation of the list will be based on the risk impact assessment for each in-scope asset to establish a most-to-least-critical replacement/upgrade ranking. The project will, based on prioritisation, implement/facilitate as many upgrades as the approved budget allows. | 2000000 | 2017-07-01T00:00:00 | DH
23/1/2018 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Initiate | G | 2020-10-30T00:00:00 |  | 2017-11-30T00:00:00 | High | 0 | G | Health Support Queensland | 52 | 0 | G | G | 35 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 23/1/2018,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. 23/1/2018, 23/1/2018,Please note that financial information is Commercial in Confidence | 0 | 2015-08-28T00:00:00 | DH
23/1/2018 | EHQ | Infrastructure Maintenance Program | 2022-06-30T00:00:00 | Initiate | G | 2022-06-30T00:00:00 | August 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 1161415 | G | eHealth Queensland | 1 | 205099 | G | G | 29 | The Infrastructure Maintenance Program (IMP) 23/1/2018,a0will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 23/1/2018,The scope includes: 23/1/2018,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 23/1/2018,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and 23/1/2018,a0 23/1/2018,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1161414 | 2017-07-03T00:00:00 | DH
23/1/2018 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery | G | 2022-06-30T00:00:00 | July 2017: Project reported for first time. Financials currently reflect the financial year 2017-18 only. | 2017-11-30T00:00:00 | Medium | 14673739 | G | Clinical Excellence | 8 | 894403 | G | G | 30 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 23/1/2018,The ongoing program of work aims to continue and build upon existing functionality by: 23/1/2018, 23/1/2018,95 Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 23/1/2018, 23/1/2018,95 Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 23/1/2018, 23/1/2018,95 Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 23/1/2018, 23/1/2018,95 Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 23/1/2018, 23/1/2018,95 Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
23/1/2018 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate | G | 2022-12-21T00:00:00 | June 2017: Project reported for first time. | 2017-11-30T00:00:00 | Medium | 6300000 | G | Queensland Ambulance Service | 16 | 373892 | G | G | 31 | Phased delivery of a system supporting QAS business intelligence. | 6300000 | 2017-01-03T00:00:00 | DH
23/1/2018 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | June 2017: Funding approval has been granted for this initiative in June 2017. 23/1/2018, 23/1/2018,May 2017: This project is within the project start-up phase. No funds have been expended to date on project delivery activities. Approval for funding has been granted in June, with the project planning to formally commence within the next reporting period. | 2017-12-01T00:00:00 | High | 33827000 | G | Clinical Excellence | 11 | 7625000 | G | G | 32 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 33827000 | 2017-03-01T00:00:00 | DH
23/1/2018 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 1 | 2016-11-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | November 2017: In October 2017 the project's governance board extended the end of Stage 1 by two months to April 2018, in order to define and complete additional scope. It is anticipated that this project will return to On Track in the following reporting month. 23/1/2018, 23/1/2018, | 2017-11-30T00:00:00 | High | 8200000 | A | Health Support Queensland | 65 | 18192695 | G | A | 33 | The IWFM project involves: 23/1/2018,- configuring additional functionality (currently available and licensed, but unutilised) within the existing Rostering and Payroll business solutions 23/1/2018,- partnering with HHSs to develop refined business models and business processes to support the roster-to-pay process 23/1/2018,- undertaking extensive training and change management to support the adoption and effective usage of new functionality and processes | 25060122 | 2016-02-17T00:00:00 | DH
23/1/2018 | GCHHS | Medical Imaging Informatics Solution (MIIS) Risk Mitigation | 2018-12-31T00:00:00 | Delivery | G | 2018-12-31T00:00:00 | September 2017: Project reported for the first time. | 2017-12-05T00:00:00 | High | 5000000 | G | Gold Coast | 18 | 416511 | G | G | 37 | The Medical Imaging Informatics Solution (MIIS) Risk Mitigation project has identified an Imaging solution which will address the risks and opportunities described in the Case for Change including the mitigation of patient safety risks, increased efficiency and productivity, improvi.ng medical imaging billing revenue collection and cash flow. The solution has user endorsement from radiologists and clinicians and will be specifically configured to meet GCHHS 23/1/2018,92s needs. | 5000000 | 2017-04-03T00:00:00 | DH
23/1/2018 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery | G | 2018-11-30T00:00:00 |  | 2017-12-12T00:00:00 | High | 4030460 | G | Metro North | 35 | 1235851 | G | G | 38 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 23/1/2018, 23/1/2018,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 23/1/2018, 23/1/2018,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
23/1/2018 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery | G | 2017-12-31T00:00:00 |  | 2017-12-12T00:00:00 | High | 6299780 | G | Metro North | 75 | 5428243 | G | G | 39 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 6299780 | 2014-06-01T00:00:00 | DH
23/1/2018 | EHQ | Metro South and East Queensland ICT Infrastructure Replacement Initiative | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | September 2017: Project reported for the first time. | 2017-11-30T00:00:00 | High | 4160449 | G | eHealth Queensland | 15 | 453541 | G | G | 40 | Will replace or uplift out of date end of life ICT assets. | 4160448 | 2017-07-01T00:00:00 | DH
23/1/2018 | EHQ | Metro South East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 | September 2017: Project reported for the first time. | 2017-11-30T00:00:00 | High | 2182844 | G | eHealth Queensland | 15 | 112664 | G | G | 41 | Will replace or uplift out of date end of life ICT assets. | 2182843 | 2017-07-01T00:00:00 | DH
23/1/2018 | EHQ | Mobile Application System for Bring Your Own Device | 2018-06-30T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | July 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 1639698 | G | eHealth Queensland | 35 | 562976 | G | G | 42 | This project leverages the investment of the previous Bring-Your-Own-Device (BYOD) 23/1/2018,a0projects to extend the capability of device mobility by building the foundations of a Mobile Application Ecosystem - the processes, products and services to enable the managed development of low/no code applications by Health and Hospital Services (HHS). 23/1/2018,a0 This project will also complete the deployment of BYOD laptops and provide recommendations on how cost savings can be made by the organisation around Corporate devices and data plans. 23/1/2018,a0 | 1639698 | 2017-07-10T00:00:00 | DH
23/1/2018 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery | G | 2018-12-19T00:00:00 |  | 2017-11-30T00:00:00 | High | 14100000 | G | eHealth Queensland | 36 | 11839765 | G | G | 43 | This project will move Queensland Health to a modern end user workspace that is: current; delivering collaboration and productivity benefits; able to be accessed anywhere, anytime and on any device; reducing the reliance and expense of on premise infrastructure and support and not constraining the business from taking advantage of modern applications and services. | 27427900 | 2016-05-12T00:00:00 | DH
23/1/2018 | CHOPD | My Health for Life | 2020-04-30T00:00:00 | Delivery | G | 2020-04-30T00:00:00 | August 2017: The My health for life platform development schedule has experienced a brief delay to ensure the final product meets high program standards. This has no impact on the overall status of the project. 23/1/2018, 23/1/2018,July 2017: Prior reporting displayed the 'Planned end date' as 30/04/2020. The ICT component of this initiative will be delivered by 31 December 2017, and the project has now been updated to reflect this date. 23/1/2018, 23/1/2018,April 2017: Prior reporting displayed the Original Total Estimated Expenditure as $27M. The ICT component of this initiative is $2,000,000 and the project has now been updated to reflect this value. | 2017-11-30T00:00:00 | High | 27000000 | G | Chief Health Officer and Prevention | 97 | 1749196 | G | G | 44 | ?The My health for life (MH4L) program represents a $27.24M election commitment that will provide a state-wide health risk assessment and lifestyle modification program targeting Queenslanders at high risk of developing type 2 diabetes, cardiovascular disease, obesity and some cancers. 23/1/2018,Delivery of the program will be led by Diabetes Queensland who have been contracted through an open tender process. 23/1/2018,The MH4L ICT solution will be a key enabler within the services procured under the program including internet, social media, process support and data collection/analysis. 23/1/2018,a0 No ICT is expected to be retained after the completion of the MH4L contract. | 2000000 | 2016-05-01T00:00:00 | DH
23/1/2018 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | July 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 1500000 | G | Queensland Ambulance Service | 65 | 459845 | G | G | 45 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1744000 | 2015-10-01T00:00:00 | DH
23/1/2018 | CHOPD | Notifiable Conditions System Replacement | 2019-06-29T00:00:00 | Delivery | G | 2020-02-28T00:00:00 | August 2017: The project has resumed as at 14 August 2017 with the recruitment of key project resources. The percentage complete has been updated to reflect the latest position of the project. 23/1/2018, 23/1/2018,July 2017: Formal governance approval has been provided for this project, with the project planning to recommence in August 2017. 23/1/2018, 23/1/2018,April 2017: Project is on hold as of 31 March 2017 pending formal governance approvals. | 2017-11-30T00:00:00 | High | 12000000 | G | Chief Health Officer and Prevention | 30 | 2124481 | G | G | 46 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 23/1/2018,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
23/1/2018 | EHQ | Patient Administration System (PAS) Replacement Program | 2017-06-30T00:00:00 | Initiate | G | 2018-03-30T00:00:00 | August 2017: The planned end date for this stage of the project was 30/09/2017, which was current as at August to deliver the strategic program business case. This has since been approved in October 2017 by the appropriate governance committee to progress to next stage and to seek further investment funding from Cabinet in 2018 . An updated status will be provided in the next reporting update. 23/1/2018, 23/1/2018,April 2017: This initiative was previously called "Queensland Connected Patient Care Program". | 2017-11-30T00:00:00 | High | 3850000 | G | eHealth Queensland | 88 | 3156249 | G | G | 47 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients 23/1/2018,92 journeys, and ensure that accurate information about our patients is readily available when and where required. 23/1/2018, 23/1/2018,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 23/1/2018, 23/1/2018,95 support for patient engagement 23/1/2018, 23/1/2018,95 integrated care 23/1/2018, 23/1/2018,95 clinical research 23/1/2018, 23/1/2018,95 population health (for patients using public health services) 23/1/2018, 23/1/2018,95 performance transparency 23/1/2018, 23/1/2018,95 resource planning. | 5479865 | 2015-11-01T00:00:00 | DH
23/1/2018 | MNHHS | Picture Archiving and Communication System (PACS) | 2017-09-29T00:00:00 | Initiate | G | 2017-12-31T00:00:00 |  | 2017-12-12T00:00:00 | High | 3114694 | G | Metro North | 75 | 2379296 | G | G | 48 | Procure and implement a contemporary Picture Archiving and Communication (PACS) system and functionality that will ensure improved service delivery for the MNHHS Medical Imaging Departments (and other PACS users) through replacement of RBWH PACS ensuring that it is scalable and able to meet the ongoing needs of Metro North Hospital and Health Service. | 3656297 | 2016-07-11T00:00:00 | DH
23/1/2018 | CSD | Practice Management Enterprise Solution | 2018-10-01T00:00:00 | Initiate | G | 2018-10-01T00:00:00 | September 2017: Project reported for the first time. | 2017-11-30T00:00:00 | Medium | 1470000 | G | Corporate Services | 28 | 270000 | G | G | 49 | The main practice management software used by HHSs to conduct private practice services and billing activities is being replaced. The initiative will procure and implement "like for like" functionality enterprise solution for participating HHSs (15 in total). | 1470000 | 2017-08-01T00:00:00 | DH
23/1/2018 | EHQ | Project, Program and Portfolio Management Application | 2018-03-31T00:00:00 | Initiate | G | 2018-06-29T00:00:00 |  | 2017-11-30T00:00:00 | High | 1344177 | G | eHealth Queensland | 20 | 334260 | G | G | 50 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 23/1/2018, | 1473632 | 2017-05-02T00:00:00 | DH
23/1/2018 | SPPD | Queensland Health Integrated Data System initiation (QHIDSi) | 2017-09-30T00:00:00 | Delivery | G | 2017-09-30T00:00:00 | November 2017: The planned end date for this initiative is 30/09/2017, which was current as at August. It is anticipated this project will be reported as completed in the next reporting update. 23/1/2018, 23/1/2018,July 2017: The project has experienced delays in finalising procurement which has impacted on the schedule and will return to 'On Track' in the coming months. 23/1/2018, 23/1/2018,April 2017: This initiative was previously called "Queensland Hospital Inpatient Processing System Replacement (QHIPSr) Project" | 2017-11-30T00:00:00 | High | 1800000 | A | Strategy Policy and Planning | 88 | 775959 | A | A | 51 | This initiative will source and implement an integrated processing solution and configure it as a replacement for QHIPS which processes detailed unit record data on admitted patients from all public acute and psychiatric hospitals and licenced private hospitals and day surgery hospitals within Queensland. The technology of the current QHIPS system is at end of life and is unable to meet evolving business requirements. The project will also train existing Statistical Services Branch (SSB) staff in the use of the licensed software providing for expansion of use of the integrated processing solution as part of business-as-usual operations (e.g. to retire other end of life SSB systems). | 1800000 | 2015-09-07T00:00:00 | DH
23/1/2018 | CED | Queensland Integrated Safety Information Project (QISIP) / Risk Management | 2017-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2017-11-29T00:00:00 | Medium | 4333120 | G | Clinical Excellence | 89 | 7380041 | G | G | 52 | This initiative will source and implement an integrated processing solution and configure it as a replacement for QHIPS which processes detailed unit record data on admitted patients from all public acute and psychiatric hospitals and licensed private hospitals and day surgery hospitals within Queensland. 23/1/2018, | 16273520 | 2013-01-25T00:00:00 | DH
23/1/2018 | EHQ | Queensland State-wide ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 | September 2017: Project reported for the first time. | 2017-11-30T00:00:00 | High | 3246247 | G | eHealth Queensland | 15 | 316190 | G | G | 53 | Will replace or uplift out of date end of life ICT assets. | 3246247 | 2017-07-01T00:00:00 | DH
23/1/2018 | EHQ | Queensland State-wide ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | September 2017: Project reported for the first time. | 2017-11-30T00:00:00 | High | 3283431 | G | eHealth Queensland | 12 | 827943 | G | G | 54 | Will replace or uplift out of date end of life ICT assets. | 3282431 | 2017-07-01T00:00:00 | DH
23/1/2018 | MNHHS | Quick Flow Project | 2019-02-01T00:00:00 | Initiate | G | 2019-06-30T00:00:00 | August 2017: This project was previously called the Ambulatory Flow Management (AFM) Project. 23/1/2018, 23/1/2018,July 20t17: The percentage complete has reduced from 10% in June to 2% in July due to revised planning activities. | 2017-12-12T00:00:00 | High | 6408600 | G | Metro North | 24 | 602477 | G | G | 55 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 23/1/2018,The key objectives of the project are to: 23/1/2018, 23/1/2018,95 Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 23/1/2018, 23/1/2018,95 Improve the outpatient experience across MNHSS facilities and community services 23/1/2018, 23/1/2018,95 Improve clinic resource utilisation 23/1/2018, 23/1/2018,95 Increase the efficiency of clinical and administrative processes 23/1/2018, 23/1/2018,95 Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
23/1/2018 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Initiate | G | 2019-12-31T00:00:00 |  | 2017-12-08T00:00:00 | High | 34950000 | G | Cairns and Hinterland | 51 | 7557922 | G | G | 56 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patient 23/1/2018,92s home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
23/1/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 | September 2017: Project reported for the first time. | 2017-11-30T00:00:00 | High | 4260336 | G | eHealth Queensland | 15 | 111298 | G | G | 57 | Will replace or uplift out of date end of life ICT assets. | 4260336 | 2017-07-01T00:00:00 | DH
23/1/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery | G | 2018-06-28T00:00:00 | September 2017: Project reported for the first time. | 2017-11-30T00:00:00 | High | 2150147 | G | eHealth Queensland | 15 | 436859 | G | G | 58 | Will replace or uplift out of date end of life ICT assets. | 2150147 | 2017-07-01T00:00:00 | DH
23/1/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 | September 2017: Project reported for the first time. | 2017-11-30T00:00:00 | High | 1651750 | G | eHealth Queensland | 15 | 118878 | G | G | 59 | Will replace or uplift out of date end of life ICT assets. | 1651750 | 2017-07-01T00:00:00 | DH
23/1/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | September 2017: Project reported for the first time. | 2017-11-30T00:00:00 | High | 4245973 | G | eHealth Queensland | 40 | 395706 | G | G | 60 | Will replace or uplift out of date end of life ICT assets. | 4245973 | 2017-07-01T00:00:00 | DH
23/1/2018 | EHQ | Replacement of the ICT Service Management system | 2016-06-30T00:00:00 | Closed | G | 2017-10-31T00:00:00 | November 2017: This project is now complete. This project delivered a new cloud-based tool to improve the end-to-end management of IT support requests and incidents, in addition to providing a self-service IT support portal for Queensland Health staff across the state. 23/1/2018, 23/1/2018,August 2017: The planned end date for this initiative is 30/09/2017, which was current as at August. The system has successfully gone live at the end of September, with the project receiving governance committee approval to close at the end of October. The project is also indicating that the project will close with a 'Green' status. | 2017-11-30T00:00:00 | High | 2000000 | G | eHealth Queensland | 100 | 6904388 | G | G | 61 | This project will deliver a new cloud-based tool to improve the end-to-end management of IT support requests and incidents. The project will be delivered in two phases. The first phase has delivered a contemporary solution for IT support staff to manage requests and incidents. The second phase will deliver a new customer focused self-service portal and other system enhancements. | 7275579 | 2015-06-08T00:00:00 | DH
23/1/2018 | EHQ | Service Delivery Excellence Project (SDEP) Stage 1 | 2018-02-28T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | November: Project reported for the first time. | 2017-11-30T00:00:00 | High | 713000 | G | eHealth Queensland | 13 | 100845 | G | G | 62 | The Service Delivery Excellence Project (SDEP) aims to improve the service delivery functions of eHealth Queensland to help the organisation achieve its Customers and services Foundation and Shared Goal: 23/1/2018,Enhance value for customers by streamlining end to end services, processes and delivery models so that we can provide an exceptional customer experience. 23/1/2018,Stage 1 has the primary objective of delivering the Project Initiation Document (PID) for the Service Delivery Excellence Project (SDEP) Stage 2. | 7136880 | 2017-10-04T00:00:00 | DH
23/1/2018 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Initiate | G | 2020-09-30T00:00:00 | August 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 10500000 | G | eHealth Queensland | 7 | 314919 | G | G | 63 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 10500000 | 2017-07-03T00:00:00 | DH
23/1/2018 | MNHHS | Royal Brisbane and Womens Hospital Wi-Fi | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 | November: Project reported for the first time. | 2017-12-12T00:00:00 | High | 5000000 | G | Metro North | 2 | 17904 | G | G | 64 | The RBWH Wi-Fi Project will provide an uplift and renewal to the latest Queensland Health (QH) standard for wireless local area network (WLAN) coverage within the internal areas of prioritised RBWH buildings in order to support digital healthcare. 23/1/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for the RBWH in the near future. | 5000000 | 2017-10-22T00:00:00 | DH
23/1/2018 | EHQ | Storage Asset Replacement | 2018-06-29T00:00:00 | Delivery | G | 2018-06-28T00:00:00 | August 2017: Project reported for first time. | 2017-11-30T00:00:00 | High | 1671556 | G | eHealth Queensland | 15 | 96579 | G | G | 65 | The Storage Asset Replacement (SAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the SAR and Backup Asset Replacement (BAR) projects. 23/1/2018,The SAR project seeks to outline architecture for storage that will provide a cost effective, scalable and fit for purpose environment for the future of storage services within Queensland Health. 23/1/2018,a0 Utilising space saving technologies which will enable further cost savings and reduce the requirement for capacity expansion in the short to medium term. 23/1/2018,The existing storage arrays at Cairns, Townsville and Gold Coast are classed as urgent and unavoidable asset replacements. 23/1/2018,a0 These storage arrays are at capacity and will be at the end of extended vendor support in May 2018. | 1671555 | 2017-07-03T00:00:00 | DH
23/1/2018 | EHQ | Telehealth Asset Replacement FY 17-18 | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2017-11-30T00:00:00 | High | 1960000 | G | eHealth Queensland | 40 | 366665 | G | G | 66 | Project Purpose: 23/1/2018,a0 23/1/2018,a0 23/1/2018,Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector 23/1/2018,a0 23/1/2018,and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. 23/1/2018,The Department of Health defines Telehealth as: 23/1/2018, 23/1/2018,95Live, audio and/or video inter-active link for clinical consultations and educational purposes 23/1/2018, 23/1/2018,95Store and forward Telehealth - this model can involve digital images, video, audio and clinical data being captured ("stored") on the client computer; then at a convenient time transmitted securely ("forwarded") 23/1/2018,a0 to a clinic at another location where they are studied by relevant specialists 23/1/2018, 23/1/2018,95Teleradiology for remote reporting and clinical advice for diagnostic images 23/1/2018, 23/1/2018,95Telehealth services and equipment to monitor people 23/1/2018,92s health in their home. 23/1/2018,Benefits of Telehealth 23/1/2018, 23/1/2018,95Improve patient access to health care 23/1/2018, 23/1/2018,95Reduce travel and inconvenience for patients, families, carers and health professionals 23/1/2018, 23/1/2018,95Provide health professionals with access to peer support and education. 23/1/2018,The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. 23/1/2018,a0 23/1/2018,The priority is to replace those end-of-life assets which pose the greatest risk to effective health service delivery. 23/1/2018,Each year the project will prioritise and maintain the replacement scope in the Prioritised Operations List based on the risk impact assessment for each in-scope asset to establish a most-to-least critical replacement ranking. 23/1/2018,The project will, based on prioritisation, replace the in-scope assets as many as the approved budget allows. 23/1/2018,Approximately 75-150 systems are replaced each year including carts, wall mounted, auditorium style set ups and Retrieval Services Queensland (RSQ) systems located in emergency bays. | 1960000 | 2017-07-03T00:00:00 | DH
23/1/2018 | MNHHS | The Prince Charles Hospital (TPCH) Wi-Fi | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | July 2017: Project reported for first time. | 2017-12-12T00:00:00 | High | 1408388 | G | Metro North | 25 | 779473 | G | G | 67 | The Prince Charles Hospital (TPCH) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the hospital campus for prioritised TPCH buildings. 23/1/2018, 23/1/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1408388 | 2017-07-27T00:00:00 | DH
23/1/2018 | CS | Child and Family Services Information and Communication Technology (ICT) Program | 2015-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | Original planned expenditure represented approved budget from start date to 30 June 2016. This program is a multi year program and the revised total expenditure has been updated to include approved funding to 30 June 2018. | 2017-11-30T00:00:00 | Critical | 7645000 | G | Child Safety | 75 | 17632000 | G | G | 1 | This five year program will investigate, provide options and implement ICT solutions to enable Child Safety in addressing recommendations of the Queensland Child Protection Commission of Inquiry. This may include enhancements to current systems, consideration of new systems and enabling activities to address changes to policy, legislation and practice reforms resulting from the outcomes of the Inquiry. | 24181000 | 2013-12-16T00:00:00 | DCCSDS
23/1/2018 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | There have been delays to the project schedule from reprioritisation of resources to community recovery activities associated with Cyclone Debbie. Additionally, the vendor, SMS Management and Technology, has not delivered within the contracted timeframes and we are negotiating with the vendor to ensure completion of the solution. | 2017-11-30T00:00:00 | High | 2208000 | G | Whole of Department | 80 | 2920000 | G | G | 2 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3333000 | 2016-07-01T00:00:00 | DCCSDS
23/1/2018 | WOD | Digital Domestic and Family Violence Prevention | 2019-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | Multi year project ending June 2019. | 2017-11-30T00:00:00 | Critical | 8050000 | G | Whole of Department | 47 | 2660000 | G | G | 3 | The Digital Domestic and Family Violence Prevention Initiative is the ICT initiative to deliver the ICT components of the government response to the Bryce Report, and also progress Digital Domestic and Family Violence Prevention digital innovations. | 8050000 | 2016-07-01T00:00:00 | DCCSDS
23/1/2018 | WOD | ICT Service Transformation Program | 2016-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | Original planned expenditure represented approved budget from start date to 30 June 2016. This program is a multi year program and the revised total expenditure has been updated to include approved funding to 30 June 2018. | 2017-11-30T00:00:00 | Low | 2916000 | G | Whole of Department | 91 | 6060000 | G | G | 4 | This program includes a number of initiatives to implement service improvement opportunities and essential capital replacement activities. The program ensures that ICT systems and services are replaced in a way that supports the department's strategic direction and includes the digital vision and future ways of work roadmap. | 7555000 | 2014-12-13T00:00:00 | DCCSDS
23/1/2018 | WOD | Reporting and Business Intelligence Project | 2017-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | Original planned expenditure represented approved budget from start date to 30 June 2016. This project is a multi year project and the revised total expenditure has been updated to include approved funding to 30 June 2018 to continue reporting and business intelligence deliverables. | 2017-11-30T00:00:00 | Medium | 750000 | G | Whole of Department | 44 | 3720000 | G | G | 5 | The department has a requirement for business intelligence, data management, information presentation and multi-level reporting. | 5691000 | 2015-07-01T00:00:00 | DCCSDS
23/1/2018 | WOD | Social Investment Program | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | The original expenditure includes the approved budget to 30 June 2017 only. The planned expenditure has been revised to include the approved expenditure to 30 June 2018 to complete tranche 1 and 2 of the program. | 2017-11-30T00:00:00 | Critical | 2230000 | G | Whole of Department | 28 | 1550000 | G | G | 6 | The project will implement systems and processes that support the departments social procurement spend and support interventions that are proven to work, offer good value for money and are contributing to the broader objectives of government. | 5028000 | 2016-07-01T00:00:00 | DCCSDS
23/1/2018 | CS | Adoption Client Management System | 2016-06-30T00:00:00 | Delivery | G | 2018-01-31T00:00:00 | Planned end date to be re-forecasted to 31 January 2018 to accommodate data migration and reconciliation assurance. | 2017-11-30T00:00:00 | Low | 523000 | G | Child Safety | 96 | 1518000 | G | G | 7 | The project will implement a contemporary and more cost effective replacement for the Adoptions Case Management System (ACMS). | 1536000 | 2016-10-01T00:00:00 | DCCSDS
23/1/2018 | WOD | Complaints Management System | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2017-11-30T00:00:00 | Low | 466000 | G | Whole of Department | 42 | 164000 | G | G | 8 | The objective of the complaints management system project which was formerly incorporated into the Technology Refresh project is to develop a complaints management system which supports the future DCCSDS business structure. The new system must also meet the recommendations made by the Queensland Ombudsman in his Management of Child Safety Complaints report in which the department has agreed that a full review of data fields for the departments complaints management database is conducted and relevant categories aligned to the departments core business practices and best practice complaints handling process. | 466000 | 2017-07-01T00:00:00 | DCCSDS
23/1/2018 | CS | ICMS Replacement | 2021-06-30T00:00:00 | Initiate | G | 2021-06-30T00:00:00 | A total estimated value will be provided once the proposal has been developed further. | 2017-11-30T00:00:00 | Critical | 0 | G | Child Safety | 11 | 2643785 | G | G | 9 | The ICMS Replacement Program will replace the current child protection and youth justice service delivery system by delivering an integrated child protection and youth justice system focused on effective customer-centric service delivery across government and Non-Government Organisations. 23/1/2018,The initiative will address the significant gaps that have developed between frontline practice and the current ICMS system. The new solution will help deliver improved effectiveness for frontline staff and therefore better outcomes for clients. It will be designed with the flexibility to be adapted over time, to respond to emerging needs and future changes. | 0 | 2017-02-01T00:00:00 | DCCSDS
23/1/2018 | CS | Our Child Project | 2019-02-28T00:00:00 | Delivery | G | 2019-02-28T00:00:00 | Project has commenced initiation activities. | 2017-11-30T00:00:00 | Critical | 4900000 | G | Child Safety | 30 | 1170000 | G | G | 10 | The Our Child project will deliver a secure multi-agency information sharing platform that will enhance agencies ability to respond to instances of children missing from out-of-home care. | 4900000 | 2017-03-01T00:00:00 | DCCSDS
23/1/2018 | WOD | Destination Information | 2019-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 |  | 2017-11-30T00:00:00 | Critical | 8500000 | G | Whole of Department | 11 | 1343000 | G | G | 11 | The Destination Information initiative will deliver smarter, simpler, better information management by improving the management of electronic information and documents, enabling the ability to file, retrieve and share information, within legislative provisions, in electronic form, removing duplication and reliance on paper based information, enabling better access to relevant information to support families and vulnerable children and enabling improved external information sharing. | 8500000 | 2017-02-01T00:00:00 | DCCSDS
23/1/2018 | Cross-Gov | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery | G | 2018-09-03T00:00:00 | The program continues to meet milestones within the set timeframes. 23/1/2018,Queensland Fire and Emergency Services Human Capital Management solution is tracking to schedule and is expected to go-live with Phase 1 in December 2017. 23/1/2018,The program is currently developing detailed business cases for Queensland Ambulance Service and Queensland Corrective Services Human Capital Management solutions. The agency review process of the final drafts will roll out in October 2017. 23/1/2018,The Queensland Ambulance Service transition to the new payroll system is keeping to set timeframes and on track for delivery in Qtr 3 FY 2017. 23/1/2018,The Program timeframe will remain amber while planning and scheduling for the QFES Payroll implementation is underway. | 2017-09-30T00:00:00 | Critical | 101500000 | G | Cross-Government program led by DSITI | 48 | 49531115 | A | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 23/1/2018, 23/1/2018,* Sustainable and supported HR and Payroll service delivery 23/1/2018,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 23/1/2018,* Strategic HR capability that supports the development, performance and safety of the departments workforce 23/1/2018,* Business Intelligence capability that provides real timely, integrated HR information 23/1/2018,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 23/1/2018,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 23/1/2018,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
23/1/2018 | QPS | Online National Police Certificate Project | 2017-06-30T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | Online National Police Certificate successfully launched on the Queensland Police website on the 13th of November 2017. | 2017-12-14T00:00:00 | High | 275000 | G | Queensland Police Service | 58 | 220000 | G | G | 1 | The Online National Police Certificate Project will implement an online service for the community to apply and pay for Name Only National Police Certificates online, rather than presenting at a police station, or using the online services of an Australian Crime Intelligence Commission accredited broker. This will provide improved customer service to the community through a more efficient and reliable QPS service, with no requirement to present at a police station, as well as provide efficiency and time savings to local police stations and the Police Information Centre. | 220000 | 2017-01-01T00:00:00 | QPS
23/1/2018 | QPS | Police Integrity and Professional Standards Project | 2020-02-17T00:00:00 | Delivery | G | 2020-02-17T00:00:00 | Partial funding for the Police Integrity and Professional Standards Project has been approved and included in the 2017-18 budget. The Invitation to Offer process has commenced and negotiation is currently being conducted with vendors to finalise the price and delivery time-frames. Additional funding is currently being sought through the QPS budget process. | 2017-12-14T00:00:00 | High | 4142000 | A | Queensland Police Service | 30 | 57500 | A | A | 2 | This initiative will deliver a new integrated Police Integrity and Professional Standards IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The Police Integrity and Professional Standards system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The Police Integrity and Professional Standards Project will also complement the Complaints Reform Project established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of the Police Integrity and Professional Standards system will place the QPS in a strong readiness position to fully implement Complaints Reform Project-generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 4142000 | 2017-03-07T00:00:00 | QPS
23/1/2018 | QPS | Advanced Data Analytics Project | 2017-07-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to deliver new capability in all streams with most capability available for use as business-as-usual during the 2018 Commonwealth Games. Current focus is on expanding the capability developed by the project in 2017-18 and the development of the business case for the next phase of QPS advanced data analytics capabilities. | 2017-12-14T00:00:00 | Low | 1730000 | G | Queensland Police Service | 83 | 1950712 | G | G | 3 | Develop the QPS Advanced Data Analytics proof-of-concept. This proof-of-concept is intended to inform a larger suite of data analytics integration and intelligence over the next four years, including the development of predictive and alert models to enhance the operational response to threats, incidents and events. | 2350000 | 2017-02-19T00:00:00 | QPS
23/1/2018 | QPS | Body Worn Cameras Project | 2018-02-28T00:00:00 | Delivery | G | 2018-02-28T00:00:00 | The Program will complete the deployment of all Stage Two body worn cameras by December 2017 and will then complete transition and closure activities by 30 June 2018. A Business Case for additional funding for a Stage Three rollout in 2018-19 has been prepared for Government consideration. A successful Stage Three rollout would see body worn cameras provided to every frontline operational police officer in Queensland. | 2017-12-14T00:00:00 | Medium Low | 6030000 | G | Queensland Police Service | 80 | 5000000 | G | G | 4 | The Queensland Police Service Body Worn Camera Project is deploying 5100 body worn cameras to frontline police officers. Body worn cameras will be deployed to 168 police stations, 16 tactical crime units, 47 road policing units, and specialist units including dog squads and the Public Safety Response Team in two stages. The cameras integrate with the QPS mobility devices, allowing officers to add metadata to videos and to review videos in the field. A system for storage and allocation of digital camera data will also be implemented as well as policy related to use of the cameras. | 6830000 | 2014-08-25T00:00:00 | QPS
23/1/2018 | PSBA | Weapons Licensing Management System Stage 2a Project | 2017-05-31T00:00:00 | Closed | G | 2017-12-29T00:00:00 | Weapons Licensing 2A Benefits Enhancement Analysis Report for the proposed benefit enhancement rule changes have now been approved by the Project Board. 23/1/2018, 23/1/2018,Weapons Licensing will implement the four rule changes as part of their business as usual schedule. The remaining project budget will also be transferred to Weapons Licensing to fund the implementation of the rules. 23/1/2018, 23/1/2018,Project now moves into Close Out phase. | 2017-12-14T00:00:00 | Medium | 2500000 | G | Public Safety Business Agency | 99 | 1888776 | G | G | 5 | Improved workflow efficiencies, reduction in work queues, less resources required to process licence renewal and weapons Permit to Acquire, etc. | 2156825 | 2015-11-11T00:00:00 | QPS
23/1/2018 | QCS | Electronic Transfer of Court Results (ETCR) Phase 3 | 2017-12-01T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is on track for completion within time and quality tolerances. It has fallen under cost tolerance as project activities were delayed between April 2017 and July 2017 to allow for other priority work affecting resource assignments. Project activities have now resumed and resource assignments confirmed as the project works towards its initial release. | 2018-01-18T00:00:00 | High | 550150 | A | Corrective Services | 31 | 457173 | G | G | 1 | * The objective of the ETCR project is to improve integration between criminal justice agencies and improve staff efficiency by reducing manual data entry effort | 1144522 | 2016-12-12T00:00:00 | DJAG
23/1/2018 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-06-30T00:00:00 | Delivery | G | 2018-12-31T00:00:00 | Original planned end date was changed from 30 June 2018 to 31 Dec 2018 due to: 23/1/2018, 23/1/2018, 23/1/2018,- initial delays in securing project resources (2016-17 Christmas/New Year shutdown) 23/1/2018, 23/1/2018, 23/1/2018,- high level of project design complexity (heterogeneous environments) 23/1/2018, 23/1/2018, 23/1/2018,- conformity with appropriate probity and procurement governance. 23/1/2018, 23/1/2018, 23/1/2018,- requirement to develop a Significant Procurement Plan (SPP). 23/1/2018, 23/1/2018, 23/1/2018, 23/1/2018,The original project estimated expenditure occurs over two years to implement Core Infrastructure DR and Oracle DR. The variance of revised cost resulting in significant savings is due to implementing a more cost effective solution proposed through the Request for Quote (RFQ) process while utilising contemporary technologies. | 2018-01-18T00:00:00 | High | 7460674 | G | Corporate Services | 25 | 3086714 | G | G | 2 | * Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 5917255 | 2016-10-01T00:00:00 | DJAG
23/1/2018 | QCS | QCS GIS Project | 2017-09-29T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | Original timeframe and expenditure were updated following contract execution to reflect increased scope, to maximise available budget, and to allow adequate timeframes for integration of third party data. | 2018-01-18T00:00:00 | Medium | 925000 | G | Corrective Services | 60 | 683258 | G | G | 3 | * Procurement and implementation of a GIS that integrates data from multiple systems to improve Business Intelligence through increased analytical capability | 1020500 | 2017-01-30T00:00:00 | DJAG
23/1/2018 | Housing | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The project has this month been focussed on providing extensive support to users across the state, with a 60-day hypercare support model in place to ensure that support requests are triaged and managed quickly and effectively. The project is now focussing on planning for a second stage Tenancy release. | 2017-11-30T00:00:00 | Critical | 56286000 | A | Housing Services | 48 | 60200000 | A | G | 1 | Replace the existing ICT housing solution with an integrated ICT system. | 70675462 | 2013-07-01T00:00:00 | HPW
23/1/2018 | PWAM | iSpace External Hosting Migration Project | 2017-01-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The User Acceptance Testing (UAT) is currently underway. Some vendor system releases had to be installed and UAT was extended as a result. The project team and the vendor are now amending the implementation plan with a new Go-live target in early 2018 (pending approval). | 2017-11-30T00:00:00 | High | 735000 | A | Queensland Government Accommodation Office | 95 | 785533 | A | A | 2 | Version upgrade and migration of the hosting of Queensland Accommodation Office core system to a hosted managed service arrangement. | 1415203 | 2016-05-01T00:00:00 | HPW
23/1/2018 | QGP | Fleet Management System Replacement Project (FMSRP - QFleet) | 2019-09-30T00:00:00 | Initiate | G | 2019-09-30T00:00:00 | Project commenced. | 2017-11-30T00:00:00 | High | 13939200 | G | QFleet | 2 | 160000 | G | G | 3 | The project will deliver for the Department of Housing and Public Works, Public Safety Business Agency and Queensland Ambulance Service a fleet management solution to replace existing aging legacy systems. | 13939200 | 2017-10-19T00:00:00 | HPW
23/1/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 23/1/2018, 23/1/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 23/1/2018,October 2017 - The project is progressing as planned. 23/1/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 23/1/2018,June 2017 - Revised Schedule approved returning the project to Green. 23/1/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 23/1/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 23/1/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 23/1/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 23/1/2018,December 2016 - The project is progressing as planned. | 2017-12-21T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 23/1/2018, 23/1/2018,* register and maintain their information 23/1/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
23/1/2018 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 23/1/2018, 23/1/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 23/1/2018,August 2017 - Approved extension of timeframe. 23/1/2018,June 2017 - The project is progressing as planned. 23/1/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 23/1/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 23/1/2018,October 2016 - Progress is continuing as planned. 23/1/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 23/1/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 23/1/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-21T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 23/1/2018, 23/1/2018,* support compliance with legislation 23/1/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 23/1/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 23/1/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 23/1/2018, | 1390000 | 2012-04-01T00:00:00 | DEWS
23/1/2018 | BQ | Biosecurity Information Management System Program | 2017-05-31T00:00:00 | Delivery | G | 2018-02-28T00:00:00 | Program delivery is complete, however, the final end date has been extended by three months to allow for full transition to business as usual, project and program closure activities and final assurance reviews. 23/1/2018, 23/1/2018,November 2017 - The planned end date has been extended by one month; this remains within acceptable program tolerances. 23/1/2018,March 2017 - The program is progressing as planned in line with approved change to scope, timeframe, benefits and cost. 23/1/2018,January 2017 - A small scope increase has been proposed, currently progressing through governance processes. 23/1/2018,November 2016 - Note, a scope review is currently under way. 23/1/2018,May 2016 - Program is continuing as planned. Note a small extension to planned end date. 23/1/2018,March 2016 - A re-baseline has brought all parameters back to Green. 23/1/2018,January 2016 - Timeframe, Cost, and Quality remain Amber, pending a business case update due early April 2016. 23/1/2018,November 2015 - Program is still Amber while the Timeframe is being re-baselined. 23/1/2018,September 2015 - The Exception Report has been accepted by the Program Board. Timeframe remains Amber pending a business case update. 23/1/2018,July 2015 - Resources continue to be redirected to assist with emergency response to the Panama banana disease. An Exception Report is being developed to address this. 23/1/2018,May 2015 - As anticipated, the emergency response to the Panama Banana disease outbreak has impacted both the project cost and the Timeframe. 23/1/2018,March 2015 - There is currently an outbreak of Panama banana disease which has potential to impact the schedule of this project. 23/1/2018,January 2015 - Actions are being taken to resolve some current scheduling issues. | 2017-12-22T00:00:00 | Critical | 18080000 | G | Biosecurity Queensland | 95 | 17843000 | G | G | 1 | Deliver an integrated toolkit consisting of various information management technologies and enhanced business processes to improve the management of biosecurity risks in Biosecurity Queensland's day-to-day business operations and in emergency responses. | 19409000 | 2013-07-01T00:00:00 | DAF
23/1/2018 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery | G | 2018-03-31T00:00:00 | A variation to scope was approved, resulting in a change to the planned end date and total estimated expenditure. 23/1/2018, 23/1/2018,November 2017 - The project is continuing as planned. 23/1/2018, 23/1/2018,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2017-12-21T00:00:00 | Medium | 608146 | G | Forestry Queensland | 80 | 726225 | G | G | 2 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 23/1/2018, 23/1/2018,* the capture, management and integration of data 23/1/2018,* value-adding opportunities for business improvement 23/1/2018,management of risk associated with ongoing use and maintenance of disparate systems. | 976431 | 2016-06-15T00:00:00 | DAF
23/1/2018 | BQCC | Communication and Stakeholder Engagement Solution | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | The project was approved to moved into delivery in October 2017 and is being published for the first time. | 2017-11-30T00:00:00 | Medium | 694000 | G | Biosecurity Queensland Control Centre | 10 | 151745 | G | G | 3 | Implement a simple, easy to use system that will facilitate the collection of information associated with the National Red Imported Fire Ant Eradication Program and the National Electric Ant Eradication Program. This will include contact management, complaints management, history of interactions, event management, training management, social media interactions, marketing campaign and reporting. | 694000 | 2017-06-01T00:00:00 | DAF
23/1/2018 | ASQ | Portfolio Activity Reporting Information System | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project was approved to moved into delivery in November 2017 and is being published for the first time. | 2017-11-24T00:00:00 | High | 500000 | G | Agri-Science Queensland | 10 | 223652 | G | G | 4 | Review and consolidate the variety of processes and technologies currently being used to manage the department's research, development and extension, and other projects. | 500000 | 2015-08-13T00:00:00 | DAF
23/1/2018 | Ag | Risk reduction for Customer Service Centre | 2019-04-19T00:00:00 | Delivery | G | 2019-04-19T00:00:00 | The project was approved to moved into delivery in November 2017 and is being published for the first time. | 2017-11-30T00:00:00 | High | 1767000 | G | Agriculture | 5 | 54337 | G | G | 5 | Implement a solution to mitigate risk of end of life for the agency's call centre logging application. | 1767000 | 2015-01-30T00:00:00 | DAF
23/1/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
23/1/2018 | PSBA | Emergency Services Computer Aided Dispatch (ESCAD) Upgrade Program | 2016-09-30T00:00:00 | Delivery | G | 2018-07-03T00:00:00 | Queensland Ambulance Service (QAS) and Queensland Fire and Emergency Services (QFES) continue progressing the User Acceptance Testing (UAT) of Production environments of the upgraded ESCAD system. The Operator trainings are on schedule. The system cut over scheduled in January 2018 remains on track, subject to any latent technical issues and any unforeseen significant events. 23/1/2018,The Planned expenditure on the Whole of Government ICT Dashboard reflects the total approved budgets funded by QAS and QFES. | 2017-12-21T00:00:00 | Critical | 6774820 | G | Public Safety Business Agency | 80 | 8568914 | G | G | 1 | A program of work for Queensland Ambulance Service and Queensland Fire and Emergency Services to upgrade the Emergency Services Computer Aided Dispatch System,including infrastructure, operating system and application software. | 10289601 | 2015-01-15T00:00:00 | PSBA
23/1/2018 | PSBA | Emergency Vehicle Priority (EVP) Project | 2017-06-30T00:00:00 | Delivery | G | 2018-10-31T00:00:00 | IDSC endorsed Project extension until 31 October 2018 to undertake another procurement for full managed service. 23/1/2018,EVP rollouts progressing across Queensland, including Ipswich, Rockhampton and Gladstone and is currently due for completion February 2018. 23/1/2018,Previous approved funding transfer (0.5x AO8) also reflected in Estimates in Completion. | 2017-12-21T00:00:00 | High | 3370000 | G | Public Safety Business Agency | 78 | 3829221 | G | G | 2 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 23/1/2018, 23/1/2018,* Responsive vehicle movements 23/1/2018,* Improve road safety 23/1/2018,* Congestion management 23/1/2018,* Community safety | 3855329 | 2013-01-01T00:00:00 | PSBA
23/1/2018 | PSBA | Inter-CAD Electronic Messaging System (ICEMS) | 2017-12-01T00:00:00 | Delivery | G | 2017-12-01T00:00:00 | The ICEMS Project closed on 1 December. 23/1/2018,The project is finalising financial, lessons learned and end project reports. 23/1/2018,The estimate at completion has been re-adjusted to reflect the removal of funds that the project was to receive but are no longer required. | 2017-12-21T00:00:00 | Critical | 560000 | G | Public Safety Business Agency | 96 | 1521821 | G | G | 3 | To implement the ICEMS protocol between the Queensland Police Service (QPS), Queensland Ambulance Service (QAS) and Queensland Fire and Emergency Services (QFES) computer aided dispatch systems to enable Triple Zero data sharing between agencies. | 1545139 | 2015-10-06T00:00:00 | PSBA
23/1/2018 | PSBA | QAS Office 365 Implementation Project | 2017-06-30T00:00:00 | Closed | G | 2017-10-31T00:00:00 | The Queensland Ambulance Service Office 365 Implementation Project is responsible for migrating all Queensland Ambulance Service email mailboxes and archive mailboxes to Office 365. 23/1/2018,Project was successfully completed on 31 October 2017. 6499 mailboxes were migrated to Office 365. 23/1/2018,Project tracked to schedule and budget. | 2017-12-21T00:00:00 | Medium | 1544817 | G | Public Safety Business Agency | 100 | 1306178 | G | G | 4 | The project will deliver digital transformation for Queensland Ambulance Service (QAS) through the implementation of the Office 365 suite of products to augment the below enhancements to their current business processes. 23/1/2018, 23/1/2018,1. Undertaking smarter meetings; 23/1/2018,2. Facilitating better administration; 23/1/2018,3. Accessing information anywhere, any time; 23/1/2018,4. Engaging and communicating better; 23/1/2018,5. Supporting capability development; 23/1/2018,6. Facilitating business intelligence; and 23/1/2018,7. Enabling efficient workflow and approvals. | 1521228 | 2017-01-23T00:00:00 | PSBA
23/1/2018 | PSBA | QPS Office 365 Implementation Project | 2018-02-28T00:00:00 | Delivery | G | 2018-02-28T00:00:00 | QPS Office 365 Implementation Project has completed Initiation and Design. 23/1/2018,The Project has progressed to Implementation with 16,500 user mailboxes migrated (representing 85% of total migration). | 2017-12-21T00:00:00 | Critical | 2207000 | G | Public Safety Business Agency | 50 | 465762 | G | G | 5 | The objective of the Queensland Police Service (QPS) Office 365 Implementation Project is to complete the following activities prior to the FDS Commonwealth Games Change Freeze (mid Feb 2018). 23/1/2018, 23/1/2018,* Migrate email, contacts and calendars to Office 365 online services for all QPS staff 23/1/2018,* Enable anywhere, anytime, any device access to email, contacts and calendar via bring your own (BYO) phone, QPS Officers operational tablets (QLiTEs) and home use for all QPS staff | 2206999 | 2017-09-07T00:00:00 | PSBA
23/1/2018 | OSR | State Penalties Enforcement Registry (SPER) Program | 2017-12-31T00:00:00 | Delivery | A | 2018-03-30T00:00:00 | Revised and detailed delivery schedule is being finalised. The SPER Program has completed the implemention of the new governance arrangements focussing on ICT delivery and the management and control of risks, designed to safeguard the new implementation approach. | 2017-10-06T00:00:00 | High | 47200000 | G | State Penalties Enforcement Registry | 46 | 38378000 | A | A | 1 | To maintain the integrity of fines as an effective sanction. To uphold confidence in the justice system. To deliver efficient and effective debt management practices which provide value for money to the State. 23/1/2018, | 47200000 | 2014-01-01T00:00:00 | QR
23/1/2018 | OSR | Contact Centre | 2017-09-30T00:00:00 | Closed | G | 2017-10-30T00:00:00 | Contact Centre transitioned from project to operations on 30 October 2017. Project Closed. | 2018-01-12T00:00:00 | Medium | 1020000 | G | Office of State Revenue | 100 | 1099277 | G | G | 2 | The Office of State Revenue's existing contact centre solution has reached its end of life. As a result, the Office of State Revenue is implementing a new comprehensive call centre solution designed to improve productivity and the client experience across all taxes and the Queensland First Home Owners' Grant administered by the office. | 1080300 | 2017-02-27T00:00:00 | QR
23/1/2018 | OIR | Renewal and Photographic Licensing System (RAPS) Assessor Portal | 2018-07-13T00:00:00 | Delivery | G | 2018-05-10T00:00:00 | Development phase and business analysis continued to progress. Business requirements to be completed by end of October. | 2017-10-04T00:00:00 | High | 766467 | G | Office of Industrial Relations | 20 | 220999 | G | G | 3 | The RAPS Assessor Portal project commenced as an initiative to target improving services for high risk work licensing accredited assessors, registered training organisations and licensing and advisory services. Currently accredited assessors must use a combination of cumbersome paper based processes, smart forms, and an online service that is difficult to use. This project will improve and integrate the external and internal applications and reduce duplicated processes for high-risk work licensing stakeholders whilst meeting legislative requirements. One simplified online service will be delivered for assessors that will save them time and make compliance easier. | 769103 | 2016-12-14T00:00:00 | QR
23/1/2018 | RI | Financial Assurance Information Registry (FAIR) | 2018-07-01T00:00:00 | Delivery | G | 2018-07-01T00:00:00 | Functionality being developed with some functionality planned to be available for testing in early 2018. | 2018-01-12T00:00:00 | Medium | 15900000 | G | Insurance Commission | 30 | 1340000 | G | G | 4 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
23/1/2018 | RI | Information Security Program | 2019-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | Program timeframe updated to include 2018-19 FY. Program is based on three project streams (Security Policies, Security Inventory, Patch and Vulnerability Management). Program now in delivery phase. | 2018-01-12T00:00:00 | Medium | 1960000 | G | Office of the Chief Information Officer | 12 | 94662 | G | G | 5 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 23/1/2018, | 1960000 | 2017-10-16T00:00:00 | QR
23/1/2018 | OSR | Office of State Revenue (OSR) Transformation Program | 2020-06-30T00:00:00 | Delivery | G | 2020-06-30T00:00:00 | Program budget updated to include OSR contribution to program funding. Program is on track. | 2018-01-12T00:00:00 | High | 73548000 | G | Office of State Revenue | 2 | 8189323 | G | G | 6 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 23/1/2018, 23/1/2018,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 73548000 | 2017-08-01T00:00:00 | QR
23/1/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
23/1/2018 | Corporate Services Improvement Systems Board | Human Resource Management Improvement | 2016-06-30T00:00:00 | Closed | G | 2017-09-15T00:00:00 | The Human Resource Management Improvement project closure report was approved by the Project Board in September 2017. This project will no longer report on the ICT Dashboard. | 2017-10-31T00:00:00 | High | 2500000 | G | Information Technology Branch | 100 | 3732726 | G | G | 1 | To improve people management processes, provide greater workforce reporting and support better workforce decisions by implementing a range of system improvements to the TMR HR data platform. | 4234000 | 2015-01-05T00:00:00 | TMR
23/1/2018 | Corporate Services Improvement Systems Board | Learnzone Improvement Project | 2017-06-30T00:00:00 | Delivery | G | 2017-09-30T00:00:00 | The LearnZone Improvement project is on track. | 2017-10-31T00:00:00 | High | 796000 | G | Transactional Services Improvement Program | 95 | 418782 | G | G | 2 | Innovate, develop and deliver an improved and centralised digital learning service and management function. 23/1/2018, 23/1/2018, | 801000 | 2016-02-01T00:00:00 | TMR
23/1/2018 | Corporate Services Improvement Systems Board | Lotus Notes Decommissioning | 2016-01-31T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project is on track. | 2017-10-31T00:00:00 | High | 8150000 | G | ERP Projects Board | 63 | 1541945 | G | G | 3 | Deliver improved information platform functions for effective ICT Strategy Alignment | 8150000 | 2015-11-01T00:00:00 | TMR
23/1/2018 | Corporate Services Improvement Systems Board | Stop Cheques - Stage 3 | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Stop Cheques Stage 3 project is on track. | 2017-10-31T00:00:00 | Medium | 200000 | G | ERP Projects Board | 20 | 101255 | G | G | 4 | Cheques are inefficient and costly to use, process and administer for both the customer and department. A range of solutions have been developed to reduce the number of cheques that the department produces or receives including refund to card at counter | 200000 | 2017-07-01T00:00:00 | TMR
23/1/2018 | Corporate Services Improvement Systems Board | Risk Management Solution | 2018-07-01T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Risk Management Solution project is on track. | 2017-10-31T00:00:00 | High | 350000 | G | Corporate Services Improvement Systems Board | 20 | 472873 | G | G | 5 | Replace the current risk management approach through the delivery of a new and contemporary enterprise Risk Management solution for TMR . | 710000 | 2017-07-02T00:00:00 | TMR
23/1/2018 | Corporate Services Improvement Systems Board | Integrated Records Information System (IRIS) | 2018-07-01T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The IRIS project is on track. | 2017-10-31T00:00:00 | High | 7967972 | G | Information Technology Branch | 25 | 1638111 | G | G | 6 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 7967972 | 2017-07-02T00:00:00 | TMR
23/1/2018 | Corporate Services Improvement Systems Board | Transactional Services Improvement Program Enhancements | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Transactional Services Improvement Program Enhancements Stage 3 is on track. | 2017-10-31T00:00:00 | Low | 200000 | G | Transactional Services Improvement Program | 20 | 103953 | G | G | 7 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolid | 200000 | 2017-07-01T00:00:00 | TMR
23/1/2018 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery | G | 2018-09-30T00:00:00 | The CDOP Online Portal project is on track. | 2017-10-31T00:00:00 | High | 1500000 | G | Customer Services, Safety and Regulation Division | 86 | 699513 | G | G | 8 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal | 1441000 | 2016-01-01T00:00:00 | TMR
23/1/2018 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The eLearner project is currently on track. | 2017-10-31T00:00:00 | High | 2500000 | G | Customer Services, Safety and Regulation Division | 94 | 3992296 | G | G | 9 | Implement an online learning and assessment program at the pre-learner and/or learner stage, to replace enhance learning outcomes. | 4176000 | 2015-06-12T00:00:00 | TMR
23/1/2018 | Customer Service, Safety and Regulation Program | Facial Recognition Replacement | 2017-03-31T00:00:00 | Delivery | G | 2017-08-31T00:00:00 | The Facial Recognition project has successfully completed its scope and a project closure report will be submitted to the Program Board for consideration in November 2017 | 2017-10-31T00:00:00 | High | 531250 | G | Customer Services, Safety and Regulation Division | 99 | 600675 | G | G | 10 | To provide Queensland integration with the National Driver Licence Facial Recognition System (NDLFRS) as part of the National Facial Recognition Matching Capability. This project will see the sharing of and upload of TMR facial image holdings to a nationa | 631250 | 2015-07-13T00:00:00 | TMR
23/1/2018 | Customer Service, Safety and Regulation Program | Hardware Security Modules (HSM) | 2016-07-29T00:00:00 | Delivery | G | 2017-08-31T00:00:00 | The HSM project has successfully completed its scope and a project closure report will be submitted to the Program Board for consideration in November 2017 | 2017-10-31T00:00:00 | High | 500000 | G | Customer Services, Safety and Regulation Division | 99 | 394206 | G | G | 11 | The Hardware Security Modules (HSMs) form part of the Queensland Driver Licence smartcard product set introduced in 2010 and generate keys for smartcard authentication and validation by TMR-authorised card readers at TMR Customer Service Centres, QGAP and | 500000 | 2015-08-01T00:00:00 | TMR
23/1/2018 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The Mobile Compliance Information System project is on track. | 2017-10-31T00:00:00 | High | 300000 | G | Customer Services, Safety and Regulation Division | 77 | 563964 | G | G | 12 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 630000 | 2016-11-01T00:00:00 | TMR
23/1/2018 | Customer Service, Safety and Regulation Program | Online Customer Experience Phase 3 | 2017-06-30T00:00:00 | Closed | G | 2017-06-30T00:00:00 | The Online Customer Experience Phase 3 project closure report was approved by the Project Board in September 2017. This project will no longer report on the ICT Dashboard. | 2017-10-31T00:00:00 | Low | 1265000 | G | Customer Services, Safety and Regulation Division | 100 | 1077498 | G | G | 13 | Within the Online Customer Experience Phase 3 Program the following initiatives will be completed: 23/1/2018, eNotices Expansion eReminder 23/1/2018, Re-architecture Authentication 23/1/2018, Disability Parking Permits 23/1/2018, OnlineWeb Chat | 1059481 | 2016-07-01T00:00:00 | TMR
23/1/2018 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery | G | 2017-12-24T00:00:00 | The Ralph Replacement project is on track. | 2017-10-31T00:00:00 | Medium | 500000 | G | Customer Services, Safety and Regulation Division | 58 | 561535 | G | G | 14 | TMR's current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace | 674000 | 2016-07-01T00:00:00 | TMR
23/1/2018 | Customer Service, Safety and Regulation Program | Voice Comms Mgt System | 2017-06-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | The Voice Comms Management System project is on track. | 2017-10-31T00:00:00 | Medium | 828000 | G | Customer Services, Safety and Regulation Division | 75 | 274738 | G | G | 15 | The Voice Comms Management project consists of two replacement of existing Voice Communication and Control Systems at Townsville and Hay Point. | 828000 | 2016-01-01T00:00:00 | TMR
23/1/2018 | Customer Service, Safety and Regulation Program | CTP Tax Invoice Online | 2017-12-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The CTP Tax Invoice Online project is on track. | 2017-10-31T00:00:00 | Medium | 300000 | G | Customer Services, Safety and Regulation Division | 10 | 49603 | G | G | 16 | The Compulsory Third Party Tax Invoice Online project will deliver a new online service which will enable Customers to self-serve and print an electronic version of the CTP Invoice, removing the need for TMR to process paper based invoices, avoiding produ | 300000 | 2017-05-01T00:00:00 | TMR
23/1/2018 | Customer Service, Safety and Regulation Program | MSQ iBase Project | 2017-06-30T00:00:00 | Delivery | G | 2017-07-28T00:00:00 | The MSQ iBase project has successfully completed its scope and a project closure report will be submitted to the Program Board for consideration in November 2017. | 2017-10-31T00:00:00 | Low | 450000 | G | Customer Services, Safety and Regulation Division | 99 | 227589 | G | G | 17 | The Maritime Safety Queensland ibase Project has commenced as the current incident register platform has been identified as requiring replacement. The future platform will work in collaboration with current field input and smart devices. | 292000 | 2017-01-01T00:00:00 | TMR
23/1/2018 | Customer Service, Safety and Regulation Program | R and L Systems Software Upgrade | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The R and L Systems Software Upgrade project is on track. | 2017-10-31T00:00:00 | Medium | 780000 | G | Customer Services, Safety and Regulation Division | 20 | 34459 | G | G | 18 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
23/1/2018 | Infrastructure Management and Delivery | Access Management System (AMS) - formerly Heavy Vehicle Permit Management System | 2015-10-31T00:00:00 | Paused | A | 2017-06-30T00:00:00 | TMR is taking steps to conclude the Access Management System project, in light of significant changes in the operating environment since it was commenced, including the way permits are issued and the role of the National Heavy Vehicle Regulator with its A | 2017-10-31T00:00:00 | High | 4281564 | A | Infrastructure Management 23/1/2018,and Delivery | 83 | 8307429 | A | A | 19 | Improve heavy vehicle and load movement safety through effective schemes, guidelines and conditions management 23/1/2018, Allow coordinated road operations such that an increase in activity will not result in economic detriment or a loss of safety and public ame | 9001258 | 2013-06-01T00:00:00 | TMR
23/1/2018 | Infrastructure Management and Delivery | Work Improvement Note (WIN) Replacement | 2016-12-19T00:00:00 | Delivery | G | 2017-10-11T00:00:00 | The WIN Replacement project project is on track. | 2017-10-31T00:00:00 | Low | 242612 | G | Infrastructure Management 23/1/2018,and Delivery | 89 | 232264 | G | G | 20 | The Work Improvement Note (WIN) System is used to capture, track, review and report on improvements, potential problems, non-conformances, corrective actions, customer feedback and complaints. The WIN System is an essential component of the overarching bu | 409763 | 2016-02-15T00:00:00 | TMR
23/1/2018 | Infrastructure Management and Delivery | 2018 Commonwealth Games Journey Planner (GJP) | 2017-10-13T00:00:00 | Delivery | G | 2018-04-27T00:00:00 | The 2018 Commonwealth GJP project is on track. | 2017-10-31T00:00:00 | High | 450000 | G | Infrastructure Management 23/1/2018,and Delivery | 65 | 477851 | G | G | 21 | A dedicated Journey Planner application supports this need by providing a single source of truth for all transport information related to the Games, and also allows for rapid changes to routes, schedules, and stops, if any are required, in order to drive | 973899 | 2016-10-16T00:00:00 | TMR
23/1/2018 | Passenger Transport Technology Program | Customer Contact Management Solution (CCMS) | 2017-06-30T00:00:00 | Delivery | G | 2017-11-10T00:00:00 | The CCMS project is on track. | 2017-10-31T00:00:00 | High | 1279000 | G | TransLink | 85 | 1406139 | G | G | 22 | To implement an industry standard, robust and extensible solution to replace the existing Commentline solution. To achieve better performance of the customer contact management functions. To provide the base platform to support the future implementation | 1279000 | 2016-04-01T00:00:00 | TMR
23/1/2018 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The STAS Auto Forms project is on track. | 2017-10-31T00:00:00 | High | 4166000 | G | TransLink | 59 | 2856066 | G | G | 23 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 5043876 | 2016-04-01T00:00:00 | TMR
23/1/2018 | Policy Planning and Investment Program | Portfolio, Program, Project and Contract Management (3PCM) - Phase 2 and 3 | 2017-03-31T00:00:00 | Delivery | A | 2017-12-22T00:00:00 | The 3PCM project is currently reporting amber for quality as there is a small number of defects from a recent data migration activity that is currently being investigated and resolved. | 2017-10-31T00:00:00 | High | 12757788 | G | Policy, Planning and Investment Division | 98 | 47629762 | G | A | 24 | Define and implement standard, consistently applied processes for planning, managing and delivering the Transport Infrastructure Portfolio across the domains of portfolio, program, project and contract management 23/1/2018, Source and implement an integrated, s | 47670648 | 2012-09-01T00:00:00 | TMR
23/1/2018 | CS | Bandwidth Upgrade Project | 2017-07-31T00:00:00 | Closed | G | 2017-08-02T00:00:00 | The project completed closure on 30 June 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | High | 5551767 | G | Corporate Services | 98 | 4575357 | G | G | 1 | To upgrade internet connectivity for Queensland State Schools, uplifting data speeds to 25kbps per student, improving access to online educational and community resources. 23/1/2018, | 4575357 | 2015-01-12T00:00:00 | DET
23/1/2018 | SS | Early Start | 2015-07-03T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Medium | 70000 | G | State Schools | 74 | 73522 | G | G | 2 | To provide schools with enhanced reporting functionality, improving their ability to analyse Prep to Year 2 student learning data. | 200992 | 2013-04-03T00:00:00 | DET
23/1/2018 | CS | eDRMS Upgrade Project | 2016-06-30T00:00:00 | Closed | G | 2017-07-04T00:00:00 | The project completed closure on 4 July 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | Critical | 2203000 | G | Corporate Services | 92 | 1734511 | G | G | 3 | To upgrade the key operational system so that it meets current and future demands and aligns with electronic information management practices. | 1680000 | 2015-01-12T00:00:00 | DET
23/1/2018 | PP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Delivery | G | 2018-02-27T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 700000 | G | Policy, Performance and Planning | 74 | 1125550 | G | G | 4 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
23/1/2018 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery | G | 2018-08-10T00:00:00 | The project is tracking to plan. The project is currently subject to procurement activities. | 2017-09-08T00:00:00 | High | 0 | G | Corporate Services | 37 | 0 | G | G | 5 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DET FBS SAP future state landscape for the next five years | 0 | 2017-01-16T00:00:00 | DET
23/1/2018 | SS | Global Learning Environment | 2018-12-30T00:00:00 | Closed | G | 2017-06-02T00:00:00 | The project completed closure on 13 July 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | Critical | 800000 | G | State Schools | 100 | 2552704 | G | G | 6 | To provide an online global learning solution which focuses on the 2018 Commonwealth Games, encouraging learning and collaboration in Queensland, nationally and internationally. | 2492000 | 2014-10-29T00:00:00 | DET
23/1/2018 | DG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery | G | 2018-01-01T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Low | 632585 | G | DG | 79 | 755722 | G | G | 7 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
23/1/2018 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery | G | 2019-12-18T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Critical | 16670000 | G | State Schools | 44 | 7426976 | G | G | 8 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 23470000 | 2015-08-03T00:00:00 | DET
23/1/2018 | PP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | The project is tracking to the revised plan. The project is currently subject to procurement activities. | 2017-09-08T00:00:00 | High | 0 | G | Policy, Performance and Planning | 54 | 0 | G | G | 9 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution | 0 | 2016-03-01T00:00:00 | DET
23/1/2018 | CS | Purchase IT Replacement Project | 2015-09-30T00:00:00 | Closed | G | 2017-09-18T00:00:00 | The project completed closure on 31 July 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | Medium | 248800 | G | Corporate Services | 99 | 905348 | G | G | 10 | To replace the existing system with a solution that meets current and future demands, provides enhanced analytics and improvements to reporting. | 1100000 | 2015-06-29T00:00:00 | DET
23/1/2018 | PP | Research Services 2.0 | 2016-09-30T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Low | 230000 | G | Policy, Performance and Planning | 85 | 404745 | G | G | 11 | To develop a solution that assists in the management of the Department of Education and Training commissioned research proposals and projects, improving resourcing and information dissemination. | 431157 | 2015-11-02T00:00:00 | DET
23/1/2018 | SS | School Budget Solution | 2017-03-31T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 2030000 | G | State Schools | 95 | 6295520 | G | G | 12 | To develop a solution that assists schools with resource management, improving their ability to support students in achieving better educational outcomes. | 6641785 | 2014-12-15T00:00:00 | DET
23/1/2018 | TS | Study Tours Support System Upgrade | 2016-06-30T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Medium | 680000 | G | Training and Skills | 96 | 772580 | G | G | 13 | To replace or upgrade the existing Study Tours system with an online solution that has enhanced functionality, improving processes, data quality and tour management. | 779894 | 2015-08-31T00:00:00 | DET
23/1/2018 | TS | Training Management System | 2016-12-31T00:00:00 | Delivery | A | 2018-04-30T00:00:00 | The project is being monitored for cost, schedule and quality. The project is currently subject to procurement activities. | 2017-09-08T00:00:00 | Critical | 0 | A | Training and Skills | 62 | 0 | A | A | 14 | To replace multiple systems with a solution that meets current and future demands, reduces costs and improves the management of vocational and educational training. | 0 | 2013-04-01T00:00:00 | DET
23/1/2018 | SS | Trial of platform for virtual academies | 2017-10-02T00:00:00 | Delivery | G | 2018-12-31T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 151641 | G | State Schools | 40 | 101875 | G | G | 15 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage; safe and secure like-minded student virtual communities; and strategic partnerships with university, industry and business. 23/1/2018, 23/1/2018, | 151641 | 2016-06-21T00:00:00 | DET
23/1/2018 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery | G | 2019-06-28T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 41000000 | G | Corporate Services | 48 | 25998875 | G | G | 16 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
23/1/2018 | [20 empty] | INVERSTMENT INFO
23/1/2018 | CSG | Coal Seam Gas Groundwater Monitoring Arrangements | 2017-12-31T00:00:00 | Paused | G | 2018-06-30T00:00:00 | A change to the planned end date has been approved; there is no impact to cost. Initiative now paused until early 2018. 23/1/2018, 23/1/2018,August 2017 - Revised total expenditure (budget) updated to include all operating costs not previously reported. 23/1/2018, 23/1/2018,June 2017 - Progress is continuing as planned. Still on schedule to complete December 2017. 23/1/2018, 23/1/2018,December 2016 - Much of the project has been completed and a significant amount of the procurement expenditure for capital equipment has occurred. 23/1/2018, 23/1/2018,October 2016 - Progress is continuing as planned. 23/1/2018, 23/1/2018,August 2016 - Cost returned to Green after a review of costs associated with activities remaining, and a correction in actual cost to date adjustment. 23/1/2018, 23/1/2018,June 2016 - Cost is Amber with a resource review under way. 23/1/2018, 23/1/2018,February 2016 - Progress is continuing as planned. | 2017-11-23T00:00:00 | High | 2380568 | G | Coal Seam Gas Compliance | 95 | 2548371 | G | G | 1 | Enhance availability of groundwater data through improvements to network monitoring of bores for clients and landholders. | 2598256 | 2014-01-13T00:00:00 | DNRM
23/1/2018 | SIMTARS | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery | G | 2017-11-10T00:00:00 | Awaiting confirmation of project closure; project is still operating within approved time-frame tolerance. 23/1/2018, 23/1/2018,November 2017 - A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 23/1/2018, 23/1/2018,October 2017 - The project is continuing as planned. 23/1/2018, 23/1/2018,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2017-12-04T00:00:00 | High | 563000 | G | SIMTARS (Safety In Mines Testing and Research Station) | 98 | 589135 | G | G | 2 | The development and delivery of a (replacement) modern and robust Safegas solution: 23/1/2018, 23/1/2018,* risk reduction increasing capability to manage the volume of queries, transactions and data 23/1/2018,* decrease database corruption related to incidents. | 619000 | 2017-01-25T00:00:00 | DNRM
23/1/2018 | SO | Mines Infrastructure Risk Mitigation Project | 2019-02-18T00:00:00 | Delivery | G | 2019-02-28T00:00:00 | The project is continuing as planned. 23/1/2018, 23/1/2018,November 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2017-12-04T00:00:00 | High | 1200000 | G | Statewide Operations | 8 | 114350 | G | G | 3 | Migrate systems to supported infrastructure and software to: 23/1/2018, 23/1/2018,* provide a stable, secure, fully supported and flexible solution 23/1/2018,* eliminate the risks to which the geoscience data assets are currently exposed. | 1200000 | 2017-08-08T00:00:00 | DNRM
23/1/2018 | GSQ | MinesOnlineMaps - Spatial Presentation Replacement | 2017-06-30T00:00:00 | Paused | G | 2018-04-30T00:00:00 | Project is paused awaiting review of a possible change in direction. Cost remains Green while investigation is undertaken to identify if deferral request was processed. | 2017-11-16T00:00:00 | Medium | 531030 | G | Geological Survey of Queensland | 60 | 98271 | G | G | 4 | Provide a web-based mapping solution for the ongoing provision of MinesOnlineMaps (MOMaps) into the future. | 531030 | 2016-08-01T00:00:00 | DNRM
23/1/2018 | LSI | Queensland Globe Improvements | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2017-12-01T00:00:00 | High | 1002450 | G | Land and Spatial Information | 25 | 277859 | G | G | 5 | Enhancements to Queensland Globe to continue to evolve and improve user satisfaction and experience, such as: 23/1/2018, 23/1/2018,* create and save user-defined topics 23/1/2018,* improve query and access 23/1/2018,* provide editable 'redlining' 23/1/2018,* improve data imports. | 1002450 | 2017-10-09T00:00:00 | DNRM
23/1/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DPC
23/1/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
23/1/2018 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 23/1/2018,* Move operational accountability and responsibility for print and imaging devices to the service provider 23/1/2018,* Reduce print and imaging costs 23/1/2018,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
23/1/2018 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
23/1/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
23/1/2018 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 23/1/2018, 23/1/2018,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
23/1/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
23/1/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 23/1/2018, 23/1/2018,* reduce operating costs 23/1/2018,* increase capacity 23/1/2018,* improve customer experience 23/1/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
23/1/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
23/1/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 23/1/2018, 23/1/2018, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
23/1/2018 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 23/1/2018, 23/1/2018,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
23/1/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
23/1/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 23/1/2018, 23/1/2018,November 2017 - Actual cost to date corrected due to input error. 23/1/2018, 23/1/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 23/1/2018, | 2017-12-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 57 | 733941 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
23/1/2018 | ESR | Environmental Management Register/Contaminated Land Register - replacement | 2017-06-30T00:00:00 | Paused | G | 2017-06-30T00:00:00 | August 2017 - The project is paused awaiting the outcome of a change request for additional scope; this will return the project to a Green state. 23/1/2018, 23/1/2018,April 2017 - A minor correction has been made to the revised total estimated expenditure to include $20,000 operating prior years. 23/1/2018, 23/1/2018,February 2017 - A change request has been approved moving the initiative cost back to Green. 23/1/2018, 23/1/2018,December 2016 - Project is continuing as planned, with a change request under way to return cost to Green. 23/1/2018, 23/1/2018,October 2016 - Project delivery activities formally commenced on 2 October 2016. 23/1/2018, 23/1/2018,August 2016 - The initiative was paused for some time but has now recommenced and moved into delivery. It is progressing as planned. | 2017-12-21T00:00:00 | High | 981680 | A | Environmental Services and Regulation | 78 | 718000 | A | A | 1 | The current system no longer supports efficient delivery of the department's responsibilities. The replacement will: 23/1/2018, 23/1/2018,* mitigate the risks associated with a system that is beyond its useful life 23/1/2018,* improve access to information by individuals, business and industry conducting searches (property lot plan) of the registers 23/1/2018,* support the creation of notices to stakeholders 23/1/2018,* reduce manual tasks through the introduction of automated workflows and customer self-serve and self-correct. 23/1/2018, | 1111680 | 2016-07-01T00:00:00 | EHP
23/1/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP
21/1/2019 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-10-31T00:00:00 | High | 5600000 |  | eHealth Queensland | 51 | 4134115 |  | G | 1 | This project aims to establish a robust, highly available and secure contemporary platform that has the capability to support the agile eHealth Strategy. | 5492863 | 2017-07-03T00:00:00 | DH
21/1/2019 | HSQ | Pathology and Forensic Laboratory System Rehosting Project | 2018-06-30T00:00:00 | Delivery |  | 2018-12-13T00:00:00 | August 2018: This project has returned to 'green'. Approval was granted in August to extend the project's schedule to December 2018. 21/1/2019, 21/1/2019,July 2018: This project is now reporting 'red' due to delays to the infrastructure component of the project. Options are being prepared to minimise the impact to the overall schedule and cost of the project, to be approved in August 2018. 21/1/2019, 21/1/2019,Reason for variance: Latest approved budget includes both operational and capital costs and delays where experienced with the provisioning of required technical infrastructure. | 2018-11-12T00:00:00 | High | 1691324 |  | Health Support Queensland | 90 | 2582135 |  | G | 2 | Delivery of a replacement hardware and visualisation solution for the AUSLAB and AUSCARE systems that will achieve improved resiliency of the architecture, updated operating system and inclusion of virtualisation. AUSLAB and AUSCARE are critical to support laboratories and patient clinical care. | 3246769 | 2017-08-28T00:00:00 | DH
21/1/2019 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2018-09-30T00:00:00 | Delivery |  | 2018-11-30T00:00:00 |  | 2018-11-12T00:00:00 | High | 3692973 |  | Metro North | 95 | 1912261 |  | G | 3 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 21/1/2019, 21/1/2019,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Women's Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 21/1/2019, 21/1/2019,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 3692973 | 2015-06-01T00:00:00 | DH
21/1/2019 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 11180394 |  | eHealth Queensland | 35 | 815399 |  | G | 4 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 21/1/2019,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work.? Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 10915391 | 2017-07-03T00:00:00 | DH
21/1/2019 | EHQ | Digital Collaboration Platform Program | 2018-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | May 2018: This project has now returned to 'green' with the project's revised schedule being approved. 21/1/2019, 21/1/2019,March 2018: Project activities have continued to be delayed, resulting in this project reporting 'Red'. A project change request has been submitted to the project's governance committee. Successful deployment was recently achieved in Townsville. 21/1/2019, 21/1/2019,January 2018: This project is experiencing delays in pre-migration activities. 21/1/2019, 21/1/2019,Reason for variance: Original budget was reflective of an original estimate based on high level planning. Detailed planning has since refined the estimated budget (including vendor licensing arrangements) which received approval for budget increase in June 2017. | 2018-10-31T00:00:00 | High | 11000000 |  | eHealth Queensland | 40 | 18853354 |  | G | 5 | This program will deliver digital collaboration tools for any time, any where, any device including: 21/1/2019,? Email and Archiving 21/1/2019,? Establishment and Collaboration 21/1/2019,? Productivity Suite Enablement | 22664506 | 2015-10-29T00:00:00 | DH
21/1/2019 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate |  | 2017-12-31T00:00:00 | June 2018: The current proposed date of completion is the 31 December 2019, which is subject to project board approval. 21/1/2019, 21/1/2019,Reason for variance: The original estimated expenditure was projected prior to the Request for Information (RFI) to the open market. Consequently, the planned expenditure was revised based on the market responses following the RFI. | 2018-11-09T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 40 | 715063 |  | G | 6 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 5697000 | 2015-12-01T00:00:00 | DH
21/1/2019 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | October 2018: The project successfully went live in late September 2018, and is currently undergoing final project closure activities. 21/1/2019, 21/1/2019,May 2018: The project has completed a solution evaluation process, with the project requiring additional schedule and financials as originally approved. The project is expecting to return to 'green' upon receiving change request approval. 21/1/2019, 21/1/2019,Reason for variance: The evaluation process further revised the original budget and implementation was delayed to facilitate extended procurement processes. | 2018-11-08T00:00:00 | High | 1166363 |  | Chief Health Officer and Prevention | 98 | 389642 |  | G | 7 | Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1384239 | 2017-07-24T00:00:00 | DH
21/1/2019 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery |  | 2019-03-01T00:00:00 | October 2018: The budget has yet to be allocated for the Financial Year 18/19. The project's governance committee is monitoring budget expenditure. 21/1/2019, 21/1/2019,September 2018: Technical issues have impacted the current implementation schedule, with the project prioritising the correction of these issues. 21/1/2019, 21/1/2019,Reason for variance: Following a change in project scope and dependent implementations, the project was slightly extended to March 2019. | 2018-11-14T00:00:00 | High | 4827917 |  | Metro North | 68 | 4571072 |  | G | 8 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (ieMR) program. 21/1/2019, 21/1/2019,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 21/1/2019, 21/1/2019,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. | 4827917 | 2016-07-01T00:00:00 | DH
21/1/2019 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | April 2018: This initiative is now 'in delivery'. | 2018-10-31T00:00:00 | High | 3792744 |  | eHealth Queensland | 30 | 887425 |  | G | 9 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment.??The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access.? | 3723476 | 2017-07-05T00:00:00 | DH
21/1/2019 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | October 2018: The project continues to work with implementation partners to finalise the schedule and cost of go-live. System integration and change management activities are continuing to be a primary focus of the project. Schedule and cost details will be updated upon approval of a change request. 21/1/2019, 21/1/2019,August 2018: The project is reporting red due to schedule delays and an anticipated funding shortfall associated with integration complexities and change management activities required. A change request is progressing to address these concerns. | 2018-11-13T00:00:00 | High | 105000000 |  | Metro North | 66 | 100020900 |  | R | 10 | The current Queensland Health Finance, Asset and Materials Maintenance Information System (FAMMIS) system is based on a heavily customised solution which is almost 20 years old and no longer supported. 21/1/2019,The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 21/1/2019, 21/1/2019,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 21/1/2019,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 21/1/2019, 21/1/2019,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
21/1/2019 | EHQ | Follow Me Desktop - Deployment | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 3952980 |  | eHealth Queensland | 71 | 2016512 |  | G | 11 | Follow Me Desktop Deployment Project will deliver: the Follow Me Desktop service (FMD) to HHS' in alignment with the Infrastructure Remediation Program (IMP) and ieMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 3621306 | 2017-07-03T00:00:00 | DH
21/1/2019 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 3301500 |  | eHealth Queensland | 41 | 1328776 |  | G | 12 | Project Purpose:?To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 2345263 | 2017-07-01T00:00:00 | DH
21/1/2019 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 1120000 |  | eHealth Queensland | 65 | 731336 |  | G | 13 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. | 1072242 | 2017-07-05T00:00:00 | DH
21/1/2019 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery |  | 2020-06-26T00:00:00 | Reason for variance: The scope and schedule for IAMP has been extended due to revised timelines to accommodate for extended development, integration, and deployment activities. | 2018-10-31T00:00:00 | High | 3215000 |  | eHealth Queensland | 40 | 6201355 |  | G | 14 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 12206443 | 2015-06-22T00:00:00 | DH
21/1/2019 | EHQ | ieMR Program (Funding Packages 3 and 4) | 2019-04-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | August 2018: The SurgiNet component of ieMR went live at The Townsville Hospital in August 2018. This builds on existing ieMR capability, providing pre and post operative documents directly into the patient chart module, to better support patient care. 21/1/2019, 21/1/2019,July 2018: The Enterprise Schedule Management (ESM) component of ieMR went live at The Townsville Hospital in July 2018. This updated patient scheduling tool will improve inpatient and outpatient scheduling processes. 21/1/2019, 21/1/2019,June 2018: The advanced version of the ieMR system has gone live at the Queen Elizabeth II (QEII) Hospital in June, which includes enhancements to the interface between ieMR and the XRay Radiology Information System. 21/1/2019, 21/1/2019,May: The advanced version of the ieMR system has gone live at the Redland Hospital. Additional clinical reporting was also enabled by ieMR in May. | 2018-10-31T00:00:00 | High | 0 |  | eHealth Queensland | 33 | 0 |  | G | 15 | ieMR will enable improved patient care through the development of a state-wide, authoritative single source of the patient records. 21/1/2019, 21/1/2019,The ieMR will provide clinicians with the ability to: 21/1/2019,* access data that is integrated, accurate and clinically relevant 21/1/2019,* support decision making and better use of information 21/1/2019,* optimise management of patients, resources and provision of services 21/1/2019,* support interaction across a network of providers by making it easier to find providers, transfer information and collaborate with multidisciplinary providers. 21/1/2019,The Program scope (all tranches) is to roll out the ieMR system to 24 hospitals across Queensland. 21/1/2019, 21/1/2019,Please note that financial information for ieMR is Commercial in Confidence | 0 | 2016-11-17T00:00:00 | DH
21/1/2019 | EHQ | Infrastructure Maintenance Program Establishment | 2018-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | March 2018: This initiative has been refocused to the establishment phase of the Infrastructure Maintenance Program, and as such the % complete and original end date have been updated to reflect this phase of the program. The latest approved end date will be updated in a following reporting month. | 2018-10-31T00:00:00 | High | 1161414 |  | eHealth Queensland | 95 | 1330542 |  | G | 16 | The Infrastructure Maintenance Program (IMP)?will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 21/1/2019,The scope includes: 21/1/2019,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 21/1/2019,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and? 21/1/2019,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1922376 | 2017-07-03T00:00:00 | DH
21/1/2019 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery |  | 2022-06-30T00:00:00 |  | 2018-11-02T00:00:00 | High | 14673739 |  | Clinical Excellence | 22 | 2596831 |  | G | 17 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 21/1/2019,The ongoing program of work aims to continue and build upon existing functionality by: 21/1/2019,? Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 21/1/2019,? Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 21/1/2019,? Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 21/1/2019,? Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 21/1/2019,? Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
21/1/2019 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate |  | 2022-12-21T00:00:00 | Reason for variance: Budget was revised following market evaluation. | 2018-11-09T00:00:00 | High | 6300000 |  | Queensland Ambulance Service | 30 | 2275278 |  | G | 18 | Phased delivery of a system supporting QAS business intelligence. | 9240000 | 2017-01-03T00:00:00 | DH
21/1/2019 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | Reason for variance: Budget has been revised as a result of reallocation of funding provided under the Specialist Outpatient Strategy to support additional statewide Smart Referrals functionality. 21/1/2019,Schedule has been impacted by only 6months yet still falls within the commitment timeframe. | 2018-11-07T00:00:00 | High | 33827000 |  | Clinical Excellence | 37 | 17931615 |  | G | 19 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 39408218 | 2017-03-01T00:00:00 | DH
21/1/2019 | EHQ | Interoperability Project | 2016-04-29T00:00:00 | Delivery |  | 2019-09-29T00:00:00 | Reason for variance: Original funding was reflective of committed funding made available to commence planning activities (including business case development) and implementation of risk mitigation activities of the existing interoperability solution, until such time (late 2017) approval for the implementation of the new solution was granted. | 2018-11-14T00:00:00 | High | 39189509 |  | eHealth Queensland | 35 | 20201276 |  | G | 20 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 21/1/2019,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 21/1/2019,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 21/1/2019, | 39189509 | 2015-02-01T00:00:00 | DH
21/1/2019 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Delivery |  | 2020-12-21T00:00:00 | Reason for variance: The latest budget was revised based on the latest governance approval. The schedule has been revised to accommodate for extended procurement timeframes and additional prototyping activities being added to the scope of the program. | 2018-11-12T00:00:00 | High | 64000000 |  | Health Support Queensland | 59 | 24872155 |  | G | 21 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 21/1/2019,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. | 63558771 | 2015-08-28T00:00:00 | DH
21/1/2019 | GCHHS | Medical Imaging Informatics Solution (MIIS) Risk Mitigation | 2018-12-31T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | October 2018: The project is continuing to report amber, with the project adjusting scope to ensure the solution aligns with the current budget. In addition, recruitment delays have impacted the project's schedule. 21/1/2019, 21/1/2019,Reason for variance: Revised project delivery costs were approved in March 2018, as part the Stage Gate 3 Business Case. 21/1/2019,Schedule was revised to align with the Digital Healthcare Program (ieMR) on the Gold Coast. | 2018-11-12T00:00:00 | High | 5000000 |  | Gold Coast | 33 | 3055548 |  | A | 22 | The Medical Imaging Informatics Solution (MIIS) Risk Mitigation project has identified an Imaging solution which will address the risks and opportunities described in the Case for Change including the mitigation of patient safety risks, increased efficiency and productivity, improvi.ng medical imaging billing revenue collection and cash flow. The solution has user endorsement from radiologists and clinicians and will be specifically configured to meet GCHHS?s needs. | 12800000 | 2017-04-03T00:00:00 | DH
21/1/2019 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Reason for variance: The end date of the project was extended to accommodate additional go-live finalisation activities. | 2018-11-12T00:00:00 | High | 4030460 |  | Metro North | 85 | 4290772 |  | G | 23 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 21/1/2019, 21/1/2019,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 21/1/2019, 21/1/2019,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
21/1/2019 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | May 2018: This project has returned to 'green', with the project's schedule and budget being monitored by the project's governance committee. 21/1/2019, 21/1/2019,April 2018: The project is continuing to report 'Red' due to continued delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. 21/1/2019, 21/1/2019,Reason for variance: The budget was extended to accommodate additional implementation scope. | 2018-11-12T00:00:00 | High | 6340000 |  | Metro North | 5 | 6925962 |  | G | 24 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 8161556 | 2014-06-01T00:00:00 | DH
21/1/2019 | EHQ | Metro South and East Queensland ICT Infrastructure Replacement Initiative | 2018-06-29T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | October 2018: The project is currently reporting red, with the project requesting additional budget to successfully complete project deliverables. A request to extend the budget has been submitted to the project's governance committee for approval. | 2018-10-31T00:00:00 | High | 4160449 |  | eHealth Queensland | 72 | 2278250 |  | R | 25 | Will replace or uplift out of date end of life ICT assets. | 3583313 | 2017-07-01T00:00:00 | DH
21/1/2019 | EHQ | Metro South East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-04-29T00:00:00 |  | 2018-10-31T00:00:00 | High | 2182844 |  | eHealth Queensland | 85 | 1170603 |  | G | 26 | Will replace or uplift out of date end of life ICT assets. | 2154311 | 2017-07-01T00:00:00 | DH
21/1/2019 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | August 2018: The project has returned to 'green'. Activities to improve project team resourcing and increase key deployment rates are continuing into September. The project will continue to monitor the performance of migration and upgrade activities. 21/1/2019, 21/1/2019,July 2018: The project is now reporting 'amber' due to a lack of technical and deployment resource availability, impacting on the project's schedule. Mitigation actions are in place to reduce the schedule and resourcing impact. 21/1/2019, 21/1/2019,May 2018: This project has now returned to 'green' with the project's revised schedule being approved. 21/1/2019, 21/1/2019,Reason for variance: Original budget was reflective of an original estimate based on high level planning. Detailed planning has since refined the estimated budget (including vendor licensing arrangements) which received approval for budget increase in June 2017. | 2018-10-31T00:00:00 | High | 14100000 |  | eHealth Queensland | 80 | 26839391 |  | G | 27 | A managed operating environment means that everyone within the organisation is running a clean, basic operating system with centralised update management. This includes upgrades of all PC operating systems, preparing QH applications for running on recent operating system environments, and Infrastructure remediation activities to ensure the deployment tools are sufficient and ready for production. | 38741697 | 2016-05-12T00:00:00 | DH
21/1/2019 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | October 2018: A technical implementation freeze and testing delays have resulted in an implementation delay of this initiative. The project's governance committee is currently reviewing the end date of this initiative. 21/1/2019, 21/1/2019,July 2018: The latest approved end date has been updated. 21/1/2019, 21/1/2019,June 2018: The latest approved end date of this project remains at 30 June 2018, pending the approval of a revised implementation date. 21/1/2019, 21/1/2019,Reason for variance: Budget and schedule were revised following a tender process as per responses from the market. | 2018-11-09T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 90 | 1104145 |  | G | 28 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1510000 | 2015-10-01T00:00:00 | DH
21/1/2019 | CHOPD | Notifiable Conditions System Replacement | 2019-06-29T00:00:00 | Delivery |  | 2020-02-28T00:00:00 | Reason for variance: Approval to extend project timelines was received November 2014. Business Case was updated and approved in November 2016, including extending the schedule to February 2020. | 2018-11-09T00:00:00 | High | 11590000 |  | Chief Health Officer and Prevention | 46 | 3159688 |  | G | 29 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 21/1/2019,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
21/1/2019 | EHQ | Patient Administration System (PAS) Replacement - Business Case Development Project | 2017-06-30T00:00:00 | Initiate |  | 2019-03-29T00:00:00 | Reason for variance: Further funding was provided in 2017-18 and 2018-19 to finalise the start-up activities, including the delivery of a detailed business case and early procurement activities. | 2018-10-31T00:00:00 | High | 3850000 |  | eHealth Queensland | 81 | 6743035 |  | G | 30 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients? journeys, and ensure that accurate information about our patients is readily available when and where required. 21/1/2019, 21/1/2019,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 21/1/2019,? support for patient engagement 21/1/2019,? integrated care 21/1/2019,? clinical research 21/1/2019,? population health (for patients using public health services) 21/1/2019,? performance transparency 21/1/2019,? resource planning. | 11890760 | 2015-11-01T00:00:00 | DH
21/1/2019 | CSD | Practice Management Enterprise Solution | 2018-11-30T00:00:00 | Delivery |  | 2019-01-31T00:00:00 | October 2018: This project is now reporting amber, with the project approving an updated project schedule and budget. This is as a result of placing the implementation of the project on hold while technical system issues are resolved. 21/1/2019, 21/1/2019,September 2018: The project is now reporting red, with the project placing the implementation on hold while technical system issues are resolved. The project's schedule and budget will be adjusted following the approval of a change request to extend the end date of the project. 21/1/2019, 21/1/2019,Reason for variance: The latest approved budget was revised to reflect additional project establishment costs and development, testing and piloting activities. The schedule was also revised following procurement outcomes. | 2018-11-08T00:00:00 | High | 1470000 |  | Corporate Services | 82 | 2351941 |  | A | 31 | The main practice management software used by HHSs to conduct private practice services and billing activities is being replaced. The initiative will procure and implement "like for like" functionality enterprise solution for participating HHSs (15 in total). | 2961432 | 2017-08-01T00:00:00 | DH
21/1/2019 | EHQ | Project, Program and Portfolio Management Application | 2018-03-31T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | May 2018: This project has now returned to 'green' with the project's revised schedule being approved. 21/1/2019, 21/1/2019,April 2018: This project is now reporting 'amber' due to re-aligning the project's schedule and finances to meet changing organisational requirements. The project has submitted | 2018-10-31T00:00:00 | High | 1344177 |  | eHealth Queensland | 60 | 802775 |  | G | 32 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 21/1/2019, | 1531491 | 2017-05-02T00:00:00 | DH
21/1/2019 | EHQ | Queensland State-wide ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 3246247 |  | eHealth Queensland | 73 | 2562355 |  | G | 33 | Will replace or uplift out of date end of life ICT assets. | 3183491 | 2017-07-01T00:00:00 | DH
21/1/2019 | EHQ | Queensland State-wide ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-10-31T00:00:00 | High | 3283431 |  | eHealth Queensland | 80 | 3469051 |  | G | 34 | Will replace or uplift out of date end of life ICT assets. | 3273746 | 2017-07-01T00:00:00 | DH
21/1/2019 | MNHHS | Quick Flow Project | 2019-06-30T00:00:00 | Initiate |  | 2019-06-30T00:00:00 |  | 2018-11-12T00:00:00 | High | 6408600 |  | Metro North | 47 | 2140216 |  | G | 35 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 21/1/2019,The key objectives of the project are to: 21/1/2019,? Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 21/1/2019,? Improve the outpatient experience across MNHSS facilities and community services 21/1/2019,? Improve clinic resource utilisation 21/1/2019,? Increase the efficiency of clinical and administrative processes 21/1/2019,? Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
21/1/2019 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Delivery |  | 2019-09-30T00:00:00 | October 2018: While the project continues to report red in October, the project has reviewed and revised upcoming milestone dates, with the full project schedule expecting to be approved in Nov/Dec 2018. 21/1/2019, 21/1/2019,September 2018: The project continues to report red due to additional functional, technical and integration requirements being added to the scope and as a result, is likely to impact the schedule. 21/1/2019, 21/1/2019,August 2018: The design and development phase of the project has been delayed to accommodate additional business and technical requirements. 21/1/2019, 21/1/2019,Reason for variance: The schedule has changed to ensure issues in project implementation are addressed. | 2018-11-09T00:00:00 | High | 34950000 |  | Cairns and Hinterland | 65 | 16445497 |  | R | 36 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patients home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
21/1/2019 | EHQ | Regional North and West Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-02-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 4260336 |  | eHealth Queensland | 80 | 2575151 |  | G | 37 | Will replace or uplift out of date end of life ICT assets. | 4213118 | 2017-07-01T00:00:00 | DH
21/1/2019 | EHQ | Regional North and West Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 2150147 |  | eHealth Queensland | 73 | 1674696 |  | G | 38 | Will replace or uplift out of date end of life ICT assets. | 2593463 | 2017-07-01T00:00:00 | DH
21/1/2019 | EHQ | Regional South and East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-10-31T00:00:00 | High | 1651750 |  | eHealth Queensland | 85 | 1386231 |  | G | 39 | Will replace or uplift out of date end of life ICT assets. | 1643098 | 2017-07-01T00:00:00 | DH
21/1/2019 | EHQ | Regional South and East Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 4245973 |  | eHealth Queensland | 83 | 3248346 |  | G | 40 | Will replace or uplift out of date end of life ICT assets. | 4216631 | 2017-07-01T00:00:00 | DH
21/1/2019 | EHQ | Service Delivery Excellence Project (SDEP) | 2018-02-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | March 2018: The latest approved end date and percentage complete has been updated. 21/1/2019, 21/1/2019,February 2018: The latest approved end date for this initiative will be updated pending advise from the project. | 2018-10-31T00:00:00 | High | 4822000 |  | eHealth Queensland | 40 | 2404342 |  | G | 41 | The Service Delivery Excellence Project (SDEP) aims to improve the service delivery functions of eHealth Queensland to help the organisation achieve its Customers and services Foundation and Shared Goal: 21/1/2019,Enhance value for customers by streamlining end to end services, processes and delivery models so that we can provide an exceptional customer experience. 21/1/2019,Stage 1 has the primary objective of delivering the Project Initiation Document (PID) for the Service Delivery Excellence Project (SDEP) Stage 2. | 4736721 | 2017-10-03T00:00:00 | DH
21/1/2019 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Delivery |  | 2020-09-30T00:00:00 |  | 2018-10-31T00:00:00 | High | 10500000 |  | eHealth Queensland | 28 | 3589457 |  | G | 42 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 10494349 | 2017-07-03T00:00:00 | DH
21/1/2019 | MNHHS | Royal Brisbane and Women's Hospital Wi-Fi | 2019-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-11-12T00:00:00 | High | 6000000 |  | Metro North | 40 | 3743502 |  | G | 43 | The RBWH Wi-Fi Project will provide an uplift and renewal to the latest Queensland Health (QH) standard for wireless local area network (WLAN) coverage within the internal areas of prioritised RBWH buildings in order to support digital healthcare. 21/1/2019,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for the RBWH in the near future. | 6000000 | 2017-10-22T00:00:00 | DH
21/1/2019 | EHQ | Sunshine Coast University Hospital (SCUH) Stage 2 ICT Expansion | 2018-06-30T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | February 2018: This project has been reported for the first time. | 2018-10-31T00:00:00 | High | 3180000 |  | eHealth Queensland | 92 | 4012107 |  | G | 44 | Sunshine Coast University Hospital (SCUH) ICT Stage 1 delivered the ICT required to achieve the successful commissioning of SCUH in March 2017. The SCUH Stage 2 ICT Expansion covers the investment period from 1 July 2017 to 31 December 2018 and is intended to support the planned expansion of SCUH to increase capacity and establish new services. | 4012107 | 2017-07-03T00:00:00 | DH
21/1/2019 | CHQ | Information Sharing Project Phase 2 | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | August 2018: The project is now reporting 'green'. The updated procurement approach was approved by the project's governance committee in August. 21/1/2019, 21/1/2019,July 2018: This project is now reporting 'amber' due to a change in procurement approach, which has impacted on the project's financials and schedule. The project's governance committee is reviewing the updated approach, returning the project to 'green' upon approval (expected to be in September). 21/1/2019, 21/1/2019,Reason for variance: Project budget was returned to support the implementation of another project. | 2018-11-05T00:00:00 | High | 4455455 |  | Children's Health Queensland | 37 | 1465673 |  | G | 45 | Department of Health, eHealth Queensland, Children's Health Queensland and Mater Health share a common vision for the seamless integration of care across organisational boundaries, in the interests of patient safety, quality, efficiency and improved access to care. This vision of integrated care processes is enabled through seamless access, at the point of care, to necessary health information and efficient transactional capabilities that support the care continuum. | 3568598 | 2018-01-10T00:00:00 | DH
21/1/2019 | CED | Consumer Integrated Mental Health Application (CIMHA) Alcohol and Other Drugs (AODS) Consumer Technical Refresh | 2019-06-28T00:00:00 | Ended |  | 2019-06-28T00:00:00 | October 2018: This project has now closed. A governance decision has been made to merge the outcomes and deliverables of this project into the new Consumer Integrated Mental Health Application (CIMHA) Secure Transfer and Technical Refresh Project. 21/1/2019, 21/1/2019,May 2018: This project has been reported for the first time. | 2018-11-02T00:00:00 | High | 1248860 |  | Clinical Excellence | 35 | 364660 |  | G | 46 | This project is refreshing the technical implementation of the CIMHA Consumer module, in preparation for the introduction of new Alcohol and Other Drugs (AODS) system functionality. | 1248860 | 2018-04-16T00:00:00 | DH
21/1/2019 | SPP | Queensland Health Integrated Processing System establishment (QHIDSe) | 2019-10-15T00:00:00 | Delivery |  | 2019-10-15T00:00:00 | May 2018: This project has been reported for the first time. | 2018-11-02T00:00:00 | High | 3257000 |  | Strategy, Policy and Planning | 31 | 1448604 |  | G | 47 | The QHIDSe project will develop in-house the foundation of an integrated processing system (i.e. QHIDS (Queensland Health Integrated Data System) using agile techniques and software development tools enabling QHIDS to be used as a replacement for the Queensland Hospital Inpatient Processing System (QHIPS, which processes the Queensland Hospital Admitted Patient Data Collection) and extended through future initiatives to provide new functionality. | 3257000 | 2018-05-25T00:00:00 | DH
21/1/2019 | HSQ | Modernised Managed Operating Environment (MOE) and Digital Collaboration Platform for HSQ | 2018-12-31T00:00:00 | Delivery |  | 2019-03-31T00:00:00 | September 2018: The project is continuing to report amber, with the project's schedule being impacted by a dependant project implementation schedule. 21/1/2019, 21/1/2019,July 2018: The project is now reporting 'red' due to project team resourcing issues, as well as technical and scheduling delays of a dependent project impacting on the overall schedule. The project's governance committee is reviewing the project's schedule, with the project expecting to return to 'green' upon approval of an updated delivery approach. 21/1/2019, 21/1/2019,Reason for variance: The original budget reflected the 2017/18 FY spend only. | 2018-11-12T00:00:00 | High | 1057000 |  | Health Support Queensland | 41 | 1600218 |  | G | 48 | Delivery of a fully functional, production managed operating environment and digital collaboration platform packaged to all desktops, laptops and some smart devices within the Health Support Queensland environment. | 3414000 | 2018-01-01T00:00:00 | DH
21/1/2019 | CHOPD | Mosquito-borne Disease Program: Spatial Database Project | 2019-06-21T00:00:00 | Initiate |  | 2019-06-21T00:00:00 | June 2018: This project has been reported for the first time. 21/1/2019, 21/1/2019,Reason for variance: The budget was revised following market scan activities. | 2018-11-09T00:00:00 | High | 940000 |  | Chief Health Officer and Prevention | 61 | 229133 |  | G | 49 | The vector surveillance and control program requires a state-wide surveillance and control solution to assist with the response to the risk of Dengue, Zika and Chikungunya virus outbreaks in vulnerable North Queensland and the mitigation of emerging risks across Central and Southern Queensland. | 1540000 | 2017-07-31T00:00:00 | DH
21/1/2019 | EHQ | Telehealth Asset Replacement | 2019-06-28T00:00:00 | Delivery |  | 2019-06-27T00:00:00 | July 2018: This project has commenced reporting for the first time. | 2018-10-31T00:00:00 | High | 1950000 |  | eHealth Queensland | 29 | 234325 |  | G | 50 | Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. | 1950000 | 2018-07-02T00:00:00 | DH
21/1/2019 | MNHHS | Connecting Care information Program (CCI) | 2022-06-30T00:00:00 | Initiate |  | 2022-06-30T00:00:00 | July 2018: This project has commenced reporting for the first time. 21/1/2019, 21/1/2019,Reason for variance: The budget was revised to include an additional financial year. | 2018-11-12T00:00:00 | High | 760455 |  | Metro North | 25 | 1009208 |  | G | 51 | The Connecting Care Information Program - CCI -will support streamlining and improvement of clinical and administrative workflows through delivery of key Information Technology (IT) enablers. | 1140000 | 2017-03-21T00:00:00 | DH
21/1/2019 | MNHHS | Metro North Health and Hospital Service Contemporary Workspace Phase 1 | 2019-01-01T00:00:00 | Delivery |  | 2019-01-01T00:00:00 | July 2018: This project has commenced reporting for the first time. 21/1/2019, 21/1/2019,Reason for variance: The latest approved budget includes additional implementation costs and funding for the 18-19 financial year. | 2018-11-12T00:00:00 | High | 233000 |  | Metro North | 50 | 717031 |  | G | 52 | This project is focusing on preparing the Metro North Hospital and Health Service (MNHHS) applications to be ready for contemporary operating system deployment. | 1665831 | 2017-08-01T00:00:00 | DH
21/1/2019 | MNHHS | Metro North Picture Archiving and Communication (PACS) Replacement for The Prince Charles Hospital | 2018-12-03T00:00:00 | Delivery |  | 2018-12-03T00:00:00 | July 2018: This project has commenced reporting for the first time. 21/1/2019, 21/1/2019,Reason for variance: The latest approved budget includes additional funding approved for the 18-19 financial year. | 2018-11-12T00:00:00 | High | 2301451 |  | Metro North | 24 | 897927 |  | G | 53 | Procure and implement a contemporary Picture Archiving and Communication (PACS) System and functionality that will ensure improved Service delivery for the MNHHS Medical Imaging Departments at The Prince Charles Hospital (TPCH). | 2301451 | 2017-12-01T00:00:00 | DH
21/1/2019 | CED | Consumer Integrated Mental Health Application (CIMHA) Secure Transfer Project | 2019-01-28T00:00:00 | Ended |  | 2019-01-28T00:00:00 | October 2018: This project has now closed. A governance decision has been made to merge the outcomes and deliverables of this project into the new Consumer Integrated Mental Health Application (CIMHA) Secure Transfer and Technical Refresh Project. 21/1/2019, 21/1/2019,July 2018: This project has commenced reporting for the first time. 21/1/2019, 21/1/2019,Reason for variance: The budget was refined after the solution design stage with extended approvals required, impacting the project schedule. | 2018-11-02T00:00:00 | High | 610000 |  | Clinical Excellence | 10 | 125001 |  | G | 54 | The purpose of this initiative is to upgrade the CIMHA application with functionality to automate the sending of selected clinical notes and data securely. This will improve the efficiency and timeliness of information sharing. | 1109521 | 2017-10-16T00:00:00 | DH
21/1/2019 | CED | Patient Online Portal (POP) | 2019-12-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | July 2018: This project has commenced reporting for the first time. | 2018-11-07T00:00:00 | High | 15500000 |  | Clinical Excellence | 8 | 2432981 |  | G | 55 | The Patient Online Portal (POP) aims to improve a patients outpatient journey through greater visibility and enhanced communication capability across specialist services. Additionally, the solution seeks to provide greater flexibility in the provision of outpatient services, allowing patients to better manage their care. | 15500000 | 2018-03-05T00:00:00 | DH
21/1/2019 | MNHHS | Digital Transformation Readiness | 2018-12-27T00:00:00 | Initiate |  | 2018-12-27T00:00:00 | July 2018: This project has commenced reporting for the first time. | 2018-11-14T00:00:00 | High | 2771674 |  | Metro North | 28 | 1005588 |  | G | 56 | The key objectives of Digital Transformation Readiness are to perform activities in preparation for Metro North Hospital and Health Service (MNHHS) Digital Transformation with a focus on the integrated electronic Medical Record (ieMR) readiness. | 2771674 | 2018-06-29T00:00:00 | DH
21/1/2019 | MNHHS | Referral Lodgement and Tracking (RLaT) | 2019-01-23T00:00:00 | Delivery |  | 2019-01-23T00:00:00 | October 2018: The project is now reporting red due to additional implementation complexities which has resulted in a 6 month schedule delay extending the planned end date to June 2019. 21/1/2019, 21/1/2019,July 2018: This project has commenced reporting for the first time. | 2018-11-12T00:00:00 | High | 3184098 |  | Metro North | 70 | 2384360 |  | R | 57 | This project will deliver a state-wide capability for referrers to lodge patient referrals electronically with Queensland Health. The referral will be automatically routed to the appropriate Hospital and Health Service (HHS). | 3184098 | 2018-02-09T00:00:00 | DH
21/1/2019 | EHQ | Infrastructure Capacity Expansion FY 18-19 | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 1192426 |  | eHealth Queensland | 30 | 33901 |  | G | 58 | The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified organic growth requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. | 1192425 | 2018-07-02T00:00:00 | DH
21/1/2019 | EHQ | Storage Asset Replacement FY 18-19 | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-31T00:00:00 | High | 4446000 |  | eHealth Queensland | 7 | 59045 |  | G | 59 | The Server Asset Replacement Project is responsible for replacing prioritised, highly utilised and critical server assets which are coming to, or have reached, end-of-financial-life. | 4446000 | 2018-07-02T00:00:00 | DH
21/1/2019 | MNHHS | Digital Dictation Upgrade Project | 2017-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | October 2018: This project is now reporting red. The implementation date is expecting to be delayed, with additional budget also required to complete the extended implementation of the solution. 21/1/2019, 21/1/2019,Reason for variance: The latest approved budget includes funding for 2018/19 financial year. The go-live date and, therefore, the project end date, has been revised in line with customer expectations. | 2018-11-12T00:00:00 | High | 828522 |  | Metro North | 90 | 1024021 |  | R | 60 | To replace the current versions of the Digital Dictation Systems in use at MNHHS facilities with the newest release of the product. The new release introduces efficiencies in the workflow process and contributes to patient care improvement through reduction in timeframe to complete patient letters. | 1048522 | 2016-07-25T00:00:00 | DH
21/1/2019 | CED | Consumer Integrated Mental Health Application (CIMHA) Secure Transfer and Technical Refresh Project | 2019-10-14T00:00:00 | Delivery |  | 2019-10-14T00:00:00 | October 2018: This initiative has been reported for the first time. | 2018-11-08T00:00:00 | High | 2828381 |  | Clinical Excellence | 17 | 479532 |  | G | 61 | Upgrade the CIMHA application with functionality to automate the sending of selected clinical notes and data to external entities. This will improve to efficiency and timeliness of information sharing with external clinicians at assist them to make better decisions at the point of care. | 2828381 | 2018-04-16T00:00:00 | DH
21/1/2019 | HSQ | iPharmacy Upgrade Project | 2019-07-29T00:00:00 | Initiate |  | 2019-07-29T00:00:00 | October 2018: This initiative has been reported for the first time. | 2018-11-12T00:00:00 | High | 1861600 |  | Health Support Queensland | 5 | 0 |  | G | 62 | Upgrade of the statewide i.Pharmacy application, infrastructure and hardware to ensure the availability and future sustainability of the Pharmacy services across the State. | 1861600 | 2018-10-01T00:00:00 | DH
21/1/2019 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 2 | 2019-09-30T00:00:00 | Delivery |  | 2019-09-30T00:00:00 | October 2018: This initiative has been reported for the first time. | 2018-11-12T00:00:00 | High | 27243224 |  | Health Support Queensland | 2 | 897164 |  | G | 63 | Stage 2 of the IWFM Project will provide direct access to managing Queensland Health employee details, provide the capability of the submission of online forms, as well as enabling manager and employee self-service. This implementation will remove duplication, reduce paperwork and return the control and accountability of workforce establishment management to the business, thereby improving visibility of information, transparency of form tracking, increasing productivity and accuracy and reducing the time and inconvenience of returned forms. | 27243224 | 2018-09-13T00:00:00 | DH
21/1/2019 | QAS | Mobile Data State-wide | 2020-06-30T00:00:00 | Initiate |  | 2020-06-30T00:00:00 | October 2018: This initiative has been reported for the first time. | 2018-11-09T00:00:00 | High | 21672000 |  | Queensland Ambulance Service | 3 | 71798 |  | G | 64 | This initiative will expand mobile data and automatic vehicle location capability statewide, and establish remote configuration, monitoring and updates to in-vehicle mobile units. | 21672000 | 2018-05-01T00:00:00 | DH
21/1/2019 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Project planned expenditure and end date have been revised due to a number of factors: 21/1/2019, 21/1/2019,- The original planned expenditure of $2.2M was a high level estimate and has been refined with the complexity of the processes and system being uncovered as the project was stood up. 21/1/2019, 21/1/2019,- An increased scope and associated effort to ensure maximum benefit is gained from the investment, so that Queenslanders are better supported during natural disasters. 21/1/2019, 21/1/2019,- Delays to project schedule and associated additional resourcing costs as a result of: 21/1/2019, 21/1/2019, - Staff diverted to priority community recovery support roles during activations over the last 12 months, including TC Debbie, TC Nora and the North Queensland floods and most recently to NQ Bushfires. During natural disasters, our agency resources are focused on providing critical support to communities and Queenslanders in need. 21/1/2019, 21/1/2019, - Extended vendor delivery times. | 2018-11-30T00:00:00 | High | 2208000 |  | Department of Communities, Disabilty Services and Seniors | 89 | 3705000 |  | G | 1 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3780000 | 2016-07-01T00:00:00 | DCCSDS
21/1/2019 | DTS_ICTSPC | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | Feedback from the Queensland Fire and Emergency Management (QFES) Human Capital Management (HCM) Project Closure Report has been received. There are activities identified through the closure report review process which need to be addressed before the closure report can be approved. A plan is being developed to finalise these activities. 21/1/2019, 21/1/2019,The Queensland Corrective Services (QCS) HCM Project has commenced implementation with an expected completion timeframe of late 2019. 21/1/2019, 21/1/2019,The QFES payroll project transitioning to Aurion is progressing to schedule. 21/1/2019, 21/1/2019,Queensland Ambulance Services (QAS) Payroll has achieved successful results from the first Parallel Pay Run Test. To provide further rigour and assurance for a successful transition, an additional Parallel Pay Run Test for the QAS payroll project has been included with a revised implementation schedule of March 2019 being approved by the Executive Steering Committee. 21/1/2019, 21/1/2019,The QAS Payroll technical integration solution has been successfully developed, tested and released into production as scheduled. 21/1/2019, 21/1/2019,At the direction of the Executive Steering Committee (3/07/18) the program scope was increased to include the procurement of a Time and Attendance solution for QFES, QAS and QCS. An Invitation to Officer (ITO) process has been undertaken to determine market suitability to agency requirements with vendor demonstrations and agency evaluation in their final stages. 21/1/2019, 21/1/2019,The Human Resource Information Solution (HRIS) Program is continuing as Amber due to the revision of scheduling for Queensland Fire and Emergency Services (QFES) and QAS Payroll. | 2018-09-30T00:00:00 | Critical | 101500000 |  | ICT Strategic Project Coordination | 68 | 62987631 |  | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 21/1/2019, 21/1/2019,* Sustainable and supported HR and Payroll service delivery 21/1/2019,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 21/1/2019,* Strategic HR capability that supports the development, performance and safety of the departments workforce 21/1/2019,* Business Intelligence capability that provides real timely, integrated HR information 21/1/2019,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 21/1/2019,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 21/1/2019,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
21/1/2019 | QPS | GPS Tracking (Bail) | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | Legislation provisioning for GPS monitoring of court bailed offenders commenced on 31/3/18. QPS established interim GPS tracking capability leveraging existing contract held by Queensland Corrective Services. 21/1/2019,QPS is now undertaking a WoG open ITO to establish a longer term contract for GPS tracking devices and monitoring of offenders. 21/1/2019,Note: The project is currently undergoing procurement/commercial activity and is therefore not publishing any financial data. 21/1/2019, 21/1/2019, 21/1/2019, | 2018-12-19T00:00:00 | High | 0 |  | Queensland Police Service | 40 | 0 |  | G | 1 | As per the Commencement of the Bail (Domestic Violence) and Another Act Amendment Act 2017 (the Amending Act) on 30 March 2018, Magistrates will be empowered to impose a tracking condition on a defendant granted bail as a condition of their bail undertaking. 21/1/2019,As such the QPS intends to progressively implement an electronic monitoring capability on a State Wide basis. 21/1/2019,An implementation project has commenced to create an electronic monitoring capability for geographically locating and monitoring a defendant on bail for QPS to meet requirements of the Amended Act. 21/1/2019,The GPS Tracking Project is an initial proposal to validate the utility of the technology prior to seeking a longer term solution. | 0 | 2018-03-30T00:00:00 | QPS
21/1/2019 | QPS | Police Integrity and Professional Standards | 2018-08-24T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | Full funding has now been approved for the Police Integrity and Professional Standards (PIPS) IT system. 21/1/2019, 21/1/2019,The Project has received a green assessment for the Gate 3 Quality Assurance Review. 21/1/2019, 21/1/2019,Feb 18: Note: original planned end date amended as previously published information was incorrect. | 2018-12-19T00:00:00 | High | 4142000 |  | Queensland Police Service | 35 | 492654 |  | G | 2 | This initiative will deliver a new integrated Police Integrity and Professional Standards (PIPS) IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The PIPS system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The PIPS Project will also complement the Complaints Reform Project (CRP) established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of the PIPS system will place the QPS in a strong readiness position to fully implement CRP-generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 6882000 | 2017-03-07T00:00:00 | QPS
21/1/2019 | QPS | eWarrants | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Phase/Gateway 1: Project Brief approved 13 Sept 2017 21/1/2019,Phase/Gateway 2: Business Case approved 17 April 2018. Project Funding (FY18/19) approved by QPS Demand and Resource Committee 22 Oct 2018. 21/1/2019,Phase/Gateway 3: Project Delivery, Business Analysis commenced and progressing according to plan. | 2018-12-19T00:00:00 | Medium | 850000 |  | Queensland Police Service | 3 | 850000 |  | G | 3 | Develop and introduce new and enhanced business processes and information exchange capabilities (requiring modifications to applications and technology) to enable the electronic creation, and management of Warrants issued by the Magistrates Courts for the duration of the Warrant. 21/1/2019, 21/1/2019,This is an inter-agency initiative involving QPS, Integrated Criminal Justice (ICJ), Department of Justice and Attorney General (DJAG), Communities and Corrections. It is anticipated that overall Program/Project Management will be the responsibility of ICJ and follow a similar model to that established for eDV (Domestic Violence). 21/1/2019, 21/1/2019,Legislative changes will need to occur with both QPS and DJAG, in regard to the current requirements regarding the receiving, processing and validity of hard copy warrants. | 0 | 2017-06-16T00:00:00 | QPS
21/1/2019 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Objectives 21/1/2019, 21/1/2019, 21/1/2019,This project will deliver a secondary DR site and hyper-converged system to provide resilience for all departmental business applications in the event of a disaster. 21/1/2019, 21/1/2019,Project Updates 21/1/2019, 21/1/2019, 21/1/2019,Core infrastructure DR implementation 80% complete. All migrated production systems successfully replicating to secondary DR site. 21/1/2019,Oracle system DR implementation is 100% complete. 21/1/2019,Oracle applications DR testing successfully completed. 21/1/2019,Legacy applications that are incompatible with Core infrastructure platform will be migrated to a new DR-capable environment by end of Nov 2018. 21/1/2019,Security DR implementation in progress. Dependency on provisioning of network connectivity has caused delays. 21/1/2019,All end-of-life ICT infrastructure will be decommissioned by Dec 2018. 21/1/2019,The newly implemented DR infrastructure will provide improved stability and life extension to existing business-critical applications. 21/1/2019,DR recovery procedure development, testing strategy and ICT DR Plan updates almost complete. Awaiting endorsement. 21/1/2019,DJAG DR failover testing has been completed and QCS DR testing scheduled to be completed by end of Nov 2018. 21/1/2019, 21/1/2019,Some issues have impacted YTD position however it is anticipated the original completion date will be met. | 2018-10-30T00:00:00 | High | 7314596 |  | Corporate Services | 90 | 5449744 |  | G | 1 | *Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 6512596 | 2016-10-01T00:00:00 | DJAG
21/1/2019 | BCS | Blue Card Services Recommendation 28.1 Project - Blue Card Home Based Care Register | 2018-12-21T00:00:00 | Delivery |  | 2019-01-31T00:00:00 | In July 2016, the Queensland Family and Child Commission QFCC released the When a child is missing Remembering Tiahleigh - A report into Queensland's children missing from out-of-home care report making 29 recommendations. Recommendation 28 required the QFCC to undertake a further review of legislation, policies and practices relating to information sharing between relevant agencies responsible for children in regulated service environments. 21/1/2019,The Recommendation 28 Supplementary Review, A report on information sharing to enhance the safety of children in regulated home based services (Supplementary Review) is the QFCC response to Recommendation 28 and makes 17 recommendations in relation to information sharing between agencies responsible for regulating and monitoring regulated services provided from the home, namely foster and kinship care, family day care and stand alone care services. 21/1/2019,Implementation of the register will require legislative amendment. | 2018-10-30T00:00:00 | High | 1573000 |  | Blue Card Services | 60 | 860628 |  | G | 2 | The objective of this project is to establish a register for recording and reporting on regulated child-related services provided from the home, specifically limited to foster/kinship care, family day care and stand-alone care. As recommended by the Queensland Family and Child Commission (QFCC) within the Recommendation 28 Supplementary Review Report (A report on information sharing to enhance the safety of children in regulated home-based services) this register will: 21/1/2019,a) identify co-located home-based services 21/1/2019,b) enable the Queensland Police Service to have line of sight to the register to access up-to-date information when Police attend a residential address to identify potential risks to children, and 21/1/2019,c) make information available to agencies, including Department of Child Safety, Youth and Women, Department of Education and the Office of the Public Guardian to assist with regulating and/or monitoring specific home-based services. | 1573000 | 2017-04-01T00:00:00 | DJAG
21/1/2019 | HHS_HH | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery |  | 2019-03-31T00:00:00 | The FOPATS Program undertook a significant re-baseline in late 2016 to inform and approve changes to its strategic direction, scope, delivery methodology, timing and costs, including strengthening program governance and revising the Business Case to complete against a two staged implementation, Property and then Tenancy. 21/1/2019, 21/1/2019,Following this review, the Property Release, the first of two stages, was delivered successfully on time on 1 November 2017 and delivered benefits including efficiencies in property management and reporting. 21/1/2019, 21/1/2019,The Program has completed more detailed planning for the second stage Tenancy Release, which will remove the operational dependency on the existing ICT housing solution entirely. Tenancy design activities are now well progressed, with a view to determining a feasible Program end date. 21/1/2019, 21/1/2019,The FOPATS Program has been updated to Amber status while the final review of design documents and system configurations against the Queensland Housing Strategy service delivery operating model reforms is completed. | 2018-09-30T00:00:00 | Critical | 56286000 |  | Housing and Homelessness | 65 | 79622498 |  | A | 1 | Replace the existing ICT housing solution with an integrated ICT system. | 121597695 | 2013-07-01T00:00:00 | HPW
21/1/2019 | BPAM_QF | Fleet Management System Replacement Project (FMSRP - QFleet) | 2019-09-30T00:00:00 | Initiate |  | 2019-09-30T00:00:00 | Delays in implementation have resulted from the onboarding of appropriate project resourcing. A senior project manager for the partner agencies has been appointed. Project stakeholder resourcing delays have been addressed and project is returning to schedule. 21/1/2019, | 2018-09-30T00:00:00 | High | 13939200 |  | QFleet | 25 | 954562 |  | A | 2 | The objective of the FMSRP is the procurement and implementation of a new common Fleet Management System that meets QFleet, QPS, QFES and QAS core business requirements and provides best value for money. It will provide a contemporary, sustainable common Fleet Management System that delivers effective and efficient business services for the agencies now and into the future. | 13937796 | 2017-10-19T00:00:00 | HPW
21/1/2019 | BPAM_QF | QFleet Car Sharing Model Implementation Project (CSMIP) | 2018-08-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Procurement activity has concluded. Contract drafting is complex and has taken longer than anticipated, resulting in delays in timing and an amber status. 21/1/2019, 21/1/2019,Implementation planning, including system testing, is continuing in parallel with the contract drafting. Once the contract is finalised, a revised timeline will be considered by the project board. 21/1/2019, | 2018-09-30T00:00:00 | High | 454735 |  | QFleet | 70 | 99458 |  | A | 3 | The objective of the Car Sharing Model Implementation Project (CSMIP) is the procurement and implementation of a fully automated, innovative and sustainable multi-agency car sharing solution delivering effective and efficient short-term motor vehicle hire services for government, now and in the future. | 454735 | 2017-11-20T00:00:00 | HPW
21/1/2019 | DTS_SSQ | Pay Safe Project | 2018-07-31T00:00:00 | Initiate |  | 2019-03-28T00:00:00 | A preferred vendor has been selected with contract negotiations to commence mid-October 2018. | 2018-09-30T00:00:00 | Critical | 1500000 |  | Smart Service Queensland | 29 | 175832 |  | G | 4 | The project will implement an improved capability for offering secure payment card transactions via the telephone. To meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS) when the new VOIP telephony solution is introduced. | 1500000 | 2018-01-29T00:00:00 | HPW
21/1/2019 | DTS_SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery |  | 2018-12-22T00:00:00 | The Smart Service Telephony Replacement Project Board is monitoring the project closely to ensure current go live dates are met. 21/1/2019, 21/1/2019,User Acceptance Testing has commenced with few critical defects identified. The defects are being investigated and root causes have been identified and are being managed. 21/1/2019, 21/1/2019,The project is currently reporting Amber due to unavoidable project delays caused by the high complexity of the technology and business configuration needed to meet requirements and ensuring adequate testing of the new system is undertaken prior to going live. | 2018-09-30T00:00:00 | Critical | 4490634 |  | Smart Service Queensland | 70 | 4051553 |  | A | 5 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 21/1/2019, 21/1/2019,* reduce operating costs 21/1/2019,* increase capacity 21/1/2019,* improve customer experience 21/1/2019,* provide new functionality. | 4566079 | 2015-04-02T00:00:00 | HPW
21/1/2019 | DTS_SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The Technology Platform Project is currently awaiting readiness of some Telephony Replacement Project deliverables before progressing the final Technology Platform Project deliverables which will result in a re-baselined end date. 21/1/2019, 21/1/2019,Discussion has commenced with vendors for revised quotes and timeframes. This information will form the basis of a re-baseline of the project with new end dates and final budget. | 2018-09-30T00:00:00 | Critical | 3390861 |  | Smart Service Queensland | 85 | 2573385 |  | A | 6 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution and the call recording solution. | 3390862 | 2017-05-15T00:00:00 | HPW
21/1/2019 | DTS_DAP | Digital Archiving Program Tranche 1 Transition-In | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | Since the execution of the Digital Archiving as-a-Service Contract on 6/08/2018, implementation is progressing well with the Initiation Stage completed. Supplier performance is good and all required Deliverables have been received on time. Service Design for archival management and control has commenced. Qld State Archives staff remain positive and have contributed strongly to the initial round of Service Design workshops. | 2018-09-30T00:00:00 | Medium | 8186387 |  | Digital Archiving Program | 10 | 555839 |  | G | 7 | Deliver archival management and control capability with access, search and discovery for use by QSA, Public Authorities and the Public | 8186387 | 2018-08-07T00:00:00 | HPW
21/1/2019 | DTS_SSQ | Customer Identity and Details Enhancements FY17-18 | 2018-10-30T00:00:00 | Delivery |  | 2019-03-01T00:00:00 | Penetration testing for the Customer Identity and Details Enhancements project has been completed and re-testing will occur once all identified penetration testing defects are resolved. 21/1/2019, 21/1/2019,Load testing for the Content Delivery Solution Project (CDS) was successfully delivered and is complete. 21/1/2019, 21/1/2019,The additional costs associated with the remediation activity has resulted in an amber status. A revised budget will be considered by the project board in due course. | 2018-09-30T00:00:00 | High | 1200000 |  | Smart Service Queensland | 75 | 1505563 |  | A | 8 | Improved technology and functionality to meet agency requirements in customer identity and details to enable agency adoption and uptake driving further value for customers. 21/1/2019, 21/1/2019,* CDM Blueprint 21/1/2019,* Transition to new platform 21/1/2019,* Auth pilot 21/1/2019,* CDM release 2 pilot | 1200000 | 2017-07-01T00:00:00 | HPW
21/1/2019 | CS_CIO | ICT Infrastructure Refresh Project | 2018-06-30T00:00:00 | Closed |  | 2018-09-30T00:00:00 | Project closed 30 September 2018. 21/1/2019, 21/1/2019,The refresh activities have increased the departments security profile in terms of managed software installations, up-to-date security patching and monitoring. 21/1/2019, 21/1/2019,The Windows 10 phase was extremely successful having deployed to over 4,000 devices across approximately 100 sites across the state. | 2018-09-30T00:00:00 | Medium | 1173338 |  | Chief Information Office | 100 | 936537 |  | G | 9 | To upgrade ICT infrastructure to maintain a fully supported and secure environment and leverage and take advantage of offerings from current DHPW licencing agreements. | 1173338 | 2017-02-13T00:00:00 | HPW
21/1/2019 | DTS_ICTSS | Government Wireless Network Contract and Administration Billing System | 2018-06-30T00:00:00 | Initiate |  | 2019-06-30T00:00:00 | The Contract and Administration Billing System (CABS) project documentation has progressed with the Business Case, Project Plan and Project Initiation Document (PID) created. The procurement phase has commenced. | 2018-09-30T00:00:00 | High | 0 |  | ICT Strategic Sourcing | 19 | 0 |  | G | 10 | The GWN Contract Directorate seeks a fully managed software-as-a-service solution to replace existing excel spreadsheets and macros that have organically grown in complexity, improve record keeping compliance, and alleviate current single points of failure and reliance. This project is to procure a purposely designed software system that is fully functional, customisable, redundant, reliable, will meet the current and future requirements of the GWN Contract, and replace current Contract Modification and Contractor Performance processes. | 0 | 2017-11-01T00:00:00 | HPW
21/1/2019 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 21/1/2019, 21/1/2019,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 21/1/2019,October 2017 - The project is progressing as planned. 21/1/2019,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 21/1/2019,June 2017 - Revised Schedule approved returning the project to Green. 21/1/2019,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 21/1/2019,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 21/1/2019,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 21/1/2019,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 21/1/2019,December 2016 - The project is progressing as planned. | 2017-12-21T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 21/1/2019, 21/1/2019,* register and maintain their information 21/1/2019,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
21/1/2019 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 21/1/2019, 21/1/2019,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 21/1/2019,August 2017 - Approved extension of timeframe. 21/1/2019,June 2017 - The project is progressing as planned. 21/1/2019,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 21/1/2019,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 21/1/2019,October 2016 - Progress is continuing as planned. 21/1/2019,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 21/1/2019,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 21/1/2019,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-21T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 21/1/2019, 21/1/2019,* support compliance with legislation 21/1/2019,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 21/1/2019,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 21/1/2019,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 21/1/2019, | 1390000 | 2012-04-01T00:00:00 | DEWS
21/1/2019 | BQCC | Communication and Stakeholder Engagement Solution | 2018-04-27T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Deliverables have been achieved and project closure documentation is being finalised. 21/1/2019, 21/1/2019,November 2018 - The project has returned to Green status. 21/1/2019,October 2018 - Timeframe will be exceeded due to resourcing issues. This has affected key capability to perform testing and the finalisation of procedures and supporting documentation. A review of timeframe and associated costs is under way. 21/1/2019,September 2018 - Timeframe is being monitored closely due to business demands impacting testing and completion of documentation. Project closure is now planned by 30 September 2018. 21/1/2019,August 2018 - The project is progressing as planned and is on schedule. 21/1/2019,July 2018 - An extension to the planned end date and additional budget has been approved by the governance committee. 21/1/2019,June 2018 - Hidden complexities around integration with other solutions has affected the timing of user acceptance testing and training schedules. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 21/1/2019,May 2018 - A change to the planned end date and cost has been approved. 21/1/2019,March 2018 - Note adjustment to planned end date corrected due to typographical error. 21/1/2019,February 2018 - The project is progressing as planned. 21/1/2019,December 2017 - The project was approved to move into delivery in October 2017 and is being published for the first time. | 2018-12-10T00:00:00 | Medium | 694000 |  | Biosecurity Queensland Control Centre | 100 | 1011823 |  | G | 1 | To implement a simple, easy to use system that will facilitate the collection of information associated with the National Red Imported Fire Ant Eradication Program and the National Electric Ant Eradication Program. This will include contact management, complaints management, history of interactions, event management, training management, social media interactions, marketing campaign and reporting. | 1048849 | 2017-06-01T00:00:00 | DAF
21/1/2019 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The project has been rebaselined and approved to encompass additional scope. Accordingly, there has been an adjustment to the percentage of deliverables achieved, the schedule, and cost. 21/1/2019, 21/1/2019,November 2018 - Stage 2 has been endorsed and is going ahead. 21/1/2019,July 2018 - The project has re-commenced. Approval has been granted for an extension to the planned end date, and an increase in associated costs. 21/1/2019,June 2018 - Field testing has identified unexpected issues that will impact on the planned end date. Effort is underway with Microsoft to apply a technical fix (patch) to resolve errors. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 21/1/2019,April 2018 - An extension to the planned end date has been approved, returning the project status to Green. 21/1/2019,March 2018 - A minor scope increase has been proposed, affecting both timeframe and cost, which is progressing through the governance process. 21/1/2019,March 2018 - The project is progressing as planned. 21/1/2019,December 2017 - A variation to scope was approved, resulting in a change to the planned end date and total estimated expenditure. 21/1/2019,November 2017 - The project is continuing as planned. 21/1/2019,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2018-12-18T00:00:00 | Medium | 608146 |  | Forestry Queensland | 70 | 1144127 |  | G | 2 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 21/1/2019, 21/1/2019,* the capture, management and integration of data 21/1/2019,* value-adding opportunities for business improvement 21/1/2019,management of risk associated with ongoing use and maintenance of disparate systems. | 1696431 | 2016-06-15T00:00:00 | DAF
21/1/2019 | FQ | Novel Commercial and Recreational Fishing Apps | 2018-09-30T00:00:00 | Delivery |  | 2019-01-31T00:00:00 | The project is Amber due to a delay with implementation of the commercial app. A review of scope is currently under way, affecting the schedule and cost. 21/1/2019, 21/1/2019,October 2018 - The project is progressing as planned and is on schedule. Note: the approved end date has been updated in accordance with the approved business case. 21/1/2019,September 2018 - Contract documentation has been finalised and the first two development cycles are under way. 21/1/2019,August 2018 - The project was approved to move to delivery in July 2018 and is publishing for the first time. | 2018-12-11T00:00:00 | High | 571000 |  | Fisheries Queensland | 40 | 459864 |  | A | 3 | * Provide up-to-date information on the rules and regulations about fishing and marine park zoning in Queensland 21/1/2019,* Achieve better compliance through access to information 21/1/2019,* More uptake of the App by providing regulations from other marine agencies 21/1/2019,* Resolve issues with offline access to information. 21/1/2019, 21/1/2019, | 571000 | 2018-02-01T00:00:00 | DAF
21/1/2019 | ASQ | Portfolio Activity Reporting Information System | 2018-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The project is progressing as planned and is on schedule. 21/1/2019, 21/1/2019,September 2018 - Extensive stakeholder consultation has been undertaken and included in documentation. 21/1/2019,August 2018 - The project is progressing as planned and is on schedule. 21/1/2019,July 2018 - Project is continuing as planned. 21/1/2019,June 2018 - Refreshed business case approved, the project has been re-baselined returning it to a Green status. 21/1/2019,May 2018 - Funding has been approved to fully implement the project and it is now in delivery. 21/1/2019,February 2018 - The project is paused until a funding source is identified. 21/1/2019,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-12-04T00:00:00 | High | 978000 |  | Agri-Science Queensland | 10 | 386509 |  | G | 4 | Review and consolidate the variety of processes and technologies currently being used to manage the department's research, development and extension, and other projects. | 978000 | 2015-08-13T00:00:00 | DAF
21/1/2019 | BQ | RBE (Registered Biosecurity Entity) Renewal Project | 2019-08-30T00:00:00 | Delivery |  | 2019-08-30T00:00:00 | The project is progressing as planned and is on schedule. 21/1/2019, 21/1/2019,August 2018 - The project was approved to move to delivery in July 2018 and is publishing for the first time. | 2018-12-05T00:00:00 | High | 2867000 |  | Biosecurity Queensland | 25 | 701272 |  | G | 5 | * Develop an efficient end-to-end registration renewal process to allow effective management of renewals 21/1/2019,* Ensure stakeholders are aware of renewal requirements and the importance of maintaining up-to-date information 21/1/2019,* Provide the ability to efficiently communicate with customers about registered biosecurity entity processes and renewals 21/1/2019,* Provide data integration between the online customer portal and the underlying technology solution 21/1/2019,* Minimise administrative overhead. | 2821000 | 2017-11-10T00:00:00 | DAF
21/1/2019 | Ag | Risk Reduction for Customer Service Centre | 2019-04-19T00:00:00 | Delivery |  | 2019-04-19T00:00:00 | The project is progressing as planned and is on schedule. 21/1/2019, 21/1/2019,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-12-17T00:00:00 | High | 1767000 |  | Customer and Business Services | 76 | 1137865 |  | G | 6 | Implement a solution to mitigate risk of end of life for the agency's call centre logging application. | 1767000 | 2015-01-30T00:00:00 | DAF
21/1/2019 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
21/1/2019 | PSBA | Emergency Vehicle Priority (EVP) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | Project delivery completed. Approved scope of EVP rollouts have been completed with vehicle fit outs finished in Rockhampton, Maryborough, Hervey Bay and Gladstone for both Queensland Ambulance Service and Queensland Fire and Emergency Services. The EVP Inter-Departmental Steering Committee approved the EVP Project to close on 31 October 2018. The project is reporting 99% completion while awaiting finalisation of financial information and sign off of Project Closure Report. Project scope was expanded to include procurement of a managed service for operational support and maintenance and increasing vehicle deployments to a total of 730 emergency vehicles, resulting in a revised timeframe from the original planned end date of 30-06-2017 to 31-10-2018, and a revised total expenditure from $3.37 million to $4.25 million. Revised total expenditure is pending approval to reduce by $96k to align to actual cost to date of $4.25M. | 2019-01-16T00:00:00 | High | 3370000 |  | Public Safety Business Agency | 99 | 4253094 |  | G | 1 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 21/1/2019, 21/1/2019,* Responsive vehicle movements 21/1/2019,* Improve road safety 21/1/2019,* Congestion management 21/1/2019,* Community safety | 4348696 | 2013-01-01T00:00:00 | PSBA
21/1/2019 | OSR | State Penalties Enforcement Registry (SPER) Program |  | Delivery |  | 2019-06-30T00:00:00 | The project completion timeframe has been extended by 6 months, from the end of 2018 to 30 June 2019, with a target go-live date for the new SPER ICT system by May 2019. 21/1/2019,The cost to deliver the new system will be met within the original budget. 21/1/2019,The design and build phase of the new system was completed on time in mid-2018. Vendor system testing and system integration testing with key partner agencies has now been completed. 21/1/2019,User testing for the new system began in November 2018. 21/1/2019,The extension of time will allow for extensive user testing with a broad range of fine issuing and referring agencies to ensure the system is reliable and has the highest standard of data integrity and security. 21/1/2019,A significant change management and training program is in progress for both staff and external stakeholders who refer their debts to SPER. | 2018-11-16T00:00:00 | High | 47200000 |  | State Penalties Enforcement Registry | 79 | 58700000 |  | A | 1 | To maintain the integrity of fines as an effective sanction. 21/1/2019,To uphold confidence in the justice system. 21/1/2019,To deliver efficient and effective debt management practices which provide value for money to the State. 21/1/2019, | 62150000 | 2014-01-01T00:00:00 | QR
21/1/2019 | RI | Financial Assurance Information Registry (FAIR) |  | Delivery |  | 2019-03-01T00:00:00 | The FAIR project is aligned with commencement of the Financial Provisioning Scheme (FPS). A deferral of the passage of the legislation to enact the FPS, which would permit the scheme to commence, has led the delivery delay event to be marked yes. Consistent with the November passage of the FPS legislation stakeholders have been informed that the FPS is expected to commence in the first half of 2019. 21/1/2019, 21/1/2019,The FAIR project required for the FPS commencement remains unchanged at 90 percent complete. Other components of the FPS reforms will be completed in subsequent years. 21/1/2019,Consistent with the expected rollout of the FPS in the first half of 2019 the IT system is currently in a final development, testing and maintenance phase preparing for scheme commencement. Given the project is reaching its conclusion, it requires close monitoring by management regarding on time delivery 21/1/2019, | 2018-11-27T00:00:00 | Medium | 15900000 |  | Insurance Commission | 90 | 9630651 |  | A | 2 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
21/1/2019 | RI | Information Security Program |  | Delivery |  | 2019-06-30T00:00:00 | The program is on track according to schedule and budget. | 2018-11-16T00:00:00 | Medium | 1960000 |  | Office of the Chief Information Officer | 60 | 710705 |  | G | 3 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 21/1/2019, | 1960000 | 2017-10-16T00:00:00 | QR
21/1/2019 | OSR | Office of State Revenue (OSR) Transformation Program |  | Delivery |  | 2020-06-30T00:00:00 | Commenced Phase 2 of Program with focus on implementing a new secure online portal for all taxpayers, extending machine learning and analytics capability, enhancing data quality, and introducing system capability to improve business processes, and intelligent process automation. 21/1/2019,In total 14 digital initiatives/products have been successfully delivered that incorporate machine learning, the establishment of an enterprise data warehouse, and implementation of an intelligent virtual assistant. 21/1/2019,Overall program is on track. | 2018-11-16T00:00:00 | High | 73548000 |  | Office of State Revenue | 35 | 20468627 |  | G | 4 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 21/1/2019, 21/1/2019,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 73548000 | 2017-08-01T00:00:00 | QR
21/1/2019 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
21/1/2019 | Corporate Services Improvement Program | Integrated Records Information System (IRIS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | In response to an internal audit review of Transport and Main Road's (TMR) Document Management System (DMS) the Integrated Records and Information System (IRIS) project was stood up in 2015. 21/1/2019,IRIS project was reviewed in 2017, and as a result the project budget was decreased from $7,967,972 down to $6,865,000 (plus contingency) of 10%. 21/1/2019, The project leveraged additional functionality requirements by including TMR's Executive Correspondence System (ECS) replacement into scope. Due to recent risks eventuating, the project has had to absorb additional costs originally scheduled to be offset. | 2018-09-30T00:00:00 | High | 7967972 |  | Corporate Division | 45 | 6404800 |  | A | 1 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 6865000 | 2015-07-01T00:00:00 | TMR
21/1/2019 | Corporate Services Improvement Program | Lotus Notes Decommissioning (OP) | 2016-01-31T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project commenced in October 2015 when concept and stage 1 was approved to engage and investigate business findings around the decommission of legacy lotus notes databases. 21/1/2019,In July 2016, three additional stages aligning to three financial years from 2016/17 through to 2018/19 were further approved via a project initiation and business case. 21/1/2019,Stage 2, 2016/17, focused on analysis and stakeholder engagement to form the scope of the project and define functionality and business requirements for individual applications. 21/1/2019,Stage 3, 2017/18, focused on proof of concepts to inform and validate the plan for stage 4 in 2018/19. The project was impacted in 2017/18 by several resourcing issues, including the departure of the original project manager. 21/1/2019,The project is scheduled to complete work and close down by 30 June 2019, with the exception of the migration of files from the departments legacy Document Management System (DMS). The migration of the DMS will align with the Integrated Records and Information System (IRIS) program and should be complete by the end of 2019. | 2018-09-30T00:00:00 | High | 8150000 |  | Corporate Division | 60 | 3490918 |  | A | 2 | Deliver improved information platform functions for effective ICT Strategy Alignment | 8150000 | 2015-11-01T00:00:00 | TMR
21/1/2019 | Corporate Services Improvement Program | Transactional Services Improvement Program 2018-19 | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | Project successfully commenced 1 July 2018. | 2018-09-30T00:00:00 | High | 400000 |  | Corporate Division | 10 | 89604 |  | G | 3 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. | 400000 | 2018-07-01T00:00:00 | TMR
21/1/2019 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | This commenced in July 2016 with delivery being phased in accordance with the development of the business processes. Original expenditure was 1.5M which has been revised to $1.441M on finalisation and approval of the business case. Phase 1 was completed in July 2017 and the schedule was adjusted in June 2017 to enable the delivery of the Phase 2 capability in mid 2019. 21/1/2019, 21/1/2019,The project is currently on track. | 2018-09-30T00:00:00 | High | 1500000 |  | Customer Services, Safety and Regulation Division | 90 | 1018266 |  | G | 4 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal services currently required. | 1441000 | 2016-01-01T00:00:00 | TMR
21/1/2019 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | The project commenced in mid 2015 with an initial exploratory phase, initially scheduled for delivery in mid 2016. Due to the uncertainty of the solution outcome and market capability the project undertook a multi stage market engagement and procurement process. Once the solution had been fully defined, the schedule was extended by 11 months and the budget increased from $2.5M to $4.1M in January 2017. 21/1/2019, 21/1/2019,Development is now complete. A pilot phase has been successfully completed. The project is now conducting final testing and preparing for a full launch. An Exception Report was approved to extend the end date to 31 October 2018 and an addtional $98k which was approved by the CSSR PB on 29 August 2018. The project is on track to be closed by October 2018. 21/1/2019, 21/1/2019, | 2018-09-30T00:00:00 | High | 2500000 |  | Customer Services, Safety and Regulation Division | 96 | 4191537 |  | G | 5 | Implement an online learning and assessment program at the prelearner and/or learner stage, to enhance learning and outcomes for new drivers. | 4274000 | 2015-06-12T00:00:00 | TMR
21/1/2019 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery |  | 2018-06-28T00:00:00 | This commenced in November 2016 with planned completion in mid 2017. Due to an extended procurement process, and the need to include analytical functionality, the schedule was extended 12 months and the budget increased from $300k to $894k in August 2017. The capability was delivered as scheduled in June 2018 and the project is presently finalising closure with formal closure scheduled for August 2018. However, this is taken longer than expected and may require a re-baseline on schedule in the closure report. 21/1/2019,Project will be closed in October 2018. 21/1/2019, | 2018-09-30T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 99 | 1016536 |  | G | 6 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 989237 | 2016-11-01T00:00:00 | TMR
21/1/2019 | Customer Service, Safety and Regulation Program | Customer Flow Mgmt and Reporting System | 2018-06-30T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | Preproject work commenced during FY15/16 with the initiation of the current project commencing in July 2017. The original budget of 300K was rebaselined to 3M once the post-market business case was finalised and approved to proceed in May 2018. 21/1/2019,The project is on track for delivery to occur within FY18/19. | 2018-09-30T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 75 | 1972536 |  | G | 7 | Replacement of the existing statewide network of customer flow management and reporting systems which is currently supplied by QMatic Australia and will be unsupported in 2017. CSB currently have 43 CSCs around the state that use QMatic systems. Replacement of the existing statewide customer flow management and reporting system which is currently supplied by QMatic Australia and will be unsupported in 2017. | 3083000 | 2015-09-01T00:00:00 | TMR
21/1/2019 | Customer Service, Safety and Regulation Program | Call Centre VOIP Upgrade | 2018-06-30T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Project commenced in July 2017. Due to a resourcing issue. Approval was given to amend the implementation date from June 2018 to August 2018. | 2018-09-30T00:00:00 | High | 1140000 |  | Customer Services, Safety and Regulation Division | 99 | 1073628 |  | G | 8 | The Call Centre VOIP Upgrade has commenced to upgrade the VOIP telephony platform within the department. The proposed solution will see a reduction in call costs, a shift in capability to a contemporary solution utilising an existing investment within the department. | 1140000 | 2017-04-01T00:00:00 | TMR
21/1/2019 | Customer Service, Safety and Regulation Program | Smart Licence Card | 2018-08-21T00:00:00 | Delivery |  | 2019-03-31T00:00:00 | Gate 3 investment decision was approved by 24 May ISC. End of contract has been signed. Project are working on delivery. | 2018-09-30T00:00:00 | High | 723000 |  | Customer Services, Safety and Regulation Division | 82 | 1501154 |  | G | 9 | The project is responsible for managing business analysis and requirements specification activities, developing relevant procurement documentation, overseeing the identification and selection of a suitably qualified vendor, facilitating the transfer of contract management responsibilities from Information Technology Branch (ITB) to Transport Regulation Branch (TRB), and managing the complete transition to a new solution before the extended contract expiry date. The estimated cost for the project is $1.68M over three (3) financial years. | 2717000 | 2016-07-01T00:00:00 | TMR
21/1/2019 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The RALPH project commenced in July 2016. Due to vendor software development issues, changes to the schedule and budget were approved in June 2017. The project is currently over schedule and reporting red. The project is working on rebaselining which is expected to be finalised by November 2018. | 2018-09-30T00:00:00 | Medium | 500000 |  | Customer Services, Safety and Regulation Division | 87 | 756494 |  | R | 10 | TMRs current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace the existing application with a contemporary and supportable alternative to assist the department in maintaining its timely updating of fees and charges. | 734000 | 2016-07-01T00:00:00 | TMR
21/1/2019 | Customer Service, Safety and Regulation Program | Vessel Traffic Services (VTS) | 2016-01-05T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | Preproject work commenced in April 2014 with the initiation of the current project commencing in July 2016. The original budget of $15.2M was rebaselined to $36.2M once the post-market business case was finalised and approved to proceed in April 2017. 21/1/2019, 21/1/2019,The project is on track for delivery in mid 2019. | 2018-09-30T00:00:00 | High | 15224694 |  | Customer Services, Safety and Regulation Division | 55 | 6209775 |  | G | 11 | Replacement of TIM and surface picture software for Reef VTS Phase 1 for the replacement of TIM and surface picture software for Reef VTS. | 36228184 | 2014-04-14T00:00:00 | TMR
21/1/2019 | Customer Service, Safety and Regulation Program | Registration and CTP Certificates Online | 2017-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | The Registration and CTP Certificates Online project commenced in May 2017 as two separate initiatives Registration Online and CTP Tax Invoice Online. Due to common system synergies the projects were merged in March 2018 resulting in the closure date being revised in accordance with the CTP component. An Exception Report was approved to extend the end date to 31 December 2018 and an addtional $233k which was approved by the CSSR PB on 29 August 2018. The project is on track for delivery and closure in late 2018. | 2018-09-30T00:00:00 | Medium | 0 |  | Customer Services, Safety and Regulation Division | 67 | 483728 |  | G | 12 | Create an online service for customers to email or print their registration certificate and CTP tax invoices, to provide customers with more convenience, and reduce reliance on paper and post. | 637000 | 2017-05-01T00:00:00 | TMR
21/1/2019 | Customer Service, Safety and Regulation Program | R and L Systems Software Upgrade - Stage 2 | 2018-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | The R and L System Software Upgrade project commenced in July 2017. The original budget of $780K was rebaselined to $1.255M once the post-market business case was finalised and approved to proceed in September 2017. Delivery was completed as scheduled in June 2018. Project was officially closed on 3 September 2018. | 2018-09-30T00:00:00 | Medium | 780000 |  | Customer Services, Safety and Regulation Division | 100 | 1115450 |  | G | 13 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
21/1/2019 | Passenger Transport Technology Program | Single Integrated Network Project (SNIP) | 2018-09-29T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | Software upgrade for TransLink users planned to complete in September. Rollout of the system to SEQ bus service providers to commence in November. Delays in vendor negotations and reduction in scope has triggered an exception report and rebaselining of the project scope, schedule and budget. An updated project plan has been approved by the governance board. | 2018-09-30T00:00:00 | High | 4992243 |  | TransLink Division | 32 | 858604 |  | G | 14 | Enable implementation of performance based contracts for SEQ buses 21/1/2019,Have a system in place that is consistent and integrated across service providers and TransLink 21/1/2019,Reduce or remove inefficiencies and data inaccuracies that occur in the current processes 21/1/2019,Improve transparency of SEQ bus service providers activities and performance 21/1/2019,Improved customer experience through more accurate and reliable SEQ bus service information 21/1/2019,To improve customer experience through more accurate and reliable service information. 21/1/2019,Contributor for achieving Government objectives. | 3637240 | 2017-02-23T00:00:00 | TMR
21/1/2019 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery |  | 2019-08-30T00:00:00 | Original project commenced in April 2016. 21/1/2019,Budget shortfall identified in November 17. 21/1/2019,In March 18 issues in gathering business data and requirements for new functionality identified. 21/1/2019,The STAS project is reporting amber as a result of unforeseen complexities associated with provisioning and transitioning of business supplied data to the new platform. The project is experiencing delays as resolution activities take place to ensure a good customer experience when the project is released to the public. 21/1/2019,The Project Board approved an exception plan in September which will enable products to be completed and released by the end of March 2019. | 2018-09-30T00:00:00 | High | 4166000 |  | TransLink Division | 68 | 5399590 |  | G | 15 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 6459560 | 2016-04-01T00:00:00 | TMR
21/1/2019 | CS | Asset Assessment System | 2016-06-30T00:00:00 | Delivery |  | 2019-02-15T00:00:00 | The project is reviewing requirements and schedule before commencing next stage. | 2018-12-11T00:00:00 | Medium | 1688788 |  | Corporate Services | 82 | 1890702 |  | G | 1 | To improve the reliability and integrity of asset information, the ability to report on asset information by applying best practice asset management principles. | 2179995 | 2014-02-27T00:00:00 | DET
21/1/2019 | CS | Automated Website Provisioning Tool | 2018-12-21T00:00:00 | Delivery |  | 2018-12-17T00:00:00 | The project is tracking to the revised plan approved by the project board. | 2018-12-11T00:00:00 | Medium | 1300000 |  | Corporate Services | 100 | 1115245 |  | G | 2 | To reduce the cost and time required to create new school and corporate websites by developing a tool that provisions new websites from a suite of reusable website templates. | 1242160 | 2017-04-03T00:00:00 | DET
21/1/2019 | CS | Copper Disconnection Management | 2021-06-30T00:00:00 | Delivery |  | 2021-06-30T00:00:00 | The project is tracking to plan. | 2018-12-11T00:00:00 | Low | 2155000 |  | Corporate Services | 25 | 1354658 |  | G | 3 | The project will migrate all copper based services mandated for disconnection to an appropriate replacement technology within the required timeframes specified by nbntm and Telstra ensuring services are not incorrectly disconnected. | 3071000 | 2017-07-03T00:00:00 | DET
21/1/2019 | PPP | Customer Complaints Management System | 2018-12-21T00:00:00 | Delivery |  | 2019-01-31T00:00:00 | The project is tracking to plan. | 2018-12-11T00:00:00 | Medium | 2753000 |  | Policy, Performance and Planning | 93 | 1485757 |  | G | 4 | Improve the management and reporting of customer complaints. | 2753000 | 2017-09-11T00:00:00 | DET
21/1/2019 | PPP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Closed |  | 2018-11-26T00:00:00 | The project completed in the month of November. | 2018-12-11T00:00:00 | High | 700000 |  | Policy, Performance and Planning | 100 | 1498286 |  | G | 5 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
21/1/2019 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery |  | 2018-12-13T00:00:00 | The project is tracking to plan. | 2018-12-11T00:00:00 | High | 659131 |  | Corporate Services | 82 | 583771 |  | G | 6 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DoE FBS SAP future state landscape for the next five years. | 619866 | 2017-01-16T00:00:00 | DET
21/1/2019 | ODG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | The project is tracking to plan. | 2018-12-11T00:00:00 | Low | 632585 |  | Office of the Director-General | 91 | 877369 |  | G | 7 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
21/1/2019 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | The project is tracking to plan. | 2018-12-11T00:00:00 | Critical | 16670000 |  | State Schools | 55 | 12894533 |  | G | 8 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 18115935 | 2015-08-03T00:00:00 | DET
21/1/2019 | ECCE | National Quality Standard Assessment and Rating Data Tool | 2018-12-13T00:00:00 | Delivery |  | 2018-12-17T00:00:00 | The project is tracking to plan. | 2018-12-11T00:00:00 | High | 467900 |  | Early Childhood and Community Engagement | 50 | 346076 |  | G | 9 | To improve the security and functionality of the tool used for the assessment and quality improvement of early childhood education and care centres. | 467900 | 2018-02-22T00:00:00 | DET
21/1/2019 | PPP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project is tracking to plan. | 2018-12-11T00:00:00 | High | 1502300 |  | Policy, Performance and Planning | 100 | 1376797 |  | G | 10 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution. | 1407880 | 2016-03-01T00:00:00 | DET
21/1/2019 | PPP | Online School Data Profile | 2018-06-30T00:00:00 | Delivery |  | 2020-02-28T00:00:00 | The project is tracking to plan. | 2018-12-11T00:00:00 | Low | 1872000 |  | Policy, Performance and Planning | 50 | 759683 |  | G | 11 | Improved data interaction capabilities for stakeholders accessing school data profiles. Improved efficiency in production and distribution of information contained in school data profiles. | 1700000 | 2017-10-02T00:00:00 | DET
21/1/2019 | SS | Pre-Departure Orientation Information Mobile Application | 2017-12-31T00:00:00 | Delivery |  | 2019-08-13T00:00:00 | The project is tracking to plan. | 2018-12-11T00:00:00 | Medium | 520000 |  | State Schools | 56 | 211784 |  | G | 12 | Improved service offerings and improved user experience in provision of information to support international students. | 832000 | 2016-02-11T00:00:00 | DET
21/1/2019 | PPP | Redevelopment of the Policy and Procedure Register | 2018-03-30T00:00:00 | Delivery |  | 2018-12-14T00:00:00 | The project is being closely monitored for cost, quality and schedule. | 2018-12-11T00:00:00 | Medium | 1015000 |  | Policy, Performance and Planning | 76 | 1160082 |  | A | 13 | The project will deliver a contemporary online repository of departmental policies and procedures for access by staff, students and the general public. The objectives of the project are to deliver a consistent user experience for customers, regardless of who they are, where they work, and what they may be looking for; a single point of truth, providing access to departmental policies and procedures; and platform to publish policy and procedures once, with multiple links to additional information where appropriate; and authoritative content that meets quality standards for publication, enabling staff and stakeholders to make good decisions. | 1409191 | 2016-10-13T00:00:00 | DET
21/1/2019 | CS | SABA Platform Upgrade | 2017-11-09T00:00:00 | Delivery |  | 2019-02-12T00:00:00 | The project is tracking to plan. | 2018-12-11T00:00:00 | Medium | 1791556 |  | Corporate Services | 89 | 2107966 |  | G | 14 | The objective of the project is to replace the existing system, currently hosted on obsolete technology, which is at end-of-service-life. In its current state, the system represents a significant business risk, due to the likelihood of increased system failures, further leading to ongoing business outages and increased maintenance and support costs. | 2303846 | 2017-08-01T00:00:00 | DET
21/1/2019 | SS | Trial of Platform for Virtual Academies | 2017-10-02T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | The project is tracking to plan. | 2018-12-11T00:00:00 | High | 151641 |  | State Schools | 98 | 168322 |  | G | 15 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage; safe and secure like-minded student virtual communities; and strategic partnerships with university, industry and business. 21/1/2019, 21/1/2019, | 227850 | 2016-06-21T00:00:00 | DET
21/1/2019 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project is tracking to plan. | 2018-12-11T00:00:00 | High | 41000000 |  | Corporate Services | 94 | 36154059 |  | G | 16 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
21/1/2019 | OIR | Investigations Management System | 2018-12-14T00:00:00 | Delivery |  | 2018-12-14T00:00:00 | The project is tracking to plan. | 2018-12-10T00:00:00 | Critical | 461742 |  | Office Of Industrial Relations | 38 | 337607 |  | G | 17 | This project will deliver a case management solution for the OIR Investigations unit. | 644711 | 2017-01-07T00:00:00 | DET
21/1/2019 | OIR | Renewal and Photographic Licensing System (RAPS) Assessor Portal | 2018-07-13T00:00:00 | Closed |  | 2018-11-06T00:00:00 | The project completed in the month of November. | 2018-12-10T00:00:00 | High | 766467 |  | Office Of Industrial Relations | 100 | 948326 |  | G | 18 | The Assessor Portal project will deliver an improved online services for high risk work licensing accredited assessors, registered training organisations and licensing and advisory services. Currently accredited assessors must use a combination of cumbersome paper based processes, smart forms, and an online service that is difficult to use. | 948326 | 2016-12-14T00:00:00 | DET
21/1/2019 | [20 empty] | INVERSTMENT INFO
21/1/2019 | ICRM | Integrated Customer and Revenue Management (ICRM) | 2021-03-30T00:00:00 | Delivery |  | 2021-03-30T00:00:00 | Progress is on track and within project tolerances. 21/1/2019, 21/1/2019,November 2018 - The project is continuing as planned and is on schedule. Update to the planned end date made to match approved business case not previously reported. 21/1/2019,October 2018 - The project is continuing as planned and is on schedule. 21/1/2019,August 2018 - This project is reporting for the first time and is progressing as planned. | 2018-12-10T00:00:00 | High | 24511345 |  | DNRM Finance | 12 | 5102418 |  | G | 1 | Improvements to the way the agency handles revenue collection: 21/1/2019, 21/1/2019,* selection of a modern, enterprise-class, integrated customer and revenue management solution 21/1/2019,* implementation and deployment of the solution to replace the use of the current at-risk receipting systems. | 24511345 | 2017-01-01T00:00:00 | DNRM
21/1/2019 | QWSR | Dam Safety Regulation Solution | 2016-10-30T00:00:00 | Closed |  | 2019-02-28T00:00:00 | Deliverables have been achieved and project closure activities are complete. 21/1/2019, 21/1/2019,November 2018 - The project is continuing as planned and remains on schedule. 21/1/2019,October 2018 - An extension to the approved end date has been endorsed, with no affect on cost. 21/1/2019,September 2018 - Documentation is being finalised; the project remains within accepted tolerances. 21/1/2019,August 2018 - A change request has been approved altering the planned end date to enable completion of end project activities. 21/1/2019,July 2018 - All deliverables have been achieved. Project closure activities are currently under way. 21/1/2019,June 2018 - A change request has been approved altering the planned end date to remediate technical difficulties that have been experienced in the move to production. 21/1/2019,May 2018 - The project is continuing within timeframe tolerance, and is expected to close prior to the end of May 2018. 21/1/2019,March 2018 - The project is continuing as planned. 21/1/2019,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 21/1/2019,August 2017 - Approved extension of timeframe. 21/1/2019,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 21/1/2019,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 21/1/2019,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 21/1/2019,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 21/1/2019,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2018-12-14T00:00:00 | High | 1390000 |  | Queensland Water Supply Regulator | 100 | 1385060 |  | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 21/1/2019, 21/1/2019,* support compliance with legislation 21/1/2019,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 21/1/2019,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 21/1/2019,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. | 1390000 | 2012-04-01T00:00:00 | DNRM
21/1/2019 | Natural Resources | Land Condition Assessment Tool | 2018-04-30T00:00:00 | Paused |  | 2019-01-25T00:00:00 | The project has paused following advice of a change in the vendor's capacity to provide all of the services specified under the contract arrangements. 21/1/2019, 21/1/2019,November 2018 - The project is currently Amber due to some features being incomplete. 21/1/2019,October 2018 - An extension to the approved end date has been endorsed, with no impact on costs. Note the change to the percentage complete, aligning with deliverable achieved thus far. 21/1/2019,September 2018 - An extension to the project end date has been approved to accommodate vendor resource constraints. There is no impact to cost. Discussions are under way with the vendor to ensure resourcing constraints will not impact quality, or further delay delivery. 21/1/2019,August 2018 - The project is continuing as planned, tracking within tolerances for time, cost and quality. 21/1/2019,June 2018 - A change request has been approved altering the planned end date and budget to allow for resolution of unforeseen complexities in deliverables. 21/1/2019,May 2018 - The project timeframe is currently being monitored, with action under way to return it to Green. 21/1/2019,April 2018 - This project is reporting for the first time and is progressing as planned. | 2018-12-20T00:00:00 | Medium | 414000 |  | Operations Support | 70 | 161671 |  | A | 3 | Implement a solution for government, industry and other stakeholders to objectively and consistently assess land conditions, including development of a pictogram-based mobile web application and a data collection tool. | 479000 | 2017-01-12T00:00:00 | DNRM
21/1/2019 | CWeHR | Coal Workers eHealth Records Project | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | A review of scope is currently under way. 21/1/2019, 21/1/2019,November 2018 - The project is progressing with a small adjustment to the expenditure due to timing of accruals. 21/1/2019,October 2018 - The project is continuing as planned, tracking within project tolerances. 21/1/2019,August 2018 - This project is reporting for the first time and is progressing as planned. Note finances reported represent Stage 0 and Stage 1. 21/1/2019, | 2018-12-07T00:00:00 | High | 3894285 |  | Occupational Health and Hygiene - Resources Safety and Health | 5 | 1296193 |  | A | 4 | Improvement in data management and surveillance for coal mine worker health assessments: 21/1/2019, 21/1/2019,* new customer digital interface 21/1/2019,* improved health assessment outcomes through improved access to longitudinal health records 21/1/2019,* enabled industry-wide health surveillance through electronic storage and access to health records 21/1/2019,* improved data management using appropriate health management systems and alignment with health record management requirements. | 3894285 | 2017-03-23T00:00:00 | DNRM
21/1/2019 | SO | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery |  | 2019-03-29T00:00:00 | The project is progressing well and is tracking within tolerances. 21/1/2019, 21/1/2019,November 2018 - The project is progressing as planned. 21/1/2019,August 2018 - The project is continuing as planned, tracking within tolerances for time, cost and quality. 21/1/2019,February 2018 - A change request was approved to alter the scope and associated percentage complete, time-frame and costs. 21/1/2019,December 2017 - Awaiting confirmation of project closure; project is still operating within approved time-frame tolerance. 21/1/2019,November 2017 - A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 21/1/2019,October 2017 - The project is continuing as planned. 21/1/2019,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2018-12-07T00:00:00 | High | 563000 |  | SIMTARS (Safety In Mines Testing and Research Station) | 84 | 935190 |  | G | 5 | The development and delivery of a (replacement) modern and robust Safegas solution: 21/1/2019, 21/1/2019,* risk reduction increasing capability to manage the volume of queries, transactions and data 21/1/2019,* decrease database corruption related to incidents. | 1170000 | 2017-01-25T00:00:00 | DNRM
21/1/2019 | DPC | Performance Information Management System (PIMS) Dynamics 365 upgrade and relocation | 2018-10-30T00:00:00 | Closed |  | 2018-10-30T00:00:00 | The project has now been delivered. The new system is live and has been rolled out across departments. | 2018-12-06T00:00:00 | High | 240494 |  | Premier and Cabinet | 100 | 240494 |  | G | 1 | To upgrade the existing PIMS solution from the current 2013 version to Microsoft Dynamics 365 and move the system to Microsoft Online. | 240494 | 2018-05-01T00:00:00 | DPC
21/1/2019 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
21/1/2019 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 21/1/2019,* Move operational accountability and responsibility for print and imaging devices to the service provider 21/1/2019,* Reduce print and imaging costs 21/1/2019,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
21/1/2019 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
21/1/2019 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
21/1/2019 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 21/1/2019, 21/1/2019,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
21/1/2019 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
21/1/2019 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 21/1/2019, 21/1/2019,* reduce operating costs 21/1/2019,* increase capacity 21/1/2019,* improve customer experience 21/1/2019,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
21/1/2019 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
21/1/2019 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 21/1/2019, 21/1/2019, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
21/1/2019 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 21/1/2019, 21/1/2019,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
21/1/2019 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
21/1/2019 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 21/1/2019, 21/1/2019,November 2017 - Actual cost to date corrected due to input error. 21/1/2019, 21/1/2019,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 21/1/2019, | 2017-12-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 57 | 733941 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
21/1/2019 | CSS | Wildlife Platform | 2018-07-31T00:00:00 | Delivery |  | 2019-07-31T00:00:00 | The project is progressing as planned. 21/1/2019, 21/1/2019,November 2018 - Project has been moved into delivery and is reporting for the first time. | 2018-11-26T00:00:00 | Medium | 395000 |  | Conservation and Sustainability Services | 4 | 14616 |  | G | 1 | Implement a platform that will increase the quality and availability of information related to wildlife sightings, in particular crocodiles. This will allow transparency and support for the public to better manage their own safety, whilst providing a central analytics and reporting resource to improve strategic analysis, planning and management. | 395000 | 2018-07-31T00:00:00 | EHP
21/1/2019 | EPP | Queensland Waste Disposal Levy System | 2018-07-10T00:00:00 | Delivery |  | 2019-08-01T00:00:00 | A small extension to the planned end date has been approved to allow for integration with the financial management system. 21/1/2019, 21/1/2019,November 2018 - The project is progressing as planned. 21/1/2019,September 2018 - The project has been approved to commence delivery and is publishing for the first time. | 2018-12-19T00:00:00 | Critical | 2248000 |  | Environmental Policy and Planning | 70 | 710361 |  | G | 2 | Implement a solution to meet new legislative arrangements for a waste disposal levy, to effectively and efficiently enable: 21/1/2019, 21/1/2019,* site operators to accurately record data 21/1/2019,* reconciliation of waste data and levy liabilities 21/1/2019,* timely access to, and interrogation of, large datasets. | 2248000 | 2018-07-10T00:00:00 | EHP
21/1/2019 | ESR | Connect Workflow Remediation | 2018-10-24T00:00:00 | Initiate |  | 2019-01-31T00:00:00 | The project is investigating options and is reporting for the first time. | 2018-12-20T00:00:00 | Medium | 0 |  | Environmental Services and Regulation | 0 | 0 |  | G | 3 | Undertake system enhancements, improvements to workflow and implementation of prioritised support backlog as identified by the Connect Taskforce Report. | 0 | 2018-10-24T00:00:00 | EHP
21/1/2019 | ESR | User Experience Improvement and Rebranding | 2018-10-30T00:00:00 | Initiate |  | 2019-05-31T00:00:00 | The project is investigating options and is reporting for the first time. | 2018-12-20T00:00:00 | Medium | 0 |  | Environmental Services and Regulation | 0 | 0 |  | G | 4 | Improve usability of the Connect system through redesign of the user interface and delivery via an enterprise platform. | 0 | 2018-10-30T00:00:00 | EHP
21/1/2019 | QPWS | Augmented Ranger Mobile Application | 2018-02-01T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | Project milestones are on target to be met. 21/1/2019, 21/1/2019,November 2018 - The project is progressing as planned. 21/1/2019,August 2018 - The project has been approved to commence delivery and is publishing for the first time. | 2018-12-03T00:00:00 | Low | 240000 |  | Queensland Parks and Wildlife Service | 30 | 125660 |  | G | 5 | Develop a mobile, optimised solution that uses Augmented Reality to: 21/1/2019, 21/1/2019,* enrich visitors? on-park engagement, experiences and understanding of cultural, historical and ecological points of interests specific to the location 21/1/2019,* provide opportunities for ranger-visitor communications 21/1/2019,* aid collection of real-time visitor data. | 240000 | 2018-02-01T00:00:00 | EHP
21/1/2019 | QPWS | Integrated Permitting System Project | 2019-02-28T00:00:00 | Initiate |  | 2020-04-03T00:00:00 | The project is investigating options and is reporting for the first time. | 2018-12-19T00:00:00 | High | 0 |  | Queensland Parks and Wildlife Service | 15 | 0 |  | G | 6 | Leverage and implement a solution to manage the lifecycle of permit and agreement applications from lodgement, assessment and approval through to completion, return of operations, and reporting for compliance monitoring. | 0 | 2017-07-03T00:00:00 | EHP
21/1/2019 | CSS | Native Animal Licensing Framework System | 2020-01-01T00:00:00 | Initiate |  | 2020-01-01T00:00:00 | The project is investigating options and is reporting for the first time. | 2018-12-19T00:00:00 | Low | 0 |  | Conservation and Sustainability Services | 0 | 0 |  | G | 7 | An enterprise solution is required for the management of Native Animal Licencing. This solution will: 21/1/2019, 21/1/2019,* streamline the issuing and management of wildlife licences 21/1/2019,* enable licence holders to digitally share information about their animals 21/1/2019,* improve data availability 21/1/2019,* enable proactive administrative support 21/1/2019,* facilitate compliance and enforcement practices. | 0 | 2018-10-05T00:00:00 | EHP
21/1/2019 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP
24/7/2018 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-05-31T00:00:00 | High | 5600000 |  | eHealth Queensland | 24 | 1238121 |  | G | 1 | This project aims to establish a robust, highly available and secure contemporary platform that has the capability to support the agile eHealth Strategy. | 5600000 | 2017-07-03T00:00:00 | DH
24/7/2018 | HSQ | Pathology and Forensic Laboratory System Rehosting Project | 2018-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | May: This project was previously known as the 'AUSLAB Rehosting Project'. This project has now returned to green, after receiving governance approval to extend the schedule and budget. 24/7/2018, 24/7/2018,April: Delays have been experienced in project deliverables, with refinements needed to the technical implementation, impacting the project's schedule. | 2018-06-06T00:00:00 | High | 1691324 |  | Health Support Queensland | 41 | 2134000 |  | G | 2 | Delivery of a replacement hardware and visualisation solution for the AUSLAB and AUSCARE systems that will achieve improved resiliency of the architecture, updated operating system and inclusion of virtualisation. AUSLAB and AUSCARE are critical to support laboratories and patient clinical care. | 2963000 | 2017-08-28T00:00:00 | DH
24/7/2018 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2016-08-01T00:00:00 | Delivery |  | 2018-07-30T00:00:00 |  | 2018-06-13T00:00:00 | High | 1858668 |  | Metro North | 90 | 1372609 |  | G | 3 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 24/7/2018, 24/7/2018,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Women 24/7/2018,92s Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 24/7/2018, 24/7/2018,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 2482431 | 2015-06-01T00:00:00 | DH
24/7/2018 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-05-31T00:00:00 | High | 11180394 |  | eHealth Queensland | 15 | 493776 |  | G | 4 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 24/7/2018,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work. 24/7/2018,a0 Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 11180394 | 2017-07-03T00:00:00 | DH
24/7/2018 | MNHHS | Business Intelligence - Enterprise Data Warehouse | 2018-06-29T00:00:00 | Delivery |  | 2018-06-28T00:00:00 | March: Project funding is currently being revised in line with proposed scope for an upcoming stage. | 2018-06-13T00:00:00 | High | 2114991 |  | Metro North | 75 | 1549544 |  | G | 5 | This project will introduce Business Intelligence and Data Warehousing capabilities at MNHHS. The project will deliver BI & DW technical skills, system infrastructure, data automation tools, a pilot dataset, data governance processes and quality control framework at MNHHS. Metro North Finance and MNIT are jointly managing the project. | 1480182 | 2016-11-01T00:00:00 | DH
24/7/2018 | EHQ | File Services Migration | 2017-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-05-31T00:00:00 | High | 3400000 |  | eHealth Queensland | 30 | 3429611 |  | G | 17 | The purpose of this investment is to adopt a contemporary, simplified file management solution for Queensland Health that enables a more cohesive customer experience. | 9907925 | 2016-08-01T00:00:00 | DH
24/7/2018 | MNHHS | Central Patient Monitoring Equipment Replacement | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 |  | 2018-06-13T00:00:00 | High | 1236416 |  | Metro North | 95 | 631449 |  | G | 6 | Metro North IT has been approached by Metro North Procurement Services (MNPS) to provide ICT advice and guidance into the Central Patient Monitoring Equipment Replacement (CPMER) Project. The Health Technology Equipment Replacement (HTER) program for central monitoring systems is providing funding in financial years 16/18 for physiological monitoring equipment requiring replacement across MNHHS hospital facilities. There is an estimated 312 pieces of equipment, primarily Physiological Monitoring devices, to be replaced under the program across MNHHS hospital facilities. MNHHS implementations are being co-ordinated by MNPS. | 1236416 | 2017-06-28T00:00:00 | DH
24/7/2018 | MNHHS | CISS (Community, Indigenous and Subacute Services) Wi-Fi | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-06-13T00:00:00 | High | 1280798 |  | Metro North | 90 | 1213316 |  | G | 7 | The Community, Indigenous and Subacute Services (CISS) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the internal areas of the prioritised CISS sites. 24/7/2018, 24/7/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1280798 | 2017-07-28T00:00:00 | DH
24/7/2018 | EHQ | Cloud First Project | 2018-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-05-31T00:00:00 | High | 4250000 |  | eHealth Queensland | 95 | 2902223 |  | G | 8 | The Cloud First project will build internal capability and establish processes within Queensland Health to appropriately utilise cloud services on an ongoing basis. | 4126918 | 2017-01-01T00:00:00 | DH
24/7/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Clinical Notes project (release 3.0) | 2018-02-06T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-06-06T00:00:00 | High | 1415000 |  | Clinical Excellence | 95 | 1787747 |  | G | 9 | Upgrading the CIMHA Mental Health Act module to accommodate a re-architecture of the CIMHA clinical notes module is required to deliver benefits to the clinical workforce associated with data entry efficiencies; improved data sharing across digital platforms; patient level information transfer to third parties to support service integration and data mining to support service improvement and research. | 1969365 | 2017-02-20T00:00:00 | DH
24/7/2018 | EHQ | Critical Network Hardware | 2018-02-28T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | February: This project has returned to 'on track'. 24/7/2018, 24/7/2018,January: The project is reporting 'Amber' due to limited resource availability and additional technical requirements, impacting the schedule of the project | 2018-05-31T00:00:00 | High | 8636364 |  | eHealth Queensland | 72 | 7671249 |  | G | 10 | The objectives of the project include: 24/7/2018,a) Mitigate the Department of Health risk that core network switches at QH facilities will no longer be supported by the manufacturer from February 2018. 24/7/2018,b) Invest in the replacement of critical ICT network hardware to maintain current capability and reliability of the data network for 120+ enterprise clinical and business applications and provide the foundation for future capability in the enterprise data centres. 24/7/2018,c) Ensure hardware replacement occurs with minimal impact to business operations in Hospital and Health Services or Corporate offices. 24/7/2018,d) Update logical and physical design and architecture documentation for ease of maintenance and management. | 8371607 | 2017-03-06T00:00:00 | DH
24/7/2018 | EHQ | Digital Collaboration Platform Program | 2018-06-30T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | May: This project has now returned to 'green' with the project's revised schedule being approved. 24/7/2018, 24/7/2018,March: Project activities have continued to be delayed, resulting in this project reporting 'Red'. A project change request has been submitted to the project's governance committee. Successful deployment was recently achieved in Townsville. 24/7/2018, 24/7/2018,January: This project is experiencing delays in pre-migration activities. | 2018-05-31T00:00:00 | High | 11000000 |  | eHealth Queensland | 34 | 12817754 |  | G | 11 | This program will deliver digital collaboration tools for any time, any where, any device including: 24/7/2018, 24/7/2018,95 Email and Archiving 24/7/2018, 24/7/2018,95 Establishment and Collaboration 24/7/2018, 24/7/2018,95 Productivity Suite Enablement | 18467291 | 2015-10-29T00:00:00 | DH
24/7/2018 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate |  | 2017-12-31T00:00:00 | February: The current proposed date of completion is the 31 December 2019, which is subject to project board approval. | 2018-05-31T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 40 | 595733 |  | G | 12 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 4167216 | 2015-12-01T00:00:00 | DH
24/7/2018 | QAS | e-ARF Redevelopment for iPad | 2016-12-31T00:00:00 | Delivery |  | 2017-12-31T00:00:00 | February: Implementation and rollout of the system was completed in late November 2017. The project is currently finalising end of project reporting processes. | 2018-05-31T00:00:00 | High | 2624000 |  | Queensland Ambulance Service | 100 | 1947991 |  | G | 13 | This is an initiative to provide the electronic Ambulance Report Form (eARF) electronic patient care solution via iPads in the field. | 1910813 | 2015-09-02T00:00:00 | DH
24/7/2018 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | May: The project has completed a solution evaluation process, with the project requiring additional time and budget as originally approved. The project is expecting to return to 'green' upon receiving change request approval. 24/7/2018, 24/7/2018,April: Further solution clarification is required, which has impacted on the overall delivery timeframe of this initiative by a number of weeks. | 2018-05-31T00:00:00 | High | 1283000 |  | Chief Health Officer and Prevention | 70 | 126591 |  | A | 14 | Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1283000 | 2017-07-24T00:00:00 | DH
24/7/2018 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery |  | 2018-11-30T00:00:00 |  | 2018-06-13T00:00:00 | High | 4827917 |  | Metro North | 68 | 3404376 |  | G | 15 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (ieMR) program. 24/7/2018, 24/7/2018,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 24/7/2018, 24/7/2018,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. | 4827917 | 2016-07-01T00:00:00 | DH
24/7/2018 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | April: This initiative is now 'in delivery'. | 2018-05-31T00:00:00 | High | 3792744 |  | eHealth Queensland | 15 | 397751 |  | G | 16 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment. 24/7/2018,a0 24/7/2018,a0The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access. 24/7/2018,a0 | 3792744 | 2017-07-05T00:00:00 | DH
24/7/2018 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | April/May: The project is currently reporting 'amber' due to the need to refine business requirements, which may have an impact on the project's schedule. 24/7/2018, 24/7/2018,March: The project has returned to 'green' and is continuing with solution testing activities. 24/7/2018, 24/7/2018,February: The project is currently monitoring several schedule risks impacting a number of configuration activities. | 2018-05-31T00:00:00 | High | 105000000 |  | Metro North | 55 | 60327930 |  | A | 18 | The current Queensland Health Finance, Asset and Materials Maintenance Information System (FAMMIS) system is based on a heavily customised solution which is almost 20 years old and no longer supported. 24/7/2018,The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 24/7/2018, 24/7/2018,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 24/7/2018,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 24/7/2018, 24/7/2018,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
24/7/2018 | EHQ | Follow Me Desktop - Deployment | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-05-31T00:00:00 | High | 3952980 |  | eHealth Queensland | 44 | 1307527 |  | G | 19 | Follow Me Desktop Deployment Project will deliver 24/7/2018,a0the Follow Me Desktop service (FMD) to HHS 24/7/2018,92 in alignment with the Infrastructure Remediation Program (IMP) and ieMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 3676980 | 2017-07-03T00:00:00 | DH
24/7/2018 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-05-31T00:00:00 | High | 3301500 |  | eHealth Queensland | 20 | 908367 |  | G | 20 | Project Purpose: 24/7/2018,a0To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 2490769 | 2017-07-01T00:00:00 | DH
24/7/2018 | EHQ | ICT Regional Wireless Infrastructure Initiatives | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-05-31T00:00:00 | High | 4170000 |  | eHealth Queensland | 85 | 2488466 |  | G | 21 | The Regional eHealth Project (ReHP) is a Wireless LAN and Network Infrastructure uplift project so that sites in Far North Qld are ready to rollout their new eHealth Application. | 3489114 | 2017-07-01T00:00:00 | DH
24/7/2018 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Initiate |  | 2019-06-28T00:00:00 |  | 2018-05-31T00:00:00 | High | 1120000 |  | eHealth Queensland | 50 | 666250 |  | G | 22 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. | 1120000 | 2017-07-05T00:00:00 | DH
24/7/2018 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery |  | 2020-06-26T00:00:00 |  | 2018-05-31T00:00:00 | High | 3215000 |  | eHealth Queensland | 28 | 5066080 |  | G | 23 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 12318334 | 2015-06-22T00:00:00 | DH
24/7/2018 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 1 | 2016-11-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | May: The project has experienced a delay to the completion of Stage 1 due to delays in the governance and assurance process and a change in delivery approach. The project is expecting to complete Stage 1 by the end of August 2018, and is currently seeking final governance approval to confirm additional time and funding to complete this stage. 24/7/2018, 24/7/2018,April: The project has experienced a delay to the completion of Stage 1 due to delays in the governance and assurance process. The project is currently seeking approval to obtain additional time and funding to complete this stage. 24/7/2018, 24/7/2018,February: Approval delays in obtaining additional funding and a slightly extended schedule has impacted the project's schedule, with approvals expected in the upcoming reporting month. | 2018-05-31T00:00:00 | High | 8200000 |  | Health Support Queensland | 91 | 24720000 |  | A | 30 | The IWFM project involves: 24/7/2018,- configuring additional functionality (currently available and licensed, but unutilised) within the existing Rostering and Payroll business solutions 24/7/2018,- partnering with HHSs to develop refined business models and business processes to support the roster-to-pay process 24/7/2018,- undertaking extensive training and change management to support the adoption and effective usage of new functionality and processes | 26909863 | 2016-02-17T00:00:00 | DH
24/7/2018 | EHQ | ieMR Program (Funding Packages 3 and 4) | 2019-04-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | May: The advanced version of the ieMR system has gone live at the Redland Hospital. Additional clinical reporting was also enabled by ieMR in May. 24/7/2018, 24/7/2018,April: The advanced version of the ieMR system has gone live at the Lady Cilento Children's Hospital in April 2018. An upgraded patient scheduling tool has also been deployed to Redland-Wynnum Hospital and Queen Elizabeth II (QEII) Hospital in April, improving inpatient and outpatient scheduling processes. | 2018-05-31T00:00:00 | High | 0 |  | eHealth Queensland | 30 | 0 |  | G | 24 | ieMR will enable improved patient care through the development of a state-wide, authoritative single source of the patient records. 24/7/2018, 24/7/2018,The ieMR will provide clinicians with the ability to: 24/7/2018,* access data that is integrated, accurate and clinically relevant 24/7/2018,* support decision making and better use of information 24/7/2018,* optimise management of patients, resources and provision of services 24/7/2018,* support interaction across a network of providers by making it easier to find providers, transfer information and collaborate with multidisciplinary providers. 24/7/2018,The Program scope (all tranches) is to roll out the ieMR system to 24 hospitals across Queensland. 24/7/2018, 24/7/2018,Please note that financial information for ieMR is Commercial in Confidence | 0 | 2016-11-17T00:00:00 | DH
24/7/2018 | EHQ | Infrastructure Capacity FY 17-18 | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-05-31T00:00:00 | High | 1000000 |  | eHealth Queensland | 75 | 906219 |  | G | 25 | Project Purpose: 24/7/2018,a0 24/7/2018,The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified 24/7/2018,91organic growth 24/7/2018,92 requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. | 2000000 | 2017-07-01T00:00:00 | DH
24/7/2018 | EHQ | Infrastructure Maintenance Program Establishment | 2018-06-29T00:00:00 | Delivery |  | 2022-06-30T00:00:00 | March: This initiative has been refocused to the establishment phase of the Infrastructure Maintenance Program, and as such the % complete and original end date have been updated to reflect this phase of the program. The latest approved end date will be updated in a following reporting month. | 2018-05-31T00:00:00 | High | 1161415 |  | eHealth Queensland | 75 | 781963 |  | G | 26 | The Infrastructure Maintenance Program (IMP) 24/7/2018,a0will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 24/7/2018,The scope includes: 24/7/2018,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 24/7/2018,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and 24/7/2018,a0 24/7/2018,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1392326 | 2017-07-03T00:00:00 | DH
24/7/2018 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery |  | 2022-06-30T00:00:00 |  | 2018-06-05T00:00:00 | High | 14673739 |  | Clinical Excellence | 18 | 2101501 |  | G | 27 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 24/7/2018,The ongoing program of work aims to continue and build upon existing functionality by: 24/7/2018, 24/7/2018,95 Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 24/7/2018, 24/7/2018,95 Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 24/7/2018, 24/7/2018,95 Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 24/7/2018, 24/7/2018,95 Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 24/7/2018, 24/7/2018,95 Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
24/7/2018 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate |  | 2022-12-21T00:00:00 |  | 2018-05-31T00:00:00 | High | 6300000 |  | Queensland Ambulance Service | 22 | 521870 |  | G | 28 | Phased delivery of a system supporting QAS business intelligence. | 6300000 | 2017-01-03T00:00:00 | DH
24/7/2018 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 |  | 2018-05-31T00:00:00 | High | 33827000 |  | Clinical Excellence | 30 | 14639367 |  | G | 29 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 39408218 | 2017-03-01T00:00:00 | DH
24/7/2018 | EHQ | Patient Administration System (PAS) Replacement - Business Case Development Project | 2017-06-30T00:00:00 | Initiate |  | 2019-03-29T00:00:00 |  | 2018-05-31T00:00:00 | High | 3850000 |  | eHealth Queensland | 64 | 4808523 |  | G | 43 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients 24/7/2018,92 journeys, and ensure that accurate information about our patients is readily available when and where required. 24/7/2018, 24/7/2018,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 24/7/2018, 24/7/2018,95 support for patient engagement 24/7/2018, 24/7/2018,95 integrated care 24/7/2018, 24/7/2018,95 clinical research 24/7/2018, 24/7/2018,95 population health (for patients using public health services) 24/7/2018, 24/7/2018,95 performance transparency 24/7/2018, 24/7/2018,95 resource planning. | 11890865 | 2015-11-01T00:00:00 | DH
24/7/2018 | EHQ | Interoperability Project | 2016-04-29T00:00:00 | Delivery |  | 2019-09-29T00:00:00 |  | 2018-05-31T00:00:00 | High | 23850000 |  | eHealth Queensland | 29 | 15226083 |  | G | 31 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 24/7/2018,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 24/7/2018,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 24/7/2018, | 39189509 | 2015-02-01T00:00:00 | DH
24/7/2018 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Delivery |  | 2020-12-21T00:00:00 |  | 2018-05-31T00:00:00 | High | 64000000 |  | Health Support Queensland | 49 | 18775478 |  | G | 32 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 24/7/2018,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. | 64000000 | 2015-08-28T00:00:00 | DH
24/7/2018 | MNHHS | Learning and Performance Management Project | 2017-06-30T00:00:00 | Delivery |  | 2018-11-26T00:00:00 |  | 2018-06-13T00:00:00 | High | 1178190 |  | Metro North | 90 | 1172129 |  | G | 33 | Implement an integrated Learning Management and Performance Management system with the capability to deliver online learning and training content, facilitate performance development and maintain centralised records for reporting purposes. | 1178190 | 2016-07-11T00:00:00 | DH
24/7/2018 | GCHHS | Medical Imaging Informatics Solution (MIIS) Risk Mitigation | 2018-12-31T00:00:00 | Delivery |  | 2019-12-31T00:00:00 |  | 2018-06-12T00:00:00 | High | 5000000 |  | Gold Coast | 20 | 2132000 |  | G | 34 | The Medical Imaging Informatics Solution (MIIS) Risk Mitigation project has identified an Imaging solution which will address the risks and opportunities described in the Case for Change including the mitigation of patient safety risks, increased efficiency and productivity, improvi.ng medical imaging billing revenue collection and cash flow. The solution has user endorsement from radiologists and clinicians and will be specifically configured to meet GCHHS 24/7/2018,92s needs. | 12800000 | 2017-04-03T00:00:00 | DH
24/7/2018 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery |  | 2018-11-30T00:00:00 |  | 2018-06-13T00:00:00 | High | 4030460 |  | Metro North | 70 | 3010873 |  | G | 35 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 24/7/2018, 24/7/2018,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 24/7/2018, 24/7/2018,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
24/7/2018 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery |  | 2017-12-31T00:00:00 | May: This project has returned to 'green', with the project's schedule and budget being monitored by the project's governance committee. 24/7/2018, 24/7/2018,April: The project is continuing to report 'Red' due to continued delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-06-13T00:00:00 | High | 6299780 |  | Metro North | 75 | 6885588 |  | G | 36 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 6299780 | 2014-06-01T00:00:00 | DH
24/7/2018 | EHQ | Metro South and East Queensland ICT Infrastructure Replacement Initiative | 2018-06-29T00:00:00 | Delivery |  | 2019-02-28T00:00:00 |  | 2018-05-31T00:00:00 | High | 4160449 |  | eHealth Queensland | 65 | 1376731 |  | G | 37 | Will replace or uplift out of date end of life ICT assets. | 3632112 | 2017-07-01T00:00:00 | DH
24/7/2018 | EHQ | Metro South East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-04-29T00:00:00 |  | 2018-05-31T00:00:00 | High | 2182844 |  | eHealth Queensland | 52 | 547892 |  | G | 38 | Will replace or uplift out of date end of life ICT assets. | 2182843 | 2017-07-01T00:00:00 | DH
24/7/2018 | EHQ | Mobile Application System for Bring Your Own Device | 2018-06-30T00:00:00 | Delivery |  | 2018-08-24T00:00:00 | May: This project is now reporting 'red'. Governance pathways and approvals have impacted on the project's overall schedule. The project is progressing with a change request to update the project's schedule and deliverables, which will return the project to 'green' upon approval. | 2018-05-31T00:00:00 | High | 1639698 |  | eHealth Queensland | 80 | 1329975 |  | R | 39 | This project leverages the investment of the previous Bring-Your-Own-Device (BYOD) 24/7/2018,a0projects to extend the capability of device mobility by building the foundations of a Mobile Application Ecosystem - the processes, products and services to enable the managed development of low/no code applications by Health and Hospital Services (HHS). 24/7/2018,a0 This project will also complete the deployment of BYOD laptops and provide recommendations on how cost savings can be made by the organisation around Corporate devices and data plans. 24/7/2018,a0 | 1538302 | 2017-07-01T00:00:00 | DH
24/7/2018 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery |  | 2018-12-19T00:00:00 | May: This project has now returned to 'green' with the project's revised schedule being approved. 24/7/2018, 24/7/2018,April: This project is experiencing delays in pre-migration activities, delays experienced in another dependent project, and requires additional resources. Further finances are required, with the schedule and finance issues being managed via the project's governance committee. 24/7/2018, 24/7/2018,January: This project is experiencing delays in pre-migration activities and delays experienced in another dependent project. | 2018-05-31T00:00:00 | High | 14100000 |  | eHealth Queensland | 52 | 19207406 |  | G | 40 | A managed operating environment means that everyone within the organisation is running a clean, basic operating system with centralised update management. This includes upgrades of all PC operating systems, preparing QH applications for running on recent operating system environments, and Infrastructure remediation activities to ensure the deployment tools are sufficient and ready for production. | 27427900 | 2016-05-12T00:00:00 | DH
24/7/2018 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Delivery |  | 2018-06-30T00:00:00 |  | 2018-05-31T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 90 | 825493 |  | G | 41 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1744000 | 2015-10-01T00:00:00 | DH
24/7/2018 | CHOPD | Notifiable Conditions System Replacement | 2019-06-29T00:00:00 | Delivery |  | 2020-02-28T00:00:00 |  | 2018-05-31T00:00:00 | High | 12750000 |  | Chief Health Officer and Prevention | 40 | 2638155 |  | G | 42 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 24/7/2018,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
24/7/2018 | MNHHS | Picture Archiving and Communication System (PACS) | 2017-09-29T00:00:00 | Delivery |  | 2017-12-31T00:00:00 | May: This project has returned to 'green', with the project's schedule and budget being monitored by the project's governance committee. 24/7/2018, 24/7/2018,April: The project is continuing to report 'Red' due to continued delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-06-13T00:00:00 | High | 3114694 |  | Metro North | 65 | 3365354 |  | G | 44 | Procure and implement a contemporary Picture Archiving and Communication (PACS) system and functionality that will ensure improved service delivery for the MNHHS Medical Imaging Departments (and other PACS users) through replacement of RBWH PACS ensuring that it is scalable and able to meet the ongoing needs of Metro North Hospital and Health Service. | 3656297 | 2016-07-11T00:00:00 | DH
24/7/2018 | CSD | Practice Management Enterprise Solution | 2018-11-01T00:00:00 | Delivery |  | 2019-01-31T00:00:00 |  | 2018-06-05T00:00:00 | High | 1470000 |  | Corporate Services | 59 | 1243134 |  | G | 45 | The main practice management software used by HHSs to conduct private practice services and billing activities is being replaced. The initiative will procure and implement "like for like" functionality enterprise solution for participating HHSs (15 in total). | 2961432 | 2017-08-01T00:00:00 | DH
24/7/2018 | EHQ | Project, Program and Portfolio Management Application | 2018-03-31T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | May: This project has now returned to 'green' with the project's revised schedule being approved. 24/7/2018, 24/7/2018,April: This project is now reporting 'amber' due to re-aligning the project's schedule and finances to meet changing organisational requirements. The project has submitted | 2018-05-31T00:00:00 | High | 1344177 |  | eHealth Queensland | 30 | 547330 |  | G | 46 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 24/7/2018, | 1473632 | 2017-05-02T00:00:00 | DH
24/7/2018 | CED | Queensland Integrated Safety Information Project (QISIP) / Risk Management | 2017-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 |  | 2018-06-01T00:00:00 | High | 4333120 |  | Clinical Excellence | 98 | 8306493 |  | G | 47 | This initiative will source a state wide system to replace existing enterprise risk management systems to support patient and staff incident reporting, feedback, case management and risk management processes. | 16273520 | 2013-01-25T00:00:00 | DH
24/7/2018 | EHQ | Queensland State-wide ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-05-31T00:00:00 | High | 3246247 |  | eHealth Queensland | 60 | 1913750 |  | G | 48 | Will replace or uplift out of date end of life ICT assets. | 3246247 | 2017-07-01T00:00:00 | DH
24/7/2018 | EHQ | Queensland State-wide ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-05-31T00:00:00 | High | 3283431 |  | eHealth Queensland | 72 | 2240560 |  | G | 49 | Will replace or uplift out of date end of life ICT assets. | 3282431 | 2017-07-01T00:00:00 | DH
24/7/2018 | MNHHS | Quick Flow Project | 2019-02-01T00:00:00 | Initiate |  | 2019-06-30T00:00:00 |  | 2018-06-13T00:00:00 | High | 6408600 |  | Metro North | 59 | 1363326 |  | G | 50 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 24/7/2018,The key objectives of the project are to: 24/7/2018, 24/7/2018,95 Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 24/7/2018, 24/7/2018,95 Improve the outpatient experience across MNHSS facilities and community services 24/7/2018, 24/7/2018,95 Improve clinic resource utilisation 24/7/2018, 24/7/2018,95 Increase the efficiency of clinical and administrative processes 24/7/2018, 24/7/2018,95 Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
24/7/2018 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Initiate |  | 2019-12-31T00:00:00 |  | 2018-06-06T00:00:00 | High | 34950000 |  | Cairns and Hinterland | 63 | 11794856 |  | G | 51 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patient 24/7/2018,92s home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
24/7/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-02-28T00:00:00 |  | 2018-05-31T00:00:00 | High | 4260336 |  | eHealth Queensland | 58 | 1142140 |  | G | 52 | Will replace or uplift out of date end of life ICT assets. | 4260336 | 2017-07-01T00:00:00 | DH
24/7/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-05-31T00:00:00 | High | 2150147 |  | eHealth Queensland | 65 | 946196 |  | G | 53 | Will replace or uplift out of date end of life ICT assets. | 2678483 | 2017-07-01T00:00:00 | DH
24/7/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-05-31T00:00:00 | High | 1651750 |  | eHealth Queensland | 52 | 677607 |  | G | 54 | Will replace or uplift out of date end of life ICT assets. | 1651750 | 2017-07-01T00:00:00 | DH
24/7/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-05-31T00:00:00 | High | 4245973 |  | eHealth Queensland | 90 | 2165912 |  | G | 55 | Will replace or uplift out of date end of life ICT assets. | 4245973 | 2017-07-01T00:00:00 | DH
24/7/2018 | EHQ | Service Delivery Excellence Project (SDEP) | 2018-02-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | March: The latest approved end date and percentage complete has been updated. 24/7/2018, 24/7/2018,February: The latest approved end date for this initiative will be updated pending advise from the project. | 2018-05-31T00:00:00 | High | 4822000 |  | eHealth Queensland | 25 | 887902 |  | G | 56 | The Service Delivery Excellence Project (SDEP) aims to improve the service delivery functions of eHealth Queensland to help the organisation achieve its Customers and services Foundation and Shared Goal: 24/7/2018,Enhance value for customers by streamlining end to end services, processes and delivery models so that we can provide an exceptional customer experience. 24/7/2018,Stage 1 has the primary objective of delivering the Project Initiation Document (PID) for the Service Delivery Excellence Project (SDEP) Stage 2. | 4821750 | 2017-10-16T00:00:00 | DH
24/7/2018 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Delivery |  | 2020-09-30T00:00:00 |  | 2018-05-31T00:00:00 | High | 10500000 |  | eHealth Queensland | 14 | 2865478 |  | G | 57 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 10500000 | 2017-07-03T00:00:00 | DH
24/7/2018 | MNHHS | Royal Brisbane and Women's Hospital Wi-Fi | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-06-13T00:00:00 | High | 6000000 |  | Metro North | 20 | 3038400 |  | G | 58 | The RBWH Wi-Fi Project will provide an uplift and renewal to the latest Queensland Health (QH) standard for wireless local area network (WLAN) coverage within the internal areas of prioritised RBWH buildings in order to support digital healthcare. 24/7/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for the RBWH in the near future. | 5000000 | 2017-10-22T00:00:00 | DH
24/7/2018 | EHQ | Storage Asset Replacement | 2018-06-29T00:00:00 | Delivery |  | 2018-08-31T00:00:00 |  | 2018-05-31T00:00:00 | High | 1671556 |  | eHealth Queensland | 40 | 287969 |  | G | 59 | The Storage Asset Replacement (SAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the SAR and Backup Asset Replacement (BAR) projects. 24/7/2018,The SAR project seeks to outline architecture for storage that will provide a cost effective, scalable and fit for purpose environment for the future of storage services within Queensland Health. 24/7/2018,a0 Utilising space saving technologies which will enable further cost savings and reduce the requirement for capacity expansion in the short to medium term. | 1659988 | 2017-07-03T00:00:00 | DH
24/7/2018 | EHQ | Telehealth Asset Replacement FY 17-18 | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-05-31T00:00:00 | High | 1960000 |  | eHealth Queensland | 92 | 1864946 |  | G | 60 | Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector 24/7/2018,a0 24/7/2018,and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. 24/7/2018,The Department of Health defines Telehealth as: 24/7/2018, 24/7/2018,95Live, audio and/or video inter-active link for clinical consultations and educational purposes 24/7/2018, 24/7/2018,95Store and forward Telehealth - this model can involve digital images, video, audio and clinical data being captured ("stored") on the client computer; then at a convenient time transmitted securely ("forwarded") 24/7/2018,a0 to a clinic at another location where they are studied by relevant specialists 24/7/2018, 24/7/2018,95Teleradiology for remote reporting and clinical advice for diagnostic images 24/7/2018, 24/7/2018,95Telehealth services and equipment to monitor people 24/7/2018,92s health in their home. 24/7/2018,Benefits of Telehealth 24/7/2018, 24/7/2018,95Improve patient access to health care 24/7/2018, 24/7/2018,95Reduce travel and inconvenience for patients, families, carers and health professionals 24/7/2018, 24/7/2018,95Provide health professionals with access to peer support and education. 24/7/2018,The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. 24/7/2018,a0 24/7/2018,The priority is to replace those end-of-life assets which pose the greatest risk to effective health service delivery. | 1957626 | 2017-07-03T00:00:00 | DH
24/7/2018 | MNHHS | The Prince Charles Hospital (TPCH) Wi-Fi | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-06-13T00:00:00 | High | 1408388 |  | Metro North | 95 | 1280007 |  | G | 61 | The Prince Charles Hospital (TPCH) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the hospital campus for prioritised TPCH buildings. 24/7/2018, 24/7/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1408388 | 2017-07-27T00:00:00 | DH
24/7/2018 | EHQ | Sunshine Coast University Hospital (SCUH) Stage 2 ICT Expansion | 2018-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | February: This project has been reported for the first time. | 2018-05-31T00:00:00 | High | 3180000 |  | eHealth Queensland | 68 | 2356774 |  | G | 62 | Sunshine Coast University Hospital (SCUH) ICT Stage 1 delivered the ICT required to achieve the successful commissioning of SCUH in March 2017. The SCUH Stage 2 ICT Expansion covers the investment period from 1 July 2017 to 31 December 2018 and is intended to support the planned expansion of SCUH to increase capacity and establish new services. | 3180422 | 2017-07-03T00:00:00 | DH
24/7/2018 | CHQ | Information Sharing Project Phase 2 | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | May: This project is now reporting 'amber' due to a change in procurement approach which has impacted on the project's financials and schedule. The project's governance committee is reviewing the updated approach which will return the project to 'green' upon approval. 24/7/2018, 24/7/2018,March: This project has been reported for the first time. | 2018-06-13T00:00:00 | High | 4455455 |  | Children's Health Queensland | 15 | 903074 |  | A | 63 | Department of Health, eHealth Queensland, Children 24/7/2018,92s Health Queensland and Mater Health share a common vision for the seamless integration of care across organisational boundaries, in the interests of patient safety, quality, efficiency and improved access to care. This vision of integrated care processes is enabled through seamless access, at the point of care, to necessary health information and efficient transactional capabilities that support the care continuum. | 4455455 | 2018-01-10T00:00:00 | DH
24/7/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Alcohol and Other Drugs (AODS) Consumer Technical Refresh | 2019-06-28T00:00:00 | Initiate |  | 2019-06-28T00:00:00 | May: This project has been reported for the first time. | 2018-06-06T00:00:00 | High | 1248860 |  | Clinical Excellence | 10 | 19440 |  | G | 64 | This project is refreshing the technical implementation of the CIMHA Consumer module, in preparation for the introduction of new Alcohol and Other Drugs (AODS) system functionality. | 1248860 | 2018-04-16T00:00:00 | DH
24/7/2018 | SPP | Queensland Health Integrated Processing System establishment (QHIDSe) | 2019-10-15T00:00:00 | Initiate |  | 2019-10-15T00:00:00 | May: This project has been reported for the first time. | 2018-05-31T00:00:00 | High | 3257000 |  | Strategy Policy and Planning | 1 | 866805 |  | G | 65 | The QHIDSe project will develop in-house the foundation of an integrated processing system (i.e. QHIDS (Queensland Health Integrated Data System) using agile techniques and software development tools enabling QHIDS to be used as a replacement for the Queensland Hospital Inpatient Processing System (QHIPS, which processes the Queensland Hospital Admitted Patient Data Collection) and extended through future initiatives to provide new functionality. | 3257000 | 2018-05-25T00:00:00 | DH
24/7/2018 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | There have been delays to the project schedule from reprioritisation of resources to community recovery activities associated with Cyclone Debbie. Additionally, the vendor has not delivered within the contracted timeframes and we are negotiating with the vendor to ensure completion of the solution. | 2018-05-31T00:00:00 | High | 2208000 |  | Whole of Department | 89 | 2977000 |  | G | 1 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3780000 | 2016-07-01T00:00:00 | DCCSDS
24/7/2018 | Cross-Gov | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | The Queensland Fire and Emergency Services (QFES) Human Capital Management Case Management module delivery has been completed with UAT and Penetration testing being finalised for implementation. The Workplace Health and Safety module is still progressing through the final testing stages to ensure quality of the solution delivery. 24/7/2018, 24/7/2018,The Queensland Corrective Services Human Capital Management Business Case has been approved with detailed project planning and resource engagement underway. Gate 3 Investment Decision review has been undertaken with final report due end of June. 24/7/2018, 24/7/2018,The Queensland Ambulance Service (QAS) and QFES payroll projects transitioning to Aurion are progressing to schedule, with QAS being the next for implementation planned for November 2018. 24/7/2018, 24/7/2018,Detailed planning of the Integration requirements for the program are currently being progressed although there have been delays experienced attracting suitably qualified and skilled resources to complete this body of work. Targeted recruitment processes are underway. 24/7/2018, 24/7/2018, 24/7/2018, | 2018-05-31T00:00:00 | Critical | 101500000 |  | Cross-Government program led by DSITI | 65 | 58419743 |  | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 24/7/2018, 24/7/2018,* Sustainable and supported HR and Payroll service delivery 24/7/2018,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 24/7/2018,* Strategic HR capability that supports the development, performance and safety of the departments workforce 24/7/2018,* Business Intelligence capability that provides real timely, integrated HR information 24/7/2018,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 24/7/2018,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 24/7/2018,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
24/7/2018 | QPS | Online National Police Certificate | 2017-06-30T00:00:00 | Delivery |  | 2018-07-31T00:00:00 | Since the successful launch of Online National Police Certificates 79.7% of all applications have been submitted online. The project is now preparing closure activities and transition to business as usual by 31 July 2018. 24/7/2018, 24/7/2018,Feb 18: The revised project budget has been amended from previously published figures to reflect the increased investment in promotional products. | 2018-06-21T00:00:00 | High | 275000 |  | Queensland Police Service | 98 | 250000 |  | G | 1 | The Online National Police Certificate Project will implement an online service for the community to apply and pay for Name Only National Police Certificates online, rather than presenting at a police station, or using the online services of an Australian Crime Intelligence Commission accredited broker. This will provide improved customer service to the community through a more efficient and reliable QPS service, with no requirement to present at a police station, as well as provide efficiency and time savings to local police stations and the Police Information Centre. | 250000 | 2017-01-01T00:00:00 | QPS
24/7/2018 | QPS | Police Integrity and Professional Standards | 2018-08-24T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | Full funding has now been approved for the Police Integrity and Professional Standards IT system. The Project will commence delivery in July 2018 with an approved revised project end date of 31 December 2019. 24/7/2018, 24/7/2018,Feb 18: Note: original planned end date amended as previously published information was incorrect. | 2018-06-21T00:00:00 | High | 4142000 |  | Queensland Police Service | 35 | 256000 |  | G | 2 | This initiative will deliver a new integrated Police Integrity and Professional Standards IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The Police Integrity and Professional Standards system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The Police Integrity and Professional Standards Project will also complement the Complaints Reform Project established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of the Police Integrity and Professional Standards system will place the QPS in a strong readiness position to fully implement Complaints Reform Project generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 6792000 | 2017-03-07T00:00:00 | QPS
24/7/2018 | QPS | Advanced Data Analytics | 2017-07-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project continues to deliver new capability by advancing the proof of concept platforms to support a wider audience. The QPS Demand and Resource Committee has approved the extension of the project closure date to 30 June 2018 and an additional $1,114,000 in funding to facilitate achievement of the projects objectives. This included delivery of additional analytics capability for use during the 2018 Commonwealth Games. | 2018-06-21T00:00:00 | Low | 1731000 |  | Queensland Police Service | 99 | 2843930 |  | G | 3 | Develop the QPS Advanced Data Analytics proof-of-concept. This proof-of-concept is intended to inform a larger suite of data analytics integration and intelligence over the next four years, including the development of predictive and alert models to enhance the operational response to threats, incidents and events. | 2845000 | 2017-02-19T00:00:00 | QPS
24/7/2018 | QPS | Body Worn Cameras | 2018-02-28T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The Project completed the deployment of all Stage Two body worn cameras in December 2017 and is now preparing closure activities and transition to business as usual by 30 June 2018. 24/7/2018, 24/7/2018,Feb 2018: The original budget was $6.03M. In May 2017, the QPS Demand and Resource Committee approved an additional $0.860M, making the total approved budget $6.890M | 2018-06-21T00:00:00 | Medium Low | 6030000 |  | Queensland Police Service | 95 | 6890000 |  | G | 4 | The Queensland Police Service Body Worn Camera Project is deploying 5100 body worn cameras to frontline police officers. Body worn cameras will be deployed to 168 police stations, 16 tactical crime units, 47 road policing units, and specialist units including dog squads and the Public Safety Response Team in two stages. The cameras integrate with the QPS mobility devices, allowing officers to add metadata to videos and to review videos in the field. A system for storage and allocation of digital camera data will also be implemented as well as policy related to use of the cameras. | 6890000 | 2014-08-25T00:00:00 | QPS
24/7/2018 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Objectives 24/7/2018,This project will deliver a secondary DR site and hyper-converged system to provide resilience for all departmental business applications in the event of a disaster. 24/7/2018, 24/7/2018,Project Updates 24/7/2018,Core infrastructure DR implementation 80% complete. All migrated production systems successfully replicating to secondary DR site. 24/7/2018,Oracle system DR implementation is 90% complete. Estimated completion July 2018. 24/7/2018,QWIC databases successfully migrated to CITEC. 24/7/2018,SPER DR failover testing successfully completed. 24/7/2018,QWIC DR failover testing scheduled for July 2018. 24/7/2018,All end-of-life ICT infrastructure will be decommissioned from July to October 2018. 24/7/2018,The newly implemented infrastructure will provide improved stability and life extension to existing business-critical applications. 24/7/2018,Documentation of DR recovery procedure, testing strategy and updating ICT DR Plan in progress. 24/7/2018,External vendor engaged to provide migration and DR strategy for some legacy applications that are unsupported on new infrastructure DR solution. 24/7/2018, 24/7/2018,Project Schedule 24/7/2018,Some issues have impacted YTD position however it is anticipated the original completion date will be met. These issues include: 24/7/2018,DR failover testing of DJAG and QCS business critical system. Anticipated completion date is October 2018. 24/7/2018,Data centre network upgrade delays are affecting delivery of IT security infrastructure to DR site. Estimated completion date for IT security DR implementation is December 2018. | 2018-06-30T00:00:00 | High | 7460674 |  | Corporate Services | 70 | 4705792 |  | G | 1 | *Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 5955792 | 2016-10-01T00:00:00 | DJAG
24/7/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | Smart Service Queensland (SSQ) delivers services on behalf of governmet via both telephone and counter channels. Some of these services involve financial transactions involving credit card payments. 24/7/2018,The Payment Card Industry (PCI) have stipulated compliance security standards that the government (through SSQ) has to meet. 24/7/2018,This project was scoped with ensuring these standards were met. Following a recent external assessment it has been confirmed that this objective has been achieved. The project is now in closure phase and should be completed before the end of June 2018. | 2018-05-31T00:00:00 | Critical | 516033 |  | Smart Service Queensland | 96 | 1118068 |  | G | 1 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | HPW
24/7/2018 | SSQ | Automated Payments Solution | 2018-07-31T00:00:00 | Initiate |  | 2018-07-31T00:00:00 | Smart Service Queensland (SSQ) is required to continue to take payments over the phone while remaining Payment Card Industry Data Security Standard (PCI DSS) compliant. 24/7/2018, 24/7/2018,SSQ has commenced the introduction of a VOIP solution to replace the existing analogue telephony capability. This forms the basis of the Telephony Replacement Project (TRP). 24/7/2018, 24/7/2018,To continue to meet ongoing PCI-DSS compliance, additional technology is required to enable secure payments over the phone in a VOIP environment. 24/7/2018, 24/7/2018,The Automated Payment Solution (APS) project will ensure this compliance is maintained and the new technology is implemented. 24/7/2018, 24/7/2018,The procurement process for an off-the-shelf solution is underway. | 2018-05-31T00:00:00 | Critical | 1500000 |  | Smart Service Queensland | 0 | 0 |  | A | 2 | The project will implement an improved capability for offering secure payment card transactions via the telephone. To meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS) when the new VOIP telephony solution is introduced. | 1500000 | 2018-01-29T00:00:00 | HPW
24/7/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | Timeframe reviewed and amended in line with broader program dependencies. | 2018-05-31T00:00:00 | Critical | 4490634 |  | Smart Service Queensland | 63 | 3550132 |  | A | 3 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 24/7/2018, 24/7/2018,* reduce operating costs 24/7/2018,* increase capacity 24/7/2018,* improve customer experience 24/7/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | HPW
24/7/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | The planned CDS cutovers have all completed within May 2018. Post implementation planning and activities are now underway. | 2018-05-31T00:00:00 | Critical | 3476245 |  | Smart Service Queensland | 90 | 2020483 |  | G | 4 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2348880 | 2015-11-20T00:00:00 | HPW
24/7/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | Smart Service Queensland (SSQ) is introducing a new VOIP based telephony platform through the Telephony Replacement Project (TRP). SSQ is also implementing a new agent scripting tool via the Content Delivery Solution (CDS) project. 24/7/2018, 24/7/2018,The Technology Platform Project (TPP) will deliver some core underlying technology used by both projects and some other shared ICT centric deliverables, such as Load and Performance Testing, and Security Penetration Testing. 24/7/2018, 24/7/2018,The core hardware platform has been successfully delivered and is being utilised by CDS and TRP. 24/7/2018, 24/7/2018, | 2018-05-31T00:00:00 | Critical | 3390862 |  | Smart Service Queensland | 82 | 2361279 |  | G | 5 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | HPW
24/7/2018 | QSA | Digital Archiving Program - Tranche 1 | 2019-12-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | Procurement stage is progressing to planned timeframes and milestones with preferred Offeror identified and contract negotiations underway. Transition-In planning has commenced. | 2018-05-31T00:00:00 | Critical | 12701000 |  | Queensland State Archives | 93 | 1740337 |  | G | 6 | To ensure the delivery of an as-a-Service eco-system to effectively archive, manage and enable search and discovery of Queensland's permanent high value records. The new digital services will support the Queensland Government's blueprint for innovation and collaboration, providing better outcomes for Queenslanders. | 12701000 | 2017-07-01T00:00:00 | HPW
24/7/2018 | CITEC ICT | z14 Mainframe Upgrade | 2018-07-31T00:00:00 | Closed |  | 2018-05-31T00:00:00 | Project completed ahead of schedule and within budget. | 2018-05-31T00:00:00 | High | 4720752 |  | CITEC ICT | 100 | 4725344 |  | G | 7 | The project will replace the two existing z12 Mainframes (Production and Disaster Recovery) with upgraded z14 Mainframes and migrate the existing data from the old to the new. 24/7/2018, 24/7/2018,The current z12 platform is unable to be upgraded and cannot provide sufficient capability for increasing client requirements. The continued use of the z12 platform represents significant risk to business continuity. 24/7/2018, 24/7/2018,The upgrade will reduce ongoing operating costs, enable improved services to clients and provide for clients' future capacity requirements. | 4725344 | 2017-12-18T00:00:00 | HPW
24/7/2018 | Housing | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery |  | 2019-03-31T00:00:00 | The FOPATS Program undertook a significant re-baseline in late 2016 to inform and approve changes to its strategic direction, scope, delivery methodology, timing and costs, including strengthening program governance and revising the Business Case to complete against a two staged implementation, Property and then Tenancy. 24/7/2018, 24/7/2018,Following this review, the Property Release, the first of two stages, was delivered successfully on time on 1 November 2017 and delivered benefits including efficiencies in property management and reporting. 24/7/2018, 24/7/2018,The refreshed business case, the Program budget and planned end date were formally re-baselined in January 2018. This formal approval, coupled with the successful delivery of the first stage Property Release, saw the Program status move to green. 24/7/2018, 24/7/2018,The Program has completed more detailed planning for the second stage Tenancy Release, which will remove the operational dependency on the existing ICT housing solution entirely. Tenancy design activities are now well progressed, with a view to determining a feasible Program end date. 24/7/2018, | 2018-05-31T00:00:00 | Critical | 56286000 |  | Housing Services | 61 | 74442963 |  | G | 8 | Replace the existing ICT housing solution with an integrated ICT system. | 121597695 | 2013-07-01T00:00:00 | HPW
24/7/2018 | QGP | Fleet Management System Replacement Project (FMSRP - Qfleet) | 2019-09-30T00:00:00 | Initiate |  | 2019-09-30T00:00:00 | The project is tracking to plan. The project is in the final stages of procurement and has commenced lead delivery activities. | 2018-05-31T00:00:00 | High | 13939200 |  | QFleet | 18 | 568190 |  | G | 9 | The project will deliver for the Department of Housing and Public Works, Public Safety Business Agency and Queensland Ambulance Service a fleet management solution to replace existing aging legacy systems. | 13939200 | 2017-10-19T00:00:00 | HPW
24/7/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 24/7/2018, 24/7/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 24/7/2018,October 2017 - The project is progressing as planned. 24/7/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 24/7/2018,June 2017 - Revised Schedule approved returning the project to Green. 24/7/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 24/7/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 24/7/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 24/7/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 24/7/2018,December 2016 - The project is progressing as planned. | 2017-12-21T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 24/7/2018, 24/7/2018,* register and maintain their information 24/7/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
24/7/2018 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 24/7/2018, 24/7/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 24/7/2018,August 2017 - Approved extension of timeframe. 24/7/2018,June 2017 - The project is progressing as planned. 24/7/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 24/7/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 24/7/2018,October 2016 - Progress is continuing as planned. 24/7/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 24/7/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 24/7/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-21T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 24/7/2018, 24/7/2018,* support compliance with legislation 24/7/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 24/7/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 24/7/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 24/7/2018, | 1390000 | 2012-04-01T00:00:00 | DEWS
24/7/2018 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The project has re-commenced. Approval has been granted for an extension to the planned end date, and an increase in associated costs. 24/7/2018, 24/7/2018,June 2018 - Field testing has identified unexpected issues that will impact on the planned end date. Effort is underway with Microsoft to apply a technical fix (patch) to resolve errors. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 24/7/2018,April 2018 - An extension to the planned end date has been approved, returning the project status to Green. 24/7/2018,March 2018 - A minor scope increase has been proposed, affecting both timeframe and cost, which is progressing through the governance process. 24/7/2018,March 2018 - The project is progressing as planned. 24/7/2018,December 2017 - A variation to scope was approved, resulting in a change to the planned end date and total estimated expenditure. 24/7/2018,November 2017 - The project is continuing as planned. 24/7/2018,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2018-07-16T00:00:00 | Medium | 608146 |  | Forestry Queensland | 90 | 999990 |  | G | 1 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 24/7/2018, 24/7/2018,* the capture, management and integration of data 24/7/2018,* value-adding opportunities for business improvement 24/7/2018,* management of risk associated with ongoing use and maintenance of disparate systems. | 1696431 | 2016-06-15T00:00:00 | DAF
24/7/2018 | BQCC | Communication and Stakeholder Engagement Solution | 2018-04-27T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | An extension to the planned end date and additional budget has been approved by the governance committee. 24/7/2018, 24/7/2018,June 2018 - Hidden complexities around integration with other solutions has affect the timing of user acceptance testing and training schedules. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 24/7/2018,May 2018 - A change to the planned end date and cost has been approved. 24/7/2018,March 2018 - Note adjustment to planned end date corrected due to typographical error. 24/7/2018,February 2018 - The project is progressing as planned. 24/7/2018,December 2017 - The project was approved to move into delivery in October 2017 and is being published for the first time. | 2018-07-16T00:00:00 | Medium | 694000 |  | Biosecurity Queensland Control Centre | 90 | 771870 |  | G | 2 | Implement a simple, easy to use system that will facilitate the collection of information associated with the National Red Imported Fire Ant Eradication Program and the National Electric Ant Eradication Program. This will include contact management, complaints management, history of interactions, event management, training management, social media interactions, marketing campaign and reporting. | 1048849 | 2017-06-01T00:00:00 | DAF
24/7/2018 | ASQ | Portfolio Activity Reporting Information System | 2018-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | Project is continuing as planned. 24/7/2018, 24/7/2018,June 2018 - Refreshed business case approved, the project has been re-baselined returning it to a Green status. 24/7/2018,May 2018 - Funding has been approved to fully implement the project and it is now in delivery. 24/7/2018,February 2018 - The project is paused until a funding source is identified. 24/7/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-07-16T00:00:00 | High | 978000 |  | Agri-Science Queensland | 10 | 231622 |  | G | 3 | Review and consolidate the variety of processes and technologies currently being used to manage the department's research, development and extension, and other projects. | 978000 | 2015-08-13T00:00:00 | DAF
24/7/2018 | Ag | Risk Reduction for Customer Service Centre | 2019-04-19T00:00:00 | Delivery |  | 2019-04-19T00:00:00 | The project is continuing as planned. 24/7/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-07-16T00:00:00 | High | 1767000 |  | Agriculture | 40 | 498164 |  | G | 4 | Implement a solution to mitigate risk of end of life for the agency's call centre logging application. | 1767000 | 2015-01-30T00:00:00 | DAF
24/7/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
24/7/2018 | PSBA | Emergency Services Computer Aided Dispatch (ESCAD) Upgrade Program | 2016-09-30T00:00:00 | Delivery |  | 2018-07-03T00:00:00 | The updated ESCAD system cut over for Queensland Ambulance Service (QAS) completed successfully on 17-01-2018, and the Queensland Fire and Emergency Services (QFES) also completed successfully on 24-01-2018. The decommissioning of hardware in the obsolete environments is complete as per schedule. The project closure is currently underway. The ESCAD System Upgrade Project, as major initiative in the program of works, experienced significant technical and implementation issues causing an approved rebaseline in January 2017. This resulted in a revised timeframe from the original plan of 30-09-2016 to 3-07-2018 and a revised approved budget from the original of $6.8 million to $9.4 million for the Program. | 2018-06-22T00:00:00 | Critical | 6774820 |  | Public Safety Business Agency | 95 | 9183050 |  | G | 1 | A program of work for Queensland Ambulance Service and Queensland Fire and Emergency Services to upgrade the Emergency Services Computer Aided Dispatch System,including infrastructure, operating system and application software. | 9380822 | 2015-01-15T00:00:00 | PSBA
24/7/2018 | PSBA | Emergency Vehicle Priority (EVP) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | EVP rollouts continuing in Rockhampton, Maryborough, Hervey Bay and Gladstone for both Queensland Ambulance Service and Queensland Fire and Emergency Services. Procurement of a managed service for operational support and maintenance in progress with implementation and project closure scheduled for completion October 2018. Procurement of the managed service has required an extension of the projects scope and schedule. This resulted in a revised timeframe from the original planned end date of 30-06-2017 to 31-10-2018, and a revised budget from the original expenditure plan of $3.4 million to $4.4 million. The approved/planned expenditure figure has been realigned from the estimate at completion to the total project budget, resulting in a $12,366 difference. | 2018-06-22T00:00:00 | High | 3370000 |  | Public Safety Business Agency | 89 | 4136737 |  | G | 2 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 24/7/2018, 24/7/2018,* Responsive vehicle movements 24/7/2018,* Improve road safety 24/7/2018,* Congestion management 24/7/2018,* Community safety | 4382697 | 2013-01-01T00:00:00 | PSBA
24/7/2018 | PSBA | Inter-CAD Electronic Messaging System (ICEMS) | 2016-08-31T00:00:00 | Delivery |  | 2018-03-16T00:00:00 | The ICEMS system cut over for Queensland Police Service (QPS) and Queensland Ambulance Service (QAS) completed successfully on 28-07-2017, and ICEMS for the Queensland Fire and Emergency Services (QFES) completed successfully on 24-01-2018. Project closure activities have finalised. The ICEMS Project experienced significant technical and implementation issues causing multiple approved re-baselines between November 2015 and September 2017. This resulted in a revised timeframe from the original planned end date 31-08-2016 to 16-03-2018 and a revised budget from the original planned expenditure of $560K to $1,571K. Further to this, a scope change was undertaken in 2016 to extend ICEMS messaging. The Priority of this initiative has been re-assessed to Medium. The approved/planned expenditure figure has been realigned from the estimate at completion to the total project budget, resulting in a $19,860 difference. | 2018-06-22T00:00:00 | Medium | 560000 |  | Public Safety Business Agency | 99 | 1570688 |  | G | 3 | To implement the ICEMS protocol between the Queensland Police Service (QPS), Queensland Ambulance Service (QAS) and Queensland Fire and Emergency Services (QFES) computer aided dispatch systems to enable Triple Zero data sharing between agencies. | 1591000 | 2015-10-06T00:00:00 | PSBA
24/7/2018 | PSBA | PSBAIGEM Office 365 Implementation Project | 2018-02-20T00:00:00 | Closed |  | 2018-06-01T00:00:00 | 01-06-2018 was the Board-approved project closure date. End Project Report has been approved and signed off. Project budget was increased to $1.1 million as a result of full rollout planning. Project had re-baselined the schedule from 20-02-2018 to 09-03-2018 due to increase in scope and again re-baselined the schedule from 09-03-2018 to 11-05-2018 as a result of moving from pilot to full rollout, with a final re-baseline from 11-05-2018 to 01-06-2018 for project closure. The priority for this initiative has been re-assessed to medium. | 2018-06-22T00:00:00 | Medium | 986000 |  | Public Safety Business Agency | 100 | 1009352 |  | G | 4 | The project will deliver digital transformation for the Public Safety Business Agency (PSBA) and Inspector-General Emergency Management (IGEM) through the implementation of the Office 365 suite of products to augment the below enhancements to their current business processes. Undertaking smarter meetings; Facilitating better administration; Accessing information anywhere, any time; Engaging and communicating better; Supporting capability development; Facilitating business intelligence; and Enabling efficient workflow and approvals. | 1136000 | 2017-09-20T00:00:00 | PSBA
24/7/2018 | PSBA | QFES Office 365 Implementation Project | 2018-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The project is on track to be completed by 29-06-2018. Project Board meeting is scheduled for 18-06-2018 to discuss project closure. Project had an underspend of $854,000. | 2018-06-22T00:00:00 | Medium | 2100000 |  | Public Safety Business Agency | 81 | 979100 |  | G | 5 | This project will deliver the most up-to-date Office 365 suite of products to all Queensland Fire and Emergency Services (QFES) staff and enable QFES to mobilise its workforce. 24/7/2018, 24/7/2018,* Upgrade QFES technology fleet to the latest Microsoft Office version 24/7/2018,* Cloud services will enable mobility 24/7/2018,* Bridge the technology gaps between Public Safety Agencies (PSA) and allow better collaboration | 2100000 | 2017-11-01T00:00:00 | PSBA
24/7/2018 | PSBA | QPS Office 365 Implementation Project | 2018-02-28T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The QPS Office 365 Implementation Project has successfully transitioned all QPS staff to Office 365 enabling anywhere, anytime, any device access. The Project is on track to be delivered within the original planned expenditure by the approved end date of 30-06-2018. The Priority of this initiative was re-assessed to Medium during this reporting period. The original planned end date of 28-02-2018 has been re-baselined to 30-06-2018 due to delivery of additional scope. | 2018-06-22T00:00:00 | Medium | 2207000 |  | Public Safety Business Agency | 81 | 1527439 |  | G | 6 | Phase 1 - Mail Migrations The objective of the Queensland Police Service (QPS) Office 365 Implementation Project Phase 1 is to complete the following activities prior to the Frontline and Digital Services Commonwealth Games Change Freeze (mid Feb 2018): 24/7/2018, 24/7/2018,* migrate email, contacts and calendars to Office 365 online services for all QPS staff; and 24/7/2018,* enable anywhere, anytime, any device access to email, contacts and calendar via bring your own (BYO) phone, QPS Officers operational tablets (QLiTEs) and home use for all QPS staff 24/7/2018, 24/7/2018,Phase 2 - a data migration and a pilot migration of email archives to Office 365 online | 2207000 | 2017-09-07T00:00:00 | PSBA
24/7/2018 | OSR | State Penalties Enforcement Registry (SPER) Program | 2017-12-31T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | Expenditure to date - $31M has been for the transformation of the SPER function, and $20.3M has been on the build phase of the ICT implementation. The broader SPER transformation program commenced in 2014, with the first stage focussed on building foundational capability. This next phase was the implementation of the new system solution (ICT SaaS) which commenced in 2016. 24/7/2018,Variation - In December 2017 the SPER Program completed a rebaselining effort which approved changes to scope, timing and costs. These changes were made to better reflect an enhanced delivery model, requiring system modifications that support improved business functionality. | 2018-06-30T00:00:00 | High | 47200000 |  | State Penalties Enforcement Registry | 77 | 51317000 |  | A | 1 | To maintain the integrity of fines as an effective sanction. 24/7/2018,To uphold confidence in the justice system. 24/7/2018,To deliver efficient and effective debt management practices which provide value for money to the State. 24/7/2018, | 62150000 | 2014-01-01T00:00:00 | QR
24/7/2018 | RI | Financial Assurance Information Registry (FAIR) | 2018-07-01T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Project cost as at end of June 2018 is $6,256,655. The FAIR project was due to be completed by 1 July 2018 to align with commencement of the Financial Provisioning Scheme (FPS). The delivery delay event is marked yes due to a deferral of the legislation to enact the FPS which would permit the scheme to commence. The FAIR project will be operational for FPS commencement. 24/7/2018, 24/7/2018,The FAIR project required for the FPS commencement is 80 percent complete. Other components of the FPS reforms will be completed in subsequent years. | 2018-06-30T00:00:00 | Medium | 15900000 |  | Insurance Commission | 80 | 6256655 |  | G | 2 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
24/7/2018 | RI | Information Security Program | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The program is on track according to schedule and budget. | 2018-06-30T00:00:00 | Medium | 1960000 |  | Office of the Chief Information Officer | 42 | 580000 |  | G | 3 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 24/7/2018, | 1960000 | 2017-10-16T00:00:00 | QR
24/7/2018 | OSR | Office of State Revenue (OSR) Transformation Program | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | Multiple initiatives in progress focussing on machine learning, analytics, data quality, and business process improvements. Overall program is on track. | 2018-06-30T00:00:00 | High | 73548000 |  | Office of State Revenue | 22 | 13434668 |  | G | 4 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 24/7/2018, 24/7/2018,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 73548000 | 2017-08-01T00:00:00 | QR
24/7/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
24/7/2018 | Corporate Services Improvement Program | Lotus Notes Decommissioning | 2016-01-31T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project commenced in October 2015 when concept and stage 1 was approved to engage and investigate business findings around the decommission of legacy lotus notes databases. 24/7/2018,In July 2016, three additional stages aligning to three financial years from 2016/17 through to 2018/19 were further approved via a project initiation and business case. 24/7/2018,Stage 2, 2016/17, focused on analysis and stakeholder engagement to form the scope of the project and define functionality and business requirements for individual applications. 24/7/2018,Stage 3, 2017/18, focused on proof of concepts to inform and validate the plan for stage 4 in 2018/19. The project was impacted in 2017/18 by several resourcing issues, including the departure of the original project manager. 24/7/2018,The project is scheduled to complete work and close down by 30 June 2019, with the exception of the migration of files from the department's legacy Document Management System (DMS). The migration of the DMS will align with the Integrated Records and Information System (IRIS) program and should be complete by the end of 2019. | 2018-06-30T00:00:00 | High | 8150000 |  | ERP Projects Board | 52 | 2729463 |  | G | 1 | Deliver improved information platform functions for effective ICT Strategy Alignment | 8150000 | 2015-11-01T00:00:00 | TMR
24/7/2018 | Corporate Services Improvement Program | Stop Cheques - Stage 3 | 2018-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Project successfully closed on time and within budget. Project was originally proposed in February 2015 for stage 1, with project brief and project initiation documentation approved in April 2015. Stage 1 was successfully closed out in March 2016. Stage 2 was approved in April 2016, and successfully closed out 30 June 2017. Stage 3 (2017-18) commenced 1 July 2017 and successfully closed 29 June 2018. 24/7/2018,Customers are already experiencing the increased convenience and reduction of costs resulting from reduced out-bound cheques, which include deceased estate cheques, cheques to known vendors, and the expansion of products available for refund at counter such as registration refunds and concessions. | 2018-06-30T00:00:00 | Medium | 200000 |  | ERP Projects Board | 100 | 200004 |  | G | 2 | Cheques are inefficient and costly to use, process and administer for both the customer and department. A range of solutions have been developed to reduce the number of cheques that the department produces or receives including refund to card at counter, Bulk Bpay solutions and the introduction of new payment methods are being delivered to be more in line with contemporary retail offerings. The outsourcing of cheque production produced a more streamlined process. 24/7/2018,The stop cheques initiative includes 3 elements: 24/7/2018,Outsourcing/cost reduction 24/7/2018,Outbound cheques 24/7/2018,Inbound cheques | 200000 | 2017-07-01T00:00:00 | TMR
24/7/2018 | Corporate Services Improvement Program | Risk Management Solution | 2018-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Project successfully closed on time and within budget. Project was proposed in February 2016, with the project brief and budget for stage 1 (2016-17) approved in October 2016 for $350,000. Stage 1 successfully closed 30 June 2017 with an underspend of $98501. Stage 2 (2017-18) was approved in March 2017 for $710,000, and commenced 1 July 2017. Stage 2 and the project successfully closed 22 June 2018 with an underspend of $1,887. 24/7/2018,The new online enterprise risk management system (RMS) provides significant improvements in efficiency for risk recording and monitoring, and provides increased transparency on risks, risk owners and treatment responsibilities, raising the overall risk maturity at significantly lower, ongoing cost. 24/7/2018, | 2018-06-30T00:00:00 | High | 350000 |  | Corporate Services Improvement Program | 100 | 959610 |  | G | 3 | Replace the current risk management approach through the delivery of a new and contemporary enterprise Risk Management solution for TMR . | 1024435 | 2016-02-01T00:00:00 | TMR
24/7/2018 | Corporate Services Improvement Program | Integrated Records Information System (IRIS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | In response to an internal audit review of review of Transport and Main Road's (TMR) Document Management System (DMS) the Integrated Records and Information System (IRIS) project was stood up in 2015. An opportunity to further leverage functionality requirements, TMR's Executive Correspondence System (ECS) replacement was also included into scope. 24/7/2018,IRIS project was reviewed in 2017 to ensure achievability, and as a result the project budget was decreased from $7,967,972 down to $6,865,000 (plus contingency) of 10%. 24/7/2018,In April 2018, a scope change with $567,500 budget increase was approved to include the delivery of a General Correspondence System deliverable to the project, maximising return on investment and better outcomes for the customer, bringing total budget to $7,432,500 excluding contingency. | 2018-06-30T00:00:00 | High | 7967972 |  | Information Technology Branch | 35 | 5500321 |  | G | 4 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 7432500 | 2015-07-01T00:00:00 | TMR
24/7/2018 | Corporate Services Improvement Program | Safety System Replacement | 2018-07-30T00:00:00 | Delivery |  | 2018-07-30T00:00:00 | Project is on track to close on time and within budget. A new Workplace Health and Safety (WHS) solution has been procured, implemented and declared production ready 28 June 2018. It provides a contemporary workflow based approach to the recording and management of hazards and incidents, safety conversations, and claims and rehabilitation. The solution is cloud based and offers functionality to support the Departments mobile workforce. 24/7/2018, | 2018-06-30T00:00:00 | Low | 680000 |  | Corporate Services Improvement Program | 98 | 688558 |  | G | 5 | The objective of the SSR project is to replace the current Work Health and Safety ICT solution with an industry standard, cost-effective safety management solution that will enable TMR to meet its obligations under the Work Health and Safety 2011 Act, the Right to Information, Information Privacy legislation and the Workers Compensation and Rehabilitation Act 2003 (Qld). | 680000 | 2016-12-05T00:00:00 | TMR
24/7/2018 | Corporate Services Improvement Program | TSIP Enhancements - Stage 3 | 2018-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Project successfully closed on time and within budget. Project was originally proposed in February 2015 for stage 1, with project brief and project initiation documentation approved in April 2015. Stage 1 was successfully closed out in March 2016. Stage 2 was approved in April 2016, and successfully closed out 30 June 2017. Stage 3 (2017/18) commenced 1 July 2017 and successfully closed 29 June 2018. 24/7/2018,The project added real value and efficiencies through reduced overheads within the department, such as the introduction of web-based Heavy Vehicle Permits. and Improvements were also made to multiple transactional services relating to payments and receipts from customers such as the additional payment options of payWave and AMEX. | 2018-06-30T00:00:00 | Low | 200000 |  | Transactional Services Improvement Program | 100 | 199878 |  | G | 6 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. | 200000 | 2017-07-01T00:00:00 | TMR
24/7/2018 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | This commenced in July 2016 with delivery being phased in accordance with the development of the business processes. Original expenditure was 1.5M which has been revised to 1.441M on finalisation and approval of the business case. Phase 1 was completed in July 2017 and the schedule was adjusted in June 2017 to enable the delivery of the Phase 2 capability in late 2018. 24/7/2018, 24/7/2018,The project is currently on track. | 2018-06-30T00:00:00 | High | 1500000 |  | Customer Services, Safety and Regulation Division | 90 | 999274 |  | G | 7 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal services currently required. | 1441000 | 2016-01-01T00:00:00 | TMR
24/7/2018 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project commenced in mid-2015 for delivery scheduled for mid-2016. Due to the uncertainty of the solution outcome and market capability the project undertook an extensive market engagement and procurement process resulting in the schedule being extended 11 months and the budget increased from $2.5M to $4.1M in January 2017. 24/7/2018, 24/7/2018,Pending the successful completion of final testing and the formal launch of the system the project remains on track for public release from August 2018. 24/7/2018, | 2018-06-30T00:00:00 | High | 2500000 |  | Customer Services, Safety and Regulation Division | 96 | 4176989 |  | G | 8 | Implement an online learning and assessment program at the pre-learner and/or learner stage, to replace enhance learning outcomes. | 4176000 | 2015-06-12T00:00:00 | TMR
24/7/2018 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery |  | 2018-06-28T00:00:00 | This commenced in November 2016 with planned completion in mid-2017. Due to an extended procurement process, and the need to include analytical functionality, the schedule was extended 12 months and the budget increased from $300k to $894k in August 2017. The capability was delivered as scheduled in June 2018 and the project is presently finalising closure with formal closure scheduled for August 2018. | 2018-06-30T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 99 | 986706 |  | G | 9 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 894071 | 2016-11-01T00:00:00 | TMR
24/7/2018 | Customer Service, Safety and Regulation Program | Call Centre VOIP Upgrade | 2018-06-30T00:00:00 | Delivery |  | 2018-08-15T00:00:00 | This commenced in July 2017 with delivery scheduled for mid-2018. Due to vendor resourcing issues approval was provided in May 2018 for the project to deliver the capability in early FY18/19. The project is currently on track for delivery. | 2018-06-30T00:00:00 | Low | 1140000 |  | Customer Services, Safety and Regulation Division | 75 | 1072928 |  | G | 10 | The Call Centre VOIP Upgrade has commenced to upgrade the VOIP telephony platform within the department. The proposed solution will see a reduction in call costs, a shift in capability to a 24/7/2018,contemporary solution utilising an existing investment within the department. | 1140000 | 2017-04-01T00:00:00 | TMR
24/7/2018 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The RALPH project commenced in July 2016. Due to vendor software development issues, changes to the schedule and budget were approved in June 2017 with a planned completion to occur by 30 June 2018. A further extension was approved for an additional two months. The project remains on track for closure in August 2018. | 2018-06-30T00:00:00 | Medium | 500000 |  | Customer Services, Safety and Regulation Division | 81 | 693683 |  | G | 11 | TMR's current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace the existing application with a contemporary and supportable alternative to assist the department in maintaining its timely updating of fees and charges. | 734000 | 2016-07-01T00:00:00 | TMR
24/7/2018 | Customer Service, Safety and Regulation Program | Voice Comms Mgt System | 2017-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | The Voice Comms Management System project commenced in Jan 2017 for completion by mid-2018 however resource availability was impacted due to Cyclone Debbie. Delivery of the capability was completed in April 2018 with the project being formally closed on 5 July 2018. | 2018-06-30T00:00:00 | Medium | 828000 |  | Customer Services, Safety and Regulation Division | 100 | 274738 |  | G | 12 | The Voice Comms Management project consists of two replacement of existing Voice Communication and Control Systems at Townsville and Hay Point. | 828000 | 2016-01-01T00:00:00 | TMR
24/7/2018 | Customer Service, Safety and Regulation Program | Registration and CTP Certificates Online | 2017-12-31T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | The Registration and CTP Certificates Online project commenced in May 2017 as two separate initiatives - Registration Online and CTP Tax Invoice Online. Due to common system synergies the projects were merged in March 2018 resulting in the closure date being revised in accordance with the CTP component. The project is on track for closure in late 2018. | 2018-06-30T00:00:00 | Medium | 450000 |  | Customer Services, Safety and Regulation Division | 41 | 404349 |  | G | 13 | Reduce the volume of mail sent by post by developing new online services allowing CTP Tax Invoices and Registration Certificates to be generated online | 450000 | 2017-05-01T00:00:00 | TMR
24/7/2018 | Customer Service, Safety and Regulation Program | Vessel Traffic Services (VTS) | 2016-01-05T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | Pre-project work commenced in April 2014 with the initiation of the current project commencing in July 2016. The original budget of $15.2M was rebaselined to $36.2M once the post-market business case was finalised and approved to proceed in April 2017. 24/7/2018, 24/7/2018,The project is on track for delivery in mid 2019. | 2018-06-30T00:00:00 | High | 15224694 |  | Customer Services, Safety and Regulation Division | 35 | 7490606 |  | G | 14 | The purpose of the project is procure and implement a replacement decision support tool for the existing Vessel Traffic Service (VTS) used by TMR to track and monitor ship movements within Queensland ports, the Great Barrier Reef and the Torres Strait. | 36228184 | 2014-04-14T00:00:00 | TMR
24/7/2018 | Customer Service, Safety and Regulation Program | R and L Systems Software Upgrade - Stage 2 | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The R and L System Software Upgrade project commenced in July 2017. The original budget of $780K was rebaselined to $1.255M once the post-market business case was finalised and approved to proceed in September 2017. Delivery was completed as scheduled in June 2018 with the project now undergoing closure. | 2018-06-30T00:00:00 | Medium | 780000 |  | Customer Services, Safety and Regulation Division | 87 | 1115666 |  | G | 15 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
24/7/2018 | Customer Service, Safety and Regulation Program | Customer Flow Management and Reporting System - OP | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | Pre-project work commenced during FY15/16 with the initiation of the current project commencing in July 2017. The original budget of 300K was rebaselined to 3M once the post-market business case was finalised and approved to proceed in May 2018. 24/7/2018,The project is on track for delivery to occur within FY18/19. | 2018-06-30T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 52 | 367537 |  | G | 16 | The objective of this project is to replace the existing Qmatic systems throughout the entire network Customer Service sites, with a supported enterprise solution that meets TMRs current and future needs. | 3083000 | 2015-09-01T00:00:00 | TMR
24/7/2018 | Infrastructure Management and Delivery | Work Improvement Note (WIN) Replacement | 2016-12-19T00:00:00 | Closed |  | 2018-02-27T00:00:00 | The project successfully delivered a new Work Improvement Notice system using SharePoint and K2 technology and has now closed. The original project end date moved from December 2016 to February 2018 as a result of delays experienced during software development, which were identified and resolved through iterative user testing and issue rectification. The increase in project budget was a product of the schedule delay. | 2018-06-30T00:00:00 | Low | 242612 |  | Infrastructure Management 24/7/2018,and Delivery | 100 | 358229 |  | G | 17 | The Work Improvement Note (WIN) System is used to capture, track, review and report on improvements, potential problems, non-conformances, corrective actions, customer feedback and complaints. The WIN System is an essential component of the overarching business management system as it meets specific certification requirements outlined in international quality, safety and environmental standards. This project will provide a replacement to the existing Work Improvement Note (WIN) system, which is dependent on unsupported technology. | 436375 | 2016-02-15T00:00:00 | TMR
24/7/2018 | Passenger Transport Technology Program | Single Integrated Network Project (SNIP) | 2018-09-29T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | Final testing of the transport schedule system is planned to be completed this month with implementation in TransLink planned for August. | 2018-06-30T00:00:00 | High | 4992243 |  | Passenger Transport Technology Program | 30 | 690580 |  | G | 18 | Have a system in place that is consistent and integrated across service providers and TransLink. 24/7/2018,Ensure business continuity of systems. 24/7/2018,Extend the existing scheduling and network capability solution to enable it to be ready for the bus contracts (SEQBCPP). 24/7/2018,Eliminate inefficiencies and inaccuracies that occur in the current processes and dispersed data entry options. 24/7/2018,Transparency of service providers activities and performance. 24/7/2018,To improve customer experience through more accurate and reliable service information. 24/7/2018,Contributor for achieving Government objectives. 24/7/2018, | 4992243 | 2017-02-23T00:00:00 | TMR
24/7/2018 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Original project commenced in April 2016. 24/7/2018,Cost estimates were revised in November 17. 24/7/2018,In March 18 issues in gathering business data and requirements for new functionality identified. 24/7/2018,The STAS project is reporting amber as a result of unforeseen complexities associated with provisioning and transitioning of business supplied data to the new platform. The project is experiencing delays as resolution activities take place to ensure a good customer experience when the project is released to the public. 24/7/2018,An Exception Report will be considered by the PTT board to enable products to be completed and released by end of March 2019. | 2018-06-30T00:00:00 | High | 4166000 |  | TransLink | 75 | 5014390 |  | A | 19 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 5303876 | 2016-04-01T00:00:00 | TMR
24/7/2018 | Policy Planning and Investment Program | Portfolio, Program, Project and Contract Management (3PCM) - Phase 2 and 3 | 2017-03-31T00:00:00 | Closed |  | 2017-12-22T00:00:00 | The Portfolio, Program, Project and Contract Management (3PCM) project commenced in 2012 with an initial original planned expenditure of $12,757,788. The initial estimate uploaded for 3PCM intentionally included only the project initiation, market assessment and business case development. The estimate was clarified at the end of contract negotiations in the post-market business case and revised to $47,908,928. The Portfolio, Program, Project and Contract Management (3PCM) project has successfully completed its scope and the Program Board endorsed the project closure report in July 2018. The Portfolio, Program, Project and Contract Management (3PCM) project will report for one additional reporting period prior to being removed from the QG ICT Dashboard. | 2018-07-16T00:00:00 | High | 12757788 |  | Policy, Planning and Investment Division | 100 | 47794126 |  | G | 20 | Define and implement standard, consistently applied processes for planning, managing and delivering the Transport Infrastructure Portfolio across the domains of portfolio, program, project and contract management 24/7/2018,Source and implement an integrated, strategic information communication technology solution that supports the business process and rules and enables a transition away from legacy applications | 47908928 | 2012-09-01T00:00:00 | TMR
24/7/2018 | CS | Asset Assessment System | 2016-06-30T00:00:00 | Delivery |  | 2018-08-06T00:00:00 | The project has returned to tracking to plan | 2018-04-10T00:00:00 | High | 1688788 |  | Corporate Services | 84 | 1631131 |  | G | 1 | To improve the reliability and integrity of asset information, the ability to report on asset information by applying best practice asset management principles. | 1967000 | 2014-02-27T00:00:00 | DET
24/7/2018 | SS | Early Start | 2015-07-03T00:00:00 | Delivery |  | 2018-07-31T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | High | 70000 |  | State Schools | 74 | 73522 |  | G | 2 | To provide schools with enhanced reporting functionality, improving their ability to analyse Prep to Year 2 student learning data. | 200992 | 2013-04-03T00:00:00 | DET
24/7/2018 | PPP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Medium | 700000 |  | Policy, Performance and Planning | 82 | 1278953 |  | G | 3 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
24/7/2018 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery |  | 2018-12-07T00:00:00 | The project is tracking to plan. The Project is undergoing procurement/commercial activities with no financial information being published. | 2018-04-10T00:00:00 | Medium | 0 |  | Corporate Services | 42 | 0 |  | G | 4 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DET FBS SAP future state landscape for the next five years | 0 | 2017-01-16T00:00:00 | DET
24/7/2018 | CS | Injury Management System | 2017-03-27T00:00:00 | Delivery |  | 2018-10-01T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Critical | 1900000 |  | Corporate Services | 0 | 900471 |  | G | 5 | To improve the management of workplace rehabilitation and claims for injured/ill staff | 1813805 | 2016-10-10T00:00:00 | DET
24/7/2018 | ODG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Medium | 632585 |  | Office of the Director-General | 90 | 885218 |  | G | 6 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
24/7/2018 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery |  | 2019-09-13T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Medium | 16670000 |  | State Schools | 50 | 9041598 |  | G | 7 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 23470000 | 2015-08-03T00:00:00 | DET
24/7/2018 | PPP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery |  | 2018-06-13T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Medium | 1502300 |  | Policy, Performance and Planning | 64 | 1077823 |  | G | 8 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution | 1266210 | 2016-03-01T00:00:00 | DET
24/7/2018 | CS | Project Delivery System | 2018-10-01T00:00:00 | Delivery |  | 2019-01-29T00:00:00 | The project is being closely monitored for schedule | 2018-04-10T00:00:00 | Medium | 1817566 |  | Corporate Services | 0 | 797688 |  | A | 9 | To improve the reliability and integrity of under construction asset information, the ability to report on asset project information by applying best practice asset management principles | 2291613 | 2016-07-05T00:00:00 | DET
24/7/2018 | PPP | Research Services 2.0 | 2016-09-30T00:00:00 | Delivery |  | 2017-09-29T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Medium | 230000 |  | Policy, Performance and Planning | 85 | 404745 |  | G | 10 | To develop a solution that assists in the management of the Department of Education and Training commissioned research proposals and projects, improving resourcing and information dissemination. | 431157 | 2015-11-02T00:00:00 | DET
24/7/2018 | TS | Study Tours Support System Upgrade | 2016-06-30T00:00:00 | Delivery |  | 2018-01-31T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Medium | 680000 |  | Training and Skills | 96 | 772580 |  | G | 11 | To replace or upgrade the existing Study Tours system with an online solution that has enhanced functionality, improving processes, data quality and tour management. | 831125 | 2015-08-31T00:00:00 | DET
24/7/2018 | SS | Trial of platform for virtual academies | 2017-10-02T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Medium | 151641 |  | State Schools | 40 | 224411 |  | G | 12 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage; safe and secure like-minded student virtual communities; and strategic partnerships with university, industry and business. 24/7/2018, 24/7/2018, | 151641 | 2016-06-21T00:00:00 | DET
24/7/2018 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | High | 41000000 |  | Corporate Services | 52 | 30228550 |  | G | 13 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
24/7/2018 | [20 empty] | INVERSTMENT INFO
24/7/2018 | CSGC | Coal Seam Gas Groundwater Monitoring Arrangements | 2017-12-31T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Project closure documents have been finalised and the project is now closed. 24/7/2018, 24/7/2018,June 2018 - Project delivery is complete, project closure activities are under way. 24/7/2018, 24/7/2018,May 2018 - The project has recommenced and is nearing completion. Closure activities are under way. 24/7/2018, 24/7/2018,January 2018 - A change to the planned end date has been approved; there is no impact to cost. Initiative is now paused until early 2018. 24/7/2018, 24/7/2018,August 2017 - Revised total expenditure (budget) updated to include all operating costs not previously reported. 24/7/2018, 24/7/2018,June 2017 - Progress is continuing as planned. Still on schedule to complete December 2017. 24/7/2018, 24/7/2018,December 2016 - Much of the project has been completed and a significant amount of the procurement expenditure for capital equipment has occurred. 24/7/2018, 24/7/2018,October 2016 - Progress is continuing as planned. 24/7/2018, 24/7/2018,August 2016 - Cost returned to Green after a review of costs associated with activities remaining, and a correction in actual cost to date adjustment. 24/7/2018, 24/7/2018,June 2016 - Cost is Amber with a resource review under way. 24/7/2018, 24/7/2018,February 2016 - Progress is continuing as planned. | 2018-07-16T00:00:00 | High | 2380568 |  | Coal Seam Gas Compliance | 100 | 2608283 |  | G | 1 | Enhance availability of groundwater data through improvements to network monitoring of bores for clients and landholders. | 2598256 | 2014-01-13T00:00:00 | DNRM
24/7/2018 | SIMTARS | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery |  | 2019-03-29T00:00:00 | The project is continuing as planned, tracking within tolerances for time, cost and quality. 24/7/2018, 24/7/2018,February 2018 - A change request was approved to alter the scope and associated percentage complete, time-frame and costs. 24/7/2018, 24/7/2018,December 2017 - Awaiting confirmation of project closure; project is still operating within approved time-frame tolerance. 24/7/2018, 24/7/2018,November 2017 - A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 24/7/2018, 24/7/2018,October 2017 - The project is continuing as planned. 24/7/2018, 24/7/2018,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2018-07-16T00:00:00 | High | 563000 |  | SIMTARS (Safety In Mines Testing and Research Station) | 66 | 782000 |  | G | 2 | The development and delivery of a (replacement) modern and robust Safegas solution: 24/7/2018, 24/7/2018,* risk reduction increasing capability to manage the volume of queries, transactions and data 24/7/2018,* decrease database corruption related to incidents. | 1170000 | 2017-01-25T00:00:00 | DNRM
24/7/2018 | SO | Mines Infrastructure Risk Mitigation Project | 2019-02-18T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | The project is continuing as planned, tracking within tolerances for time, cost and quality. 24/7/2018, 24/7/2018,April 2018 - A minor adjustment to scope has been approved; there is no impact to timeframe or cost. 24/7/2018, 24/7/2018,March 2018 - The project is continuing as planned. 24/7/2018, 24/7/2018,November 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-07-16T00:00:00 | High | 1200000 |  | Statewide Operations | 60 | 567400 |  | G | 3 | Migrate systems to supported infrastructure and software to: 24/7/2018, 24/7/2018,* provide a stable, secure, fully supported and flexible solution 24/7/2018,* eliminate the risks to which the geoscience data assets are currently exposed. | 1200000 | 2017-08-08T00:00:00 | DNRM
24/7/2018 | LSI | Queensland Globe Improvements | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | All deliverables have been achieved. Project closure activities are currently under way. 24/7/2018, 24/7/2018,May 2018 - The project is continuing as planned. 24/7/2018, 24/7/2018,December 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-07-16T00:00:00 | High | 1002450 |  | Land and Spatial Information | 98 | 992226 |  | G | 4 | Enhancements to Queensland Globe to continue to evolve and improve user satisfaction and experience, such as: 24/7/2018, 24/7/2018,* create and save user-defined topics 24/7/2018,* improve query and access 24/7/2018,* provide editable 'redlining' 24/7/2018,* improve data imports. | 1002450 | 2017-10-09T00:00:00 | DNRM
24/7/2018 | QWSR | Dam Safety Regulation Solution | 2016-10-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | All deliverables have been achieved. Project closure activities are currently under way. 24/7/2018, 24/7/2018,June 2018 - A change request has been approved altering the planned end date to remediate technical difficulties that have been experienced in the move to production. 24/7/2018, 24/7/2018,May 2018 - The project is continuing within timeframe tolerance, and is expected to close prior to the end of May 2018. 24/7/2018, 24/7/2018,March 2018 - The project is continuing as planned. 24/7/2018, 24/7/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 24/7/2018, 24/7/2018,August 2017 - Approved extension of timeframe. 24/7/2018, 24/7/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 24/7/2018, 24/7/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 24/7/2018, 24/7/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 24/7/2018, 24/7/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 24/7/2018, 24/7/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2018-07-16T00:00:00 | High | 1390000 |  | Queensland Water Supply Regulator | 98 | 1385060 |  | G | 5 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 24/7/2018, 24/7/2018,* support compliance with legislation 24/7/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 24/7/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 24/7/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 24/7/2018, | 1390000 | 2012-04-01T00:00:00 | DNRM
24/7/2018 | Natural Resources | Land Condition Assessment Tool | 2018-04-30T00:00:00 | Delivery |  | 2018-09-26T00:00:00 | The project is continuing as planned, tracking within tolerances for time, cost and quality. 24/7/2018, 24/7/2018,June 2018 - A change request has been approved altering the planned end date and budget to allow for resolution of unforeseen complexities in deliverables. 24/7/2018, 24/7/2018,May 2018 - The project timeframe is currently being monitored, with action under way to return it to Green. 24/7/2018, 24/7/2018,April 2018 - This project is reporting for the first time and is progressing as planned. | 2018-07-16T00:00:00 | Medium | 414000 |  | Operations Support | 70 | 117960 |  | G | 6 | Implement a solution for government, industry and other stakeholders to objectively and consistently assess land conditions, including development of a pictogram-based mobile web application and a data collection tool. | 479000 | 2017-01-12T00:00:00 | DNRM
24/7/2018 | DPC | Performance Information Management Systems (PIMS) Dynamic 365 upgrade and relocation. | 2018-10-30T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | The project commenced in May 2018 and is on track for delivery. The Discovery Phase has been completed and the scope of work for the upgrade project finalised. The PIMS Upgrade Oversight Group is meeting regularly to oversee implementation. Development work has been completed and system testing in Dynamics 365 has now commenced. | 2018-07-05T00:00:00 | High | 240494 |  | Premier and Cabinet | 55 | 29274 |  | G | 1 | To upgrade the existing PIMS solution to Microsoft Dynamics 365 and move the system to Microsoft Online. | 240494 | 2018-05-01T00:00:00 | DPC
24/7/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
24/7/2018 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 24/7/2018,* Move operational accountability and responsibility for print and imaging devices to the service provider 24/7/2018,* Reduce print and imaging costs 24/7/2018,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
24/7/2018 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
24/7/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
24/7/2018 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 24/7/2018, 24/7/2018,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
24/7/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
24/7/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 24/7/2018, 24/7/2018,* reduce operating costs 24/7/2018,* increase capacity 24/7/2018,* improve customer experience 24/7/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
24/7/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
24/7/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 24/7/2018, 24/7/2018, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
24/7/2018 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 24/7/2018, 24/7/2018,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
24/7/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
24/7/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 24/7/2018, 24/7/2018,November 2017 - Actual cost to date corrected due to input error. 24/7/2018, 24/7/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 24/7/2018, | 2017-12-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 57 | 733941 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
24/7/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | Key deliverables have been achieved within project time-frames. Project closure activities are under way, to be finalised within the next two weeks. 24/7/2018, 24/7/2018,June 2018 - User acceptance testing is almost complete; the solution is about to move into production with project closure activities under way. 24/7/2018, 24/7/2018,May 2018 - The project is progressing as planned. 24/7/2018, 24/7/2018,November 2017 - Actual cost to date corrected due to input error. 24/7/2018, 24/7/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. | 2018-07-16T00:00:00 | Medium | 1750000 |  | Queensland Parks and Wildlife Service | 98 | 1209048 |  | G | 1 | Acquire one or more solution components to operate in conjunction with the agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | EHP
24/7/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP
21/6/2018 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-04-30T00:00:00 | High | 5600000 |  | eHealth Queensland | 18 | 903408 |  | G | 1 | This project aims to establish a robust, highly available and secure contemporary platform that has the capability to support the agile eHealth Strategy. | 5600000 | 2017-07-03T00:00:00 | DH
21/6/2018 | HSQ | AUSLAB Re-hosting project | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | April: Delays have been experienced in project deliverables, with refinements needed to the technical implementation, impacting the project's schedule. | 2018-05-01T00:00:00 | High | 1691324 |  | Health Support Queensland | 40 | 425294 |  | R | 2 | Delivery of a replacement hardware and visualisation solution for the AUSLAB and AUSCARE systems that will achieve improved resiliency of the architecture, updated operating system and inclusion of virtualisation. AUSLAB and AUSCARE are critical to support laboratories and patient clinical care. | 1554952 | 2017-08-28T00:00:00 | DH
21/6/2018 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2016-08-01T00:00:00 | Delivery |  | 2018-07-30T00:00:00 |  | 2018-05-14T00:00:00 | High | 1858668 |  | Metro North | 75 | 1227437 |  | G | 3 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 21/6/2018, 21/6/2018,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Women 21/6/2018,92s Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 21/6/2018, 21/6/2018,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 2482431 | 2015-06-01T00:00:00 | DH
21/6/2018 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-04-30T00:00:00 | High | 11180394 |  | eHealth Queensland | 14 | 384625 |  | G | 4 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 21/6/2018,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work. 21/6/2018,a0 Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 11180394 | 2017-07-03T00:00:00 | DH
21/6/2018 | MNHHS | Business Intelligence - Enterprise Data Warehouse | 2018-06-29T00:00:00 | Delivery |  | 2018-06-28T00:00:00 | March: Project funding is currently being revised in line with proposed scope for an upcoming stage. | 2018-05-14T00:00:00 | High | 2114991 |  | Metro North | 75 | 1481641 |  | G | 5 | This project will introduce Business Intelligence and Data Warehousing capabilities at MNHHS. The project will deliver BI & DW technical skills, system infrastructure, data automation tools, a pilot dataset, data governance processes and quality control framework at MNHHS. Metro North Finance and MNIT are jointly managing the project. | 1480182 | 2016-11-01T00:00:00 | DH
21/6/2018 | MNHHS | Central Patient Monitoring Equipment Replacement | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 |  | 2018-05-14T00:00:00 | High | 1236416 |  | Metro North | 62 | 540543 |  | G | 6 | Metro North IT has been approached by Metro North Procurement Services (MNPS) to provide ICT advice and guidance into the Central Patient Monitoring Equipment Replacement (CPMER) Project. The Health Technology Equipment Replacement (HTER) program for central monitoring systems is providing funding in financial years 16/18 for physiological monitoring equipment requiring replacement across MNHHS hospital facilities. There is an estimated 312 pieces of equipment, primarily Physiological Monitoring devices, to be replaced under the program across MNHHS hospital facilities. MNHHS implementations are being co-ordinated by MNPS. | 1236416 | 2017-06-28T00:00:00 | DH
21/6/2018 | MNHHS | CISS (Community, Indigenous and Subacute Services) Wi-Fi | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-05-14T00:00:00 | High | 1280798 |  | Metro North | 64 | 1051143 |  | G | 7 | The Community, Indigenous and Subacute Services (CISS) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the internal areas of the prioritised CISS sites. 21/6/2018, 21/6/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1280798 | 2017-07-28T00:00:00 | DH
21/6/2018 | EHQ | Cloud First Project | 2018-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-04-30T00:00:00 | High | 4250000 |  | eHealth Queensland | 80 | 2783488 |  | G | 8 | The Cloud First project will build internal capability and establish processes within Queensland Health to appropriately utilise cloud services on an ongoing basis. | 4126918 | 2017-01-01T00:00:00 | DH
21/6/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Clinical Notes project (release 3.0) | 2018-02-06T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-04-30T00:00:00 | High | 1415000 |  | Clinical Excellence | 85 | 1625078 |  | G | 9 | Upgrading the CIMHA Mental Health Act module to accommodate a re-architecture of the CIMHA clinical notes module is required to deliver benefits to the clinical workforce associated with data entry efficiencies; improved data sharing across digital platforms; patient level information transfer to third parties to support service integration and data mining to support service improvement and research. | 1969365 | 2017-02-20T00:00:00 | DH
21/6/2018 | EHQ | Critical Network Hardware | 2018-02-28T00:00:00 | Delivery |  | 2018-05-31T00:00:00 | February: This project has returned to 'on track'. 21/6/2018, 21/6/2018,January: The project is reporting 'Amber' due to limited resource availability and additional technical requirements, impacting the schedule of the project | 2018-04-30T00:00:00 | High | 8636364 |  | eHealth Queensland | 70 | 7511057 |  | G | 10 | The objectives of the project include: 21/6/2018,a) Mitigate the Department of Health risk that core network switches at QH facilities will no longer be supported by the manufacturer from February 2018. 21/6/2018,b) Invest in the replacement of critical ICT network hardware to maintain current capability and reliability of the data network for 120+ enterprise clinical and business applications and provide the foundation for future capability in the enterprise data centres. 21/6/2018,c) Ensure hardware replacement occurs with minimal impact to business operations in Hospital and Health Services or Corporate offices. 21/6/2018,d) Update logical and physical design and architecture documentation for ease of maintenance and management. | 8371607 | 2017-03-06T00:00:00 | DH
21/6/2018 | EHQ | Digital Collaboration Platform Program | 2018-06-30T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | March: Project activities have continued to be delayed, resulting in this project reporting 'Red'. A project change request has been submitted to the project's governance committee. Successful deployment was recently achieved in Townsville. 21/6/2018, 21/6/2018,January: This project is experiencing delays in pre-migration activities. | 2018-04-30T00:00:00 | High | 11000000 |  | eHealth Queensland | 35 | 11303009 |  | G | 11 | This program will deliver digital collaboration tools for any time, any where, any device including: 21/6/2018, 21/6/2018,95 Email and Archiving 21/6/2018, 21/6/2018,95 Establishment and Collaboration 21/6/2018, 21/6/2018,95 Productivity Suite Enablement | 18467291 | 2015-10-29T00:00:00 | DH
21/6/2018 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Initiate |  | 2019-07-02T00:00:00 |  | 2018-04-30T00:00:00 | High | 1120000 |  | eHealth Queensland | 47 | 421949 |  | G | 23 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. | 1120000 | 2017-07-05T00:00:00 | DH
21/6/2018 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate |  | 2017-12-31T00:00:00 | February: The current prosposed date of completion is the 31 December 2019, which is subject to project board approval. | 2018-04-30T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 40 | 574006 |  | G | 12 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 4167216 | 2015-12-01T00:00:00 | DH
21/6/2018 | QAS | e-ARF Redevelopment for iPad | 2016-12-31T00:00:00 | Delivery |  | 2017-12-31T00:00:00 | February: Implementation and rollout of the system was completed in late November 2017. The project is currently finalising end of project reporting processes. | 2018-04-30T00:00:00 | High | 2624000 |  | Queensland Ambulance Service | 100 | 1860951 |  | G | 13 | This is an initiative to provide the electronic Ambulance Report Form (eARF) electronic patient care solution via iPads in the field. | 1910813 | 2015-09-02T00:00:00 | DH
21/6/2018 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | April: Further solution clarification is required, which has impacted on the overall delivery timeframe of this initiative by a number of weeks. | 2018-04-30T00:00:00 | High | 1283000 |  | Chief Health Officer and Prevention | 70 | 105000 |  | A | 14 | Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1283000 | 2017-07-24T00:00:00 | DH
21/6/2018 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery |  | 2018-11-30T00:00:00 |  | 2018-05-14T00:00:00 | High | 4827917 |  | Metro North | 60 | 3066406 |  | G | 15 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (ieMR) program. 21/6/2018, 21/6/2018,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 21/6/2018, 21/6/2018,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. | 4827917 | 2016-07-01T00:00:00 | DH
21/6/2018 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | April: This initiative is now 'in delivery'. | 2018-04-30T00:00:00 | High | 3792744 |  | eHealth Queensland | 12 | 339803 |  | G | 16 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment. 21/6/2018,a0 21/6/2018,a0The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access. 21/6/2018,a0 | 3792744 | 2017-07-05T00:00:00 | DH
21/6/2018 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery |  | 2020-06-26T00:00:00 |  | 2018-04-30T00:00:00 | High | 3215000 |  | eHealth Queensland | 25 | 4819895 |  | G | 24 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 12318334 | 2015-06-22T00:00:00 | DH
21/6/2018 | QAS | Enterprise Rostering System | 2018-12-31T00:00:00 | Ended |  | 2018-12-31T00:00:00 | April: The business requirements gathered for this initiatives require further refinement and review, with a decision made by Queensland Ambulance Service (QAS) management to close this project at this time. Upon the completion of other preliminary project activities, QAS Management will re-consider this project in 2018/19. | 2018-04-30T00:00:00 | High | 1000000 |  | Queensland Ambulance Service | 10 | 507397 |  | G | 17 | The initiative is to provide a centralised electronic rostering system to replace existing aging and disparate manual systems currently being utilised across the state. | 1194682 | 2016-12-01T00:00:00 | DH
21/6/2018 | EHQ | File Services Migration | 2017-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-04-30T00:00:00 | High | 3400000 |  | eHealth Queensland | 30 | 3353037 |  | G | 18 | The purpose of this investment is to adopt a contemporary, simplified file management solution for Queensland Health that enables a more cohesive customer experience. | 9907925 | 2016-08-01T00:00:00 | DH
21/6/2018 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | April: The project is currently reporting 'amber' due to the need to refine business requirements, which may have an impact on the project's schedule. 21/6/2018, 21/6/2018,March: The project has returned to 'green' and is continuing with solution testing activities. 21/6/2018, 21/6/2018,February:The project is currently monitoring several schedule risks impacting a number of configuration activities. | 2018-04-30T00:00:00 | High | 105000000 |  | Metro North | 55 | 60327930 |  | A | 19 | The current Queensland Health Finance, Asset and Materials Maintenance Information System (FAMMIS) system is based on a heavily customised solution which is almost 20 years old and no longer supported. 21/6/2018,The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 21/6/2018, 21/6/2018,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 21/6/2018,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 21/6/2018, 21/6/2018,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
21/6/2018 | EHQ | Follow Me Desktop - Deployment | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-04-30T00:00:00 | High | 3952980 |  | eHealth Queensland | 41 | 1222013 |  | G | 20 | Follow Me Desktop Deployment Project will deliver 21/6/2018,a0the Follow Me Desktop service (FMD) to HHS 21/6/2018,92 in alignment with the Infrastructure Remediation Program (IMP) and ieMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 3676980 | 2017-07-03T00:00:00 | DH
21/6/2018 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-04-30T00:00:00 | High | 3301500 |  | eHealth Queensland | 16 | 239830 |  | G | 21 | Project Purpose: 21/6/2018,a0To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 2490769 | 2017-07-01T00:00:00 | DH
21/6/2018 | EHQ | ICT Regional Wireless Infrastructure Initiatives | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-04-30T00:00:00 | High | 4170000 |  | eHealth Queensland | 70 | 2486680 |  | G | 22 | The Regional eHealth Project (ReHP) is a Wireless LAN and Network Infrastructure uplift project so that sites in Far North Qld are ready to rollout their new eHealth Application. | 3489114 | 2017-07-01T00:00:00 | DH
21/6/2018 | EHQ | ieMR Program (Funding Packages 3 and 4) | 2019-04-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | April: The advanced version of the ieMR system has gone live at the Lady Cilento Children's Hospital in April 2018. An upgraded patient scheduling tool has also been deployed to Redland-Wynnum Hospita and Queen Ellizabeth II (QEII) Hospital in April, improving inpatient and outpatient scheduling processes. | 2018-04-30T00:00:00 | High | 0 |  | eHealth Queensland | 26 | 0 |  | G | 25 | ieMR will enable improved patient care through the development of a state-wide, authoritative single source of the patient records. 21/6/2018, 21/6/2018,The ieMR will provide clinicians with the ability to: 21/6/2018,* access data that is integrated, accurate and clinically relevant 21/6/2018,* support decision making and better use of information 21/6/2018,* optimise management of patients, resources and provision of services 21/6/2018,* support interaction across a network of providers by making it easier to find providers, transfer information and collaborate with multidisciplinary providers. 21/6/2018,The Program scope (all tranches) is to roll out the ieMR system to 24 hospitals across Queensland. 21/6/2018, 21/6/2018,Please note that financial information for ieMR is Commercial in Confidence | 0 | 2016-11-17T00:00:00 | DH
21/6/2018 | EHQ | Infrastructure Capacity FY 17-18 | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-04-30T00:00:00 | High | 1000000 |  | eHealth Queensland | 61 | 823161 |  | G | 26 | Project Purpose: 21/6/2018,a0 21/6/2018,The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified 21/6/2018,91organic growth 21/6/2018,92 requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. | 2000000 | 2017-07-01T00:00:00 | DH
21/6/2018 | EHQ | Infrastructure Maintenance Program Establishment | 2018-06-29T00:00:00 | Delivery |  | 2022-06-30T00:00:00 | March: This initiative has been refocused to the establishment phase of the Infrastrucutre Maintenance Program, and as such the % complete and original end date have been updated to reflect this phase of the program. The latest approved end date will be updated in a following reporting month. | 2018-04-30T00:00:00 | High | 1161415 |  | eHealth Queensland | 60 | 615872 |  | G | 27 | The Infrastructure Maintenance Program (IMP) 21/6/2018,a0will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 21/6/2018,The scope includes: 21/6/2018,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 21/6/2018,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and 21/6/2018,a0 21/6/2018,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1392326 | 2017-07-03T00:00:00 | DH
21/6/2018 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery |  | 2022-06-30T00:00:00 |  | 2018-04-30T00:00:00 | High | 14673739 |  | Clinical Excellence | 10 | 1336461 |  | G | 28 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 21/6/2018,The ongoing program of work aims to continue and build upon existing functionality by: 21/6/2018, 21/6/2018,95 Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 21/6/2018, 21/6/2018,95 Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 21/6/2018, 21/6/2018,95 Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 21/6/2018, 21/6/2018,95 Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 21/6/2018, 21/6/2018,95 Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
21/6/2018 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate |  | 2022-12-21T00:00:00 |  | 2018-04-30T00:00:00 | High | 6300000 |  | Queensland Ambulance Service | 22 | 500943 |  | G | 29 | Phased delivery of a system supporting QAS business intelligence. | 6300000 | 2017-01-03T00:00:00 | DH
21/6/2018 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 |  | 2018-05-10T00:00:00 | High | 33827000 |  | Clinical Excellence | 28 | 14483645 |  | G | 30 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 39408218 | 2017-03-01T00:00:00 | DH
21/6/2018 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 1 | 2016-11-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | April: The project has experienced a delay to the completion of Stage 1 due to delays in the governance and assurance process. The project is currently seeking approval to obtain additonal time and funding to complete this stage. 21/6/2018, 21/6/2018,February: Approval delays in obtaining additional funding and a slightly extended schedule has impacted the project's schedule, with approvals expected in the upcoming reporting month. | 2018-04-30T00:00:00 | High | 8200000 |  | Health Support Queensland | 91 | 24298159 |  | A | 31 | The IWFM project involves: 21/6/2018,- configuring additional functionality (currently available and licensed, but unutilised) within the existing Rostering and Payroll business solutions 21/6/2018,- partnering with HHSs to develop refined business models and business processes to support the roster-to-pay process 21/6/2018,- undertaking extensive training and change management to support the adoption and effective usage of new functionality and processes | 26909863 | 2016-02-17T00:00:00 | DH
21/6/2018 | EHQ | Interoperability Project | 2016-04-29T00:00:00 | Delivery |  | 2019-09-29T00:00:00 |  | 2018-04-30T00:00:00 | High | 23850000 |  | eHealth Queensland | 27 | 14044526 |  | G | 32 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 21/6/2018,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 21/6/2018,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 21/6/2018, | 39189509 | 2015-02-01T00:00:00 | DH
21/6/2018 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Delivery |  | 2020-12-21T00:00:00 |  | 2018-04-30T00:00:00 | High | 64000000 |  | Health Support Queensland | 48 | 17939191 |  | G | 33 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 21/6/2018,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. | 64000000 | 2015-08-28T00:00:00 | DH
21/6/2018 | MNHHS | Learning and Performance Management Project | 2017-06-30T00:00:00 | Delivery |  | 2018-11-26T00:00:00 |  | 2018-05-14T00:00:00 | High | 1178190 |  | Metro North | 90 | 1095324 |  | G | 34 | Implement an integrated Learning Management and Performance Management system with the capability to deliver online learning and training content, facilitate performance development and maintain centralised records for reporting purposes. | 1178190 | 2016-07-11T00:00:00 | DH
21/6/2018 | GCHHS | Medical Imaging Informatics Solution (MIIS) Risk Mitigation | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-05-09T00:00:00 | High | 5000000 |  | Gold Coast | 18 | 808316 |  | G | 35 | The Medical Imaging Informatics Solution (MIIS) Risk Mitigation project has identified an Imaging solution which will address the risks and opportunities described in the Case for Change including the mitigation of patient safety risks, increased efficiency and productivity, improvi.ng medical imaging billing revenue collection and cash flow. The solution has user endorsement from radiologists and clinicians and will be specifically configured to meet GCHHS 21/6/2018,92s needs. | 5000000 | 2017-04-03T00:00:00 | DH
21/6/2018 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery |  | 2018-11-30T00:00:00 |  | 2018-05-14T00:00:00 | High | 4030460 |  | Metro North | 40 | 1987339 |  | G | 36 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 21/6/2018, 21/6/2018,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 21/6/2018, 21/6/2018,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
21/6/2018 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery |  | 2017-12-31T00:00:00 | April: The project is continuing to report 'Red' due to continued delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-05-14T00:00:00 | High | 6299780 |  | Metro North | 75 | 6671836 |  | R | 37 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 6299780 | 2014-06-01T00:00:00 | DH
21/6/2018 | EHQ | Metro South and East Queensland ICT Infrastructure Replacement Initiative | 2018-06-29T00:00:00 | Delivery |  | 2019-02-28T00:00:00 |  | 2018-04-30T00:00:00 | High | 4160449 |  | eHealth Queensland | 63 | 1349795 |  | G | 38 | Will replace or uplift out of date end of life ICT assets. | 3632112 | 2017-07-01T00:00:00 | DH
21/6/2018 | EHQ | Metro South East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-04-29T00:00:00 |  | 2018-04-30T00:00:00 | High | 2182844 |  | eHealth Queensland | 45 | 546469 |  | G | 39 | Will replace or uplift out of date end of life ICT assets. | 2182843 | 2017-07-01T00:00:00 | DH
21/6/2018 | EHQ | Mobile Application System for Bring Your Own Device | 2018-06-30T00:00:00 | Delivery |  | 2018-08-24T00:00:00 |  | 2018-04-30T00:00:00 | High | 1639698 |  | eHealth Queensland | 75 | 1176442 |  | G | 40 | This project leverages the investment of the previous Bring-Your-Own-Device (BYOD) 21/6/2018,a0projects to extend the capability of device mobility by building the foundations of a Mobile Application Ecosystem - the processes, products and services to enable the managed development of low/no code applications by Health and Hospital Services (HHS). 21/6/2018,a0 This project will also complete the deployment of BYOD laptops and provide recommendations on how cost savings can be made by the organisation around Corporate devices and data plans. 21/6/2018,a0 | 1538302 | 2017-07-01T00:00:00 | DH
21/6/2018 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery |  | 2018-12-19T00:00:00 | April: This project is experiencing delays in pre-migration activities, delays experienced in another dependent project, and requires additional resources. Further finances are required, with the schedule and finance issues being managed via the project's governance committee. 21/6/2018, 21/6/2018,January: This project is experiencing delays in pre-migration activities and delays experienced in another dependent project. | 2018-04-30T00:00:00 | High | 14100000 |  | eHealth Queensland | 50 | 17755071 |  | R | 41 | A managed operating environment means that everyone within the organisation is running a clean, basic operating system with centralised update management. This includes upgrades of all PC operating systems, preparing QH applications for running on recent operating system environments, and Infrastructure remediation activities to ensure the deployment tools are sufficient and ready for production. | 27427900 | 2016-05-12T00:00:00 | DH
21/6/2018 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Delivery |  | 2018-06-30T00:00:00 |  | 2018-04-30T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 86 | 702476 |  | G | 42 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1744000 | 2015-10-01T00:00:00 | DH
21/6/2018 | CHOPD | Notifiable Conditions System Replacement | 2019-06-29T00:00:00 | Delivery |  | 2020-02-28T00:00:00 |  | 2018-04-30T00:00:00 | High | 12750000 |  | Chief Health Officer and Prevention | 39 | 2525427 |  | G | 43 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 21/6/2018,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
21/6/2018 | EHQ | Patient Administration System (PAS) Replacement - Business Case Development Project | 2017-06-30T00:00:00 | Initiate |  | 2019-03-29T00:00:00 |  | 2018-04-30T00:00:00 | High | 3850000 |  | eHealth Queensland | 60 | 4139911 |  | G | 44 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients 21/6/2018,92 journeys, and ensure that accurate information about our patients is readily available when and where required. 21/6/2018, 21/6/2018,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 21/6/2018, 21/6/2018,95 support for patient engagement 21/6/2018, 21/6/2018,95 integrated care 21/6/2018, 21/6/2018,95 clinical research 21/6/2018, 21/6/2018,95 population health (for patients using public health services) 21/6/2018, 21/6/2018,95 performance transparency 21/6/2018, 21/6/2018,95 resource planning. | 11890865 | 2015-11-01T00:00:00 | DH
21/6/2018 | MNHHS | Picture Archiving and Communication System (PACS) | 2017-09-29T00:00:00 | Delivery |  | 2017-12-31T00:00:00 | April: The project is continuing to report 'Red' due to continued delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-05-14T00:00:00 | High | 3114694 |  | Metro North | 65 | 3259398 |  | R | 45 | Procure and implement a contemporary Picture Archiving and Communication (PACS) system and functionality that will ensure improved service delivery for the MNHHS Medical Imaging Departments (and other PACS users) through replacement of RBWH PACS ensuring that it is scalable and able to meet the ongoing needs of Metro North Hospital and Health Service. | 3656297 | 2016-07-11T00:00:00 | DH
21/6/2018 | CSD | Practice Management Enterprise Solution | 2018-11-01T00:00:00 | Delivery |  | 2019-02-01T00:00:00 |  | 2018-05-08T00:00:00 | High | 1470000 |  | Corporate Services | 53 | 707868 |  | G | 46 | The main practice management software used by HHSs to conduct private practice services and billing activities is being replaced. The initiative will procure and implement "like for like" functionality enterprise solution for participating HHSs (15 in total). | 2961432 | 2017-08-01T00:00:00 | DH
21/6/2018 | EHQ | Project, Program and Portfolio Management Application | 2018-03-31T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | April: This project is now reporting 'amber' due to re-aligning the project's schedule and finances to meet changing organisational requirements. The project has submitted | 2018-04-30T00:00:00 | High | 1344177 |  | eHealth Queensland | 30 | 511214 |  | A | 47 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 21/6/2018, | 1473632 | 2017-05-02T00:00:00 | DH
21/6/2018 | CED | Queensland Integrated Safety Information Project (QISIP) / Risk Management | 2017-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 |  | 2018-04-30T00:00:00 | High | 4333120 |  | Clinical Excellence | 89 | 8101301 |  | G | 48 | This initiative will source a state wide system to replace existing enterprise risk management systems to support patient and staff incident reporting, feedback, case management and risk management processes. | 16273520 | 2013-01-25T00:00:00 | DH
21/6/2018 | EHQ | Queensland State-wide ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-04-30T00:00:00 | High | 3246247 |  | eHealth Queensland | 45 | 1717850 |  | G | 49 | Will replace or uplift out of date end of life ICT assets. | 3246247 | 2017-07-01T00:00:00 | DH
21/6/2018 | EHQ | Queensland State-wide ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-04-30T00:00:00 | High | 3283431 |  | eHealth Queensland | 70 | 1984962 |  | G | 50 | Will replace or uplift out of date end of life ICT assets. | 3282431 | 2017-07-01T00:00:00 | DH
21/6/2018 | MNHHS | Quick Flow Project | 2019-02-01T00:00:00 | Initiate |  | 2019-06-30T00:00:00 |  | 2018-05-23T00:00:00 | High | 6408600 |  | Metro North | 49 | 1061693 |  | G | 51 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 21/6/2018,The key objectives of the project are to: 21/6/2018, 21/6/2018,95 Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 21/6/2018, 21/6/2018,95 Improve the outpatient experience across MNHSS facilities and community services 21/6/2018, 21/6/2018,95 Improve clinic resource utilisation 21/6/2018, 21/6/2018,95 Increase the efficiency of clinical and administrative processes 21/6/2018, 21/6/2018,95 Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
21/6/2018 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Initiate |  | 2019-12-31T00:00:00 |  | 2018-05-09T00:00:00 | High | 34950000 |  | Cairns and Hinterland | 61 | 10572622 |  | G | 52 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patient 21/6/2018,92s home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
21/6/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-02-28T00:00:00 |  | 2018-04-30T00:00:00 | High | 4260336 |  | eHealth Queensland | 45 | 1134125 |  | G | 53 | Will replace or uplift out of date end of life ICT assets. | 4260336 | 2017-07-01T00:00:00 | DH
21/6/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-04-30T00:00:00 | High | 2150147 |  | eHealth Queensland | 62 | 877218 |  | G | 54 | Will replace or uplift out of date end of life ICT assets. | 2678483 | 2017-07-01T00:00:00 | DH
21/6/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-04-30T00:00:00 | High | 1651750 |  | eHealth Queensland | 45 | 677607 |  | G | 55 | Will replace or uplift out of date end of life ICT assets. | 1651750 | 2017-07-01T00:00:00 | DH
21/6/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-04-30T00:00:00 | High | 4245973 |  | eHealth Queensland | 68 | 2212833 |  | G | 56 | Will replace or uplift out of date end of life ICT assets. | 4245973 | 2017-07-01T00:00:00 | DH
21/6/2018 | EHQ | Service Delivery Excellence Project (SDEP) | 2018-02-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | March: The latest approved end date and percentage complete has been updated. 21/6/2018, 21/6/2018,February: The latest approved end date for this initiative will be updated pending advise from the project. | 2018-04-30T00:00:00 | High | 4822000 |  | eHealth Queensland | 23 | 751912 |  | G | 57 | The Service Delivery Excellence Project (SDEP) aims to improve the service delivery functions of eHealth Queensland to help the organisation achieve its Customers and services Foundation and Shared Goal: 21/6/2018,Enhance value for customers by streamlining end to end services, processes and delivery models so that we can provide an exceptional customer experience. 21/6/2018,Stage 1 has the primary objective of delivering the Project Initiation Document (PID) for the Service Delivery Excellence Project (SDEP) Stage 2. | 4821750 | 2017-10-16T00:00:00 | DH
21/6/2018 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Delivery |  | 2020-09-30T00:00:00 |  | 2018-04-30T00:00:00 | High | 10500000 |  | eHealth Queensland | 12 | 2748197 |  | G | 58 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 10500000 | 2017-07-03T00:00:00 | DH
21/6/2018 | MNHHS | Royal Brisbane and Womens Hospital Wi-Fi | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-05-14T00:00:00 | High | 5000000 |  | Metro North | 20 | 2382805 |  | G | 59 | The RBWH Wi-Fi Project will provide an uplift and renewal to the latest Queensland Health (QH) standard for wireless local area network (WLAN) coverage within the internal areas of prioritised RBWH buildings in order to support digital healthcare. 21/6/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for the RBWH in the near future. | 5000000 | 2017-10-22T00:00:00 | DH
21/6/2018 | EHQ | Storage Asset Replacement | 2018-06-29T00:00:00 | Delivery |  | 2018-07-24T00:00:00 |  | 2018-04-30T00:00:00 | High | 1671556 |  | eHealth Queensland | 35 | 235593 |  | G | 60 | The Storage Asset Replacement (SAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the SAR and Backup Asset Replacement (BAR) projects. 21/6/2018,The SAR project seeks to outline architecture for storage that will provide a cost effective, scalable and fit for purpose environment for the future of storage services within Queensland Health. 21/6/2018,a0 Utilising space saving technologies which will enable further cost savings and reduce the requirement for capacity expansion in the short to medium term. | 1659988 | 2017-07-03T00:00:00 | DH
21/6/2018 | EHQ | Telehealth Asset Replacement FY 17-18 | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-04-30T00:00:00 | High | 1960000 |  | eHealth Queensland | 85 | 1868124 |  | G | 61 | Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector 21/6/2018,a0 21/6/2018,and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. 21/6/2018,The Department of Health defines Telehealth as: 21/6/2018, 21/6/2018,95Live, audio and/or video inter-active link for clinical consultations and educational purposes 21/6/2018, 21/6/2018,95Store and forward Telehealth - this model can involve digital images, video, audio and clinical data being captured ("stored") on the client computer; then at a convenient time transmitted securely ("forwarded") 21/6/2018,a0 to a clinic at another location where they are studied by relevant specialists 21/6/2018, 21/6/2018,95Teleradiology for remote reporting and clinical advice for diagnostic images 21/6/2018, 21/6/2018,95Telehealth services and equipment to monitor people 21/6/2018,92s health in their home. 21/6/2018,Benefits of Telehealth 21/6/2018, 21/6/2018,95Improve patient access to health care 21/6/2018, 21/6/2018,95Reduce travel and inconvenience for patients, families, carers and health professionals 21/6/2018, 21/6/2018,95Provide health professionals with access to peer support and education. 21/6/2018,The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. 21/6/2018,a0 21/6/2018,The priority is to replace those end-of-life assets which pose the greatest risk to effective health service delivery. | 1957626 | 2017-07-03T00:00:00 | DH
21/6/2018 | MNHHS | The Prince Charles Hospital (TPCH) Wi-Fi | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-05-14T00:00:00 | High | 1408388 |  | Metro North | 40 | 1180695 |  | G | 62 | The Prince Charles Hospital (TPCH) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the hospital campus for prioritised TPCH buildings. 21/6/2018, 21/6/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1408388 | 2017-07-27T00:00:00 | DH
21/6/2018 | EHQ | Sunshine Coast University Hospital (SCUH) Stage 2 ICT Expansion | 2018-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | February: This project has been reported for the first time. | 2018-04-30T00:00:00 | High | 3180000 |  | eHealth Queensland | 65 | 2178938 |  | G | 63 | Sunshine Coast University Hospital (SCUH) ICT Stage 1 delivered the ICT required to achieve the successful commissioning of SCUH in March 2017. The SCUH Stage 2 ICT Expansion covers the investment period from 1 July 2017 to 31 December 2018 and is intended to support the planned expansion of SCUH to increase capacity and establish new services. | 3180422 | 2017-07-03T00:00:00 | DH
21/6/2018 | CHQ | Information Sharing Project Phase 2 | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | March: This project has been reported for the first time. | 2018-05-15T00:00:00 | High | 4455455 |  | Children's Health Queensland | 10 | 542128 |  | G | 64 | Department of Health, eHealth Queensland, Children 21/6/2018,92s Health Queensland and Mater Health share a common vision for the seamless integration of care across organisational boundaries, in the interests of patient safety, quality, efficiency and improved access to care. This vision of integrated care processes is enabled through seamless access, at the point of care, to necessary health information and efficient transactional capabilities that support the care continuum. | 4455455 | 2018-01-10T00:00:00 | DH
21/6/2018 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | There have been delays to the project schedule from reprioritisation of resources to community recovery activities associated with Cyclone Debbie. Additionally, the vendor has not delivered within the contracted timeframes and we are negotiating with the vendor to ensure completion of the solution. | 2018-04-30T00:00:00 | High | 2208000 |  | Whole of Department | 88 | 3183000 |  | G | 1 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3483000 | 2016-07-01T00:00:00 | DCCSDS
21/6/2018 | Cross-Gov | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | The Queensland Fire and Emergency Services (QFES) Human Capital Management Workplace Health and Safety and Case Management functionality continues to track to its revised implementation date of mid-June 2018. 21/6/2018, 21/6/2018,The Queensland Corrective Services Human Capital Management Business Case has been approved with detailed project planning continuing. 21/6/2018, 21/6/2018,The Queensland Ambulance Service (QAS) and QFES payroll projects transitioning to Aurion are progressing to schedule, with QAS being the next for implementation planned for November 2018. 21/6/2018, 21/6/2018,Detailed planning of the Integration requirements for the program are currently being progressed although there have been delays experienced attracting suitably qualified and skilled resources to complete this body of work. 21/6/2018, 21/6/2018,The program is expecting to move to a 'green' status in the next reporting cycle. | 2018-04-30T00:00:00 | Critical | 101500000 |  | Cross-Government program led by DSITI | 63 | 57364591 |  | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 21/6/2018, 21/6/2018,* Sustainable and supported HR and Payroll service delivery 21/6/2018,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 21/6/2018,* Strategic HR capability that supports the development, performance and safety of the departments workforce 21/6/2018,* Business Intelligence capability that provides real timely, integrated HR information 21/6/2018,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 21/6/2018,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 21/6/2018,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
21/6/2018 | QPS | Online National Police Certificate | 2017-06-30T00:00:00 | Delivery |  | 2018-07-31T00:00:00 | Since the successful launch of Online National Police Certificates 72% of all applications have been submitted online. The overall number of applications submitted online, has doubled from December 2017 to January 2018. 21/6/2018, 21/6/2018,National Police Certificate campaign material has been distributed to all Police Districts for display in all Stations and Police Beats. External marketing via social media will commence in April 2018. 21/6/2018, 21/6/2018,Feb 2018: The revised project budget has been amended from previously published figures to reflect the increased investment in promotional products. | 2018-04-18T00:00:00 | High | 275000 |  | Queensland Police Service | 95 | 218000 |  | G | 1 | The Online National Police Certificate Project will implement an online service for the community to apply and pay for Name Only National Police Certificates online, rather than presenting at a police station, or using the online services of an Australian Crime Intelligence Commission accredited broker. This will provide improved customer service to the community through a more efficient and reliable QPS service, with no requirement to present at a police station, as well as provide efficiency and time savings to local police stations and the Police Information Centre. | 250000 | 2017-01-01T00:00:00 | QPS
21/6/2018 | QPS | Police Integrity and Professional Standards | 2018-08-24T00:00:00 | Delivery |  | 2019-08-31T00:00:00 | Project Board has approved a revised end date of 31 August 2019. Previous Invitation to Offer considered and not proceeded with as it was deemed financially un-viable. Meeting with relevant stakeholders held to discuss way forward. Project now reviewing budget and some requirements with a view to establish if a smaller funding request is viable. 21/6/2018, 21/6/2018,Note: original planned end date amended as previously published information was incorrect. | 2018-04-18T00:00:00 | High | 4142000 |  | Queensland Police Service | 30 | 176151 |  | A | 2 | This initiative will deliver a new integrated Police Integrity and Professional Standards IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The Police Integrity and Professional Standards system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The Police Integrity and Professional Standards Project will also complement the Complaints Reform Project established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of the Police Integrity and Professional Standards system will place the QPS in a strong readiness position to fully implement Complaints Reform Project generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 4142000 | 2017-03-07T00:00:00 | QPS
21/6/2018 | QPS | Advanced Data Analytics | 2017-07-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project continues to deliver new capability in all streams with most capability available for use during the 2018 Commonwealth Games. Current focus is on expanding the capability developed by the project into 2017-18 as business-as-usual capability and positioning the outputs/products of the project for developing the next phase of QPS advanced analytics capabilities. | 2018-04-18T00:00:00 | Low | 1730000 |  | Queensland Police Service | 92 | 2154400 |  | G | 3 | Develop the QPS Advanced Data Analytics proof-of-concept. This proof-of-concept is intended to inform a larger suite of data analytics integration and intelligence over the next four years, including the development of predictive and alert models to enhance the operational response to threats, incidents and events. | 2350000 | 2017-02-19T00:00:00 | QPS
21/6/2018 | QPS | Body Worn Cameras | 2018-02-28T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The Project completed the deployment of all Stage Two body worn cameras in December 2017 and is now preparing closure activities and transition to business as usual by 30 June 2018. 21/6/2018, 21/6/2018,Feb 2018: The original approved budget was $6.03M. In May 2017 the QPS Demand and Resource Committee approved an additional $0.860M, making the total approved budget $6.890M. | 2018-04-18T00:00:00 | Medium Low | 6030000 |  | Queensland Police Service | 90 | 6890000 |  | G | 4 | The Queensland Police Service Body Worn Camera Project is deploying 5100 body worn cameras to frontline police officers. Body worn cameras will be deployed to 168 police stations, 16 tactical crime units, 47 road policing units, and specialist units including dog squads and the Public Safety Response Team in two stages. The cameras integrate with the QPS mobility devices, allowing officers to add metadata to videos and to review videos in the field. A system for storage and allocation of digital camera data will also be implemented as well as policy related to use of the cameras. | 6890000 | 2014-08-25T00:00:00 | QPS
21/6/2018 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Objectives 21/6/2018,- This project will deliver a secondary DR site and hyper-converged system to provide resilience for all departmental business applications in the event of a disaster. 21/6/2018, 21/6/2018,Project Updates 21/6/2018,- Core infrastructure DR implementation 70% complete. All migrated production systems successfully replicating to secondary DR site. 21/6/2018,Oracle system DR implementation is 90% complete. Estimated completion June 2018. 21/6/2018,- SPER and QWIC databases successfully migrated to CITEC. 21/6/2018,- SPER DR failover testing scheduled for May 2018. 21/6/2018,- QWIC DR failover testing scheduled for June 2018. 21/6/2018,- All end-of-life ICT infrastructure will be decommissioned from July to October 2018. 21/6/2018,- The newly implemented infrastructure will provide improved stability and life extension to existing business-critical applications. 21/6/2018,- Documentation of DR recovery procedure, testing strategy and updating ICT DR plan in progress. 21/6/2018, 21/6/2018,Project Schedule 21/6/2018,- Some issues have impacted YTD position however it is anticipated that the original completion date will be met. These include: 21/6/2018,- Commonwealth Games change freeze in March and April 2018. 21/6/2018,- DR failover testing of DJAG and QCS business critical system 21/6/2018,- network upgrade delays are delaying project deliverables. | 2018-04-30T00:00:00 | High | 7460674 |  | Corporate Services | 70 | 3512449 |  | G | 1 | Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 5917255 | 2016-10-01T00:00:00 | DJAG
21/6/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Closed |  | 2018-04-30T00:00:00 | Exception report was approved and project closure date was changed to 30 April 2018. Project Closure documentation approved and project now changed to status 'closed'. | 2018-04-30T00:00:00 | Medium | 800000 |  | Chief Information Office | 100 | 910802 |  | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | HPW
21/6/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project is on track. | 2018-04-30T00:00:00 | Critical | 516033 |  | Smart Service Queensland | 93 | 1045900 |  | G | 2 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | HPW
21/6/2018 | SSQ | Automated Payments Solution | 2018-07-31T00:00:00 | Initiate |  | 2018-07-31T00:00:00 | This project is currently in the procurement phase and is on track. | 2018-04-30T00:00:00 | Critical | 1500000 |  | Smart Service Queensland | 0 | 0 |  | G | 3 | The Automated Payments project will implement an improved capability for offering secure payment card transactions via the telephone. This is a dependency for achieving compliance meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1500000 | 2018-01-29T00:00:00 | HPW
21/6/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery |  | 2018-07-31T00:00:00 | Timeframe and budget for the project are being reviewed as a result of Payment Card Industry Remediation Implementation project dependency and the need for additional integration identified. | 2018-04-30T00:00:00 | Critical | 4490634 |  | Smart Service Queensland | 61 | 3433232 |  | A | 4 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 21/6/2018, 21/6/2018,* reduce operating costs 21/6/2018,* increase capacity 21/6/2018,* improve customer experience 21/6/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | HPW
21/6/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | The project is on track with rollout of the system commencing in May across four stages. 21/6/2018,Exception report approved revised cost and timeframe. | 2018-04-30T00:00:00 | Critical | 3476245 |  | Smart Service Queensland | 85 | 1950701 |  | G | 5 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2348880 | 2015-11-20T00:00:00 | HPW
21/6/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. | 2018-04-30T00:00:00 | Critical | 3390861 |  | Smart Service Queensland | 82 | 2305265 |  | G | 6 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | HPW
21/6/2018 | QSA | Digital Archiving Program - Tranche 1 | 2019-12-31T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | The procurement activity is progressing to planned timeframes and milestones. | 2018-04-30T00:00:00 | Critical | 12701000 |  | Queensland State Archives | 77 | 1527596 |  | G | 7 | To ensure the delivery of an as-a-Service eco-system to effectively archive, manage and enable search and discovery of Queensland's permanent high value records. The new digital services will support the Queensland Government's blueprint for innovation and collaboration, providing better outcomes for Queenslanders. | 12701000 | 2017-07-01T00:00:00 | HPW
21/6/2018 | CITEC ICT | z14 Mainframe Upgrade | 2018-07-31T00:00:00 | Delivery |  | 2018-07-31T00:00:00 | Phase one has been completed. The majority of the budget and project cost to date relates to the purchase of hardware and associated cabling. The remaining budget is for the labour required for installation. Project remains on track. | 2018-04-30T00:00:00 | High | 4720752 |  | CITEC ICT | 75 | 4717784 |  | G | 8 | The project will replace the two existing z12 Mainframes (Production and Disaster Recovery) with upgraded z14 Mainframes and migrate the existing data from the old to the new. 21/6/2018, 21/6/2018,The current z12 platform is unable to be upgraded and cannot provide sufficient capability for increasing client requirements. The continued use of the z12 platform represents significant risk to business continuity. 21/6/2018, 21/6/2018,The upgrade will reduce ongoing operating costs, enable improved services to clients and provide for clients' future capacity requirements. 21/6/2018, | 4720752 | 2017-12-18T00:00:00 | HPW
21/6/2018 | Housing | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery |  | 2019-03-31T00:00:00 | The FOPATS Program undertook a significant re-baseline in late 2016 to inform and approve changes to its strategic direction, scope, delivery methodology, timing and costs, including strengthening program governance and revising the Business Case to complete against a two staged implementation, Property and then Tenancy. 21/6/2018, 21/6/2018,Following this review, the Property Release, the first of two stages, was delivered successfully on time on 1 November 2017 and delivered benefits including efficiencies in property management and reporting. 21/6/2018, 21/6/2018,The refreshed business case, the Program budget and planned end date were formally re-baselined in January 2018. This formal approval, coupled with the successful delivery of the first stage Property Release, saw the Program status move to green. 21/6/2018, 21/6/2018,The Program has completed more detailed planning for the second stage Tenancy Release, which will remove the operational dependency on the existing ICT housing solution entirely. Tenancy design activities are now well progressed, with a view to determining a feasible Program end date. | 2018-04-30T00:00:00 | Critical | 56286000 |  | Housing Services | 58 | 72334857 |  | G | 9 | Replace the existing ICT housing solution with an integrated ICT system. | 121597695 | 2013-07-01T00:00:00 | HPW
21/6/2018 | PWAM | iSpace External Hosting Migration Project | 2017-01-31T00:00:00 | Closed |  | 2018-04-30T00:00:00 | iSpace Upgrade has been delivered. Project closure activities have been completed and approved with residual follow on activities being transferred to business as usual tasks. 21/6/2018,The total cost of the project is less than planned due to full contingency not being expended. | 2018-04-30T00:00:00 | High | 735000 |  | Queensland Government Accommodation Office | 100 | 1095722 |  | A | 10 | Version upgrade and migration of the hosting of Queensland Accommodation Office core system to a hosted managed service arrangement. | 1415203 | 2016-05-01T00:00:00 | HPW
21/6/2018 | QGP | Fleet Management System Replacement Project (FMSRP - QFleet) | 2019-09-30T00:00:00 | Initiate |  | 2019-09-30T00:00:00 | The project is tracking to plan. The project is currently subject to procurement activities. | 2018-04-30T00:00:00 | High | 13939200 |  | QFleet | 12 | 520876 |  | G | 11 | The project will deliver for the Department of Housing and Public Works, Public Safety Business Agency and Queensland Ambulance Service a fleet management solution to replace existing aging legacy systems. | 13939200 | 2017-10-19T00:00:00 | HPW
21/6/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 21/6/2018, 21/6/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 21/6/2018,October 2017 - The project is progressing as planned. 21/6/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 21/6/2018,June 2017 - Revised Schedule approved returning the project to Green. 21/6/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 21/6/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 21/6/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 21/6/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 21/6/2018,December 2016 - The project is progressing as planned. | 2017-12-21T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 21/6/2018, 21/6/2018,* register and maintain their information 21/6/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
21/6/2018 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 21/6/2018, 21/6/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 21/6/2018,August 2017 - Approved extension of timeframe. 21/6/2018,June 2017 - The project is progressing as planned. 21/6/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 21/6/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 21/6/2018,October 2016 - Progress is continuing as planned. 21/6/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 21/6/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 21/6/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-21T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 21/6/2018, 21/6/2018,* support compliance with legislation 21/6/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 21/6/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 21/6/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 21/6/2018, | 1390000 | 2012-04-01T00:00:00 | DEWS
21/6/2018 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | Field testing has identified unexpected issues that will impact on the planned end date. Effort is underway with Microsoft to apply a technical fix (patch) to resolve errors. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 21/6/2018, 21/6/2018,April 2018 - An extension to the planned end date has been approved, returning the project status to Green. 21/6/2018,March 2018 - A minor scope increase has been proposed, affecting both timeframe and cost, which is progressing through the governance process. 21/6/2018,March 2018 - The project is progressing as planned. 21/6/2018,December 2017 - A variation to scope was approved, resulting in a change to the planned end date and total estimated expenditure. 21/6/2018,November 2017 - The project is continuing as planned. 21/6/2018,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2018-06-08T00:00:00 | Medium | 608146 |  | Forestry Queensland | 90 | 999990 |  | A | 1 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 21/6/2018, 21/6/2018,* the capture, management and integration of data 21/6/2018,* value-adding opportunities for business improvement 21/6/2018,* management of risk associated with ongoing use and maintenance of disparate systems. | 976431 | 2016-06-15T00:00:00 | DAF
21/6/2018 | BQCC | Communication and Stakeholder Engagement Solution | 2018-04-27T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | Hidden complexities around integration with other solutions has affect the timing of user acceptance testing and training schedules. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 21/6/2018, 21/6/2018,May 2018 - A change to the planned end date and cost has been approved. 21/6/2018,March 2018 - Note adjustment to planned end date corrected due to typographical error. 21/6/2018,February 2018 - The project is progressing as planned. 21/6/2018,December 2017 - The project was approved to move into delivery in October 2017 and is being published for the first time. | 2018-06-08T00:00:00 | Medium | 694000 |  | Biosecurity Queensland Control Centre | 90 | 590509 |  | A | 2 | Implement a simple, easy to use system that will facilitate the collection of information associated with the National Red Imported Fire Ant Eradication Program and the National Electric Ant Eradication Program. This will include contact management, complaints management, history of interactions, event management, training management, social media interactions, marketing campaign and reporting. | 847000 | 2017-06-01T00:00:00 | DAF
21/6/2018 | ASQ | Portfolio Activity Reporting Information System | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | Refreshed business case approved, the project has been re-baselined returning it to a Green status. 21/6/2018, 21/6/2018,May 2018 - Funding has been approved to fully implement the project and it is now in delivery. 21/6/2018,February 2018 - The project is paused until a funding source is identified. 21/6/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-06-08T00:00:00 | High | 978000 |  | Agri-Science Queensland | 10 | 231622 |  | G | 3 | Review and consolidate the variety of processes and technologies currently being used to manage the department's research, development and extension, and other projects. | 978000 | 2015-08-13T00:00:00 | DAF
21/6/2018 | Ag | Risk Reduction for Customer Service Centre | 2019-04-19T00:00:00 | Delivery |  | 2019-04-19T00:00:00 | The project is continuing as planned. 21/6/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-06-08T00:00:00 | High | 1767000 |  | Agriculture | 40 | 498164 |  | G | 4 | Implement a solution to mitigate risk of end of life for the agency's call centre logging application. | 1767000 | 2015-01-30T00:00:00 | DAF
21/6/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
21/6/2018 | PSBA | Emergency Services Computer Aided Dispatch (ESCAD) Upgrade Program | 2016-09-30T00:00:00 | Delivery |  | 2018-07-03T00:00:00 | The updated ESCAD system cut over for Queensland Ambulance Service (QAS) completed successfully on 17-01-2018, and the Queensland Fire and Emergency Services (QFES) also completed successfully on 24-01-2018. The decommissioning of hardware in the obsolete environments is currently underway. The ESCAD System Upgrade Project, as major initiative in the program of works, experienced significant technical and implementation issues causing an approved rebaseline in January 2017. This resulted in a revised timeframe from the original plan of 30-09-2016 to 3-07-2018 and a revised estimate at completion from the original of $6,774,820 to $9,789,600 for the Program. | 2018-04-27T00:00:00 | Critical | 6774820 |  | Public Safety Business Agency | 88 | 9026125 |  | G | 1 | A program of work for Queensland Ambulance Service and Queensland Fire and Emergency Services to upgrade the Emergency Services Computer Aided Dispatch System,including infrastructure, operating system and application software. | 9789600 | 2015-01-15T00:00:00 | PSBA
21/6/2018 | PSBA | Emergency Vehicle Priority (EVP) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | All rollouts of devices into vehicles will be completed by 30-06-2018. Procurement of a managed service for operational support and maintenance has required an extension of the project schedule. This resulted in a revised timeframe from the original planned end date of 30-06-2017 to 31-10-2018, and a revised budget from the original expenditure plan of $3.4 million to $4.4 million. | 2018-04-27T00:00:00 | High | 3370000 |  | Public Safety Business Agency | 87 | 4062462 |  | G | 2 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 21/6/2018, 21/6/2018,* Responsive vehicle movements 21/6/2018,* Improve road safety 21/6/2018,* Congestion management 21/6/2018,* Community safety | 4370331 | 2013-01-01T00:00:00 | PSBA
21/6/2018 | PSBA | Inter-CAD Electronic Messaging System (ICEMS) | 2016-08-31T00:00:00 | Delivery |  | 2018-03-16T00:00:00 | The ICEMS system cut over for Queensland Police Service (QPS) and Queensland Ambulance Service (QAS) completed successfully on 28-07-2017, and ICEMS for the Queensland Fire and Emergency Services (QFES) completed successfully on 24-01-2018. Project closure activities are being finalised. The ICEMS Project experienced significant technical and implementation issues causing multiple approved re-baselines between November 2015 and September 2017. This resulted in a revised timeframe from the original planned end date 31-08-2016 to 16-03-2018 and a revised budget from the original planned expenditure of $560K to $1,571K. The original planned end date has been updated to 31-08-2016 as it was previously incorrectly reported. | 2018-04-27T00:00:00 | Critical | 560000 |  | Public Safety Business Agency | 99 | 1570683 |  | G | 3 | To implement the ICEMS protocol between the Queensland Police Service (QPS), Queensland Ambulance Service (QAS) and Queensland Fire and Emergency Services (QFES) computer aided dispatch systems to enable Triple Zero data sharing between agencies. | 1571139 | 2015-10-06T00:00:00 | PSBA
21/6/2018 | PSBA | PSBAIGEM Office 365 Implementation Project | 2018-02-20T00:00:00 | Delivery |  | 2018-05-11T00:00:00 | Project budget has been increased to $1.1 million as a result of full rollout planning. 21/6/2018,Project has re-baselined the schedule from 09-03-2018 to 11-05-2018 as a result of moving from pilot to full rollout. 21/6/2018,Schedule was previously re-baselined from 20-02-2018 to 9-03-2018 due to increase in scope, regarding mobility solutions for users. 21/6/2018,To date 235 PSBA users have been successfully migrated to Office 365 services. 21/6/2018,The project is currently working through the preparation tasks for the remaining PSBA users to be migrated to Office 365 (approximately 1100 users). | 2018-04-27T00:00:00 | Critical | 986000 |  | Public Safety Business Agency | 93 | 757613 |  | G | 4 | The project will deliver digital transformation for the Public Safety Business Agency (PSBA) and Inspector-General Emergency Management (IGEM) through the implementation of the Office 365 suite of products to augment the below enhancements to their current business processes. Undertaking smarter meetings; Facilitating better administration; Accessing information anywhere, any time; Engaging and communicating better; Supporting capability development; Facilitating business intelligence; and Enabling efficient workflow and approvals. | 1136000 | 2017-09-20T00:00:00 | PSBA
21/6/2018 | PSBA | QFES Office 365 Implementation Project | 2018-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The Queensland Fire and Emergency Services (QFES) Office 365 Project is scheduled to be delivered by 30-06-2018. Underspends for FY17/18 will be requested to be deferred to FY18/19, to fund additional Office 365 projects. | 2018-04-27T00:00:00 | Medium | 2100000 |  | Public Safety Business Agency | 52 | 628395 |  | G | 5 | This project will deliver the most up-to-date Office 365 suite of products to all Queensland Fire and Emergency Services (QFES) staff and enable QFES to mobilise its workforce. 21/6/2018, 21/6/2018,* Upgrade QFES technology fleet to the latest Microsoft Office version 21/6/2018,* Cloud services will enable mobility 21/6/2018,* Bridge the technology gaps between Public Safety Agencies (PSA) and allow better collaboration | 2100000 | 2017-11-01T00:00:00 | PSBA
21/6/2018 | PSBA | QPS Office 365 Implementation Project | 2018-02-28T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The migration of all QPS mailboxes to Office 365 online services was completed by the original planned end date of 28-02-2018. QPS has approved additional scope to be delivered by 30-06-2018 within the original planned expenditure. The Project Objective has been amended to reflect the scope change. | 2018-04-27T00:00:00 | Critical | 2207000 |  | Public Safety Business Agency | 44 | 1086750 |  | G | 6 | Phase 1 - Mail Migrations The objective of the Queensland Police Service (QPS) Office 365 Implementation Project Phase 1 is to complete the following activities prior to the Frontline and Digital Services Commonwealth Games Change Freeze (mid Feb 2018): 21/6/2018, 21/6/2018,* migrate email, contacts and calendars to Office 365 online services for all QPS staff; and 21/6/2018,* enable anywhere, anytime, any device access to email, contacts and calendar via bring your own (BYO) phone, QPS Officers operational tablets (QLiTEs) and home use for all QPS staff. 21/6/2018, 21/6/2018,Phase 2 - a data migration and a pilot migration of email archives to Office 365 online | 2207000 | 2017-09-07T00:00:00 | PSBA
21/6/2018 | OSR | State Penalties Enforcement Registry (SPER) Program | 2017-12-31T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | Expenditure to date: $30.1M has been for the transformation of the SPER function; and $20.2M has been on the build phase of the ICT Implementation. 21/6/2018,A contract variation has been negotiated and executed as jurisdictional differences required system modifications. | 2018-06-06T00:00:00 | High | 47200000 |  | State Penalties Enforcement Registry | 74 | 50318000 |  | A | 1 | To maintain the integrity of fines as an effective sanction. To uphold confidence in the justice system. To deliver efficient and effective debt management practices which provide value for money to the State. 21/6/2018, | 62150000 | 2014-01-01T00:00:00 | QR
21/6/2018 | RI | Financial Assurance Information Registry (FAIR) | 2018-07-01T00:00:00 | Delivery |  | 2018-07-01T00:00:00 | Project cost to date is at end of April 2018. Project is on track for the system to be operational by 1 July 2018, however, a revised go-live date is under review. | 2018-06-04T00:00:00 | Medium | 15900000 |  | Insurance Commission | 80 | 4818000 |  | G | 2 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
21/6/2018 | RI | Information Security Program | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The program is on track according to schedule and budget. | 2018-06-08T00:00:00 | Medium | 1960000 |  | Office of the Chief Information Officer | 40 | 560596 |  | G | 3 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 21/6/2018, | 1960000 | 2017-10-16T00:00:00 | QR
21/6/2018 | OSR | Office of State Revenue (OSR) Transformation Program | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | Multiple initiatives in progress focussing on machine learning, analytics, data quality, and business process improvements. Overall program is on track. | 2018-06-07T00:00:00 | High | 73548000 |  | Office of State Revenue | 20 | 11660524 |  | G | 4 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 21/6/2018, 21/6/2018,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 73548000 | 2017-08-01T00:00:00 | QR
21/6/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
21/6/2018 | Corporate Services Improvement Systems Board | Lotus Notes Decommissioning | 2016-01-31T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project is on track. | 2018-04-30T00:00:00 | High | 8150000 |  | ERP Projects Board | 46 | 2399000 |  | G | 1 | Deliver improved information platform functions for effective ICT Strategy Alignment | 8150000 | 2015-11-01T00:00:00 | TMR
21/6/2018 | Corporate Services Improvement Systems Board | Stop Cheques - Stage 3 | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The Stop Cheques Stage 3 project is on track. | 2018-04-30T00:00:00 | Medium | 200000 |  | ERP Projects Board | 85 | 200004 |  | G | 2 | Cheques are inefficient and costly to use, process and administer for both the customer and department. A range of solutions have been developed to reduce the number of cheques that the department produces or receives including refund to card at counter, Bulk Bpay solutions and the introduction of new payment methods are being delivered to be more in line with contemporary retail offerings. The outsourcing of cheque production produced a more streamlined process. 21/6/2018,The stop cheques initiative includes 3 elements: 21/6/2018,Outsourcing/cost reduction 21/6/2018,Outbound cheques 21/6/2018,Inbound cheques | 200000 | 2015-02-01T00:00:00 | TMR
21/6/2018 | Corporate Services Improvement Systems Board | Risk Management Solution | 2018-07-01T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The Risk Management Solution project is on track. | 2018-04-30T00:00:00 | High | 350000 |  | Corporate Services Improvement Systems Board | 85 | 920884 |  | G | 3 | Replace the current risk management approach through the delivery of a new and contemporary enterprise Risk Management solution for TMR . | 1024435 | 2016-02-01T00:00:00 | TMR
21/6/2018 | Corporate Services Improvement Systems Board | Integrated Records Information System (IRIS) | 2018-07-01T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The IRIS project is on track. | 2018-04-30T00:00:00 | High | 7967972 |  | Information Technology Branch | 35 | 4701068 |  | G | 4 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 7967972 | 2015-07-01T00:00:00 | TMR
21/6/2018 | Corporate Services Improvement Systems Board | Safety, Health and Environment tool (SHE) | 2018-07-02T00:00:00 | Delivery |  | 2018-07-30T00:00:00 | The Safety, Health and Environment tool project is on track. | 2018-04-30T00:00:00 | Low | 680000 |  | Corporate Services Improvement Systems Board | 40 | 419551 |  | G | 5 | The objective of the SHE project is to replace the current Work Health and Safety ICT solution with an industry standard, cost effective safety management solution that will enable TMR to meet its obligations under the Work Health and Safety 2011 Act, the Right to Information, Information Privacy legislation and the Workers Compensation and Rehabilitation Act 2003 (Qld). | 680000 | 2016-12-05T00:00:00 | TMR
21/6/2018 | Corporate Services Improvement Systems Board | Transactional Services Improvement Program Enhancements | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The Transactional Services Improvement Program Enhancements Stage 3 is on track. | 2018-04-30T00:00:00 | Low | 200000 |  | Transactional Services Improvement Program | 80 | 190070 |  | G | 6 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. | 200000 | 2015-02-01T00:00:00 | TMR
21/6/2018 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | The CDOP Online Portal project is on track. | 2018-04-30T00:00:00 | High | 1500000 |  | Customer Services, Safety and Regulation Division | 90 | 999274 |  | G | 7 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal services currently required. | 1441000 | 2016-01-01T00:00:00 | TMR
21/6/2018 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The eLearner project is currently on track. | 2018-04-30T00:00:00 | High | 2500000 |  | Customer Services, Safety and Regulation Division | 96 | 4126039 |  | G | 8 | Implement an online learning and assessment program at the pre-learner and/or learner stage, to replace enhance learning outcomes. | 4176000 | 2015-06-12T00:00:00 | TMR
21/6/2018 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery |  | 2018-06-28T00:00:00 | The Mobile Compliance Information System project is on track. | 2018-04-30T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 92 | 772381 |  | G | 9 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 894071 | 2016-11-01T00:00:00 | TMR
21/6/2018 | Customer Service, Safety and Regulation Program | Call Centre VOIP Upgrade | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The Call Centre VOIP Upgrade project is on track. | 2018-04-30T00:00:00 | Low | 1140000 |  | Customer Services, Safety and Regulation Division | 60 | 564183 |  | G | 10 | The Call Centre VOIP Upgrade has commenced to upgrade the VOIP telephony platform within the department. The proposed solution will see a reduction in call costs, a shift in capability to a 21/6/2018,contemporary solution utilising an existing investment within the department. | 1140000 | 2017-04-01T00:00:00 | TMR
21/6/2018 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The Ralph Replacement project is on track. An Exception Report for extending the project end date to 29 June 2018 and increasing the budget due to additional scope being identified was approved by the program board in April 2018. | 2018-04-30T00:00:00 | Medium | 500000 |  | Customer Services, Safety and Regulation Division | 75 | 590114 |  | G | 11 | TMR's current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace the existing application with a contemporary and supportable alternative to assist the department in maintaining its timely updating of fees and charges. | 734000 | 2016-07-01T00:00:00 | TMR
21/6/2018 | Customer Service, Safety and Regulation Program | Voice Comms Mgt System | 2017-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The Voice Comms mgt System project is on track. | 2018-04-30T00:00:00 | Medium | 828000 |  | Customer Services, Safety and Regulation Division | 80 | 274738 |  | G | 12 | The Voice Comms Management project consists of two replacement of existing Voice Communication and Control Systems at Townsville and Hay Point. | 828000 | 2016-01-01T00:00:00 | TMR
21/6/2018 | Customer Service, Safety and Regulation Program | Registration and CTP Certificates Online | 2017-12-31T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | The Registration and CTP Certificates Online project is on track. | 2018-04-30T00:00:00 | Medium | 450000 |  | Customer Services, Safety and Regulation Division | 30 | 312037 |  | G | 13 | Create an online service for customers to register their vehicle | 450000 | 2017-05-01T00:00:00 | TMR
21/6/2018 | Customer Service, Safety and Regulation Program | Vessel Traffic Services (VTS) | 2016-01-05T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | The Vessel Traffic Services (VTS) project is on track. | 2018-04-30T00:00:00 | High | 15224694 |  | Customer Services, Safety and Regulation Division | 30 | 6901394 |  | G | 14 | The purpose of the project is procure and implement a replacement decision support tool for the existing Vessel Traffic Service (VTS) used by TMR to track and monitor ship movements within Queensland ports, the Great Barrier Reef and the Torres Strait. | 25569044 | 2014-04-14T00:00:00 | TMR
21/6/2018 | Customer Service, Safety and Regulation Program | R and L Systems Software Upgrade - Stage 2 | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The R and L Systems Software Upgrade Stage 2 project is on track. Last reporting period this projects Actual Cost to date was reported incorrectly. The R and L Systems Software Upgrade Stage 2 project has spent $920,299 to date, which is now correctly reflected in the April 2018 TMR dashboard data upload. | 2018-04-30T00:00:00 | Medium | 780000 |  | Customer Services, Safety and Regulation Division | 80 | 920299 |  | G | 15 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
21/6/2018 | Infrastructure Management and Delivery | Work Improvement Note (WIN) Replacement | 2016-12-19T00:00:00 | Delivery |  | 2018-02-27T00:00:00 | The WIN Replacement project has successfully completed its scope and a project closure report will be submitted to the Program Board for consideration in May 2018. | 2018-04-30T00:00:00 | Low | 242612 |  | Infrastructure Management 21/6/2018,and Delivery | 99 | 358229 |  | G | 16 | The Work Improvement Note (WIN) System is used to capture, track, review and report on improvements, potential problems, non-conformances, corrective actions, customer feedback and complaints. The WIN System is an essential component of the overarching business management system as it meets specific certification requirements outlined in international quality, safety and environmental standards. This project will provide a replacement to the existing Work Improvement Note (WIN) system, which is dependent on unsupported technology. | 436375 | 2016-02-15T00:00:00 | TMR
21/6/2018 | Passenger Transport Technology Program | 2018 Commonwealth Games Journey Planner (GJP) | 2017-10-13T00:00:00 | Closed |  | 2018-04-27T00:00:00 | The 2018 Games Journey Planner project has successfully completed its scope and the Program Board endorsed the project closure report in April 2018. The 2018 Games Journey Planner project will report for one additional reporting period prior to being removed from the QG ICT Dashboard. | 2018-04-30T00:00:00 | High | 450000 |  | Commonwealth Games | 100 | 863063 |  | G | 17 | A dedicated Journey Planner application supports this need by providing a single source of truth for all transport information related to the Games, and also allows for rapid changes to routes, schedules, and stops, if any are required, in order to drive transport behaviour and maintain network efficiency. | 1348255 | 2016-10-16T00:00:00 | TMR
21/6/2018 | Passenger Transport Technology Program | Single Integrated Network Project (SNIP) | 2018-09-29T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | The Single Integrated Network Project (SNIP) project has not previously reported on the ICT Dashboard. The project is on track. | 2018-04-30T00:00:00 | High | 4992243 |  | Passenger Transport Technology Program | 30 | 495789 |  | G | 18 | Have a system in place that is consistent and integrated across service providers and TransLink. 21/6/2018,Ensure business continuity of systems. 21/6/2018,Extend the existing scheduling and network capability solution to enable it to be ready for the bus contracts (SEQBCPP). 21/6/2018,Eliminate inefficiencies and inaccuracies that occur in the current processes and dispersed data entry options. 21/6/2018,Transparency of service providers activities and performance. 21/6/2018,To improve customer experience through more accurate and reliable service information. 21/6/2018,Contributor for achieving Government objectives. | 4992243 | 2017-02-23T00:00:00 | TMR
21/6/2018 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | The STAS project is reporting amber as a result of unforeseen complexities associated with provisioning and transitioning of business supplied data to the new platform. The project is experiencing delays as resolution activities take place to ensure a good customer experience when the project is released to the public. | 2018-04-30T00:00:00 | High | 4166000 |  | TransLink | 65 | 4580562 |  | A | 19 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 5303876 | 2016-04-01T00:00:00 | TMR
21/6/2018 | Policy Planning and Investment Program | Portfolio, Program, Project and Contract Management (3PCM) - Phase 2 and 3 | 2017-03-31T00:00:00 | Delivery |  | 2017-12-22T00:00:00 | The 3PCM project is 'closely monitored' due to finalising approvals of the Project Closure Report. Once the Project Closure Report is approved and noted, the project will be marked as closed on the QG ICT Dashboard. | 2018-04-30T00:00:00 | High | 12757788 |  | Policy, Planning and Investment Division | 99 | 47794126 |  | A | 20 | Define and implement standard, consistently applied processes for planning, managing and delivering the Transport Infrastructure Portfolio across the domains of portfolio, program, project and contract management 21/6/2018,Source and implement an integrated, strategic information communication technology solution that supports the business process and rules and enables a transition away from legacy applications | 47908928 | 2012-09-01T00:00:00 | TMR
21/6/2018 | CS | Asset Assessment System | 2016-06-30T00:00:00 | Delivery |  | 2018-08-06T00:00:00 | The project has returned to tracking to plan | 2018-04-10T00:00:00 | High | 1688788 |  | Corporate Services | 84 | 1631131 |  | G | 1 | To improve the reliability and integrity of asset information, the ability to report on asset information by applying best practice asset management principles. | 1967000 | 2014-02-27T00:00:00 | DET
21/6/2018 | SS | Early Start | 2015-07-03T00:00:00 | Delivery |  | 2018-07-31T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | High | 70000 |  | State Schools | 74 | 73522 |  | G | 2 | To provide schools with enhanced reporting functionality, improving their ability to analyse Prep to Year 2 student learning data. | 200992 | 2013-04-03T00:00:00 | DET
21/6/2018 | PPP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Medium | 700000 |  | Policy, Performance and Planning | 82 | 1278953 |  | G | 3 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
21/6/2018 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery |  | 2018-12-07T00:00:00 | The project is tracking to plan. The Project is undergoing procurement/commercial activities with no financial information being published. | 2018-04-10T00:00:00 | Medium | 0 |  | Corporate Services | 42 | 0 |  | G | 4 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DET FBS SAP future state landscape for the next five years | 0 | 2017-01-16T00:00:00 | DET
21/6/2018 | CS | Injury Management System | 2017-03-27T00:00:00 | Delivery |  | 2018-10-01T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Critical | 1900000 |  | Corporate Services | 0 | 900471 |  | G | 5 | To improve the management of workplace rehabilitation and claims for injured/ill staff | 1813805 | 2016-10-10T00:00:00 | DET
21/6/2018 | ODG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Medium | 632585 |  | Office of the Director-General | 90 | 885218 |  | G | 6 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
21/6/2018 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery |  | 2019-09-13T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Medium | 16670000 |  | State Schools | 50 | 9041598 |  | G | 7 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 23470000 | 2015-08-03T00:00:00 | DET
21/6/2018 | PPP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery |  | 2018-06-13T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Medium | 1502300 |  | Policy, Performance and Planning | 64 | 1077823 |  | G | 8 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution | 1266210 | 2016-03-01T00:00:00 | DET
21/6/2018 | CS | Project Delivery System | 2018-10-01T00:00:00 | Delivery |  | 2019-01-29T00:00:00 | The project is being closely monitored for schedule | 2018-04-10T00:00:00 | Medium | 1817566 |  | Corporate Services | 0 | 797688 |  | A | 9 | To improve the reliability and integrity of under construction asset information, the ability to report on asset project information by applying best practice asset management principles | 2291613 | 2016-07-05T00:00:00 | DET
21/6/2018 | PPP | Research Services 2.0 | 2016-09-30T00:00:00 | Delivery |  | 2017-09-29T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Medium | 230000 |  | Policy, Performance and Planning | 85 | 404745 |  | G | 10 | To develop a solution that assists in the management of the Department of Education and Training commissioned research proposals and projects, improving resourcing and information dissemination. | 431157 | 2015-11-02T00:00:00 | DET
21/6/2018 | TS | Study Tours Support System Upgrade | 2016-06-30T00:00:00 | Delivery |  | 2018-01-31T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Medium | 680000 |  | Training and Skills | 96 | 772580 |  | G | 11 | To replace or upgrade the existing Study Tours system with an online solution that has enhanced functionality, improving processes, data quality and tour management. | 831125 | 2015-08-31T00:00:00 | DET
21/6/2018 | SS | Trial of platform for virtual academies | 2017-10-02T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | Medium | 151641 |  | State Schools | 40 | 224411 |  | G | 12 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage; safe and secure like-minded student virtual communities; and strategic partnerships with university, industry and business. 21/6/2018, 21/6/2018, | 151641 | 2016-06-21T00:00:00 | DET
21/6/2018 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | The project is tracking to plan | 2018-04-10T00:00:00 | High | 41000000 |  | Corporate Services | 52 | 30228550 |  | G | 13 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
21/6/2018 | [20 empty] | INVERSTMENT INFO
21/6/2018 | CSGC | Coal Seam Gas Groundwater Monitoring Arrangements | 2017-12-31T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | Project delivery is complete, project closure activities are underway 21/6/2018, 21/6/2018,May 2018 - The project has recommenced and is nearing completion. Closure activities are under way. 21/6/2018, 21/6/2018,January 2018 - A change to the planned end date has been approved; there is no impact to cost. Initiative is now paused until early 2018. 21/6/2018, 21/6/2018,August 2017 - Revised total expenditure (budget) updated to include all operating costs not previously reported. 21/6/2018, 21/6/2018,June 2017 - Progress is continuing as planned. Still on schedule to complete December 2017. 21/6/2018, 21/6/2018,December 2016 - Much of the project has been completed and a significant amount of the procurement expenditure for capital equipment has occurred. 21/6/2018, 21/6/2018,October 2016 - Progress is continuing as planned. 21/6/2018, 21/6/2018,August 2016 - Cost returned to Green after a review of costs associated with activities remaining, and a correction in actual cost to date adjustment. 21/6/2018, 21/6/2018,June 2016 - Cost is Amber with a resource review under way. 21/6/2018, 21/6/2018,February 2016 - Progress is continuing as planned. | 2018-06-08T00:00:00 | High | 2380568 |  | Coal Seam Gas Compliance | 100 | 2608283 |  | G | 1 | Enhance availability of groundwater data through improvements to network monitoring of bores for clients and landholders. | 2598256 | 2014-01-13T00:00:00 | DNRM
21/6/2018 | SIMTARS | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery |  | 2019-03-01T00:00:00 | The project is continuing as planned. 21/6/2018, 21/6/2018,February 2018 - A change request was approved to alter the scope and associated percentage complete, time-frame and costs. 21/6/2018, 21/6/2018,December 2017 - Awaiting confirmation of project closure; project is still operating within approved time-frame tolerance. 21/6/2018, 21/6/2018,November 2017 - A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 21/6/2018, 21/6/2018,October 2017 - The project is continuing as planned. 21/6/2018, 21/6/2018,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2018-06-08T00:00:00 | High | 563000 |  | SIMTARS (Safety In Mines Testing and Research Station) | 65 | 717781 |  | G | 2 | The development and delivery of a (replacement) modern and robust Safegas solution: 21/6/2018, 21/6/2018,* risk reduction increasing capability to manage the volume of queries, transactions and data 21/6/2018,* decrease database corruption related to incidents. | 1170000 | 2017-01-25T00:00:00 | DNRM
21/6/2018 | SO | Mines Infrastructure Risk Mitigation Project | 2019-02-18T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | The project is continuing as planned. 21/6/2018, 21/6/2018,April 2018 - A minor adjustment to scope has been approved; there is no impact to timeframe or cost. 21/6/2018, 21/6/2018,March 2018 - The project is continuing as planned. 21/6/2018, 21/6/2018,November 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-06-08T00:00:00 | High | 1200000 |  | Statewide Operations | 35 | 380000 |  | G | 3 | Migrate systems to supported infrastructure and software to: 21/6/2018, 21/6/2018,* provide a stable, secure, fully supported and flexible solution 21/6/2018,* eliminate the risks to which the geoscience data assets are currently exposed. | 1200000 | 2017-08-08T00:00:00 | DNRM
21/6/2018 | LSI | Queensland Globe Improvements | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project is continuing as planned. 21/6/2018, 21/6/2018,December 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-06-08T00:00:00 | High | 1002450 |  | Land and Spatial Information | 90 | 926761 |  | G | 4 | Enhancements to Queensland Globe to continue to evolve and improve user satisfaction and experience, such as: 21/6/2018, 21/6/2018,* create and save user-defined topics 21/6/2018,* improve query and access 21/6/2018,* provide editable 'redlining' 21/6/2018,* improve data imports. | 1002450 | 2017-10-09T00:00:00 | DNRM
21/6/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Closed |  | 2018-05-25T00:00:00 | Closed - Close out activities complete 15-05-2018. 21/6/2018, 21/6/2018,April 2018 - The project is nearing completion. A small extension to the planned end da+S3te has been approved to allow for closure activities. 21/6/2018, 21/6/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 21/6/2018, 21/6/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 21/6/2018, 21/6/2018,June 2017 - Revised Schedule approved returning the project to Green. 21/6/2018, 21/6/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 21/6/2018, 21/6/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 21/6/2018, 21/6/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 21/6/2018, 21/6/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. | 2018-06-08T00:00:00 | Critical | 567500 |  | Governance and Engagement, Energy | 100 | 920000 |  | G | 5 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 21/6/2018, 21/6/2018,* register and maintain their information 21/6/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DNRM
21/6/2018 | QWSR | Dam Safety Regulation Solution | 2016-10-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | A change request has been approved altering the planned end date to remediate technical difficulties that have been expereinced in the move to production. 21/6/2018, 21/6/2018,May 2018 - The project is continuing within timeframe tolerance, and is expected to close prior to the end of May 2018. 21/6/2018, 21/6/2018,March 2018 - The project is continuing as planned. 21/6/2018, 21/6/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 21/6/2018, 21/6/2018,August 2017 - Approved extension of timeframe. 21/6/2018, 21/6/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 21/6/2018, 21/6/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 21/6/2018, 21/6/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 21/6/2018, 21/6/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 21/6/2018, 21/6/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2018-06-08T00:00:00 | High | 1390000 |  | Queensland Water Supply Regulator | 98 | 1385060 |  | G | 6 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 21/6/2018, 21/6/2018,* support compliance with legislation 21/6/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 21/6/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 21/6/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 21/6/2018, | 1390000 | 2012-04-01T00:00:00 | DNRM
21/6/2018 | Natural Resources | Land Condition Assessment Tool | 2018-04-30T00:00:00 | Delivery |  | 2018-09-26T00:00:00 | A change request has been approved altering the planned end date and budget to allow for resolution of unforeseen complexities in deliverables. 21/6/2018, 21/6/2018,May 2018 - The project timeframe is currently being monitored, with action under way to return it to Green. 21/6/2018, 21/6/2018,April 2018 - This project is reporting for the first time and is progressing as planned. | 2018-06-08T00:00:00 | Medium | 414000 |  | Operations Support | 43 | 117960 |  | G | 7 | Implement a solution for government, industry and other stakeholders to objectively and consistently assess land condition, including development of a pictogram-based mobile web application and a data collection tool. | 414000 | 2017-01-12T00:00:00 | DNRM
21/6/2018 | DPC | Performance Information Management Systems (PIMS) Dynamic 365 upgrade and relocation. | 2018-10-30T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | The project commenced in May 2018 and is on track for delivery. The Discovery Phase has been completed and the scope of work for the upgrade project finalised. The first meeting of the PIMS Upgrade Oversight Group was held in late May. | 2018-05-30T00:00:00 | High | 240494 |  | Premier and Cabinet | 15 | 29274 |  | G | 1 | To upgrade the existing PIMS solution from the current 2013 version to Microsoft Dynamics 365 and move the system to Microsoft Online. | 240494 | 2018-05-01T00:00:00 | DPC
21/6/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
21/6/2018 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 21/6/2018,* Move operational accountability and responsibility for print and imaging devices to the service provider 21/6/2018,* Reduce print and imaging costs 21/6/2018,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
21/6/2018 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
21/6/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
21/6/2018 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 21/6/2018, 21/6/2018,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
21/6/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
21/6/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 21/6/2018, 21/6/2018,* reduce operating costs 21/6/2018,* increase capacity 21/6/2018,* improve customer experience 21/6/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
21/6/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
21/6/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 21/6/2018, 21/6/2018, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
21/6/2018 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 21/6/2018, 21/6/2018,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
21/6/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
21/6/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 21/6/2018, 21/6/2018,November 2017 - Actual cost to date corrected due to input error. 21/6/2018, 21/6/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 21/6/2018, | 2017-12-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 57 | 733941 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
21/6/2018 | ESR | Environmental Management Register/Contaminated Land Register - replacement | 2017-06-30T00:00:00 | Paused |  | 2017-06-30T00:00:00 | Approval to re-commence has been denied and the project has been directed to end. End project activities are currently underway. 21/6/2018, 21/6/2018,May 2018 - A review of resource availability is under way. 21/6/2018, 21/6/2018,March 2018 - The project remains paused with a new change request under development that will see the project move back into delivery with a Green status 21/6/2018, 21/6/2018,August 2017 - The project is paused awaiting the outcome of a change request for additional scope; this will return the project to a Green status. 21/6/2018, 21/6/2018,April 2017 - A minor correction has been made to the revised total estimated expenditure to include $20,000 operating prior years. 21/6/2018, 21/6/2018,February 2017 - A change request has been approved moving the initiative cost back to Green. 21/6/2018, 21/6/2018,December 2016 - Project is continuing as planned, with a change request under way to return cost to Green. 21/6/2018, 21/6/2018,October 2016 - Project delivery activities formally commenced on 2 October 2016. 21/6/2018, 21/6/2018,August 2016 - The initiative was paused for some time but has now recommenced and moved into delivery. It is progressing as planned. | 2018-06-08T00:00:00 | High | 981680 |  | Environmental Services and Regulation | 78 | 718000 |  | A | 1 | The current system no longer supports efficient delivery of the department's responsibilities. The replacement will: 21/6/2018, 21/6/2018,* mitigate the risks associated with a system that is beyond its useful life 21/6/2018,* improve access to information by individuals, business and industry conducting searches (property lot plan) of the registers 21/6/2018,* support the creation of notices to stakeholders 21/6/2018,* reduce manual tasks through the introduction of automated workflows and customer self-serve and self-correct. 21/6/2018, | 1111680 | 2016-07-01T00:00:00 | EHP
21/6/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project is progressing as planned. 21/6/2018, 21/6/2018,November 2017 - Actual cost to date corrected due to input error. 21/6/2018, 21/6/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. | 2018-06-08T00:00:00 | Medium | 1750000 |  | Queensland Parks and Wildlife Service | 78 | 1209048 |  | G | 2 | Acquire one or more solution components to operate in conjunction with the agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | EHP
21/6/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP
20/3/2018 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Initiate | G | 2018-12-31T00:00:00 |  | 2018-01-31T00:00:00 | High | 5600000 | G | eHealth Queensland | 10 | 412698 | G | G | 1 | This project aims to establish a robust, highly available and secure contemporary platform that has the capability to support the agile eHealth Strategy. | 5600000 | 2017-07-03T00:00:00 | DH
20/3/2018 | HSQ | AUSLAB Re-hosting project | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-01-31T00:00:00 | High | 1691324 | G | Health Support Queensland | 20 | 215663 | G | G | 2 | Delivery of a replacement hardware and visualisation solution for the AUSLAB and AUSCARE systems that will achieve improved resiliency of the architecture, updated operating system and inclusion of virtualisation. AUSLAB and AUSCARE are critical to support laboratories and patient clinical care. | 1691324 | 2017-08-28T00:00:00 | DH
20/3/2018 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2016-08-01T00:00:00 | Delivery | G | 2018-07-30T00:00:00 |  | 2018-02-13T00:00:00 | High | 1858668 | G | Metro North | 35 | 974181 | G | G | 3 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 20/3/2018, 20/3/2018,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Women 20/3/2018,92s Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 20/3/2018, 20/3/2018,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 2482431 | 2015-06-01T00:00:00 | DH
20/3/2018 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 11180394 | G | eHealth Queensland | 11 | 244358 | G | G | 4 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 20/3/2018,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work. 20/3/2018,a0 Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 11180394 | 2017-07-03T00:00:00 | DH
20/3/2018 | MNHHS | Business Intelligence - Enterprise Data Warehouse | 2018-06-29T00:00:00 | Delivery | G | 2018-06-28T00:00:00 |  | 2018-02-13T00:00:00 | High | 2114991 | G | Metro North | 72 | 1470224 | G | G | 5 | This project will introduce Business Intelligence and Data Warehousing capabilities at MNHHS. The project will deliver BI & DW technical skills, system infrastructure, data automation tools, a pilot dataset, data governance processes and quality control framework at MNHHS. Metro North Finance and MNIT are jointly managing the project. | 2114991 | 2016-11-01T00:00:00 | DH
20/3/2018 | MNHHS | Central Patient Monitoring Equipment Replacement | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-02-13T00:00:00 | High | 1236416 | G | Metro North | 40 | 374088 | G | G | 6 | Metro North IT has been approached by Metro North Procurement Services (MNPS) to provide ICT advice and guidance into the Central Patient Monitoring Equipment Replacement (CPMER) Project. The Health Technology Equipment Replacement (HTER) program for central monitoring systems is providing funding in financial years 16/18 for physiological monitoring equipment requiring replacement across MNHHS hospital facilities. There is an estimated 312 pieces of equipment, primarily Physiological Monitoring devices, to be replaced under the program across MNHHS hospital facilities. MNHHS implementations are being co-ordinated by MNPS. | 1236416 | 2017-06-28T00:00:00 | DH
20/3/2018 | MNHHS | CISS (Community, Indigenous and Subacute Services) Wi-Fi | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-02-13T00:00:00 | Medium | 1280798 | G | Metro North | 51 | 777860 | G | G | 7 | The Community, Indigenous and Subacute Services (CISS) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the internal areas of the prioritised CISS sites. 20/3/2018, 20/3/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1280798 | 2017-07-28T00:00:00 | DH
20/3/2018 | EHQ | Cloud First Project | 2018-06-30T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-01-31T00:00:00 | High | 4250000 | G | eHealth Queensland | 45 | 2304030 | G | G | 8 | The Cloud First project will build internal capability and establish processes within Queensland Health to appropriately utilise cloud services on an ongoing basis. | 4107007 | 2017-01-01T00:00:00 | DH
20/3/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Clinical Notes project (release 3.0) | 2018-02-06T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-02-05T00:00:00 | High | 1415000 | G | Clinical Excellence | 75 | 1434705 | G | G | 9 | Upgrading the CIMHA Mental Health Act module to accommodate a re-architecture of the CIMHA clinical notes module is required to deliver benefits to the clinical workforce associated with data entry efficiencies; improved data sharing across digital platforms; patient level information transfer to third parties to support service integration and data mining to support service improvement and research. | 1969365 | 2017-02-20T00:00:00 | DH
20/3/2018 | EHQ | Critical Network Hardware | 2018-02-28T00:00:00 | Delivery | G | 2018-05-31T00:00:00 | January: The project is reporting 'Amber' due to limited resource availability and additional technical requirements, impacting the schedule of the project. | 2018-01-31T00:00:00 | High | 8636364 | A | eHealth Queensland | 60 | 7352201 | A | A | 10 | The objectives of the project include: 20/3/2018,a) Mitigate the Department of Health risk that core network switches at QH facilities will no longer be supported by the manufacturer from February 2018. 20/3/2018,b) Invest in the replacement of critical ICT network hardware to maintain current capability and reliability of the data network for 120+ enterprise clinical and business applications and provide the foundation for future capability in the enterprise data centres. 20/3/2018,c) Ensure hardware replacement occurs with minimal impact to business operations in Hospital and Health Services or Corporate offices. 20/3/2018,d) Update logical and physical design and architecture documentation for ease of maintenance and management. | 8001607 | 2017-03-06T00:00:00 | DH
20/3/2018 | EHQ | Digital Collaboration Platform Program | 2018-06-30T00:00:00 | Delivery | G | 2019-02-28T00:00:00 | January: This project is experiencing delays in pre-migration activities. | 2018-01-31T00:00:00 | High | 11000000 | A | eHealth Queensland | 32 | 8151262 | R | R | 11 | This program will deliver digital collaboration tools for any time, any where, any device including: 20/3/2018, 20/3/2018,95 Email and Archiving 20/3/2018, 20/3/2018,95 Establishment and Collaboration 20/3/2018, 20/3/2018,95 Productivity Suite Enablement | 18467291 | 2015-10-29T00:00:00 | DH
20/3/2018 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate | G | 2017-12-31T00:00:00 | January: The planned end date will be updated within following reporting periods to reflect the project's updated schedule. | 2018-01-31T00:00:00 | High | 1500000 | G | Queensland Ambulance Service | 40 | 517744 | G | G | 12 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 4167216 | 2015-12-01T00:00:00 | DH
20/3/2018 | QAS | e-ARF Redevelopment for iPad | 2016-12-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | January: The system was implemented in late November, and the project is currently within the project closure stage. | 2018-01-31T00:00:00 | High | 2624000 | G | Queensland Ambulance Service | 99 | 1762732 | G | G | 13 | This is an initiative to provide the electronic Ambulance Report Form (eARF) electronic patient care solution via iPads in the field. | 1910813 | 2015-09-02T00:00:00 | DH
20/3/2018 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | January: Further solution clarification is required, which has impacted on the delivery timeframe of this project. | 2018-01-31T00:00:00 | High | 1283000 | G | Chief Health Officer and Prevention | 49 | 59500 | A | A | 14 | ?Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1283000 | 2017-03-01T00:00:00 | DH
20/3/2018 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery | G | 2018-11-30T00:00:00 |  | 2018-02-13T00:00:00 | High | 4827917 | G | Metro North | 55 | 2360602 | G | G | 15 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (ieMR) program. 20/3/2018, 20/3/2018,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 20/3/2018, 20/3/2018,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. | 4827917 | 2016-07-01T00:00:00 | DH
20/3/2018 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 3792744 | G | eHealth Queensland | 6 | 157529 | G | G | 16 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment. 20/3/2018,a0 20/3/2018,a0The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access. 20/3/2018,a0 | 3792744 | 2017-07-05T00:00:00 | DH
20/3/2018 | QAS | Enterprise Rostering System | 2018-12-31T00:00:00 | Paused | G | 2018-12-31T00:00:00 |  | 2018-01-31T00:00:00 | High | 1000000 | G | Queensland Ambulance Service | 10 | 505297 | G | G | 17 | The initiative is to provide a centralised electronic rostering system to replace existing aging and disparate manual systems currently being utilised across the state. | 1194682 | 2016-12-01T00:00:00 | DH
20/3/2018 | EHQ | File Services Migration | 2017-06-30T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 3400000 | G | eHealth Queensland | 25 | 2676132 | G | G | 18 | The purpose of this investment is to adopt a contemporary, simplified file management solution for Queensland Health that enables a more cohesive customer experience. | 9907925 | 2016-08-01T00:00:00 | DH
20/3/2018 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 |  | 2018-02-02T00:00:00 | High | 33827000 | G | Clinical Excellence | 17 | 8169763 | G | G | 30 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 33827000 | 2017-03-01T00:00:00 | DH
20/3/2018 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Delivery | G | 2018-12-31T00:00:00 |  | 2018-01-31T00:00:00 | High | 105000000 | G | Metro North | 52 | 47469241 | G | G | 19 | The current Queensland Health Finance, Asset and Materials Maintenance Information System (FAMMIS) system is based on a heavily customised solution which is almost 20 years old and no longer supported. 20/3/2018,The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 20/3/2018, 20/3/2018,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 20/3/2018,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 20/3/2018, 20/3/2018,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
20/3/2018 | EHQ | Follow Me Desktop - Deployment | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 3952980 | G | eHealth Queensland | 35 | 809182 | G | G | 20 | Follow Me Desktop Deployment Project will deliver 20/3/2018,a0the Follow Me Desktop service (FMD) to HHS 20/3/2018,92 in alignment with the Infrastructure Remediation Program (IMP) and ieMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 3952980 | 2017-07-03T00:00:00 | DH
20/3/2018 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-01-31T00:00:00 | High | 3301500 | G | eHealth Queensland | 13 | 117505 | G | G | 21 | Project Purpose: 20/3/2018,a0To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 2490769 | 2017-07-01T00:00:00 | DH
20/3/2018 | EHQ | ICT Regional Wireless Infrastructure Initiatives | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-01-31T00:00:00 | High | 4170000 | G | eHealth Queensland | 35 | 2435249 | G | G | 22 | The Regional eHealth Project (ReHP) is a Wireless LAN and Network Infrastructure uplift project so that sites in Far North Qld are ready to rollout their new eHealth Application. | 3489114 | 2017-07-01T00:00:00 | DH
20/3/2018 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | Critical | 1120000 | G | eHealth Queensland | 20 | 342946 | G | G | 23 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. | 1120000 | 2017-07-05T00:00:00 | DH
20/3/2018 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 3215000 | G | eHealth Queensland | 36 | 4323547 | G | G | 24 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 12318334 | 2015-06-22T00:00:00 | DH
20/3/2018 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-01-31T00:00:00 | High | 1500000 | G | Queensland Ambulance Service | 80 | 591017 | G | G | 42 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1744000 | 2015-10-01T00:00:00 | DH
20/3/2018 | EHQ | ieMR Program (Funding Packages 3 and 4) | 2019-04-30T00:00:00 | Delivery | G | 2019-04-30T00:00:00 |  | 2018-01-31T00:00:00 | High | 0 | G | eHealth Queensland | 25 | 0 | G | G | 25 | ieMR will enable improved patient care through the development of a state-wide, authoritative single source of the patient records. 20/3/2018, 20/3/2018,The ieMR will provide clinicians with the ability to: 20/3/2018,* access data that is integrated, accurate and clinically relevant 20/3/2018,* support decision making and better use of information 20/3/2018,* optimise management of patients, resources and provision of services 20/3/2018,* support interaction across a network of providers by making it easier to find providers, transfer information and collaborate with multidisciplinary providers. 20/3/2018,The Program scope (all tranches) is to roll out the ieMR system to 24 hospitals across Queensland. 20/3/2018, 20/3/2018,Please note that financial information for ieMR is Commercial in Confidence | 0 | 2016-11-17T00:00:00 | DH
20/3/2018 | EHQ | Infrastructure Capacity FY 17-18 | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-01-31T00:00:00 | Medium | 1000000 | G | eHealth Queensland | 35 | 351452 | G | G | 26 | Project Purpose: 20/3/2018,a0 20/3/2018,The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified 20/3/2018,91organic growth 20/3/2018,92 requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. | 2000000 | 2017-07-01T00:00:00 | DH
20/3/2018 | EHQ | Infrastructure Maintenance Program | 2022-06-30T00:00:00 | Initiate | G | 2022-06-30T00:00:00 |  | 2018-01-31T00:00:00 | Medium | 1161415 | G | eHealth Queensland | 1 | 289325 | G | G | 27 | The Infrastructure Maintenance Program (IMP) 20/3/2018,a0will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 20/3/2018,The scope includes: 20/3/2018,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 20/3/2018,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and 20/3/2018,a0 20/3/2018,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1161414 | 2017-07-03T00:00:00 | DH
20/3/2018 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery | G | 2022-06-30T00:00:00 |  | 2018-02-05T00:00:00 | High | 14673739 | G | Clinical Excellence | 10 | 1336461 | G | G | 28 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 20/3/2018,The ongoing program of work aims to continue and build upon existing functionality by: 20/3/2018, 20/3/2018,95 Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 20/3/2018, 20/3/2018,95 Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 20/3/2018, 20/3/2018,95 Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 20/3/2018, 20/3/2018,95 Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 20/3/2018, 20/3/2018,95 Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
20/3/2018 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate | G | 2022-12-21T00:00:00 |  | 2018-01-31T00:00:00 | High | 6300000 | G | Queensland Ambulance Service | 18 | 424267 | G | G | 29 | Phased delivery of a system supporting QAS business intelligence. | 6300000 | 2017-01-03T00:00:00 | DH
20/3/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 4245973 | G | eHealth Queensland | 59 | 1103433 | G | G | 56 | Will replace or uplift out of date end of life ICT assets. | 4245973 | 2017-07-01T00:00:00 | DH
20/3/2018 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 1 | 2016-11-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | January: Additional scope requirements have caused the project to extend the schedule and request additional finances, which is progressing through the project 20/3/2018,92s governance committee. | 2018-01-31T00:00:00 | High | 8200000 | A | Health Support Queensland | 87 | 20502185 | A | A | 31 | The IWFM project involves: 20/3/2018,- configuring additional functionality (currently available and licensed, but unutilised) within the existing Rostering and Payroll business solutions 20/3/2018,- partnering with HHSs to develop refined business models and business processes to support the roster-to-pay process 20/3/2018,- undertaking extensive training and change management to support the adoption and effective usage of new functionality and processes | 25060122 | 2016-02-17T00:00:00 | DH
20/3/2018 | EHQ | Interoperability Project | 2016-04-29T00:00:00 | Delivery | G | 2019-09-29T00:00:00 |  | 2018-01-31T00:00:00 | High | 23850000 | G | eHealth Queensland | 15 | 9787999 | G | G | 32 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 20/3/2018,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 20/3/2018,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 20/3/2018, | 39189509 | 2015-02-01T00:00:00 | DH
20/3/2018 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Delivery | G | 2020-10-30T00:00:00 |  | 2018-01-31T00:00:00 | High | 64000000 | G | Health Support Queensland | 44 | 16183025 | G | G | 33 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 20/3/2018,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. | 64000000 | 2015-08-28T00:00:00 | DH
20/3/2018 | MNHHS | Learning and Performance Management Project | 2017-06-30T00:00:00 | Initiate | G | 2018-11-26T00:00:00 |  | 2018-02-13T00:00:00 | High | 1178190 | G | Metro North | 70 | 1027734 | G | G | 34 | Implement an integrated Learning Management and Performance Management system with the capability to deliver online learning and training content, facilitate performance development and maintain centralised records for reporting purposes. | 1178190 | 2016-07-11T00:00:00 | DH
20/3/2018 | GCHHS | Medical Imaging Informatics Solution (MIIS) Risk Mitigation | 2018-12-31T00:00:00 | Delivery | G | 2018-12-31T00:00:00 |  | 2018-02-07T00:00:00 | High | 5000000 | G | Gold Coast | 18 | 643136 | G | G | 35 | The Medical Imaging Informatics Solution (MIIS) Risk Mitigation project has identified an Imaging solution which will address the risks and opportunities described in the Case for Change including the mitigation of patient safety risks, increased efficiency and productivity, improvi.ng medical imaging billing revenue collection and cash flow. The solution has user endorsement from radiologists and clinicians and will be specifically configured to meet GCHHS 20/3/2018,92s needs. | 5000000 | 2017-04-03T00:00:00 | DH
20/3/2018 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery | G | 2018-11-30T00:00:00 |  | 2018-02-13T00:00:00 | High | 4030460 | G | Metro North | 35 | 1430660 | G | G | 36 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 20/3/2018, 20/3/2018,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 20/3/2018, 20/3/2018,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
20/3/2018 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | January: The project is now reporting 'Red' due to delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-02-16T00:00:00 | High | 6299780 | R | Metro North | 75 | 5583203 | R | R | 37 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 6299780 | 2014-06-01T00:00:00 | DH
20/3/2018 | EHQ | Metro South and East Queensland ICT Infrastructure Replacement Initiative | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-01-31T00:00:00 | High | 4160449 | G | eHealth Queensland | 58 | 546719 | G | G | 38 | Will replace or uplift out of date end of life ICT assets. | 4160448 | 2017-07-01T00:00:00 | DH
20/3/2018 | EHQ | Metro South East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 2182844 | G | eHealth Queensland | 35 | 153318 | G | G | 39 | Will replace or uplift out of date end of life ICT assets. | 2182843 | 2017-07-01T00:00:00 | DH
20/3/2018 | EHQ | Mobile Application System for Bring Your Own Device | 2018-06-30T00:00:00 | Delivery | G | 2018-07-06T00:00:00 |  | 2018-01-31T00:00:00 | High | 1639698 | G | eHealth Queensland | 50 | 758156 | G | G | 40 | This project leverages the investment of the previous Bring-Your-Own-Device (BYOD) 20/3/2018,a0projects to extend the capability of device mobility by building the foundations of a Mobile Application Ecosystem - the processes, products and services to enable the managed development of low/no code applications by Health and Hospital Services (HHS). 20/3/2018,a0 This project will also complete the deployment of BYOD laptops and provide recommendations on how cost savings can be made by the organisation around Corporate devices and data plans. 20/3/2018,a0 | 1639698 | 2017-07-01T00:00:00 | DH
20/3/2018 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery | G | 2018-12-19T00:00:00 | January: This project is experiencing delays in pre-migration activities and delays experienced in another dependent project. | 2018-01-31T00:00:00 | High | 14100000 | G | eHealth Queensland | 40 | 13879589 | R | R | 41 | This project will move Queensland Health to a modern end user workspace that is: current; delivering collaboration and productivity benefits; able to be accessed anywhere, anytime and on any device; reducing the reliance and expense of on premise infrastructure and support and not constraining the business from taking advantage of modern applications and services. | 27427900 | 2016-05-12T00:00:00 | DH
20/3/2018 | CHOPD | Notifiable Conditions System Replacement | 2019-06-29T00:00:00 | Delivery | G | 2020-02-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 12000000 | G | Chief Health Officer and Prevention | 35 | 2232472 | G | G | 43 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 20/3/2018,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
20/3/2018 | EHQ | Patient Administration System (PAS) Replacement Program | 2017-06-30T00:00:00 | Initiate | G | 2019-03-29T00:00:00 |  | 2018-01-31T00:00:00 | Medium | 3850000 | G | eHealth Queensland | 51 | 3468054 | G | G | 44 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients 20/3/2018,92 journeys, and ensure that accurate information about our patients is readily available when and where required. 20/3/2018, 20/3/2018,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 20/3/2018, 20/3/2018,95 support for patient engagement 20/3/2018, 20/3/2018,95 integrated care 20/3/2018, 20/3/2018,95 clinical research 20/3/2018, 20/3/2018,95 population health (for patients using public health services) 20/3/2018, 20/3/2018,95 performance transparency 20/3/2018, 20/3/2018,95 resource planning. | 11890865 | 2015-11-01T00:00:00 | DH
20/3/2018 | MNHHS | Picture Archiving and Communication System (PACS) | 2017-09-29T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | January: The project is now reporting 'Red' due to delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-02-16T00:00:00 | High | 3114694 | R | Metro North | 75 | 3300756 | R | R | 45 | Procure and implement a contemporary Picture Archiving and Communication (PACS) system and functionality that will ensure improved service delivery for the MNHHS Medical Imaging Departments (and other PACS users) through replacement of RBWH PACS ensuring that it is scalable and able to meet the ongoing needs of Metro North Hospital and Health Service. | 3656297 | 2016-07-11T00:00:00 | DH
20/3/2018 | CSD | Practice Management Enterprise Solution | 2018-11-01T00:00:00 | Initiate | G | 2018-11-01T00:00:00 |  | 2017-12-31T00:00:00 | High | 1470000 | G | Corporate Services | 35 | 341000 | G | G | 46 | The main practice management software used by HHSs to conduct private practice services and billing activities is being replaced. The initiative will procure and implement "like for like" functionality enterprise solution for participating HHSs (15 in total). | 1470000 | 2017-08-01T00:00:00 | DH
20/3/2018 | EHQ | Project, Program and Portfolio Management Application | 2018-03-31T00:00:00 | Initiate | G | 2018-06-29T00:00:00 |  | 2018-01-31T00:00:00 | Medium | 1344177 | G | eHealth Queensland | 25 | 427305 | G | G | 47 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 20/3/2018, | 1473632 | 2017-05-02T00:00:00 | DH
20/3/2018 | CED | Queensland Integrated Safety Information Project (QISIP) / Risk Management | 2017-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-02-01T00:00:00 | High | 4333120 | G | Clinical Excellence | 89 | 7526725 | G | G | 48 | This initiative will source a state wide system to replace existing enterprise risk management systems to support patient and staff incident reporting, feedback, case management and risk management processes. | 16273520 | 2013-01-25T00:00:00 | DH
20/3/2018 | EHQ | Queensland State-wide ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 3246247 | G | eHealth Queensland | 30 | 375571 | G | G | 49 | Will replace or uplift out of date end of life ICT assets. | 3246247 | 2017-07-01T00:00:00 | DH
20/3/2018 | EHQ | Queensland State-wide ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 3283431 | G | eHealth Queensland | 63 | 1488343 | G | G | 50 | Will replace or uplift out of date end of life ICT assets. | 3282431 | 2017-07-01T00:00:00 | DH
20/3/2018 | MNHHS | Quick Flow Project | 2019-02-01T00:00:00 | Initiate | G | 2019-06-30T00:00:00 |  | 2018-02-13T00:00:00 | High | 6408600 | G | Metro North | 35 | 818106 | G | G | 51 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 20/3/2018,The key objectives of the project are to: 20/3/2018, 20/3/2018,95 Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 20/3/2018, 20/3/2018,95 Improve the outpatient experience across MNHSS facilities and community services 20/3/2018, 20/3/2018,95 Improve clinic resource utilisation 20/3/2018, 20/3/2018,95 Increase the efficiency of clinical and administrative processes 20/3/2018, 20/3/2018,95 Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
20/3/2018 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Initiate | G | 2019-12-31T00:00:00 |  | 2018-02-08T00:00:00 | High | 34950000 | G | Cairns and Hinterland | 0 | 8544386 | G | G | 52 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patient 20/3/2018,92s home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
20/3/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 4260336 | G | eHealth Queensland | 35 | 259921 | G | G | 53 | Will replace or uplift out of date end of life ICT assets. | 4260336 | 2017-07-01T00:00:00 | DH
20/3/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 2150147 | G | eHealth Queensland | 55 | 531979 | G | G | 54 | Will replace or uplift out of date end of life ICT assets. | 2150147 | 2017-07-01T00:00:00 | DH
20/3/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 1651750 | G | eHealth Queensland | 35 | 249954 | G | G | 55 | Will replace or uplift out of date end of life ICT assets. | 1651750 | 2017-07-01T00:00:00 | DH
20/3/2018 | EHQ | Service Delivery Excellence Project (SDEP) Stage 1 | 2018-02-28T00:00:00 | Delivery | G | 2018-03-29T00:00:00 |  | 2018-01-31T00:00:00 | High | 713000 | G | eHealth Queensland | 18 | 248836 | G | G | 57 | The Service Delivery Excellence Project (SDEP) aims to improve the service delivery functions of eHealth Queensland to help the organisation achieve its Customers and services Foundation and Shared Goal: 20/3/2018,Enhance value for customers by streamlining end to end services, processes and delivery models so that we can provide an exceptional customer experience. 20/3/2018,Stage 1 has the primary objective of delivering the Project Initiation Document (PID) for the Service Delivery Excellence Project (SDEP) Stage 2. | 7136880 | 2017-10-04T00:00:00 | DH
20/3/2018 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Initiate | G | 2020-09-30T00:00:00 |  | 2018-01-31T00:00:00 | High | 10500000 | G | eHealth Queensland | 9 | 386161 | G | G | 58 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 10500000 | 2017-07-03T00:00:00 | DH
20/3/2018 | MNHHS | Royal Brisbane and Women's Hospital Wi-Fi | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 |  | 2018-02-13T00:00:00 | High | 5000000 | G | Metro North | 12 | 1980023 | G | G | 59 | The RBWH Wi-Fi Project will provide an uplift and renewal to the latest Queensland Health (QH) standard for wireless local area network (WLAN) coverage within the internal areas of prioritised RBWH buildings in order to support digital healthcare. 20/3/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for the RBWH in the near future. | 5000000 | 2017-10-22T00:00:00 | DH
20/3/2018 | EHQ | Storage Asset Replacement | 2018-06-29T00:00:00 | Delivery | G | 2018-06-28T00:00:00 |  | 2018-01-31T00:00:00 | High | 1671556 | G | eHealth Queensland | 22 | 140609 | G | G | 60 | The Storage Asset Replacement (SAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the SAR and Backup Asset Replacement (BAR) projects. 20/3/2018,The SAR project seeks to outline architecture for storage that will provide a cost effective, scalable and fit for purpose environment for the future of storage services within Queensland Health. 20/3/2018,a0 Utilising space saving technologies which will enable further cost savings and reduce the requirement for capacity expansion in the short to medium term. | 1671555 | 2017-07-03T00:00:00 | DH
20/3/2018 | EHQ | Telehealth Asset Replacement FY 17-18 | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2018-01-31T00:00:00 | High | 1960000 | G | eHealth Queensland | 55 | 731742 | G | G | 61 | Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector 20/3/2018,a0 20/3/2018,and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. 20/3/2018,The Department of Health defines Telehealth as: 20/3/2018, 20/3/2018,95Live, audio and/or video inter-active link for clinical consultations and educational purposes 20/3/2018, 20/3/2018,95Store and forward Telehealth - this model can involve digital images, video, audio and clinical data being captured ("stored") on the client computer; then at a convenient time transmitted securely ("forwarded") 20/3/2018,a0 to a clinic at another location where they are studied by relevant specialists 20/3/2018, 20/3/2018,95Teleradiology for remote reporting and clinical advice for diagnostic images 20/3/2018, 20/3/2018,95Telehealth services and equipment to monitor people 20/3/2018,92s health in their home. 20/3/2018,Benefits of Telehealth 20/3/2018, 20/3/2018,95Improve patient access to health care 20/3/2018, 20/3/2018,95Reduce travel and inconvenience for patients, families, carers and health professionals 20/3/2018, 20/3/2018,95Provide health professionals with access to peer support and education. 20/3/2018,The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. 20/3/2018,a0 20/3/2018,The priority is to replace those end-of-life assets which pose the greatest risk to effective health service delivery. | 1960000 | 2017-07-03T00:00:00 | DH
20/3/2018 | MNHHS | The Prince Charles Hospital (TPCH) Wi-Fi | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 |  | 2018-02-13T00:00:00 | High | 1408388 | G | Metro North | 30 | 952844 | G | G | 62 | The Prince Charles Hospital (TPCH) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the hospital campus for prioritised TPCH buildings. 20/3/2018, 20/3/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1408388 | 2017-07-27T00:00:00 | DH
20/3/2018 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery | G | 2018-03-31T00:00:00 | There have been delays to the project schedule from reprioritisation of resources to community recovery activities associated with Cyclone Debbie. Additionally, the vendor, SMS Management and Technology, has not delivered within the contracted timeframes and we are negotiating with the vendor to ensure completion of the solution. | 2018-01-31T00:00:00 | High | 2208000 | G | Whole of Department | 83 | 3072000 | G | G | 1 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3483000 | 2016-07-01T00:00:00 | DCCSDS
20/3/2018 | WOD | ICT Service Transformation Program | 2016-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | Original planned expenditure represented approved budget from start date to 30 June 2016. This program is a multi year program and the revised total expenditure has been updated to include approved funding to 30 June 2018. | 2018-01-31T00:00:00 | Low | 2916000 | G | Whole of Department | 93 | 6605000 | G | G | 2 | This program includes a number of initiatives to implement service improvement opportunities and essential capital replacement activities. The program ensures that ICT systems and services are replaced in a way that supports the department's strategic direction and includes the digital vision and future ways of work roadmap. | 7555000 | 2014-12-13T00:00:00 | DCCSDS
20/3/2018 | WOD | Reporting and Business Intelligence Project | 2017-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | Original planned expenditure represented approved budget from start date to 30 June 2016. This project is a multi year project and the revised total expenditure has been updated to include approved funding to 30 June 2018 to continue reporting and business intelligence deliverables. | 2018-01-31T00:00:00 | Medium | 750000 | G | Whole of Department | 45 | 4026000 | G | G | 3 | The department has a requirement for business intelligence, data management, information presentation and multi-level reporting. | 5541000 | 2015-07-01T00:00:00 | DCCSDS
20/3/2018 | WOD | Social Investment Program | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | The original expenditure includes the approved budget to 30 June 2017 only. The planned expenditure has been revised to include the approved expenditure to 30 June 2018 to complete tranche 1 and 2 of the program. | 2018-01-31T00:00:00 | Critical | 2230000 | G | Whole of Department | 30 | 1762000 | G | G | 4 | The project will implement systems and processes that support the departments social procurement spend and support interventions that are proven to work, offer good value for money and are contributing to the broader objectives of government. | 5028000 | 2016-07-01T00:00:00 | DCCSDS
20/3/2018 | WOD | Complaints Management System | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2018-01-31T00:00:00 | Low | 466000 | G | Whole of Department | 60 | 339000 | G | G | 5 | The objective of the complaints management system project which was formerly incorporated into the Technology Refresh project is to develop a complaints management system which supports the future DCCSDS business structure. The new system must also meet the recommendations made by the Queensland Ombudsman in his Management of Child Safety Complaints report in which the department has agreed that a full review of data fields for the departments complaints management database is conducted and relevant categories aligned to the departments core business practices and best practice complaints handling process. | 466000 | 2017-07-01T00:00:00 | DCCSDS
20/3/2018 | Cross-Gov | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery | G | 2019-12-24T00:00:00 | The Queensland Fire and Emergency Services (QFES) Human Capital Management on-boarding and recruitment functionality was introduced into full business operation in February 2018. Workplace Health and Safety and Case Management functionality will be implemented for QFES in May 2018. 20/3/2018, 20/3/2018,The approach to transition for the Queensland Ambulance Service payroll to Aurion has been reviewed and approved with the implementation timeframe changed from March 2018 to November 2018. 20/3/2018, 20/3/2018,The Executive Steering Committee has also approved the revised program end date which accommodates the introduction of the additional project for the time and attendance solution and the revised schedule for the Queensland Fire and Emergency Services Payroll transition to Aurion. | 2018-02-28T00:00:00 | Critical | 101500000 | G | Cross-Government program led by DSITI | 57 | 54983899 | G | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 20/3/2018, 20/3/2018,* Sustainable and supported HR and Payroll service delivery 20/3/2018,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 20/3/2018,* Strategic HR capability that supports the development, performance and safety of the departments workforce 20/3/2018,* Business Intelligence capability that provides real timely, integrated HR information 20/3/2018,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 20/3/2018,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 20/3/2018,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
20/3/2018 | QPS | Online National Police Certificate Project | 2017-06-30T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | Since the successful launch of Online National Police Certificates 72% of all applications have been submitted online. The overall number of applications submitted online, has doubled from December 2017 to January 2018. 20/3/2018, 20/3/2018,National Police Certificate campaign material is currently being distributed to all Police Districts for display in all Stations and Police Beats. External marketing via social media will commence in February-March 2018. 20/3/2018, 20/3/2018,The revised project budget has been amended from previously published figures to reflect the increased investment in promotional products. | 2018-02-19T00:00:00 | High | 275000 | G | Queensland Police Service | 85 | 230000 | G | G | 1 | The Online National Police Certificate Project will implement an online service for the community to apply and pay for Name Only National Police Certificates online, rather than presenting at a police station, or using the online services of an Australian Crime Intelligence Commission accredited broker. This will provide improved customer service to the community through a more efficient and reliable QPS service, with no requirement to present at a police station, as well as provide efficiency and time savings to local police stations and the Police Information Centre. | 250000 | 2017-01-01T00:00:00 | QPS
20/3/2018 | QPS | Police Integrity and Professional Standards Project | 2020-02-17T00:00:00 | Delivery | G | 2020-02-17T00:00:00 | Previous Invitation to Offer considered and not proceeded with as it was deemed financially un-viable. Project asked to re-scope the market and conduct new Invitation to Offer to establish if vendors for a more affordable and innovative solution are available. Meeting with relevant stakeholders to be organised to discuss way forward. | 2018-02-19T00:00:00 | High | 4142000 | A | Queensland Police Service | 30 | 99000 | A | A | 2 | This initiative will deliver a new integrated Police Integrity and Professional Standards IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The Police Integrity and Professional Standards system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The Police Integrity and Professional Standards Project will also complement the Complaints Reform Project established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of the Police Integrity and Professional Standards system will place the QPS in a strong readiness position to fully implement Complaints Reform Project-generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 4142000 | 2017-03-07T00:00:00 | QPS
20/3/2018 | QPS | Advanced Data Analytics Project | 2017-07-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to deliver new capability in all streams with most capability available for use during the 2018 Commonwealth Games. Current focus is on expanding the capability developed by the project into 2017-18 as business-as-usual capability and positioning the outputs/products of the project for developing the next phase of QPS advanced analytics capabilities. | 2018-02-19T00:00:00 | Low | 1730000 | G | Queensland Police Service | 87 | 2050602 | G | G | 3 | Develop the QPS Advanced Data Analytics proof-of-concept. This proof-of-concept is intended to inform a larger suite of data analytics integration and intelligence over the next four years, including the development of predictive and alert models to enhance the operational response to threats, incidents and events. | 2350000 | 2017-02-19T00:00:00 | QPS
20/3/2018 | QPS | Body Worn Cameras Project | 2018-02-28T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Project completed the deployment of all Stage Two body worn cameras in December 2017 and is now preparing closure activities and transition to business as usual by 30 June 2018. 20/3/2018, 20/3/2018,The original approved budget was $6.03M. In May 2017 the QPS Demand and Resource Committee approved an additional $0.860M, making the total approved budget $6.890M. | 2018-02-19T00:00:00 | Medium Low | 6030000 | G | Queensland Police Service | 80 | 5400000 | G | G | 4 | The Queensland Police Service Body Worn Camera Project is deploying 5100 body worn cameras to frontline police officers. Body worn cameras will be deployed to 168 police stations, 16 tactical crime units, 47 road policing units, and specialist units including dog squads and the Public Safety Response Team in two stages. The cameras integrate with the QPS mobility devices, allowing officers to add metadata to videos and to review videos in the field. A system for storage and allocation of digital camera data will also be implemented as well as policy related to use of the cameras. | 6890000 | 2014-08-25T00:00:00 | QPS
20/3/2018 | PSBA | Weapons Licensing Management System Stage 2a Project | 2017-05-31T00:00:00 | Closed | G | 2017-12-29T00:00:00 | Weapons Licensing 2A Benefits Enhancement Analysis Report for the proposed benefit enhancement rule changes has now been approved by the Project Board. The project has been handed over to Weapons Licensing. Weapons Licensing will implement the four rule changes as part of their business as usual schedule. The remaining project budget has been transferred to Weapons Licensing to fund the implementation of the rule changes. The Project is now going through approval for formal closure. | 2018-02-19T00:00:00 | Medium | 2500000 | G | Public Safety Business Agency | 100 | 1888776 | G | G | 5 | Improved workflow efficiencies, reduction in work queues, less resources required to process licence renewal and weapons Permit to Acquire, etc. | 2156825 | 2015-11-11T00:00:00 | QPS
20/3/2018 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-06-30T00:00:00 | Delivery | G | 2018-12-31T00:00:00 | Objectives: This project will deliver a secondary DR site and hyper-converged system to provide resilience for all departmental applications in the event of disaster. 20/3/2018, 20/3/2018,Secondary datacentre with new hyper-converged infrastructure established. As at Feb 2018 - Project schedule is on track and within budget. 20/3/2018, 20/3/2018,Core infrastructure 70% complete. Estimated completion March 2018. All migrated production system successfully replicating to secondary DR site. 20/3/2018,Oracle infrastructure 50% complete. Estimated completion June 2018. SPER databases successfully migrated to CITEC. QWIC migration in progress. 20/3/2018,By the end of project, all end-of-life ICT infrastructure ready to be decommission which provide stability and life extension to existing business critical applications. 20/3/2018, 20/3/2018,Original planned end date was changed from 30 June 2018 to 31 Dec 2018 due to: 20/3/2018, 20/3/2018,- initial delays in securing project resources (2016-17 Christmas/New Year shutdown) 20/3/2018, 20/3/2018,- high level of project design complexity (heterogeneous environments) 20/3/2018, 20/3/2018,- conformity with appropriate probity and procurement governance. 20/3/2018, 20/3/2018,- requirement to develop a Significant Procurement Plan (SPP). 20/3/2018, | 2018-03-13T00:00:00 | High | 7460674 | G | Corporate Services | 60 | 3390115 | G | G | 1 | * Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 5917255 | 2016-10-01T00:00:00 | DJAG
20/3/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2018-03-31T00:00:00 | Due to delays in the completion of minor works the planned end date has changed to 31 March 2018. The change to the planned end date has been approved by the Project Board. | 2018-01-31T00:00:00 | Medium | 800000 | G | Chief Information Office | 99 | 913763 | A | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | HPW
20/3/2018 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2018-01-31T00:00:00 | The project closed on 31 January 2018 as approved by the project board. | 2018-01-31T00:00:00 | High | 144000 | G | Chief Information Office | 100 | 206000 | G | G | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 20/3/2018,* Move operational accountability and responsibility for print and imaging devices to the service provider 20/3/2018,* Reduce print and imaging costs 20/3/2018,* Leverage innovative technologies. | 206000 | 2016-01-01T00:00:00 | HPW
20/3/2018 | QSS | Legacy Finance Archiving Project | 2018-03-29T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2018-01-31T00:00:00 | High | 845949 | G | Queensland Shared Services | 89 | 487200 | G | G | 3 | This project will archive finance data for legacy finance solution into a standard archive/enquiry solution. | 845949 | 2016-09-01T00:00:00 | HPW
20/3/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2018-03-16T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2018-01-31T00:00:00 | High | 1800000 | G | Queensland Shared Services | 92 | 1597810 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | HPW
20/3/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The automated payment solution has been established as a separate project with key dependencies to the PCI activities. The timeframe is achievable and continues to be closely monitored by the Project Board. | 2018-01-31T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 86 | 986509 | A | A | 5 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | HPW
20/3/2018 | SSQ | Automated Payments Solution | 2018-07-31T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | This project is currently in the procurement phase and is on track. | 2018-01-31T00:00:00 | Critical | 1500000 | G | Smart Service Queensland | 0 | 0 | G | G | 6 | The Automated Payments project will implement an improved capability for offering secure payment card transactions via the telephone. This is a dependency for achieving compliance meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1500000 | 2018-01-29T00:00:00 | HPW
20/3/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The Project Board continues to closely monitor the dependencies with the Content Delivery Solution Project. All other aspects of the project remain on track. | 2018-01-31T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 72 | 3075257 | A | A | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 20/3/2018, 20/3/2018,* reduce operating costs 20/3/2018,* increase capacity 20/3/2018,* improve customer experience 20/3/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | HPW
20/3/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-04-30T00:00:00 | The testing phase of the CDS Project is continuing. The Project Board endorsed an approach to extend the planned end date to 30/4/18 and expand the current testing approach to ensure the product meets the needs of users from a functionality and performance perspective. | 2018-01-31T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 72 | 1662926 | A | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | HPW
20/3/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. | 2018-01-31T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 72 | 1947844 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | HPW
20/3/2018 | QSA | Digital Archiving Program - Tranche 1 | 2019-12-31T00:00:00 | Delivery | G | 2019-12-31T00:00:00 | The % complete relates to the procurement activity which is progressing to planned timeframes and milestones. | 2018-01-31T00:00:00 | Critical | 12701000 | G | Queensland State Archives | 57 | 761721 | G | G | 10 | To ensure the delivery of an as-a-Service eco-system to effectively archive, manage and enable search and discovery of Queensland's permanent high value records. The new digital services will support the Queensland Government's blueprint for innovation and collaboration, providing better outcomes for Queenslanders. | 12701000 | 2017-07-01T00:00:00 | HPW
20/3/2018 | CITEC ICT | z14 Mainframe Upgrade | 2018-07-31T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | The production and disaster recovery machines have been installed and migration of data will commence in February. | 2018-01-31T00:00:00 | High | 4720752 | G | CITEC ICT | 21 | 4472562 | G | G | 11 | The project will replace the two existing z12 Mainframes (Production and Disaster Recovery) with upgraded z14 Mainframes and migrate the existing data from the old to the new. 20/3/2018, 20/3/2018,The current z12 platform is unable to be upgraded and cannot provide sufficient capability for increasing client requirements. The continued use of the z12 platform represents significant risk to business continuity. 20/3/2018, 20/3/2018,The upgrade will reduce ongoing operating costs, enable improved services to clients and provide for clients' future capacity requirements. 20/3/2018, | 4720752 | 2017-12-18T00:00:00 | HPW
20/3/2018 | Housing | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery | G | 2019-03-31T00:00:00 | The intensive period of post go-live support for the first phase Property Release was completed during January. 20/3/2018,The Program continues to progress planning for the second of the two releases, Tenancy, which will remove the operational dependency on the existing ICT housing solution entirely. | 2018-01-31T00:00:00 | Critical | 56286000 | G | Housing Services | 53 | 64784420 | G | G | 12 | Replace the existing ICT housing solution with an integrated ICT system. | 121597695 | 2013-07-01T00:00:00 | HPW
20/3/2018 | PWAM | iSpace External Hosting Migration Project | 2017-01-31T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is scheduled to go live in February 2018. | 2018-01-31T00:00:00 | High | 735000 | A | Queensland Government Accommodation Office | 92 | 851755 | A | A | 13 | Version upgrade and migration of the hosting of Queensland Accommodation Office core system to a hosted managed service arrangement. | 1415203 | 2016-05-01T00:00:00 | HPW
20/3/2018 | QGP | Fleet Management System Replacement Project (FMSRP - QFleet) | 2019-09-30T00:00:00 | Initiate | G | 2019-09-30T00:00:00 | The project is tracking to plan. The project is currently subject to procurement activities. | 2018-01-31T00:00:00 | High | 13939200 | G | QFleet | 2 | 281620 | G | G | 14 | The project will deliver for the Department of Housing and Public Works, Public Safety Business Agency and Queensland Ambulance Service a fleet management solution to replace existing aging legacy systems. | 13939200 | 2017-10-19T00:00:00 | HPW
20/3/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 20/3/2018, 20/3/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 20/3/2018,October 2017 - The project is progressing as planned. 20/3/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 20/3/2018,June 2017 - Revised Schedule approved returning the project to Green. 20/3/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 20/3/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 20/3/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 20/3/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 20/3/2018,December 2016 - The project is progressing as planned. | 2017-12-21T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 20/3/2018, 20/3/2018,* register and maintain their information 20/3/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
20/3/2018 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 20/3/2018, 20/3/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 20/3/2018,August 2017 - Approved extension of timeframe. 20/3/2018,June 2017 - The project is progressing as planned. 20/3/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 20/3/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 20/3/2018,October 2016 - Progress is continuing as planned. 20/3/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 20/3/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 20/3/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-21T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 20/3/2018, 20/3/2018,* support compliance with legislation 20/3/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 20/3/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 20/3/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 20/3/2018, | 1390000 | 2012-04-01T00:00:00 | DEWS
20/3/2018 | BQ | Biosecurity Information Management System Program | 2017-05-31T00:00:00 | Delivery | G | 2018-02-28T00:00:00 | The program is progressing as planned, awaiting formal closure. 20/3/2018, 20/3/2018,December 2017 - Program delivery is complete, however, the final end date has been extended by three months to allow for full transition to business as usual, project and program closure activities and final assurance reviews. 20/3/2018,November 2017 - The planned end date has been extended by one month; this remains within acceptable program tolerances. 20/3/2018,March 2017 - The program is progressing as planned in line with approved change to scope, timeframe, benefits and cost. 20/3/2018,January 2017 - A small scope increase has been proposed, currently progressing through governance processes. 20/3/2018,November 2016 - Note, a scope review is currently under way. 20/3/2018,May 2016 - Program is continuing as planned. Note a small extension to planned end date. 20/3/2018,March 2016 - A re-baseline has brought all parameters back to Green. 20/3/2018,January 2016 - Timeframe, Cost, and Quality remain Amber, pending a business case update due early April 2016. 20/3/2018,November 2015 - Program is still Amber while the Timeframe is being re-baselined. 20/3/2018,September 2015 - The Exception Report has been accepted by the Program Board. Timeframe remains Amber pending a business case update. 20/3/2018,July 2015 - Resources continue to be redirected to assist with emergency response to the Panama banana disease. An Exception Report is being developed to address this. 20/3/2018,May 2015 - As anticipated, the emergency response to the Panama Banana disease outbreak has impacted both the project cost and the Timeframe. 20/3/2018,March 2015 - There is currently an outbreak of Panama banana disease which has potential to impact the schedule of this project. 20/3/2018,January 2015 - Actions are being taken to resolve some current scheduling issues. | 2018-03-16T00:00:00 | Critical | 18080000 | G | Biosecurity Queensland | 98 | 18230000 | G | G | 1 | Deliver an integrated toolkit consisting of various information management technologies and enhanced business processes to improve the management of biosecurity risks in Biosecurity Queensland's day-to-day business operations and in emergency responses. | 19409000 | 2013-07-01T00:00:00 | DAF
20/3/2018 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery | G | 2018-03-31T00:00:00 | A minor scope increase has been proposed, affecting both timeframe and cost, which is progressing through the governance process. 20/3/2018, 20/3/2018,March 2018 - The project is progressing as planned. 20/3/2018, 20/3/2018,December 2017 - A variation to scope was approved, resulting in a change to the planned end date and total estimated expenditure. 20/3/2018, 20/3/2018,November 2017 - The project is continuing as planned. 20/3/2018, 20/3/2018,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2018-03-16T00:00:00 | Medium | 608146 | A | Forestry Queensland | 80 | 784500 | A | A | 2 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 20/3/2018, 20/3/2018,* the capture, management and integration of data 20/3/2018,* value-adding opportunities for business improvement 20/3/2018,* management of risk associated with ongoing use and maintenance of disparate systems. | 976431 | 2016-06-15T00:00:00 | DAF
20/3/2018 | BQCC | Communication and Stakeholder Engagement Solution | 2018-06-29T00:00:00 | Delivery | G | 2018-04-27T00:00:00 | A request for an extension to the timeframe is under consideration, and is currently progressing through the governance process. 20/3/2018, 20/3/2018,March 2018 - Note adjustment to planned end date corrected due to typographical error. 20/3/2018, 20/3/2018,February 2018 - The project is progressing as planned. 20/3/2018, 20/3/2018,December 2017 - The project was approved to move into delivery in October 2017 and is being published for the first time. | 2018-03-16T00:00:00 | Medium | 694000 | G | Biosecurity Queensland Control Centre | 32 | 354603 | A | A | 3 | Implement a simple, easy to use system that will facilitate the collection of information associated with the National Red Imported Fire Ant Eradication Program and the National Electric Ant Eradication Program. This will include contact management, complaints management, history of interactions, event management, training management, social media interactions, marketing campaign and reporting. | 694000 | 2017-06-01T00:00:00 | DAF
20/3/2018 | ASQ | Portfolio Activity Reporting Information System | 2018-06-30T00:00:00 | Paused | G | 2018-06-30T00:00:00 | The project is paused until a funding source is identified. 20/3/2018, 20/3/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-03-16T00:00:00 | High | 500000 | G | Agri-Science Queensland | 10 | 231622 | G | G | 4 | Review and consolidate the variety of processes and technologies currently being used to manage the department's research, development and extension, and other projects. | 500000 | 2015-08-13T00:00:00 | DAF
20/3/2018 | Ag | Risk Reduction for Customer Service Centre | 2019-04-19T00:00:00 | Delivery | G | 2019-04-19T00:00:00 | The project is continuing as planned. 20/3/2018, 20/3/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-03-16T00:00:00 | High | 1767000 | G | Agriculture | 10 | 211278 | G | G | 5 | Implement a solution to mitigate risk of end of life for the agency's call centre logging application. | 1767000 | 2015-01-30T00:00:00 | DAF
20/3/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
20/3/2018 | PSBA | Emergency Services Computer Aided Dispatch (ESCAD) Upgrade Program | 2016-09-30T00:00:00 | Delivery | G | 2018-07-03T00:00:00 | The updated ESCAD system cut over for Queensland Ambulance Service (QAS) completed successfully on 17 January 2018, and the Queensland Fire and Emergency Services (QFES) also completed successfully on 24 January 2018. | 2018-02-20T00:00:00 | Critical | 6774820 | G | Public Safety Business Agency | 86 | 8812255 | G | G | 1 | A program of work for Queensland Ambulance Service and Queensland Fire and Emergency Services to upgrade the Emergency Services Computer Aided Dispatch System,including infrastructure, operating system and application software. | 10289600 | 2015-01-15T00:00:00 | PSBA
20/3/2018 | PSBA | Emergency Vehicle Priority (EVP) Project | 2017-06-30T00:00:00 | Delivery | G | 2018-10-31T00:00:00 | EVP rollouts continuing across Queensland, including Ipswich, Rockhampton and Gladstone. EVP rollout is currently due for completion April 2018, which will be ahead of scheduled completion date of end of 2018. More vehicles are proposed to be fitted beyond the scope of the project subject to approval. Budget figure now reflects $515k increase to support approved project extension to October 2018. | 2018-02-20T00:00:00 | High | 3370000 | G | Public Safety Business Agency | 80 | 3920604 | G | G | 2 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 20/3/2018, 20/3/2018,* Responsive vehicle movements 20/3/2018,* Improve road safety 20/3/2018,* Congestion management 20/3/2018,* Community safety | 4370331 | 2013-01-01T00:00:00 | PSBA
20/3/2018 | PSBA | Inter-CAD Electronic Messaging System (ICEMS) | 2017-12-01T00:00:00 | Delivery | G | 2018-02-23T00:00:00 | Project delivery completed 1 December 2017. End date has been extended to 23 February 2018 to allow for project closure activities to be completed. % complete revised to reflect extended duration. | 2018-02-20T00:00:00 | Critical | 560000 | G | Public Safety Business Agency | 91 | 1548783 | G | G | 3 | To implement the ICEMS protocol between the Queensland Police Service (QPS), Queensland Ambulance Service (QAS) and Queensland Fire and Emergency Services (QFES) computer aided dispatch systems to enable Triple Zero data sharing between agencies. | 1545139 | 2015-10-06T00:00:00 | PSBA
20/3/2018 | PSBA | QPS Office 365 Implementation Project | 2018-02-28T00:00:00 | Delivery | G | 2018-02-28T00:00:00 | QPS Office 365 Implementation Project has completed the migration of all employee and business accounts to Office 365 online services. | 2018-02-14T00:00:00 | Critical | 2207000 | G | Public Safety Business Agency | 75 | 675267 | G | G | 4 | The objective of the Queensland Police Service (QPS) Office 365 Implementation Project is to complete the following activities prior to the FDS Commonwealth Games Change Freeze (mid Feb 2018). 20/3/2018, 20/3/2018,* Migrate email, contacts and calendars to Office 365 online services for all QPS staff 20/3/2018,* Enable anywhere, anytime, any device access to email, contacts and calendar via bring your own (BYO) phone, QPS Officers operational tablets (QLiTEs) and home use for all QPS staff | 2207000 | 2017-09-07T00:00:00 | PSBA
20/3/2018 | OSR | State Penalties Enforcement Registry (SPER) Program | 2017-12-31T00:00:00 | Delivery | G | 2018-10-31T00:00:00 | Expenditure to date: $28.61M has been for the transformation of the SPER function; and $16.5M has been on the build phase of the ICT Implementation (Software as a Service - SaaS). 20/3/2018,A contract variation has been negotiated and executed as jurisdictional differences required system modifications. | 2018-03-06T00:00:00 | High | 47200000 | G | State Penalties Enforcement Registry | 55 | 45100000 | A | A | 1 | To maintain the integrity of fines as an effective sanction. To uphold confidence in the justice system. To deliver efficient and effective debt management practices which provide value for money to the State. 20/3/2018, | 62150000 | 2014-01-01T00:00:00 | QR
20/3/2018 | RI | Financial Assurance Information Registry (FAIR) | 2018-07-01T00:00:00 | Delivery | G | 2018-07-01T00:00:00 | Project cost to date is at end of January 2018. Project is on track for the system to be operational by 1 July 2018. Due to the delay in legislation being passed, some functionality and enhancements are planned to be delivered in the next financial year. | 2018-03-16T00:00:00 | Medium | 15900000 | G | Insurance Commission | 60 | 2050000 | G | G | 2 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
20/3/2018 | RI | Information Security Program | 2019-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The program is on track according to schedule and budget. | 2018-03-16T00:00:00 | Medium | 1960000 | G | Office of the Chief Information Officer | 30 | 299405 | G | G | 3 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 20/3/2018, | 1960000 | 2017-10-16T00:00:00 | QR
20/3/2018 | OSR | Office of State Revenue (OSR) Transformation Program | 2020-06-30T00:00:00 | Delivery | G | 2020-06-30T00:00:00 | Web-based Intelligent virtual assistant (IVA) pilot successfully went live on external websites 13 February 2018 for payroll tax clients. Multiple initiatives in progress focussing on machine learning, analytics and data quality improvements. Overall program is on track. | 2018-02-28T00:00:00 | High | 73548000 | G | Office of State Revenue | 10 | 9327354 | G | G | 4 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 20/3/2018, 20/3/2018,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 73548000 | 2017-08-01T00:00:00 | QR
20/3/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
20/3/2018 | Corporate Services Improvement Systems Board | Learnzone Improvement Project | 2017-06-30T00:00:00 | Delivery | G | 2017-09-30T00:00:00 | The LearnZone Improvement project continues to report action required due to delays in finalising approvals of the Project End Report. Once the Project End Report is approved and noted, scheduled 15 February 2018, the project will be marked as closed on the QG ICT Dashboard. It should be noted that both the original total estimated expenditure and revised total estimated expenditure reported last period were incorrect. As per the approved Business Case and subsequent exception report these figures have now been corrected. | 2018-01-31T00:00:00 | High | 350000 | G | Transactional Services Improvement Program | 98 | 447977 | R | R | 1 | Innovate, develop and deliver an improved and centralised digital learning service and management function. 20/3/2018, 20/3/2018, | 442000 | 2016-02-01T00:00:00 | TMR
20/3/2018 | Corporate Services Improvement Systems Board | Lotus Notes Decommissioning | 2016-01-31T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project is on track. | 2018-01-31T00:00:00 | High | 8150000 | G | ERP Projects Board | 63 | 1970247 | G | G | 2 | Deliver improved information platform functions for effective ICT Strategy Alignment | 8150000 | 2015-11-01T00:00:00 | TMR
20/3/2018 | Corporate Services Improvement Systems Board | Stop Cheques - Stage 3 | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Stop Cheques Stage 3 project is on track. | 2018-01-31T00:00:00 | Medium | 200000 | G | ERP Projects Board | 85 | 183770 | G | G | 3 | Cheques are inefficient and costly to use, process and administer for both the customer and department. A range of solutions have been developed to reduce the number of cheques that the department produces or receives including refund to card at counter, Bulk Bpay solutions and the introduction of new payment methods are being delivered to be more in line with contemporary retail offerings. The outsourcing of cheque production produced a more streamlined process. 20/3/2018,The stop cheques initiative includes 3 elements: 20/3/2018,Outsourcing/cost reduction 20/3/2018,Outbound cheques 20/3/2018,Inbound cheques | 200000 | 2015-02-01T00:00:00 | TMR
20/3/2018 | Corporate Services Improvement Systems Board | Risk Management Solution | 2018-07-01T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Risk Management Solution project is on track. | 2018-01-31T00:00:00 | High | 350000 | G | Corporate Services Improvement Systems Board | 78 | 607676 | G | G | 4 | Replace the current risk management approach through the delivery of a new and contemporary enterprise Risk Management solution for TMR . | 710000 | 2016-02-01T00:00:00 | TMR
20/3/2018 | Corporate Services Improvement Systems Board | Integrated Records Information System (IRIS) | 2018-07-01T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The IRIS project is on track. | 2018-01-31T00:00:00 | High | 7967972 | G | Information Technology Branch | 35 | 1900809 | G | G | 5 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 7967972 | 2015-07-01T00:00:00 | TMR
20/3/2018 | Customer Service, Safety and Regulation Program | CTP Tax Invoice Online | 2017-12-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The CTP Tax Invoice Online project is on track. | 2018-01-31T00:00:00 | Medium | 300000 | G | Customer Services, Safety and Regulation Division | 25 | 17281 | G | G | 16 | The Compulsory Third Party Tax Invoice Online project will deliver a new online service which will enable Customers to self-serve and print an electronic version of the CTP Invoice, removing the need for TMR to process paper based invoices, avoiding production and postage charges. | 300000 | 2017-05-01T00:00:00 | TMR
20/3/2018 | Corporate Services Improvement Systems Board | Safety, Health and Environment tool (SHE) | 2018-07-02T00:00:00 | Delivery | G | 2018-07-30T00:00:00 | The SHE project has not previously reported on the ICT Dashboard. The project is on track. | 2018-01-31T00:00:00 | Low | 680000 | G | Corporate Services Improvement Systems Board | 40 | 215901 | G | G | 6 | The objective of the SHE project is to replace the current Work Health and Safety ICT solution with an industry standard, cost-effective safety management solution that will enable TMR to meet its obligations under the Work Health and Safety 2011 Act, the Right to Information, Information Privacy legislation and the Workers Compensation and Rehabilitation Act 2003 Qld. | 680000 | 2016-12-05T00:00:00 | TMR
20/3/2018 | Corporate Services Improvement Systems Board | Transactional Services Improvement Program Enhancements | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Transactional Services Improvement Program Enhancements Stage 3 is on track. | 2018-01-31T00:00:00 | Low | 200000 | G | Transactional Services Improvement Program | 80 | 143537 | G | G | 7 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. | 200000 | 2015-02-01T00:00:00 | TMR
20/3/2018 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery | G | 2018-09-30T00:00:00 | The CDOP Online Portal project is on track. | 2018-01-31T00:00:00 | High | 1500000 | G | Customer Services, Safety and Regulation Division | 87 | 1066506 | G | G | 8 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal services currently required. | 1441000 | 2016-01-01T00:00:00 | TMR
20/3/2018 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The eLearner project is currently on track. | 2018-01-31T00:00:00 | High | 2500000 | G | Customer Services, Safety and Regulation Division | 93 | 4085912 | G | G | 9 | Implement an online learning and assessment program at the pre-learner and/or learner stage, to replace enhance learning outcomes. | 4176000 | 2015-06-12T00:00:00 | TMR
20/3/2018 | Customer Service, Safety and Regulation Program | Facial Recognition Replacement | 2017-03-31T00:00:00 | Closed | G | 2017-11-28T00:00:00 | The Facial Recognition project closure report was approved by the Project Board in December 2017. The Facial Recognition project will no longer report to the ICT Dashboard. | 2018-01-31T00:00:00 | High | 531250 | G | Customer Services, Safety and Regulation Division | 100 | 183076 | G | G | 10 | Upgrade TMRs facial image capture and recognition software to their latest versions and re-template its entire image gallery (approx. 3.5 million facial images). | 631250 | 2015-07-13T00:00:00 | TMR
20/3/2018 | Customer Service, Safety and Regulation Program | Hardware Security Modules (HSM) | 2016-07-29T00:00:00 | Closed | G | 2017-12-01T00:00:00 | The HSM project closure report was approved by the Project Board in December 2017. The HSM project will no longer report to the ICT Dashboard. | 2018-01-31T00:00:00 | High | 500000 | G | Customer Services, Safety and Regulation Division | 100 | 395016 | G | G | 11 | The Hardware Security Modules (HSMs) form part of the Queensland Driver Licence smartcard product set introduced in 2010 and generate keys for smartcard authentication and validation by TMR-authorised card readers at TMR Customer Service Centres, QGAP and Queensland Police Service locations throughout Queensland. These HSMs are coming to end of life and will be required to be replaced to continue the protection of smartcard authenticity and key validation for the TMR products. | 500000 | 2015-08-01T00:00:00 | TMR
20/3/2018 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery | G | 2018-06-28T00:00:00 | The Mobile Compliance Information System project is on track. | 2018-01-31T00:00:00 | High | 300000 | G | Customer Services, Safety and Regulation Division | 80 | 683980 | G | G | 12 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 630000 | 2016-11-01T00:00:00 | TMR
20/3/2018 | Customer Service, Safety and Regulation Program | Call Centre VOIP Upgrade | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Call Centre VOIP Upgrade project is on track. | 2018-01-31T00:00:00 | Low | 1140000 | G | Customer Services, Safety and Regulation Division | 25 | 564183 | G | G | 13 | The Call Centre VOIP Upgrade has commenced to upgrade the VOIP telephony platform within the department. The proposed solution will see a reduction in call costs, a shift in capability to a 20/3/2018,contemporary solution utilising an existing investment within the department. | 1140000 | 2017-04-01T00:00:00 | TMR
20/3/2018 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery | G | 2017-12-24T00:00:00 | The Ralph Replacement project is on track. An exception report to rebasline the project's end date is currently being reviewed by the project's governance board. | 2018-01-31T00:00:00 | Medium | 500000 | G | Customer Services, Safety and Regulation Division | 59 | 572111 | G | G | 14 | TMR's current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace the existing application with a contemporary and supportable alternative to assist the department in maintaining its timely updating of fees and charges. | 674000 | 2016-07-01T00:00:00 | TMR
20/3/2018 | Customer Service, Safety and Regulation Program | Voice Comms Mgt System | 2017-06-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | The Voice Comms Management System project is on track. | 2018-01-31T00:00:00 | Medium | 828000 | G | Customer Services, Safety and Regulation Division | 75 | 274738 | G | G | 15 | The Voice Comms Management project consists of two replacement of existing Voice Communication and Control Systems at Townsville and Hay Point. | 828000 | 2016-01-01T00:00:00 | TMR
20/3/2018 | Customer Service, Safety and Regulation Program | MSQ iBase Project | 2017-06-30T00:00:00 | Closed | G | 2017-12-04T00:00:00 | The MSQ iBase project closure report was approved by the Project Board in November 2017. This project will no longer report on the ICT Dashboard. | 2018-01-31T00:00:00 | Low | 450000 | G | Customer Services, Safety and Regulation Division | 100 | 227589 | G | G | 17 | The Maritime Safety Queensland ibase Project has commenced as the current incident register platform has been identified as requiring replacement. The future platform will work in collaboration with current field input and smart devices. | 292000 | 2017-01-01T00:00:00 | TMR
20/3/2018 | Customer Service, Safety and Regulation Program | Vessel Traffic Services (VTS) | 2016-01-05T00:00:00 | Delivery | G | 2018-11-30T00:00:00 | The Vessel Traffic Services VTS project is on track. | 2018-01-31T00:00:00 | High | 15224694 | G | Customer Services, Safety and Regulation Division | 25 | 5873350 | G | G | 18 | The purpose of the project is procure and implement a replacement decision support tool for the existing Vessel Traffic Service (VTS) used by TMR to track and monitor ship movements within Queensland ports, the Great Barrier Reef and the Torres Strait. | 25569044 | 2014-04-14T00:00:00 | TMR
20/3/2018 | Customer Service, Safety and Regulation Program | R and L Systems Software Upgrade | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The R and L Systems Software Upgrade project is on track. | 2018-01-31T00:00:00 | Medium | 780000 | G | Customer Services, Safety and Regulation Division | 20 | 21799 | G | G | 19 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
20/3/2018 | Infrastructure Management and Delivery | Access Management System (AMS) - formerly Heavy Vehicle Permit Management System | 2015-10-31T00:00:00 | Paused | A | 2017-06-30T00:00:00 | The department of Transport and Main Roads has concluded the Access Management System (formerly Heavy Vehicle Permit Management System) Project. The AMS project will report for one more reporting period prior to being removed from the QG ICT Dashboard. | 2018-01-31T00:00:00 | High | 4281564 | A | Infrastructure Management 20/3/2018,and Delivery | 83 | 8307429 | A | A | 20 | Improve heavy vehicle and load movement safety through effective schemes, guidelines and conditions management 20/3/2018, Allow coordinated road operations such that an increase in activity will not result in economic detriment or a loss of safety and public amenity. | 9001258 | 2013-06-01T00:00:00 | TMR
20/3/2018 | Infrastructure Management and Delivery | Work Improvement Note (WIN) Replacement | 2016-12-19T00:00:00 | Delivery | G | 2018-02-27T00:00:00 | The WIN Replacement project is on track. | 2018-01-31T00:00:00 | Low | 242612 | G | Infrastructure Management 20/3/2018,and Delivery | 89 | 281997 | G | G | 21 | The Work Improvement Note (WIN) System is used to capture, track, review and report on improvements, potential problems, non-conformances, corrective actions, customer feedback and complaints. The WIN System is an essential component of the overarching business management system as it meets specific certification requirements outlined in international quality, safety and environmental standards. This project will provide a replacement to the existing Work Improvement Note (WIN) system, which is dependent on unsupported technology. | 436375 | 2016-02-15T00:00:00 | TMR
20/3/2018 | Passenger Transport Technology Program | 2018 Commonwealth Games Journey Planner (GJP) | 2017-10-13T00:00:00 | Delivery | G | 2018-04-27T00:00:00 | The 2018 Commonwealth GJP project is project is on track. | 2018-01-31T00:00:00 | High | 450000 | G | Commonwealth Games | 67 | 477851 | G | G | 22 | A dedicated Journey Planner application supports this need by providing a single source of truth for all transport information related to the Games, and also allows for rapid changes to routes, schedules, and stops, if any are required, in order to drive transport behaviour and maintain network efficiency. | 973899 | 2016-10-16T00:00:00 | TMR
20/3/2018 | Passenger Transport Technology Program | Customer Contact Management Solution (CCMS) | 2017-06-30T00:00:00 | Closed | G | 2018-01-16T00:00:00 | The CCMS project has successfully completed its scope and the Program Board endorsed the project closure report in January 2018. As previously reported, the planned expenditure versus the actual cost to date variance will be rectified once the departments internal budgeting processes are completed for the current quarter. The CCMS project will report for one additional reporting period prior to being removed from the QG ICT Dashboard. | 2018-01-31T00:00:00 | High | 1279000 | G | TransLink | 100 | 1486927 | G | G | 23 | To implement an industry standard, robust and extensible solution to replace the existing Commentline solution. To achieve better performance of the customer contact management functions. To provide the base platform to support the future implementation of an xRM roadmap | 1486927 | 2016-04-01T00:00:00 | TMR
20/3/2018 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery | G | 2018-08-31T00:00:00 | The STAS Auto Forms project is on track. | 2018-01-31T00:00:00 | High | 4166000 | G | TransLink | 59 | 4092926 | G | G | 24 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 5043876 | 2016-04-01T00:00:00 | TMR
20/3/2018 | Policy Planning and Investment Program | Portfolio, Program, Project and Contract Management (3PCM) - Phase 2 and 3 | 2017-03-31T00:00:00 | Delivery | G | 2017-12-22T00:00:00 | The 3PCM project is reporting closely monitored due to finalising approvals of the Project End Report. Once the Project End Report is approved and noted the project will be marked as closed on the QG ICT Dashboard. | 2018-01-31T00:00:00 | High | 12757788 | G | Policy, Planning and Investment Division | 99 | 47794048 | A | A | 25 | Define and implement standard, consistently applied processes for planning, managing and delivering the Transport Infrastructure Portfolio across the domains of portfolio, program, project and contract management 20/3/2018,Source and implement an integrated, strategic information communication technology solution that supports the business process and rules and enables a transition away from legacy applications | 47908928 | 2012-09-01T00:00:00 | TMR
20/3/2018 | CS | Asset Assessment System | 2016-06-30T00:00:00 | Delivery | A | 2018-08-06T00:00:00 | The project is being closely monitored for quality and schedule | 2018-02-08T00:00:00 | High | 1688788 | G | Corporate Services | 82 | 1502089 | A | A | 1 | To improve the reliability and integrity of asset information, the ability to report on asset information by applying best practice asset management principles. | 1957139 | 2014-02-27T00:00:00 | DET
20/3/2018 | SS | Early Start | 2015-07-03T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | High | 70000 | G | State Schools | 74 | 73522 | G | G | 2 | To provide schools with enhanced reporting functionality, improving their ability to analyse Prep to Year 2 student learning data. | 200992 | 2013-04-03T00:00:00 | DET
20/3/2018 | PPP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Delivery | G | 2018-02-27T00:00:00 | The project is being closely monitored for schedule | 2018-02-08T00:00:00 | Medium | 700000 | G | Policy, Performance and Planning | 86 | 1247953 | A | A | 3 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
20/3/2018 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery | G | 2018-12-07T00:00:00 | The project is tracking to plan. The Project is undergoing procurement/commercial activities with no financial information being published. | 2018-02-08T00:00:00 | Medium | 0 | G | Corporate Services | 46 | 0 | G | G | 4 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DET FBS SAP future state landscape for the next five years | 0 | 2017-01-16T00:00:00 | DET
20/3/2018 | CS | Injury Management System | 2017-03-27T00:00:00 | Delivery | G | 2018-10-01T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Critical | 1900000 | G | Corporate Services | 46 | 758816 | G | G | 5 | To improve the management of workplace rehabilitation and claims for injured/ill staff | 1813805 | 2016-10-10T00:00:00 | DET
20/3/2018 | ODG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery | G | 2017-12-29T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 632585 | G | Office of the Director-General | 90 | 817626 | G | G | 6 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
20/3/2018 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery | G | 2019-09-13T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 16670000 | G | State Schools | 50 | 8756279 | G | G | 7 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 23470000 | 2015-08-03T00:00:00 | DET
20/3/2018 | PPP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery | G | 2018-06-13T00:00:00 | The project is tracking to plan. The Project is undergoing procurement/commercial activities with no financial information being published. | 2018-02-08T00:00:00 | Medium | 0 | G | Policy, Performance and Planning | 70 | 0 | G | G | 8 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution | 0 | 2016-03-01T00:00:00 | DET
20/3/2018 | CS | Project Delivery System | 2018-10-01T00:00:00 | Delivery | G | 2019-01-29T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 1817566 | G | Corporate Services | 61 | 773116 | G | G | 9 | To improve the reliability and integrity of under construction asset information, the ability to report on asset project information by applying best practice asset management principles | 2291613 | 2015-04-01T00:00:00 | DET
20/3/2018 | PPP | Research Services 2.0 | 2016-09-30T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 230000 | G | Policy, Performance and Planning | 85 | 404745 | G | G | 10 | To develop a solution that assists in the management of the Department of Education and Training commissioned research proposals and projects, improving resourcing and information dissemination. | 431157 | 2015-11-02T00:00:00 | DET
20/3/2018 | TS | Study Tours Support System Upgrade | 2016-06-30T00:00:00 | Delivery | G | 2018-01-31T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 680000 | G | Training and Skills | 96 | 772580 | G | G | 11 | To replace or upgrade the existing Study Tours system with an online solution that has enhanced functionality, improving processes, data quality and tour management. | 831125 | 2015-08-31T00:00:00 | DET
20/3/2018 | SS | Trial of platform for virtual academies | 2017-10-02T00:00:00 | Delivery | G | 2018-12-31T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 151641 | G | State Schools | 55 | 224017 | G | G | 12 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage. | 151641 | 2016-06-21T00:00:00 | DET
20/3/2018 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery | G | 2020-06-30T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | High | 41000000 | G | Corporate Services | 55 | 27032972 | G | G | 13 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
20/3/2018 | [20 empty] | INVERSTMENT INFO
20/3/2018 | CSGC | Coal Seam Gas Groundwater Monitoring Arrangements | 2017-12-31T00:00:00 | Paused | G | 2018-06-30T00:00:00 | A change to the planned end date has been approved; there is no impact to cost. Initiative is now paused until early 2018. 20/3/2018, 20/3/2018,August 2017 - Revised total expenditure (budget) updated to include all operating costs not previously reported. 20/3/2018, 20/3/2018,June 2017 - Progress is continuing as planned. Still on schedule to complete December 2017. 20/3/2018, 20/3/2018,December 2016 - Much of the project has been completed and a significant amount of the procurement expenditure for capital equipment has occurred. 20/3/2018, 20/3/2018,October 2016 - Progress is continuing as planned. 20/3/2018, 20/3/2018,August 2016 - Cost returned to Green after a review of costs associated with activities remaining, and a correction in actual cost to date adjustment. 20/3/2018, 20/3/2018,June 2016 - Cost is Amber with a resource review under way. 20/3/2018, 20/3/2018,February 2016 - Progress is continuing as planned. | 2018-03-16T00:00:00 | High | 2380568 | G | Coal Seam Gas Compliance | 95 | 2548371 | G | G | 1 | Enhance availability of groundwater data through improvements to network monitoring of bores for clients and landholders. | 2598256 | 2014-01-13T00:00:00 | DNRM
20/3/2018 | SIMTARS | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery | G | 2019-03-01T00:00:00 | The project is continuing as planned. 20/3/2018, 20/3/2018,February 2018 - A change request was approved to alter the scope and associated percentage complete, time-frame and costs. 20/3/2018, 20/3/2018,December 2017 - Awaiting confirmation of project closure; project is still operating within approved time-frame tolerance. 20/3/2018, 20/3/2018,November 2017 - A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 20/3/2018, 20/3/2018,October 2017 - The project is continuing as planned. 20/3/2018, 20/3/2018,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2018-03-16T00:00:00 | High | 563000 | G | SIMTARS (Safety In Mines Testing and Research Station) | 60 | 622419 | G | G | 2 | The development and delivery of a (replacement) modern and robust Safegas solution: 20/3/2018, 20/3/2018,* risk reduction increasing capability to manage the volume of queries, transactions and data 20/3/2018,* decrease database corruption related to incidents. | 1170000 | 2017-01-25T00:00:00 | DNRM
20/3/2018 | SO | Mines Infrastructure Risk Mitigation Project | 2019-02-18T00:00:00 | Delivery | G | 2019-02-28T00:00:00 | The project is continuing as planned. 20/3/2018, 20/3/2018,November 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-03-16T00:00:00 | High | 1200000 | G | Statewide Operations | 25 | 237000 | G | G | 3 | Migrate systems to supported infrastructure and software to: 20/3/2018, 20/3/2018,* provide a stable, secure, fully supported and flexible solution 20/3/2018,* eliminate the risks to which the geoscience data assets are currently exposed. | 1200000 | 2017-08-08T00:00:00 | DNRM
20/3/2018 | GSQ | MinesOnlineMaps - Spatial Presentation Replacement | 2017-06-30T00:00:00 | Paused | G | 2018-04-30T00:00:00 | The project is planning to end as the outputs will be delivered by another initiative. 20/3/2018, 20/3/2018,December 2017 - Project is paused awaiting review of a possible change in direction. Cost remains Green while investigation is undertaken to identify if deferral request was processed. | 2018-03-16T00:00:00 | Medium | 531030 | G | Geological Survey of Queensland | 60 | 98271 | G | G | 4 | Provide a web-based mapping solution for the ongoing provision of MinesOnlineMaps (MOMaps) into the future. | 531030 | 2016-08-01T00:00:00 | DNRM
20/3/2018 | LSI | Queensland Globe Improvements | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is continuing as planned. 20/3/2018, 20/3/2018,December 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-03-16T00:00:00 | High | 1002450 | G | Land and Spatial Information | 50 | 511935 | G | G | 5 | Enhancements to Queensland Globe to continue to evolve and improve user satisfaction and experience, such as: 20/3/2018, 20/3/2018,* create and save user-defined topics 20/3/2018,* improve query and access 20/3/2018,* provide editable 'redlining' 20/3/2018,* improve data imports. | 1002450 | 2017-10-09T00:00:00 | DNRM
20/3/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | The project is continuing as planned. 20/3/2018, 20/3/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 20/3/2018,October 2017 - The project is progressing as planned. 20/3/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 20/3/2018,June 2017 - Revised Schedule approved returning the project to Green. 20/3/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 20/3/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 20/3/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 20/3/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 20/3/2018,December 2016 - The project is progressing as planned. | 2018-03-16T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 97 | 853487 | G | G | 6 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 20/3/2018, 20/3/2018,* register and maintain their information 20/3/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DNRM
20/3/2018 | QWSR | Dam Safety Regulation Solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | The project is continuing as planned. 20/3/2018, 20/3/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 20/3/2018,August 2017 - Approved extension of timeframe. 20/3/2018,June 2017 - The project is progressing as planned. 20/3/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 20/3/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 20/3/2018,October 2016 - Progress is continuing as planned. 20/3/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 20/3/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 20/3/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2018-03-16T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 95 | 1370000 | G | G | 7 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 20/3/2018, 20/3/2018,* support compliance with legislation 20/3/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 20/3/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 20/3/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 20/3/2018, | 1390000 | 2012-04-01T00:00:00 | DNRM
20/3/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DPC
20/3/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
20/3/2018 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 20/3/2018,* Move operational accountability and responsibility for print and imaging devices to the service provider 20/3/2018,* Reduce print and imaging costs 20/3/2018,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
20/3/2018 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
20/3/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
20/3/2018 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 20/3/2018, 20/3/2018,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
20/3/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
20/3/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 20/3/2018, 20/3/2018,* reduce operating costs 20/3/2018,* increase capacity 20/3/2018,* improve customer experience 20/3/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
20/3/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
20/3/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 20/3/2018, 20/3/2018, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
20/3/2018 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 20/3/2018, 20/3/2018,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
20/3/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
20/3/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 20/3/2018, 20/3/2018,November 2017 - Actual cost to date corrected due to input error. 20/3/2018, 20/3/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 20/3/2018, | 2017-12-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 57 | 733941 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
20/3/2018 | ESR | Environmental Management Register/Contaminated Land Register - replacement | 2017-06-30T00:00:00 | Paused | G | 2017-06-30T00:00:00 | The project remains paused with a new change request under development that will see the project move back into delivery with a Green status. 20/3/2018, 20/3/2018,August 2017 - The project is paused awaiting the outcome of a change request for additional scope; this will return the project to a Green status. 20/3/2018, 20/3/2018,April 2017 - A minor correction has been made to the revised total estimated expenditure to include $20,000 operating prior years. 20/3/2018, 20/3/2018,February 2017 - A change request has been approved moving the initiative cost back to Green. 20/3/2018, 20/3/2018,December 2016 - Project is continuing as planned, with a change request under way to return cost to Green. 20/3/2018, 20/3/2018,October 2016 - Project delivery activities formally commenced on 2 October 2016. 20/3/2018, 20/3/2018,August 2016 - The initiative was paused for some time but has now recommenced and moved into delivery. It is progressing as planned. | 2018-03-16T00:00:00 | High | 981680 | A | Environmental Services and Regulation | 78 | 718000 | A | A | 1 | The current system no longer supports efficient delivery of the department's responsibilities. The replacement will: 20/3/2018, 20/3/2018,* mitigate the risks associated with a system that is beyond its useful life 20/3/2018,* improve access to information by individuals, business and industry conducting searches (property lot plan) of the registers 20/3/2018,* support the creation of notices to stakeholders 20/3/2018,* reduce manual tasks through the introduction of automated workflows and customer self-serve and self-correct. 20/3/2018, | 1111680 | 2016-07-01T00:00:00 | EHP
20/3/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 20/3/2018, 20/3/2018,November 2017 - Actual cost to date corrected due to input error. 20/3/2018, 20/3/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 20/3/2018, | 2018-03-16T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 68 | 925706 | G | G | 2 | Acquire one or more solution components to operate in conjunction with the agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | EHP
20/3/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP
25/5/2018 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-03-31T00:00:00 | High | 5600000 |  | eHealth Queensland | 14 | 666257 |  | G | 1 | This project aims to establish a robust, highly available and secure contemporary platform that has the capability to support the agile eHealth Strategy. | 5600000 | 2017-07-03T00:00:00 | DH
25/5/2018 | HSQ | AUSLAB Re-hosting project | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 |  | 2018-03-31T00:00:00 | High | 1691324 |  | Health Support Queensland | 35 | 425294 |  | G | 2 | Delivery of a replacement hardware and visualisation solution for the AUSLAB and AUSCARE systems that will achieve improved resiliency of the architecture, updated operating system and inclusion of virtualisation. AUSLAB and AUSCARE are critical to support laboratories and patient clinical care. | 1554952 | 2017-08-28T00:00:00 | DH
25/5/2018 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2016-08-01T00:00:00 | Delivery |  | 2018-07-30T00:00:00 |  | 2018-04-20T00:00:00 | High | 1858668 |  | Metro North | 75 | 1136112 |  | G | 3 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 25/5/2018, 25/5/2018,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Women 25/5/2018,92s Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 25/5/2018, 25/5/2018,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 2482431 | 2015-06-01T00:00:00 | DH
25/5/2018 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-03-31T00:00:00 | High | 11180394 |  | eHealth Queensland | 13 | 326018 |  | G | 4 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 25/5/2018,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work. 25/5/2018,a0 Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 11180394 | 2017-07-03T00:00:00 | DH
25/5/2018 | MNHHS | Business Intelligence - Enterprise Data Warehouse | 2018-06-29T00:00:00 | Delivery |  | 2018-06-28T00:00:00 | March: Project funding is currently being revised in line with proposed scope for an upcoming stage. | 2018-04-20T00:00:00 | High | 2114991 |  | Metro North | 72 | 1505967 |  | G | 5 | This project will introduce Business Intelligence and Data Warehousing capabilities at MNHHS. The project will deliver BI & DW technical skills, system infrastructure, data automation tools, a pilot dataset, data governance processes and quality control framework at MNHHS. Metro North Finance and MNIT are jointly managing the project. | 1480182 | 2016-11-01T00:00:00 | DH
25/5/2018 | MNHHS | Central Patient Monitoring Equipment Replacement | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 |  | 2018-04-20T00:00:00 | High | 1236416 |  | Metro North | 62 | 458480 |  | G | 6 | Metro North IT has been approached by Metro North Procurement Services (MNPS) to provide ICT advice and guidance into the Central Patient Monitoring Equipment Replacement (CPMER) Project. The Health Technology Equipment Replacement (HTER) program for central monitoring systems is providing funding in financial years 16/18 for physiological monitoring equipment requiring replacement across MNHHS hospital facilities. There is an estimated 312 pieces of equipment, primarily Physiological Monitoring devices, to be replaced under the program across MNHHS hospital facilities. MNHHS implementations are being co-ordinated by MNPS. | 1236416 | 2017-06-28T00:00:00 | DH
25/5/2018 | MNHHS | CISS (Community, Indigenous and Subacute Services) Wi-Fi | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-04-20T00:00:00 | Medium | 1280798 |  | Metro North | 64 | 934449 |  | G | 7 | The Community, Indigenous and Subacute Services (CISS) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the internal areas of the prioritised CISS sites. 25/5/2018, 25/5/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1280798 | 2017-07-28T00:00:00 | DH
25/5/2018 | EHQ | Cloud First Project | 2018-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-03-31T00:00:00 | High | 4250000 |  | eHealth Queensland | 70 | 2615832 |  | G | 8 | The Cloud First project will build internal capability and establish processes within Queensland Health to appropriately utilise cloud services on an ongoing basis. | 4126918 | 2017-01-01T00:00:00 | DH
25/5/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Clinical Notes project (release 3.0) | 2018-02-06T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-04-13T00:00:00 | High | 1415000 |  | Clinical Excellence | 85 | 1625078 |  | G | 9 | Upgrading the CIMHA Mental Health Act module to accommodate a re-architecture of the CIMHA clinical notes module is required to deliver benefits to the clinical workforce associated with data entry efficiencies; improved data sharing across digital platforms; patient level information transfer to third parties to support service integration and data mining to support service improvement and research. | 1969365 | 2017-02-20T00:00:00 | DH
25/5/2018 | EHQ | Critical Network Hardware | 2018-02-28T00:00:00 | Delivery |  | 2018-05-31T00:00:00 | February: This project has returned to 'on track'. 25/5/2018, 25/5/2018,January: The project is reporting 'Amber' due to limited resource availability and additional technical requirements, impacting the schedule of the project | 2018-03-31T00:00:00 | High | 8636364 |  | eHealth Queensland | 65 | 7440920 |  | G | 10 | The objectives of the project include: 25/5/2018,a) Mitigate the Department of Health risk that core network switches at QH facilities will no longer be supported by the manufacturer from February 2018. 25/5/2018,b) Invest in the replacement of critical ICT network hardware to maintain current capability and reliability of the data network for 120+ enterprise clinical and business applications and provide the foundation for future capability in the enterprise data centres. 25/5/2018,c) Ensure hardware replacement occurs with minimal impact to business operations in Hospital and Health Services or Corporate offices. 25/5/2018,d) Update logical and physical design and architecture documentation for ease of maintenance and management. | 8371607 | 2017-03-06T00:00:00 | DH
25/5/2018 | EHQ | Digital Collaboration Platform Program | 2018-06-30T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | March: Project activities have continued to be delayed, resulting in this project reporting 'Red'. A project change request has been submitted to the project's governance committee. Successful deployment was recently achieved in Townsville. 25/5/2018, 25/5/2018,January: This project is experiencing delays in pre-migration activities. | 2018-03-31T00:00:00 | High | 11000000 |  | eHealth Queensland | 34 | 10127968 |  | R | 11 | This program will deliver digital collaboration tools for any time, any where, any device including: 25/5/2018, 25/5/2018,95 Email and Archiving 25/5/2018, 25/5/2018,95 Establishment and Collaboration 25/5/2018, 25/5/2018,95 Productivity Suite Enablement | 18467291 | 2015-10-29T00:00:00 | DH
25/5/2018 | EHQ | File Services Migration | 2017-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-03-31T00:00:00 | High | 3400000 |  | eHealth Queensland | 29 | 2953759 |  | G | 18 | The purpose of this investment is to adopt a contemporary, simplified file management solution for Queensland Health that enables a more cohesive customer experience. | 9907925 | 2016-08-01T00:00:00 | DH
25/5/2018 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate |  | 2017-12-31T00:00:00 | February: The current proposed date of completion is the December 2019, which is subject to project board approval. | 2018-03-31T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 40 | 541285 |  | G | 12 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 4167216 | 2015-12-01T00:00:00 | DH
25/5/2018 | QAS | e-ARF Redevelopment for iPad | 2016-12-31T00:00:00 | Delivery |  | 2017-12-31T00:00:00 | February: Implementation and rollout of the system was completed in late November 2017. The project is currently finalising end of project reporting processes. | 2018-03-31T00:00:00 | High | 2624000 |  | Queensland Ambulance Service | 100 | 1898050 |  | G | 13 | This is an initiative to provide the electronic Ambulance Report Form (eARF) electronic patient care solution via iPads in the field. | 1910813 | 2015-09-02T00:00:00 | DH
25/5/2018 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | March: Further solution clarification is required, which has impacted on the overall delivery timeframe of this initiative by a number of weeks. | 2018-03-31T00:00:00 | High | 1283000 |  | Chief Health Officer and Prevention | 66 | 87000 |  | A | 14 | ?Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1283000 | 2017-07-24T00:00:00 | DH
25/5/2018 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery |  | 2018-11-30T00:00:00 |  | 2018-04-20T00:00:00 | High | 4827917 |  | Metro North | 60 | 2850156 |  | G | 15 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (ieMR) program. 25/5/2018, 25/5/2018,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 25/5/2018, 25/5/2018,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. | 4827917 | 2016-07-01T00:00:00 | DH
25/5/2018 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Initiate |  | 2020-02-10T00:00:00 |  | 2018-03-31T00:00:00 | High | 3792744 |  | eHealth Queensland | 10 | 287762 |  | G | 16 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment. 25/5/2018,a0 25/5/2018,a0The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access. 25/5/2018,a0 | 3792744 | 2017-07-05T00:00:00 | DH
25/5/2018 | QAS | Enterprise Rostering System | 2018-12-31T00:00:00 | Paused |  | 2018-12-31T00:00:00 |  | 2018-03-31T00:00:00 | High | 1000000 |  | Queensland Ambulance Service | 10 | 505297 |  | G | 17 | The initiative is to provide a centralised electronic rostering system to replace existing aging and disparate manual systems currently being utilised across the state. | 1194682 | 2016-12-01T00:00:00 | DH
25/5/2018 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | March: The project has returned to 'green' and is continuing with solution testing activities. 25/5/2018, 25/5/2018,February: The project is currently monitoring several schedule risks impacting a number of configuration activities. | 2018-03-31T00:00:00 | High | 105000000 |  | Metro North | 55 | 52525192 |  | G | 19 | The current Queensland Health Finance, Asset and Materials Maintenance Information System (FAMMIS) system is based on a heavily customised solution which is almost 20 years old and no longer supported. 25/5/2018,The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 25/5/2018, 25/5/2018,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 25/5/2018,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 25/5/2018, 25/5/2018,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
25/5/2018 | EHQ | Follow Me Desktop - Deployment | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-03-31T00:00:00 | High | 3952980 |  | eHealth Queensland | 39 | 981514 |  | G | 20 | Follow Me Desktop Deployment Project will deliver 25/5/2018,a0the Follow Me Desktop service (FMD) to HHS 25/5/2018,92 in alignment with the Infrastructure Remediation Program (IMP) and ieMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 3676980 | 2017-07-03T00:00:00 | DH
25/5/2018 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Delivery |  | 2018-06-28T00:00:00 |  | 2018-03-31T00:00:00 | High | 3301500 |  | eHealth Queensland | 15 | 177416 |  | G | 21 | Project Purpose: 25/5/2018,a0To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 2490769 | 2017-07-01T00:00:00 | DH
25/5/2018 | EHQ | ICT Regional Wireless Infrastructure Initiatives | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-03-31T00:00:00 | High | 4170000 |  | eHealth Queensland | 40 | 2435249 |  | G | 22 | The Regional eHealth Project (ReHP) is a Wireless LAN and Network Infrastructure uplift project so that sites in Far North Qld are ready to rollout their new eHealth Application. | 3489080 | 2017-07-01T00:00:00 | DH
25/5/2018 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Initiate |  | 2019-06-28T00:00:00 |  | 2018-03-31T00:00:00 | Critical | 1120000 |  | eHealth Queensland | 45 | 384037 |  | G | 23 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. | 1120000 | 2017-07-05T00:00:00 | DH
25/5/2018 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-03-31T00:00:00 | High | 3215000 |  | eHealth Queensland | 45 | 4628620 |  | G | 24 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 12318334 | 2015-06-22T00:00:00 | DH
25/5/2018 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 1 | 2016-11-30T00:00:00 | Delivery |  | 2018-04-30T00:00:00 | March: The project has experienced a delay to the completion of Stage 1 due to delays in governance and assurance processes. The project is currently seeking approval to obtain additional time to complete this stage. 25/5/2018, 25/5/2018,February: Approval delays in obtaining additional funding and a slightly extended schedule has impacted the project's schedule, with approvals expected in the upcoming reporting month. | 2018-03-31T00:00:00 | High | 8200000 |  | Health Support Queensland | 91 | 22024483 |  | R | 31 | The IWFM project involves: 25/5/2018,- configuring additional functionality (currently available and licensed, but unutilised) within the existing Rostering and Payroll business solutions 25/5/2018,- partnering with HHSs to develop refined business models and business processes to support the roster-to-pay process 25/5/2018,- undertaking extensive training and change management to support the adoption and effective usage of new functionality and processes | 25060122 | 2016-02-17T00:00:00 | DH
25/5/2018 | EHQ | ieMR Program (Funding Packages 3 and 4) | 2019-04-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-03-31T00:00:00 | High | 0 |  | eHealth Queensland | 25 | 0 |  | G | 25 | ieMR will enable improved patient care through the development of a state-wide, authoritative single source of the patient records. 25/5/2018, 25/5/2018,The ieMR will provide clinicians with the ability to: 25/5/2018,* access data that is integrated, accurate and clinically relevant 25/5/2018,* support decision making and better use of information 25/5/2018,* optimise management of patients, resources and provision of services 25/5/2018,* support interaction across a network of providers by making it easier to find providers, transfer information and collaborate with multidisciplinary providers. 25/5/2018,The Program scope (all tranches) is to roll out the ieMR system to 24 hospitals across Queensland. 25/5/2018, 25/5/2018,Please note that financial information for ieMR is Commercial in Confidence | 0 | 2016-11-17T00:00:00 | DH
25/5/2018 | EHQ | Infrastructure Capacity FY 17-18 | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-03-31T00:00:00 | Medium | 1000000 |  | eHealth Queensland | 60 | 456878 |  | G | 26 | Project Purpose: 25/5/2018,a0 25/5/2018,The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified 25/5/2018,91organic growth 25/5/2018,92 requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. | 2000000 | 2017-07-01T00:00:00 | DH
25/5/2018 | EHQ | Infrastructure Maintenance Program Establishment | 2018-06-29T00:00:00 | Initiate |  | 2022-06-30T00:00:00 | March: This initiative has been refocused to the establishment phase of the Infrastructure Maintenance Program, and as such the % complete and original end date have been updated to reflect this phase of the program. The latest approved end date will be updated in a following reporting month. | 2018-03-31T00:00:00 | Medium | 1161415 |  | eHealth Queensland | 45 | 439613 |  | G | 27 | The Infrastructure Maintenance Program (IMP) 25/5/2018,a0will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 25/5/2018,The scope includes: 25/5/2018,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 25/5/2018,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and 25/5/2018,a0 25/5/2018,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1161819 | 2017-07-03T00:00:00 | DH
25/5/2018 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery |  | 2022-06-30T00:00:00 |  | 2018-04-13T00:00:00 | High | 14673739 |  | Clinical Excellence | 10 | 1336461 |  | G | 28 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 25/5/2018,The ongoing program of work aims to continue and build upon existing functionality by: 25/5/2018, 25/5/2018,95 Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 25/5/2018, 25/5/2018,95 Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 25/5/2018, 25/5/2018,95 Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 25/5/2018, 25/5/2018,95 Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 25/5/2018, 25/5/2018,95 Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
25/5/2018 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate |  | 2022-12-21T00:00:00 |  | 2018-03-31T00:00:00 | High | 6300000 |  | Queensland Ambulance Service | 21 | 469211 |  | G | 29 | Phased delivery of a system supporting QAS business intelligence. | 6300000 | 2017-01-03T00:00:00 | DH
25/5/2018 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 |  | 2018-03-31T00:00:00 | High | 33827000 |  | Clinical Excellence | 21 | 10960515 |  | G | 30 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 39408218 | 2017-03-01T00:00:00 | DH
25/5/2018 | EHQ | Interoperability Project | 2016-04-29T00:00:00 | Delivery |  | 2019-09-29T00:00:00 |  | 2018-03-31T00:00:00 | High | 23850000 |  | eHealth Queensland | 25 | 13044093 |  | G | 32 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 25/5/2018,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 25/5/2018,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 25/5/2018, | 39189509 | 2015-02-01T00:00:00 | DH
25/5/2018 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Delivery |  | 2020-12-21T00:00:00 |  | 2018-04-06T00:00:00 | High | 64000000 |  | Health Support Queensland | 48 | 16794104 |  | G | 33 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 25/5/2018,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. | 64000000 | 2015-08-28T00:00:00 | DH
25/5/2018 | MNHHS | Learning and Performance Management Project | 2017-06-30T00:00:00 | Delivery |  | 2018-11-26T00:00:00 |  | 2018-04-20T00:00:00 | High | 1178190 |  | Metro North | 90 | 1064817 |  | G | 34 | Implement an integrated Learning Management and Performance Management system with the capability to deliver online learning and training content, facilitate performance development and maintain centralised records for reporting purposes. | 1178190 | 2016-07-11T00:00:00 | DH
25/5/2018 | GCHHS | Medical Imaging Informatics Solution (MIIS) Risk Mitigation | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-04-12T00:00:00 | High | 5000000 |  | Gold Coast | 18 | 808316 |  | G | 35 | The Medical Imaging Informatics Solution (MIIS) Risk Mitigation project has identified an Imaging solution which will address the risks and opportunities described in the Case for Change including the mitigation of patient safety risks, increased efficiency and productivity, improvi.ng medical imaging billing revenue collection and cash flow. The solution has user endorsement from radiologists and clinicians and will be specifically configured to meet GCHHS 25/5/2018,92s needs. | 5000000 | 2017-04-03T00:00:00 | DH
25/5/2018 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery |  | 2018-11-30T00:00:00 |  | 2018-04-20T00:00:00 | High | 4030460 |  | Metro North | 40 | 1716453 |  | G | 36 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 25/5/2018, 25/5/2018,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 25/5/2018, 25/5/2018,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
25/5/2018 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery |  | 2017-12-31T00:00:00 | March: The project is continuing to report 'Red' due to delays resulting from integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-04-20T00:00:00 | High | 6299780 |  | Metro North | 75 | 6461885 |  | R | 37 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 6299780 | 2014-06-01T00:00:00 | DH
25/5/2018 | EHQ | Metro South and East Queensland ICT Infrastructure Replacement Initiative | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-03-31T00:00:00 | High | 4160449 |  | eHealth Queensland | 63 | 1101988 |  | G | 38 | Will replace or uplift out of date end of life ICT assets. | 3614877 | 2017-07-01T00:00:00 | DH
25/5/2018 | EHQ | Metro South East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-03-31T00:00:00 | High | 2182844 |  | eHealth Queensland | 40 | 505046 |  | G | 39 | Will replace or uplift out of date end of life ICT assets. | 2182843 | 2017-07-01T00:00:00 | DH
25/5/2018 | EHQ | Mobile Application System for Bring Your Own Device | 2018-06-30T00:00:00 | Delivery |  | 2018-07-06T00:00:00 |  | 2018-03-31T00:00:00 | High | 1639698 |  | eHealth Queensland | 65 | 994172 |  | G | 40 | This project leverages the investment of the previous Bring-Your-Own-Device (BYOD) 25/5/2018,a0projects to extend the capability of device mobility by building the foundations of a Mobile Application Ecosystem - the processes, products and services to enable the managed development of low/no code applications by Health and Hospital Services (HHS). 25/5/2018,a0 This project will also complete the deployment of BYOD laptops and provide recommendations on how cost savings can be made by the organisation around Corporate devices and data plans. 25/5/2018,a0 | 1549504 | 2017-07-01T00:00:00 | DH
25/5/2018 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery |  | 2018-12-19T00:00:00 | March: This project is experiencing delays in pre-migration activities and delays experienced in another dependent project. Additional finances and resources are required, with these issues being managed by the project's governance committee. 25/5/2018, 25/5/2018,January: This project is experiencing delays in pre-migration activities and delays experienced in another dependent project. | 2018-03-31T00:00:00 | High | 14100000 |  | eHealth Queensland | 49 | 17827149 |  | R | 41 | This project will move Queensland Health to a modern end user workspace that is: current; delivering collaboration and productivity benefits; able to be accessed anywhere, anytime and on any device; reducing the reliance and expense of on premise infrastructure and support and not constraining the business from taking advantage of modern applications and services. | 27427900 | 2016-05-12T00:00:00 | DH
25/5/2018 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Delivery |  | 2018-06-30T00:00:00 |  | 2018-03-31T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 85 | 614712 |  | G | 42 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1744000 | 2015-10-01T00:00:00 | DH
25/5/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-03-31T00:00:00 | High | 4245973 |  | eHealth Queensland | 65 | 1319090 |  | G | 56 | Will replace or uplift out of date end of life ICT assets. | 4245973 | 2017-07-01T00:00:00 | DH
25/5/2018 | CHOPD | Notifiable Conditions System Replacement | 2019-06-29T00:00:00 | Delivery |  | 2020-02-28T00:00:00 |  | 2018-03-31T00:00:00 | High | 12000000 |  | Chief Health Officer and Prevention | 38 | 2430061 |  | G | 43 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 25/5/2018,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
25/5/2018 | EHQ | Patient Administration System (PAS) Replacement - Business Case Development Project | 2017-06-30T00:00:00 | Initiate |  | 2019-03-29T00:00:00 |  | 2018-03-31T00:00:00 | Medium | 3850000 |  | eHealth Queensland | 57 | 3988256 |  | G | 44 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients 25/5/2018,92 journeys, and ensure that accurate information about our patients is readily available when and where required. 25/5/2018, 25/5/2018,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 25/5/2018, 25/5/2018,95 support for patient engagement 25/5/2018, 25/5/2018,95 integrated care 25/5/2018, 25/5/2018,95 clinical research 25/5/2018, 25/5/2018,95 population health (for patients using public health services) 25/5/2018, 25/5/2018,95 performance transparency 25/5/2018, 25/5/2018,95 resource planning. | 11890865 | 2015-11-01T00:00:00 | DH
25/5/2018 | MNHHS | Picture Archiving and Communication System (PACS) | 2017-09-29T00:00:00 | Delivery |  | 2017-12-31T00:00:00 | March: The project is continuing to report 'Red' due to delays resulting from integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-04-20T00:00:00 | High | 3114694 |  | Metro North | 75 | 3097853 |  | R | 45 | Procure and implement a contemporary Picture Archiving and Communication (PACS) system and functionality that will ensure improved service delivery for the MNHHS Medical Imaging Departments (and other PACS users) through replacement of RBWH PACS ensuring that it is scalable and able to meet the ongoing needs of Metro North Hospital and Health Service. | 3656297 | 2016-07-11T00:00:00 | DH
25/5/2018 | CSD | Practice Management Enterprise Solution | 2018-11-01T00:00:00 | Initiate |  | 2018-11-01T00:00:00 |  | 2018-04-06T00:00:00 | High | 1470000 |  | Corporate Services | 56 | 707868 |  | G | 46 | The main practice management software used by HHSs to conduct private practice services and billing activities is being replaced. The initiative will procure and implement "like for like" functionality enterprise solution for participating HHSs (15 in total). | 2961432 | 2017-08-01T00:00:00 | DH
25/5/2018 | EHQ | Project, Program and Portfolio Management Application | 2018-03-31T00:00:00 | Initiate |  | 2018-06-29T00:00:00 |  | 2018-03-31T00:00:00 | Medium | 1344177 |  | eHealth Queensland | 30 | 477915 |  | G | 47 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 25/5/2018, | 1473632 | 2017-05-02T00:00:00 | DH
25/5/2018 | CED | Queensland Integrated Safety Information Project (QISIP) / Risk Management | 2017-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 |  | 2018-04-11T00:00:00 | High | 4333120 |  | Clinical Excellence | 89 | 7871447 |  | G | 48 | This initiative will source a state wide system to replace existing enterprise risk management systems to support patient and staff incident reporting, feedback, case management and risk management processes. | 16273520 | 2013-01-25T00:00:00 | DH
25/5/2018 | EHQ | Queensland State-wide ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-03-31T00:00:00 | High | 3246247 |  | eHealth Queensland | 42 | 676673 |  | G | 49 | Will replace or uplift out of date end of life ICT assets. | 3246247 | 2017-07-01T00:00:00 | DH
25/5/2018 | EHQ | Queensland State-wide ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-03-31T00:00:00 | High | 3283431 |  | eHealth Queensland | 68 | 2122466 |  | G | 50 | Will replace or uplift out of date end of life ICT assets. | 3282431 | 2017-07-01T00:00:00 | DH
25/5/2018 | MNHHS | Quick Flow Project | 2019-02-01T00:00:00 | Initiate |  | 2019-06-30T00:00:00 |  | 2018-04-20T00:00:00 | High | 6408600 |  | Metro North | 49 | 1061693 |  | G | 51 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 25/5/2018,The key objectives of the project are to: 25/5/2018, 25/5/2018,95 Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 25/5/2018, 25/5/2018,95 Improve the outpatient experience across MNHSS facilities and community services 25/5/2018, 25/5/2018,95 Improve clinic resource utilisation 25/5/2018, 25/5/2018,95 Increase the efficiency of clinical and administrative processes 25/5/2018, 25/5/2018,95 Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
25/5/2018 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Initiate |  | 2019-12-31T00:00:00 |  | 2018-04-09T00:00:00 | High | 34950000 |  | Cairns and Hinterland | 59 | 9918061 |  | G | 52 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patient 25/5/2018,92s home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
25/5/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-03-31T00:00:00 | High | 4260336 |  | eHealth Queensland | 40 | 1051706 |  | G | 53 | Will replace or uplift out of date end of life ICT assets. | 4260336 | 2017-07-01T00:00:00 | DH
25/5/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-03-31T00:00:00 | High | 2150147 |  | eHealth Queensland | 60 | 754879 |  | G | 54 | Will replace or uplift out of date end of life ICT assets. | 2678483 | 2017-07-01T00:00:00 | DH
25/5/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-03-31T00:00:00 | High | 1651750 |  | eHealth Queensland | 40 | 617565 |  | G | 55 | Will replace or uplift out of date end of life ICT assets. | 1651750 | 2017-07-01T00:00:00 | DH
25/5/2018 | EHQ | Service Delivery Excellence Project (SDEP) | 2018-02-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | March: The latest approved end date and percentage complete has been updated to reflect the whole of program life for this initiative. 25/5/2018, 25/5/2018,February: The latest approved end date for this initiative will be updated pending advise from the project. | 2018-03-31T00:00:00 | High | 4822000 |  | eHealth Queensland | 15 | 487924 |  | G | 57 | The Service Delivery Excellence Project (SDEP) aims to improve the service delivery functions of eHealth Queensland to help the organisation achieve its Customers and services Foundation and Shared Goal: 25/5/2018,Enhance value for customers by streamlining end to end services, processes and delivery models so that we can provide an exceptional customer experience. 25/5/2018,Stage 1 has the primary objective of delivering the Project Initiation Document (PID) for the Service Delivery Excellence Project (SDEP) Stage 2. | 4821750 | 2017-10-16T00:00:00 | DH
25/5/2018 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Initiate |  | 2020-09-30T00:00:00 |  | 2018-03-31T00:00:00 | High | 10500000 |  | eHealth Queensland | 10 | 480893 |  | G | 58 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 10500000 | 2017-07-03T00:00:00 | DH
25/5/2018 | MNHHS | Royal Brisbane and Womens Hospital Wi-Fi | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-04-20T00:00:00 | High | 5000000 |  | Metro North | 18 | 2226045 |  | G | 59 | The RBWH Wi-Fi Project will provide an uplift and renewal to the latest Queensland Health (QH) standard for wireless local area network (WLAN) coverage within the internal areas of prioritised RBWH buildings in order to support digital healthcare. 25/5/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for the RBWH in the near future. | 5000000 | 2017-10-22T00:00:00 | DH
25/5/2018 | EHQ | Storage Asset Replacement | 2018-06-29T00:00:00 | Delivery |  | 2018-06-22T00:00:00 |  | 2018-03-31T00:00:00 | High | 1671556 |  | eHealth Queensland | 30 | 176951 |  | G | 60 | The Storage Asset Replacement (SAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the SAR and Backup Asset Replacement (BAR) projects. 25/5/2018,The SAR project seeks to outline architecture for storage that will provide a cost effective, scalable and fit for purpose environment for the future of storage services within Queensland Health. 25/5/2018,a0 Utilising space saving technologies which will enable further cost savings and reduce the requirement for capacity expansion in the short to medium term. | 1659988 | 2017-07-03T00:00:00 | DH
25/5/2018 | EHQ | Telehealth Asset Replacement FY 17-18 | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-03-31T00:00:00 | High | 1960000 |  | eHealth Queensland | 73 | 1819393 |  | G | 61 | Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector 25/5/2018,a0 25/5/2018,and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. 25/5/2018,The Department of Health defines Telehealth as: 25/5/2018, 25/5/2018,95Live, audio and/or video inter-active link for clinical consultations and educational purposes 25/5/2018, 25/5/2018,95Store and forward Telehealth - this model can involve digital images, video, audio and clinical data being captured ("stored") on the client computer; then at a convenient time transmitted securely ("forwarded") 25/5/2018,a0 to a clinic at another location where they are studied by relevant specialists 25/5/2018, 25/5/2018,95Teleradiology for remote reporting and clinical advice for diagnostic images 25/5/2018, 25/5/2018,95Telehealth services and equipment to monitor people 25/5/2018,92s health in their home. 25/5/2018,Benefits of Telehealth 25/5/2018, 25/5/2018,95Improve patient access to health care 25/5/2018, 25/5/2018,95Reduce travel and inconvenience for patients, families, carers and health professionals 25/5/2018, 25/5/2018,95Provide health professionals with access to peer support and education. 25/5/2018,The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. 25/5/2018,a0 25/5/2018,The priority is to replace those end-of-life assets which pose the greatest risk to effective health service delivery. | 1957626 | 2017-07-03T00:00:00 | DH
25/5/2018 | MNHHS | The Prince Charles Hospital (TPCH) Wi-Fi | 2018-06-29T00:00:00 | Delivery |  | 2018-06-29T00:00:00 |  | 2018-04-20T00:00:00 | High | 1408388 |  | Metro North | 40 | 1015271 |  | G | 62 | The Prince Charles Hospital (TPCH) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the hospital campus for prioritised TPCH buildings. 25/5/2018, 25/5/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1408388 | 2017-07-27T00:00:00 | DH
25/5/2018 | EHQ | Sunshine Coast University Hospital (SCUH) Stage 2 ICT Expansion | 2018-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | February: This project has been reported for the first time. | 2018-03-31T00:00:00 | High | 3180000 |  | eHealth Queensland | 57 | 1903171 |  | G | 63 | Sunshine Coast University Hospital (SCUH) ICT Stage 1 delivered the ICT required to achieve the successful commissioning of SCUH in March 2017. The SCUH Stage 2 ICT Expansion covers the investment period from 1 July 2017 to 31 December 2018 and is intended to support the planned expansion of SCUH to increase capacity and establish new services. | 3180422 | 2017-07-03T00:00:00 | DH
25/5/2018 | CHQ | Information Sharing Project Phase 2 | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | March: This project has been reported for the first time. | 2018-03-31T00:00:00 | High | 4455455 |  | Childrens Health Queensland | 10 | 542128 |  | G | 64 | Department of Health, eHealth Queensland, Children 25/5/2018,92s Health Queensland and Mater Health share a common vision for the seamless integration of care across organisational boundaries, in the interests of patient safety, quality, efficiency and improved access to care. This vision of integrated care processes is enabled through seamless access, at the point of care, to necessary health information and efficient transactional capabilities that support the care continuum. | 4455455 | 2018-01-10T00:00:00 | DH
25/5/2018 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | There have been delays to the project schedule from reprioritisation of resources to community recovery activities associated with Cyclone Debbie. Additionally, the vendor, SMS Management and Technology, has not delivered within the contracted timeframes and we are negotiating with the vendor to ensure completion of the solution. | 2018-04-30T00:00:00 | High | 2208000 |  | Whole of Department | 88 | 3183000 |  | G | 1 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3483000 | 2016-07-01T00:00:00 | DCCSDS
25/5/2018 | Cross-Gov | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | The Queensland Fire and Emergency Services (QFES) Human Capital Management Workplace Health and Safety and Case Management functionality has a revised implementation of mid-June 2018 due to the identification and rectification of some testing defects and final penetration testing prior to go-live. 25/5/2018, 25/5/2018,The Queensland Corrective Services Human Capital Management Business Case has been approved with detailed project planning commencing. 25/5/2018, 25/5/2018,The Queensland Ambulance Service and QFES payroll projects transitioning to Aurion are progressing to schedule. | 2018-03-31T00:00:00 | Critical | 101500000 |  | Cross-Government program led by DSITI | 59 | 56036775 |  | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 25/5/2018, 25/5/2018,* Sustainable and supported HR and Payroll service delivery 25/5/2018,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 25/5/2018,* Strategic HR capability that supports the development, performance and safety of the departments workforce 25/5/2018,* Business Intelligence capability that provides real timely, integrated HR information 25/5/2018,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 25/5/2018,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 25/5/2018,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
25/5/2018 | QPS | Online National Police Certificate | 2017-06-30T00:00:00 | Delivery |  | 2018-07-31T00:00:00 | Since the successful launch of Online National Police Certificates 72% of all applications have been submitted online. The overall number of applications submitted online, has doubled from December 2017 to January 2018. 25/5/2018, 25/5/2018,National Police Certificate campaign material has been distributed to all Police Districts for display in all Stations and Police Beats. External marketing via social media will commence in April 2018. 25/5/2018, 25/5/2018,Feb 2018: The revised project budget has been amended from previously published figures to reflect the increased investment in promotional products. | 2018-04-18T00:00:00 | High | 275000 |  | Queensland Police Service | 95 | 218000 |  | G | 1 | The Online National Police Certificate Project will implement an online service for the community to apply and pay for Name Only National Police Certificates online, rather than presenting at a police station, or using the online services of an Australian Crime Intelligence Commission accredited broker. This will provide improved customer service to the community through a more efficient and reliable QPS service, with no requirement to present at a police station, as well as provide efficiency and time savings to local police stations and the Police Information Centre. | 250000 | 2017-01-01T00:00:00 | QPS
25/5/2018 | QPS | Police Integrity and Professional Standards | 2018-08-24T00:00:00 | Delivery |  | 2019-08-31T00:00:00 | Project Board has approved a revised end date of 31 August 2019. Previous Invitation to Offer considered and not proceeded with as it was deemed financially un-viable. Meeting with relevant stakeholders held to discuss way forward. Project now reviewing budget and some requirements with a view to establish if a smaller funding request is viable. 25/5/2018, 25/5/2018,Note: original planned end date amended as previously published information was incorrect. | 2018-04-18T00:00:00 | High | 4142000 |  | Queensland Police Service | 30 | 176151 |  | A | 2 | This initiative will deliver a new integrated Police Integrity and Professional Standards IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The Police Integrity and Professional Standards system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The Police Integrity and Professional Standards Project will also complement the Complaints Reform Project established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of the Police Integrity and Professional Standards system will place the QPS in a strong readiness position to fully implement Complaints Reform Project generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 4142000 | 2017-03-07T00:00:00 | QPS
25/5/2018 | QPS | Advanced Data Analytics | 2017-07-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project continues to deliver new capability in all streams with most capability available for use during the 2018 Commonwealth Games. Current focus is on expanding the capability developed by the project into 2017-18 as business-as-usual capability and positioning the outputs/products of the project for developing the next phase of QPS advanced analytics capabilities. | 2018-04-18T00:00:00 | Low | 1730000 |  | Queensland Police Service | 92 | 2154400 |  | G | 3 | Develop the QPS Advanced Data Analytics proof-of-concept. This proof-of-concept is intended to inform a larger suite of data analytics integration and intelligence over the next four years, including the development of predictive and alert models to enhance the operational response to threats, incidents and events. | 2350000 | 2017-02-19T00:00:00 | QPS
25/5/2018 | QPS | Body Worn Cameras | 2018-02-28T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The Project completed the deployment of all Stage Two body worn cameras in December 2017 and is now preparing closure activities and transition to business as usual by 30 June 2018. 25/5/2018, 25/5/2018,Feb 2018: The original approved budget was $6.03M. In May 2017 the QPS Demand and Resource Committee approved an additional $0.860M, making the total approved budget $6.890M. | 2018-04-18T00:00:00 | Medium Low | 6030000 |  | Queensland Police Service | 90 | 6890000 |  | G | 4 | The Queensland Police Service Body Worn Camera Project is deploying 5100 body worn cameras to frontline police officers. Body worn cameras will be deployed to 168 police stations, 16 tactical crime units, 47 road policing units, and specialist units including dog squads and the Public Safety Response Team in two stages. The cameras integrate with the QPS mobility devices, allowing officers to add metadata to videos and to review videos in the field. A system for storage and allocation of digital camera data will also be implemented as well as policy related to use of the cameras. | 6890000 | 2014-08-25T00:00:00 | QPS
25/5/2018 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Objectives 25/5/2018,- This project will deliver a secondary DR site and hyper-converged system to provide resilience for all departmental business applications in the event of a disaster. 25/5/2018, 25/5/2018,Project Updates 25/5/2018,- Core infrastructure DR implementation 70% complete. All migrated production systems successfully replicating to secondary DR site. 25/5/2018,Oracle system DR implementation is 90% complete. Estimated completion June 2018. 25/5/2018,- SPER and QWIC databases successfully migrated to CITEC. 25/5/2018,- SPER DR failover testing scheduled for May 2018. 25/5/2018,- QWIC DR failover testing scheduled for June 2018. 25/5/2018,- All end-of-life ICT infrastructure will be decommissioned from July to October 2018. 25/5/2018,- The newly implemented infrastructure will provide improved stability and life extension to existing business-critical applications. 25/5/2018,- Documentation of DR recovery procedure, testing strategy and updating ICT DR plan in progress. 25/5/2018, 25/5/2018,Project Schedule 25/5/2018,- Some issues have impacted YTD position however it is anticipated that the original completion date will be met. These include: 25/5/2018,- Commonwealth Games change freeze in March and April 2018. 25/5/2018,- DR failover testing of DJAG and QCS business critical system 25/5/2018,- network upgrade delays are delaying project deliverables. | 2018-04-30T00:00:00 | High | 7460674 |  | Corporate Services | 70 | 3512449 |  | G | 1 | Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 5917255 | 2016-10-01T00:00:00 | DJAG
25/5/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery |  | 2018-03-31T00:00:00 | Project closure activities are underway. The Board is re-baselining timelines to allow project closure by the end of April. | 2018-03-31T00:00:00 | Medium | 800000 |  | Chief Information Office | 99 | 910802 |  | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | HPW
25/5/2018 | QSS | Legacy Finance Archiving Project | 2018-03-29T00:00:00 | Closed |  | 2018-03-29T00:00:00 | Project has been delivered successfully. | 2018-03-31T00:00:00 | High | 845949 |  | Queensland Shared Services | 100 | 843024 |  | G | 2 | This project will archive finance data for legacy finance solution into a standard archive/enquiry solution. | 845949 | 2016-09-01T00:00:00 | HPW
25/5/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Closed |  | 2018-03-16T00:00:00 | Project has been delivered successfully. | 2018-03-31T00:00:00 | High | 1800000 |  | Queensland Shared Services | 100 | 1867957 |  | G | 3 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | HPW
25/5/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project is on track. | 2018-03-31T00:00:00 | Critical | 516033 |  | Smart Service Queensland | 93 | 1034872 |  | G | 4 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | HPW
25/5/2018 | SSQ | Automated Payments Solution | 2018-07-31T00:00:00 | Initiate |  | 2018-07-31T00:00:00 | This project is currently in the procurement phase and is on track. | 2018-03-31T00:00:00 | Critical | 1500000 |  | Smart Service Queensland | 0 | 0 |  | G | 5 | The Automated Payments project will implement an improved capability for offering secure payment card transactions via the telephone. This is a dependency for achieving compliance meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1500000 | 2018-01-29T00:00:00 | HPW
25/5/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery |  | 2018-07-31T00:00:00 | Timeframe and budget for the project are being reviewed as a result of Payment Card Industry Remediation Implementation project dependency and the need for additional integration identified. | 2018-03-31T00:00:00 | Critical | 4490634 |  | Smart Service Queensland | 58 | 3295396 |  | A | 6 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 25/5/2018, 25/5/2018,* reduce operating costs 25/5/2018,* increase capacity 25/5/2018,* improve customer experience 25/5/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | HPW
25/5/2018 | PWAM | iSpace External Hosting Migration Project | 2017-01-31T00:00:00 | Delivery |  | 2018-03-30T00:00:00 | Project closure activities are underway and project costs are being finalised. The costs to date now include the vendor payments for the delivered milestones. The total cost of the project is expected to be slightly less than planned expenditure. | 2018-03-31T00:00:00 | High | 735000 |  | Queensland Government Accommodation Office | 98 | 1084244 |  | A | 12 | Version upgrade and migration of the hosting of Queensland Accommodation Office core system to a hosted managed service arrangement. | 1415203 | 2016-05-01T00:00:00 | HPW
25/5/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery |  | 2018-07-18T00:00:00 | A live trial was conducted with a number of customer agents taking calls on the solution with positive results. Focus remains on ensuring testing and security issues are addressed. Business readiness is progressing well with user training underway and ensuring the workforce are fully supported for go-live. | 2018-03-31T00:00:00 | Critical | 3476245 |  | Smart Service Queensland | 70 | 1849584 |  | G | 7 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | HPW
25/5/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. | 2018-03-31T00:00:00 | Critical | 3390861 |  | Smart Service Queensland | 81 | 2097852 |  | G | 8 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | HPW
25/5/2018 | QSA | Digital Archiving Program - Tranche 1 | 2019-12-31T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | The procurement activity is progressing to planned timeframes and milestones. | 2018-03-31T00:00:00 | Critical | 12701000 |  | Queensland State Archives | 72 | 1327100 |  | G | 9 | To ensure the delivery of an as-a-Service eco-system to effectively archive, manage and enable search and discovery of Queensland's permanent high value records. The new digital services will support the Queensland Government's blueprint for innovation and collaboration, providing better outcomes for Queenslanders. | 12701000 | 2017-07-01T00:00:00 | HPW
25/5/2018 | CITEC ICT | z14 Mainframe Upgrade | 2018-07-31T00:00:00 | Delivery |  | 2018-07-31T00:00:00 | Phase one has been completed. The majority of the budget and project cost to date relates to the purchase of hardware and associated cabling. The remaining budget is for the labour required for installation. Project remains on track. | 2018-03-31T00:00:00 | High | 4720752 |  | CITEC ICT | 70 | 4566947 |  | G | 10 | The project will replace the two existing z12 Mainframes (Production and Disaster Recovery) with upgraded z14 Mainframes and migrate the existing data from the old to the new. 25/5/2018, 25/5/2018,The current z12 platform is unable to be upgraded and cannot provide sufficient capability for increasing client requirements. The continued use of the z12 platform represents significant risk to business continuity. 25/5/2018, 25/5/2018,The upgrade will reduce ongoing operating costs, enable improved services to clients and provide for clients' future capacity requirements. 25/5/2018, | 4720752 | 2017-12-18T00:00:00 | HPW
25/5/2018 | Housing | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery |  | 2019-03-31T00:00:00 | The FOPATS Program undertook a significant re-baseline in late 2016 to inform and approve changes to its strategic direction, scope, delivery methodology, timing and costs, including strengthening program governance and revising the Business Case to complete against a two staged implementation, Property and then Tenancy. 25/5/2018, 25/5/2018,Following this review, the Property Release, the first of two stages, was delivered successfully on time on 1 November 2017 and delivered benefits including efficiencies in property management and reporting. 25/5/2018, 25/5/2018,The refreshed business case, the Program budget and planned end date were formally re-baselined in January 2018. This formal approval, coupled with the successful delivery of the first stage Property Release, saw the Program status move to green. 25/5/2018, 25/5/2018,The Program has completed more detailed planning for the second stage Tenancy Release, which will remove the operational dependency on the existing ICT housing solution entirely. Tenancy design activities are now well progressed, and the Program is expected to be in a position to publish the revised Program end date in the next reporting period. | 2018-03-31T00:00:00 | Critical | 56286000 |  | Housing Services | 57 | 69100000 |  | G | 11 | Replace the existing ICT housing solution with an integrated ICT system. | 121597695 | 2013-07-01T00:00:00 | HPW
25/5/2018 | QGP | Fleet Management System Replacement Project (FMSRP - QFleet) | 2019-09-30T00:00:00 | Initiate |  | 2019-09-30T00:00:00 | The project is tracking to plan. The project is currently subject to procurement activities. | 2018-03-31T00:00:00 | High | 13939200 |  | QFleet | 7 | 405085 |  | G | 13 | The project will deliver for the Department of Housing and Public Works, Public Safety Business Agency and Queensland Ambulance Service a fleet management solution to replace existing aging legacy systems. | 13939200 | 2017-10-19T00:00:00 | HPW
25/5/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 25/5/2018, 25/5/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 25/5/2018,October 2017 - The project is progressing as planned. 25/5/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 25/5/2018,June 2017 - Revised Schedule approved returning the project to Green. 25/5/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 25/5/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 25/5/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 25/5/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 25/5/2018,December 2016 - The project is progressing as planned. | 2017-12-21T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 25/5/2018, 25/5/2018,* register and maintain their information 25/5/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
25/5/2018 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 25/5/2018, 25/5/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 25/5/2018,August 2017 - Approved extension of timeframe. 25/5/2018,June 2017 - The project is progressing as planned. 25/5/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 25/5/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 25/5/2018,October 2016 - Progress is continuing as planned. 25/5/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 25/5/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 25/5/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-21T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 25/5/2018, 25/5/2018,* support compliance with legislation 25/5/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 25/5/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 25/5/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 25/5/2018, | 1390000 | 2012-04-01T00:00:00 | DEWS
25/5/2018 | BQ | Biosecurity Information Management System Program | 2017-05-31T00:00:00 | Delivery |  | 2018-04-30T00:00:00 | The program is progressing as planned, awaiting formal closure. 25/5/2018, 25/5/2018,December 2017 - Program delivery is complete, however, the final end date has been extended by three months to allow for full transition to business as usual, project and program closure activities and final assurance reviews. 25/5/2018,November 2017 - The planned end date has been extended by one month; this remains within acceptable program tolerances. 25/5/2018,March 2017 - The program is progressing as planned in line with approved change to scope, timeframe, benefits and cost. 25/5/2018,January 2017 - A small scope increase has been proposed, currently progressing through governance processes. 25/5/2018,November 2016 - Note, a scope review is currently under way. 25/5/2018,May 2016 - Program is continuing as planned. Note a small extension to planned end date. 25/5/2018,March 2016 - A re-baseline has brought all parameters back to Green. 25/5/2018,January 2016 - Timeframe, Cost, and Quality remain Amber, pending a business case update due early April 2016. 25/5/2018,November 2015 - Program is still Amber while the Timeframe is being re-baselined. 25/5/2018,September 2015 - The Exception Report has been accepted by the Program Board. Timeframe remains Amber pending a business case update. 25/5/2018,July 2015 - Resources continue to be redirected to assist with emergency response to the Panama banana disease. An Exception Report is being developed to address this. 25/5/2018,May 2015 - As anticipated, the emergency response to the Panama Banana disease outbreak has impacted both the project cost and the Timeframe. 25/5/2018,March 2015 - There is currently an outbreak of Panama banana disease which has potential to impact the schedule of this project. 25/5/2018,January 2015 - Actions are being taken to resolve some current scheduling issues. | 2018-05-11T00:00:00 | Critical | 18080000 |  | Biosecurity Queensland | 98 | 18230000 |  | G | 1 | Deliver an integrated toolkit consisting of various information management technologies and enhanced business processes to improve the management of biosecurity risks in Biosecurity Queensland's day-to-day business operations and in emergency responses. | 19409000 | 2013-07-01T00:00:00 | DAF
25/5/2018 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | Field testing identified unexpected issues that will impact on the planned end date. A review of time-frame and budget is under way. 25/5/2018, 25/5/2018,April 2018 - An extension to the planned end date has been approved, returning the project status to Green. 25/5/2018, 25/5/2018,March 2018 - A minor scope increase has been proposed, affecting both timeframe and cost, which is progressing through the governance process. 25/5/2018, 25/5/2018,March 2018 - The project is progressing as planned. 25/5/2018, 25/5/2018,December 2017 - A variation to scope was approved, resulting in a change to the planned end date and total estimated expenditure. 25/5/2018, 25/5/2018,November 2017 - The project is continuing as planned. 25/5/2018, 25/5/2018,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2018-05-11T00:00:00 | Medium | 608146 |  | Forestry Queensland | 90 | 967606 |  | A | 2 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 25/5/2018, 25/5/2018,* the capture, management and integration of data 25/5/2018,* value-adding opportunities for business improvement 25/5/2018,* management of risk associated with ongoing use and maintenance of disparate systems. | 976431 | 2016-06-15T00:00:00 | DAF
25/5/2018 | BQCC | Communication and Stakeholder Engagement Solution | 2018-04-27T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | A change to the planned end date and cost has been approved. 25/5/2018, 25/5/2018,March 2018 - Note adjustment to planned end date corrected due to typographical error. 25/5/2018, 25/5/2018,February 2018 - The project is progressing as planned. 25/5/2018, 25/5/2018,December 2017 - The project was approved to move into delivery in October 2017 and is being published for the first time. | 2018-05-11T00:00:00 | Medium | 694000 |  | Biosecurity Queensland Control Centre | 70 | 513542 |  | G | 3 | Implement a simple, easy to use system that will facilitate the collection of information associated with the National Red Imported Fire Ant Eradication Program and the National Electric Ant Eradication Program. This will include contact management, complaints management, history of interactions, event management, training management, social media interactions, marketing campaign and reporting. | 694000 | 2017-06-01T00:00:00 | DAF
25/5/2018 | ASQ | Portfolio Activity Reporting Information System | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | Funding has been approved to fully implement the project and it is now in delivery. 25/5/2018, 25/5/2018,February 2018 - The project is paused until a funding source is identified. 25/5/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-05-11T00:00:00 | High | 500000 |  | Agri-Science Queensland | 10 | 231622 |  | G | 4 | Review and consolidate the variety of processes and technologies currently being used to manage the department's research, development and extension, and other projects. | 500000 | 2015-08-13T00:00:00 | DAF
25/5/2018 | Ag | Risk Reduction for Customer Service Centre | 2019-04-19T00:00:00 | Delivery |  | 2019-04-19T00:00:00 | The project is continuing as planned. 25/5/2018, 25/5/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-05-11T00:00:00 | High | 1767000 |  | Agriculture | 35 | 377517 |  | G | 5 | Implement a solution to mitigate risk of end of life for the agency's call centre logging application. | 1767000 | 2015-01-30T00:00:00 | DAF
25/5/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
25/5/2018 | PSBA | Emergency Services Computer Aided Dispatch (ESCAD) Upgrade Program | 2016-09-30T00:00:00 | Delivery |  | 2018-07-03T00:00:00 | The updated ESCAD system cut over for Queensland Ambulance Service (QAS) completed successfully on 17-01-2018, and the Queensland Fire and Emergency Services (QFES) also completed successfully on 24-01-2018. The decommissioning of hardware in the obsolete environments is currently underway. The ESCAD System Upgrade Project, as major initiative in the program of works, experienced significant technical and implementation issues causing an approved rebaseline in January 2017. This resulted in a revised timeframe from the original plan of 30-09-2016 to 3-07-2018 and a revised estimate at completion from the original of $6,774,820 to $9,789,600 for the Program. | 2018-04-27T00:00:00 | Critical | 6774820 |  | Public Safety Business Agency | 88 | 9026125 |  | G | 1 | A program of work for Queensland Ambulance Service and Queensland Fire and Emergency Services to upgrade the Emergency Services Computer Aided Dispatch System,including infrastructure, operating system and application software. | 9789600 | 2015-01-15T00:00:00 | PSBA
25/5/2018 | PSBA | Emergency Vehicle Priority (EVP) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | All rollouts of devices into vehicles will be completed by 30-06-2018. Procurement of a managed service for operational support and maintenance has required an extension of the project schedule. This resulted in a revised timeframe from the original planned end date of 30-06-2017 to 31-10-2018, and a revised budget from the original expenditure plan of $3.4 million to $4.4 million. | 2018-04-27T00:00:00 | High | 3370000 |  | Public Safety Business Agency | 87 | 4062462 |  | G | 2 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 25/5/2018, 25/5/2018,* Responsive vehicle movements 25/5/2018,* Improve road safety 25/5/2018,* Congestion management 25/5/2018,* Community safety | 4370331 | 2013-01-01T00:00:00 | PSBA
25/5/2018 | PSBA | Inter-CAD Electronic Messaging System (ICEMS) | 2016-08-31T00:00:00 | Delivery |  | 2018-03-16T00:00:00 | The ICEMS system cut over for Queensland Police Service (QPS) and Queensland Ambulance Service (QAS) completed successfully on 28-07-2017, and ICEMS for the Queensland Fire and Emergency Services (QFES) completed successfully on 24-01-2018. Project closure activities are being finalised. The ICEMS Project experienced significant technical and implementation issues causing multiple approved re-baselines between November 2015 and September 2017. This resulted in a revised timeframe from the original planned end date 31-08-2016 to 16-03-2018 and a revised budget from the original planned expenditure of $560K to $1,571K. The original planned end date has been updated to 31-08-2016 as it was previously incorrectly reported. | 2018-04-27T00:00:00 | Critical | 560000 |  | Public Safety Business Agency | 99 | 1570683 |  | G | 3 | To implement the ICEMS protocol between the Queensland Police Service (QPS), Queensland Ambulance Service (QAS) and Queensland Fire and Emergency Services (QFES) computer aided dispatch systems to enable Triple Zero data sharing between agencies. | 1571139 | 2015-10-06T00:00:00 | PSBA
25/5/2018 | PSBA | PSBAIGEM Office 365 Implementation Project | 2018-02-20T00:00:00 | Delivery |  | 2018-05-11T00:00:00 | Project budget has been increased to $1.1 million as a result of full rollout planning. 25/5/2018,Project has re-baselined the schedule from 09-03-2018 to 11-05-2018 as a result of moving from pilot to full rollout. 25/5/2018,Schedule was previously re-baselined from 20-02-2018 to 9-03-2018 due to increase in scope, regarding mobility solutions for users. 25/5/2018,To date 235 PSBA users have been successfully migrated to Office 365 services. 25/5/2018,The project is currently working through the preparation tasks for the remaining PSBA users to be migrated to Office 365 (approximately 1100 users). | 2018-04-27T00:00:00 | Critical | 986000 |  | Public Safety Business Agency | 93 | 757613 |  | G | 4 | The project will deliver digital transformation for the Public Safety Business Agency (PSBA) and Inspector-General Emergency Management (IGEM) through the implementation of the Office 365 suite of products to augment the below enhancements to their current business processes. Undertaking smarter meetings; Facilitating better administration; Accessing information anywhere, any time; Engaging and communicating better; Supporting capability development; Facilitating business intelligence; and Enabling efficient workflow and approvals. | 1136000 | 2017-09-20T00:00:00 | PSBA
25/5/2018 | PSBA | QFES Office 365 Implementation Project | 2018-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The Queensland Fire and Emergency Services (QFES) Office 365 Project is scheduled to be delivered by 30-06-2018. Underspends for FY17/18 will be requested to be deferred to FY18/19, to fund additional Office 365 projects. | 2018-04-27T00:00:00 | Medium | 2100000 |  | Public Safety Business Agency | 52 | 628395 |  | G | 5 | This project will deliver the most up-to-date Office 365 suite of products to all Queensland Fire and Emergency Services (QFES) staff and enable QFES to mobilise its workforce. 25/5/2018, 25/5/2018,* Upgrade QFES technology fleet to the latest Microsoft Office version 25/5/2018,* Cloud services will enable mobility 25/5/2018,* Bridge the technology gaps between Public Safety Agencies (PSA) and allow better collaboration | 2100000 | 2017-11-01T00:00:00 | PSBA
25/5/2018 | PSBA | QPS Office 365 Implementation Project | 2018-02-28T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The migration of all QPS mailboxes to Office 365 online services was completed by the original planned end date of 28-02-2018. QPS has approved additional scope to be delivered by 30-06-2018 within the original planned expenditure. The Project Objective has been amended to reflect the scope change. | 2018-04-27T00:00:00 | Critical | 2207000 |  | Public Safety Business Agency | 44 | 1086750 |  | G | 6 | Phase 1 - Mail Migrations The objective of the Queensland Police Service (QPS) Office 365 Implementation Project Phase 1 is to complete the following activities prior to the Frontline and Digital Services Commonwealth Games Change Freeze (mid Feb 2018): 25/5/2018, 25/5/2018,* migrate email, contacts and calendars to Office 365 online services for all QPS staff; and 25/5/2018,* enable anywhere, anytime, any device access to email, contacts and calendar via bring your own (BYO) phone, QPS Officers operational tablets (QLiTEs) and home use for all QPS staff. 25/5/2018, 25/5/2018,Phase 2 - a data migration and a pilot migration of email archives to Office 365 online | 2207000 | 2017-09-07T00:00:00 | PSBA
25/5/2018 | OSR | State Penalties Enforcement Registry (SPER) Program | 2017-12-31T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | Expenditure to date: $29.6M has been for the transformation of the SPER function; and $18.3M has been on the build phase of the ICT Implementation. 25/5/2018,A contract variation has been negotiated and executed as jurisdictional differences required system modifications. | 2018-05-11T00:00:00 | High | 47200000 |  | State Penalties Enforcement Registry | 64 | 47900000 |  | A | 1 | To maintain the integrity of fines as an effective sanction. To uphold confidence in the justice system. To deliver efficient and effective debt management practices which provide value for money to the State. 25/5/2018, | 62150000 | 2014-01-01T00:00:00 | QR
25/5/2018 | RI | Financial Assurance Information Registry (FAIR) | 2018-07-01T00:00:00 | Delivery |  | 2018-07-01T00:00:00 | Project cost to date is at end of March 2018. Project is on track for the system to be operational by 1 July 2018. Due to the delay in legislation being passed, some functionality and enhancements are planned to be delivered in the next financial year. | 2018-04-20T00:00:00 | Medium | 15900000 |  | Insurance Commission | 75 | 3939000 |  | G | 2 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
25/5/2018 | RI | Information Security Program | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The program is on track according to schedule and budget. | 2018-04-20T00:00:00 | Medium | 1960000 |  | Office of the Chief Information Officer | 35 | 392169 |  | G | 3 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 25/5/2018, | 1960000 | 2017-10-16T00:00:00 | QR
25/5/2018 | OSR | Office of State Revenue (OSR) Transformation Program | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | Completed business process re-design sprint for a buisness area. Multiple initiatives in progress focussing on machine learning, analytics and data quality improvements. Overall program is on track. | 2018-04-20T00:00:00 | High | 73548000 |  | Office of State Revenue | 10 | 10589263 |  | G | 4 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 25/5/2018, 25/5/2018,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 73548000 | 2017-08-01T00:00:00 | QR
25/5/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
25/5/2018 | Corporate Services Improvement Systems Board | Learnzone Improvement Project | 2017-06-30T00:00:00 | Closed |  | 2018-02-15T00:00:00 | The LearnZone Improvement project continues to report action required due to delays in finalising approvals of the Project End Report. Once the Project End Report is approved and noted, scheduled 15 February 2018, the project will be marked as closed on the QG ICT Dashboard. It should be noted that both the original total estimated expenditure and revised total estimated expenditure reported last period were incorrect. As per the approved Business Case and subsequent exception report these figures have now been corrected. | 2018-02-28T00:00:00 | High | 350000 |  | Transactional Services Improvement Program | 100 | 449936 |  | R | 1 | Innovate, develop and deliver an improved and centralised digital learning service and management function. 25/5/2018, 25/5/2018, | 442000 | 2016-02-01T00:00:00 | TMR
25/5/2018 | Corporate Services Improvement Systems Board | Lotus Notes Decommissioning | 2016-01-31T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project is on track. | 2018-02-28T00:00:00 | High | 8150000 |  | ERP Projects Board | 63 | 2120899 |  | G | 2 | Deliver improved information platform functions for effective ICT Strategy Alignment | 8150000 | 2015-11-01T00:00:00 | TMR
25/5/2018 | Corporate Services Improvement Systems Board | Stop Cheques - Stage 3 | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The Stop Cheques Stage 3 project is on track. | 2018-02-28T00:00:00 | Medium | 200000 |  | ERP Projects Board | 85 | 221972 |  | G | 3 | Cheques are inefficient and costly to use, process and administer for both the customer and department. A range of solutions have been developed to reduce the number of cheques that the department produces or receives including refund to card at counter, Bulk Bpay solutions and the introduction of new payment methods are being delivered to be more in line with contemporary retail offerings. The outsourcing of cheque production produced a more streamlined process. 25/5/2018,The stop cheques initiative includes 3 elements: 25/5/2018,Outsourcing/cost reduction 25/5/2018,Outbound cheques 25/5/2018,Inbound cheques | 200000 | 2015-02-01T00:00:00 | TMR
25/5/2018 | Corporate Services Improvement Systems Board | Risk Management Solution | 2018-07-01T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The Risk Management Solution project is on track. Planned expenditure was incorrectly displaying 17/18 budget only. | 2018-02-28T00:00:00 | High | 350000 |  | Corporate Services Improvement Systems Board | 78 | 777613 |  | G | 4 | Replace the current risk management approach through the delivery of a new and contemporary enterprise Risk Management solution for TMR . | 1024435 | 2016-02-01T00:00:00 | TMR
25/5/2018 | Corporate Services Improvement Systems Board | Integrated Records Information System (IRIS) | 2018-07-01T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The IRIS project is on track. | 2018-02-28T00:00:00 | High | 7967972 |  | Information Technology Branch | 35 | 3966166 |  | G | 5 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 7967972 | 2015-07-01T00:00:00 | TMR
25/5/2018 | Corporate Services Improvement Systems Board | Safety, Health and Environment tool (SHE) | 2018-07-02T00:00:00 | Delivery |  | 2018-07-30T00:00:00 | The SHE project is on track. | 2018-02-28T00:00:00 | Low | 680000 |  | Corporate Services Improvement Systems Board | 40 | 224369 |  | G | 6 | The objective of the SHE project is to replace the current Work Health and Safety ICT solution with an industry standard, cost-effective safety management solution that will enable TMR to meet its obligations under the Work Health and Safety 2011 Act, the Right to Information, Information Privacy legislation and the Workers Compensation and Rehabilitation Act 2003 (Qld). | 680000 | 2016-12-05T00:00:00 | TMR
25/5/2018 | Corporate Services Improvement Systems Board | Transactional Services Improvement Program Enhancements | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The Transactional Services Improvement Program Enhancements Stage 3 is on track. | 2018-02-28T00:00:00 | Low | 200000 |  | Transactional Services Improvement Program | 80 | 142956 |  | G | 7 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. | 200000 | 2015-02-01T00:00:00 | TMR
25/5/2018 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | The CDOP Online Portal project is on track. | 2018-02-28T00:00:00 | High | 1500000 |  | Customer Services, Safety and Regulation Division | 90 | 999274 |  | G | 8 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal services currently required. | 1441000 | 2016-01-01T00:00:00 | TMR
25/5/2018 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The eLearner project is currently on track. | 2018-02-28T00:00:00 | High | 2500000 |  | Customer Services, Safety and Regulation Division | 95 | 4093456 |  | G | 9 | Implement an online learning and assessment program at the pre-learner and/or learner stage, to replace enhance learning outcomes. | 4176000 | 2015-06-12T00:00:00 | TMR
25/5/2018 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery |  | 2018-06-28T00:00:00 | The Mobile Compliance Information System project is on track. An Exception Report to increase the project's scope and budget was approved by the program board in January 2018. | 2018-02-28T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 90 | 757855 |  | G | 10 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 630000 | 2016-11-01T00:00:00 | TMR
25/5/2018 | Customer Service, Safety and Regulation Program | Call Centre VOIP Upgrade | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The Call Centre VOIP Upgrade project is on track. | 2018-02-28T00:00:00 | Low | 1140000 |  | Customer Services, Safety and Regulation Division | 50 | 564183 |  | G | 11 | The Call Centre VOIP Upgrade has commenced to upgrade the VOIP telephony platform within the department. The proposed solution will see a reduction in call costs, a shift in capability to a 25/5/2018,contemporary solution utilising an existing investment within the department. | 1140000 | 2017-04-01T00:00:00 | TMR
25/5/2018 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery |  | 2017-12-24T00:00:00 | The Ralph Replacement project is on track. An exception report to rebasline the project's end date is currently being reviewed by the project's governance board. | 2018-02-28T00:00:00 | Medium | 500000 |  | Customer Services, Safety and Regulation Division | 70 | 576018 |  | G | 12 | TMR's current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace the existing application with a contemporary and supportable alternative to assist the department in maintaining its timely updating of fees and charges. | 674000 | 2016-07-01T00:00:00 | TMR
25/5/2018 | Customer Service, Safety and Regulation Program | Voice Comms Mgt System | 2017-06-30T00:00:00 | Delivery |  | 2017-12-30T00:00:00 | The Voice Comms Management System project is on track. | 2018-02-28T00:00:00 | Medium | 828000 |  | Customer Services, Safety and Regulation Division | 75 | 274738 |  | G | 13 | The Voice Comms Management project consists of two replacement of existing Voice Communication and Control Systems at Townsville and Hay Point. | 828000 | 2016-01-01T00:00:00 | TMR
25/5/2018 | Customer Service, Safety and Regulation Program | CTP Tax Invoice Online | 2017-12-31T00:00:00 | Delivery |  | 2017-12-31T00:00:00 | The CTP Tax Invoice Online project will merge with the Registration Certificates Online project at the next reporting cycle. This is due to both projects having a shared goal to improving the online delivery of related correspondence. | 2018-02-28T00:00:00 | Medium | 300000 |  | Customer Services, Safety and Regulation Division | 25 | 17281 |  | G | 14 | The Compulsory Third Party Tax Invoice Online project will deliver a new online service which will enable Customers to self-serve and print an electronic version of the CTP Invoice, removing the need for TMR to process paper based invoices, avoiding production and postage charges. | 300000 | 2017-05-01T00:00:00 | TMR
25/5/2018 | Customer Service, Safety and Regulation Program | Vessel Traffic Services (VTS) | 2016-01-05T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | The Vessel Traffic Services (VTS) project is on track. | 2018-02-28T00:00:00 | High | 15224694 |  | Customer Services, Safety and Regulation Division | 25 | 6048630 |  | G | 15 | The purpose of the project is procure and implement a replacement decision support tool for the existing Vessel Traffic Service (VTS) used by TMR to track and monitor ship movements within Queensland ports, the Great Barrier Reef and the Torres Strait. | 25569044 | 2014-04-14T00:00:00 | TMR
25/5/2018 | Customer Service, Safety and Regulation Program | R and L Systems Software Upgrade | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The R and L Systems Software Upgrade project is on track. | 2018-02-28T00:00:00 | Medium | 780000 |  | Customer Services, Safety and Regulation Division | 20 | 21799 |  | G | 16 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
25/5/2018 | Infrastructure Management and Delivery | Work Improvement Note (WIN) Replacement | 2016-12-19T00:00:00 | Delivery |  | 2018-02-27T00:00:00 | The WIN Replacement project is on track. | 2018-02-28T00:00:00 | Low | 242612 |  | Infrastructure Management 25/5/2018,and Delivery | 98 | 349325 |  | G | 17 | The Work Improvement Note (WIN) System is used to capture, track, review and report on improvements, potential problems, non-conformances, corrective actions, customer feedback and complaints. The WIN System is an essential component of the overarching business management system as it meets specific certification requirements outlined in international quality, safety and environmental standards. This project will provide a replacement to the existing Work Improvement Note (WIN) system, which is dependent on unsupported technology. | 436375 | 2016-02-15T00:00:00 | TMR
25/5/2018 | Passenger Transport Technology Program | 2018 Commonwealth Games Journey Planner (GJP) | 2017-10-13T00:00:00 | Delivery |  | 2018-04-27T00:00:00 | The 2018 Commonwealth GJP project is project is on track. | 2018-02-28T00:00:00 | High | 450000 |  | Commonwealth Games | 95 | 848048 |  | G | 18 | A dedicated Journey Planner application supports this need by providing a single source of truth for all transport information related to the Games, and also allows for rapid changes to routes, schedules, and stops, if any are required, in order to drive transport behaviour and maintain network efficiency. | 973899 | 2016-10-16T00:00:00 | TMR
25/5/2018 | Passenger Transport Technology Program | Customer Contact Management Solution (CCMS) | 2017-06-30T00:00:00 | Closed |  | 2018-01-16T00:00:00 | The CCMS project has successfully completed its scope and the Program Board endorsed the project closure report in January 2018. The planned expenditure versus the actual cost to date variance has been rectified. The CCMS project will no longer report to the ICT Dashboard. | 2018-02-28T00:00:00 | High | 1279000 |  | TransLink | 100 | 1486927 |  | G | 19 | To implement an industry standard, robust and extensible solution to replace the existing Commentline solution. To achieve better performance of the customer contact management functions. To provide the base platform to support the future implementation of an xRM roadmap 25/5/2018, | 1486927 | 2016-04-01T00:00:00 | TMR
25/5/2018 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | The STAS Auto Forms project is on track. | 2018-02-28T00:00:00 | High | 4166000 |  | TransLink | 59 | 4396781 |  | G | 20 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 5043876 | 2016-04-01T00:00:00 | TMR
25/5/2018 | Policy Planning and Investment Program | Portfolio, Program, Project and Contract Management (3PCM) - Phase 2 and 3 | 2017-03-31T00:00:00 | Delivery |  | 2017-12-22T00:00:00 | The 3PCM project is on track. | 2018-02-28T00:00:00 | High | 12757788 |  | Policy, Planning and Investment Division | 99 | 47794188 |  | G | 21 | Define and implement standard, consistently applied processes for planning, managing and delivering the Transport Infrastructure Portfolio across the domains of portfolio, program, project and contract management 25/5/2018,Source and implement an integrated, strategic information communication technology solution that supports the business process and rules and enables a transition away from legacy applications | 47908928 | 2012-09-01T00:00:00 | TMR
25/5/2018 | CS | Asset Assessment System | 2016-06-30T00:00:00 | Delivery |  | 2018-08-06T00:00:00 | The project is being closely monitored for quality and schedule | 2018-02-08T00:00:00 | High | 1688788 |  | Corporate Services | 82 | 1502089 |  | A | 1 | To improve the reliability and integrity of asset information, the ability to report on asset information by applying best practice asset management principles. | 1957139 | 2014-02-27T00:00:00 | DET
25/5/2018 | SS | Early Start | 2015-07-03T00:00:00 | Delivery |  | 2018-07-31T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | High | 70000 |  | State Schools | 74 | 73522 |  | G | 2 | To provide schools with enhanced reporting functionality, improving their ability to analyse Prep to Year 2 student learning data. | 200992 | 2013-04-03T00:00:00 | DET
25/5/2018 | PPP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Delivery |  | 2018-02-27T00:00:00 | The project is being closely monitored for schedule | 2018-02-08T00:00:00 | Medium | 700000 |  | Policy, Performance and Planning | 86 | 1247953 |  | A | 3 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
25/5/2018 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery |  | 2018-12-07T00:00:00 | The project is tracking to plan. The Project is undergoing procurement/commercial activities with no financial information being published. | 2018-02-08T00:00:00 | Medium | 0 |  | Corporate Services | 46 | 0 |  | G | 4 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DET FBS SAP future state landscape for the next five years | 0 | 2017-01-16T00:00:00 | DET
25/5/2018 | CS | Injury Management System | 2017-03-27T00:00:00 | Delivery |  | 2018-10-01T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Critical | 1900000 |  | Corporate Services | 46 | 758816 |  | G | 5 | To improve the management of workplace rehabilitation and claims for injured/ill staff | 1813805 | 2016-10-10T00:00:00 | DET
25/5/2018 | ODG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery |  | 2017-12-29T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 632585 |  | Office of the Director-General | 90 | 817626 |  | G | 6 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
25/5/2018 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery |  | 2019-09-13T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 16670000 |  | State Schools | 50 | 8756279 |  | G | 7 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 23470000 | 2015-08-03T00:00:00 | DET
25/5/2018 | PPP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery |  | 2018-06-13T00:00:00 | The project is tracking to plan. The Project is undergoing procurement/commercial activities with no financial information being published. | 2018-02-08T00:00:00 | Medium | 0 |  | Policy, Performance and Planning | 70 | 0 |  | G | 8 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution | 0 | 2016-03-01T00:00:00 | DET
25/5/2018 | CS | Project Delivery System | 2018-10-01T00:00:00 | Delivery |  | 2019-01-29T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 1817566 |  | Corporate Services | 61 | 773116 |  | G | 9 | To improve the reliability and integrity of under construction asset information, the ability to report on asset project information by applying best practice asset management principles | 2291613 | 2015-04-01T00:00:00 | DET
25/5/2018 | PPP | Research Services 2.0 | 2016-09-30T00:00:00 | Delivery |  | 2017-09-29T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 230000 |  | Policy, Performance and Planning | 85 | 404745 |  | G | 10 | To develop a solution that assists in the management of the Department of Education and Training commissioned research proposals and projects, improving resourcing and information dissemination. | 431157 | 2015-11-02T00:00:00 | DET
25/5/2018 | TS | Study Tours Support System Upgrade | 2016-06-30T00:00:00 | Delivery |  | 2018-01-31T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 680000 |  | Training and Skills | 96 | 772580 |  | G | 11 | To replace or upgrade the existing Study Tours system with an online solution that has enhanced functionality, improving processes, data quality and tour management. | 831125 | 2015-08-31T00:00:00 | DET
25/5/2018 | SS | Trial of platform for virtual academies | 2017-10-02T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | Medium | 151641 |  | State Schools | 55 | 224017 |  | G | 12 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage. | 151641 | 2016-06-21T00:00:00 | DET
25/5/2018 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | The project is tracking to plan | 2018-02-08T00:00:00 | High | 41000000 |  | Corporate Services | 55 | 27032972 |  | G | 13 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
25/5/2018 | [20 empty] | INVERSTMENT INFO
25/5/2018 | CSGC | Coal Seam Gas Groundwater Monitoring Arrangements | 2017-12-31T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project has recommenced and is nearing completion. Closure activities are now under way. 25/5/2018, 25/5/2018,January 2018 - A change to the planned end date has been approved; there is no impact to cost. Initiative is now paused until early 2018. 25/5/2018, 25/5/2018,August 2017 - Revised total expenditure (budget) updated to include all operating costs not previously reported. 25/5/2018, 25/5/2018,June 2017 - Progress is continuing as planned. Still on schedule to complete December 2017. 25/5/2018, 25/5/2018,December 2016 - Much of the project has been completed and a significant amount of the procurement expenditure for capital equipment has occurred. 25/5/2018, 25/5/2018,October 2016 - Progress is continuing as planned. 25/5/2018, 25/5/2018,August 2016 - Cost returned to Green after a review of costs associated with activities remaining, and a correction in actual cost to date adjustment. 25/5/2018, 25/5/2018,June 2016 - Cost is Amber with a resource review under way. 25/5/2018, 25/5/2018,February 2016 - Progress is continuing as planned. | 2018-05-11T00:00:00 | High | 2380568 |  | Coal Seam Gas Compliance | 99 | 2608283 |  | G | 1 | Enhance availability of groundwater data through improvements to network monitoring of bores for clients and landholders. | 2598256 | 2014-01-13T00:00:00 | DNRM
25/5/2018 | SIMTARS | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery |  | 2019-03-01T00:00:00 | The project is continuing as planned. 25/5/2018, 25/5/2018,February 2018 - A change request was approved to alter the scope and associated percentage complete, time-frame and costs. 25/5/2018, 25/5/2018,December 2017 - Awaiting confirmation of project closure; project is still operating within approved time-frame tolerance. 25/5/2018, 25/5/2018,November 2017 - A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 25/5/2018, 25/5/2018,October 2017 - The project is continuing as planned. 25/5/2018, 25/5/2018,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2018-05-11T00:00:00 | High | 563000 |  | SIMTARS (Safety In Mines Testing and Research Station) | 64 | 685723 |  | G | 2 | The development and delivery of a (replacement) modern and robust Safegas solution: 25/5/2018, 25/5/2018,* risk reduction increasing capability to manage the volume of queries, transactions and data 25/5/2018,* decrease database corruption related to incidents. | 1170000 | 2017-01-25T00:00:00 | DNRM
25/5/2018 | SO | Mines Infrastructure Risk Mitigation Project | 2019-02-18T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | The project is continuing as planned. 25/5/2018, 25/5/2018,April 2018 - A minor adjustment to scope has been approved; there is no impact to timeframe or cost. 25/5/2018, 25/5/2018,March 2018 - The project is continuing as planned. 25/5/2018, 25/5/2018,November 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-05-11T00:00:00 | High | 1200000 |  | Statewide Operations | 30 | 312339 |  | G | 3 | Migrate systems to supported infrastructure and software to: 25/5/2018, 25/5/2018,* provide a stable, secure, fully supported and flexible solution 25/5/2018,* eliminate the risks to which the geoscience data assets are currently exposed. | 1200000 | 2017-08-08T00:00:00 | DNRM
25/5/2018 | LSI | Queensland Globe Improvements | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project is continuing as planned. 25/5/2018, 25/5/2018,December 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-05-11T00:00:00 | High | 1002450 |  | Land and Spatial Information | 80 | 773592 |  | G | 4 | Enhancements to Queensland Globe to continue to evolve and improve user satisfaction and experience, such as: 25/5/2018, 25/5/2018,* create and save user-defined topics 25/5/2018,* improve query and access 25/5/2018,* provide editable 'redlining' 25/5/2018,* improve data imports. | 1002450 | 2017-10-09T00:00:00 | DNRM
25/5/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery |  | 2018-05-25T00:00:00 | Project closure documents are being prepared for review and approval. 25/5/2018, 25/5/2018,April 2018 - The project is nearing completion. A small extension to the planned end date has been approved to allow for closure activities. 25/5/2018,March 2018 - The project is continuing as planned. 25/5/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 25/5/2018,October 2017 - The project is progressing as planned. 25/5/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 25/5/2018,June 2017 - Revised Schedule approved returning the project to Green. 25/5/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 25/5/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 25/5/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 25/5/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 25/5/2018,December 2016 - The project is progressing as planned. | 2018-05-11T00:00:00 | Critical | 567500 |  | Governance and Engagement, Energy | 97 | 882957 |  | G | 5 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 25/5/2018, 25/5/2018,* register and maintain their information 25/5/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DNRM
25/5/2018 | QWSR | Dam Safety Regulation Solution | 2016-10-30T00:00:00 | Delivery |  | 2018-04-30T00:00:00 | The project is continuing within time-frame tolerance, and is expected to close prior to the end of May 2018. 25/5/2018, 25/5/2018,March 2018 - The project is continuing as planned. 25/5/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 25/5/2018,August 2017 - Approved extension of timeframe. 25/5/2018,June 2017 - The project is progressing as planned. 25/5/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 25/5/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 25/5/2018,October 2016 - Progress is continuing as planned. 25/5/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 25/5/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 25/5/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2018-05-11T00:00:00 | High | 1390000 |  | Queensland Water Supply Regulator | 98 | 1385060 |  | G | 6 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 25/5/2018, 25/5/2018,* support compliance with legislation 25/5/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 25/5/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 25/5/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 25/5/2018, | 1390000 | 2012-04-01T00:00:00 | DNRM
25/5/2018 | Natural Resources | Land Condition Assessment Tool | 2018-04-30T00:00:00 | Delivery |  | 2018-06-26T00:00:00 | The project has encountered some resourcing issues and will not meet the planned completion date. The time-frame is being re-estimated to return the project to Green status. 25/5/2018, 25/5/2018,April 2018 - This project is reporting for the first time and is progressing as planned. | 2018-05-11T00:00:00 | Medium | 414000 |  | Operations Support | 42 | 117960 |  | A | 7 | Implement a solution for government, industry and other stakeholders to objectively and consistently assess land condition, including development of a pictogram-based mobile web application and a data collection tool. | 414000 | 2017-01-12T00:00:00 | DNRM
25/5/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DPC
25/5/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
25/5/2018 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 25/5/2018,* Move operational accountability and responsibility for print and imaging devices to the service provider 25/5/2018,* Reduce print and imaging costs 25/5/2018,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
25/5/2018 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
25/5/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
25/5/2018 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 25/5/2018, 25/5/2018,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
25/5/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
25/5/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 25/5/2018, 25/5/2018,* reduce operating costs 25/5/2018,* increase capacity 25/5/2018,* improve customer experience 25/5/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
25/5/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
25/5/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 25/5/2018, 25/5/2018, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
25/5/2018 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 25/5/2018, 25/5/2018,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
25/5/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
25/5/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 25/5/2018, 25/5/2018,November 2017 - Actual cost to date corrected due to input error. 25/5/2018, 25/5/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 25/5/2018, | 2017-12-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 57 | 733941 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
25/5/2018 | ESR | Environmental Management Register/Contaminated Land Register - replacement | 2017-06-30T00:00:00 | Paused |  | 2017-06-30T00:00:00 | A review of resource availability is under way. 25/5/2018, 25/5/2018,March 2018 - The project remains paused with a new change request under development that will see the project move back into delivery with a Green status 25/5/2018, 25/5/2018,August 2017 - The project is paused awaiting the outcome of a change request for additional scope; this will return the project to a Green status. 25/5/2018, 25/5/2018,April 2017 - A minor correction has been made to the revised total estimated expenditure to include $20,000 operating prior years. 25/5/2018, 25/5/2018,February 2017 - A change request has been approved moving the initiative cost back to Green. 25/5/2018, 25/5/2018,December 2016 - Project is continuing as planned, with a change request under way to return cost to Green. 25/5/2018, 25/5/2018,October 2016 - Project delivery activities formally commenced on 2 October 2016. 25/5/2018, 25/5/2018,August 2016 - The initiative was paused for some time but has now recommenced and moved into delivery. It is progressing as planned. | 2018-05-11T00:00:00 | High | 981680 |  | Environmental Services and Regulation | 78 | 718000 |  | A | 1 | The current system no longer supports efficient delivery of the department's responsibilities. The replacement will: 25/5/2018, 25/5/2018,* mitigate the risks associated with a system that is beyond its useful life 25/5/2018,* improve access to information by individuals, business and industry conducting searches (property lot plan) of the registers 25/5/2018,* support the creation of notices to stakeholders 25/5/2018,* reduce manual tasks through the introduction of automated workflows and customer self-serve and self-correct. 25/5/2018, | 1111680 | 2016-07-01T00:00:00 | EHP
25/5/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project is progressing as planned. 25/5/2018, 25/5/2018,November 2017 - Actual cost to date corrected due to input error. 25/5/2018, 25/5/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 25/5/2018, | 2018-05-11T00:00:00 | Medium | 1750000 |  | Queensland Parks and Wildlife Service | 74 | 1166727 |  | G | 2 | Acquire one or more solution components to operate in conjunction with the agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | EHP
25/5/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP
24/11/2017 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2016-08-01T00:00:00 | Delivery | G | 2018-07-30T00:00:00 | July 2017: The planned end date has been brought forward, from 31/12/2018 to 30/07/2018. This is due to a revised delivery schedule. | 2017-09-12T00:00:00 | High | 1858668 | G | Metro North | 35 | 599020 | G | G | 1 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 24/11/2017, 24/11/2017,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Women 24/11/2017,92s Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 24/11/2017, 24/11/2017,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 1858668 | 2015-06-01T00:00:00 | DH
24/11/2017 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 11180394 | G | eHealth Queensland | 4 | 32527 | G | G | 2 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 24/11/2017,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work. 24/11/2017,a0 Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 6000000 | 2017-07-03T00:00:00 | DH
24/11/2017 | CHOPD | BreastScreen Queensland Online Bookings | 2016-01-01T00:00:00 | Delivery | G | 2017-09-30T00:00:00 | August 2017: The planned end date for this initiative is 30/09/2017, which was current as at August. An updated status will be provided in the next reporting update. 24/11/2017, 24/11/2017,May 2017: Online Portal now available for women (eligible for a Breast Screening) to book their Breast Screen appointments through the Internet. Electronic GP Letters is progressing well and is on track to go live early September. 24/11/2017, 24/11/2017,April 2017: Online Portal now available for women (eligible for a Breast Screen) to book their Breast Screen appointments through the Internet. | 2017-08-31T00:00:00 | High | 3103657 | G | Chief Health Officer and Prevention | 98 | 3796330 | G | G | 3 | The BreastScreen Online Booking Project incorporates the following: 24/11/2017,Phase 1 - The Online Portal which is 90% of the Online Bookings Project went live on 5 December 2016. 24/11/2017,a0 The Online Portal enables women to register, book and reschedule their BreastScreen appointment, manage their contact details and view their BSQ notifications including invitations, reminders and results. 24/11/2017,Phase 2 - Incorporates the facility for GP's to receive patient results and reminders electronically. This initiative is scheduled to 'go live' on the 4th September 2017. | 4000000 | 2014-10-13T00:00:00 | DH
24/11/2017 | MNHHS | Business Intelligence - Enterprise Data Warehouse | 2018-06-29T00:00:00 | Initiate | G | 2018-06-28T00:00:00 | June 2017: Project reported for first time. | 2017-09-12T00:00:00 | High | 3730003 | G | Metro North | 20 | 990466 | G | G | 4 | This project will introduce Business Intelligence and Data Warehousing capabilities at MNHHS. The project will deliver BI and DW technical skills, system infrastructure, data automation tools, a pilot dataset, data governance processes and quality control framework at MNHHS. Metro North Finance and MNIT are jointly managing the project. | 2114991 | 2016-11-01T00:00:00 | DH
24/11/2017 | MNHHS | Central Patient Monitoring Equipment Replacement | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | July 2017: Project reported for first time. | 2017-09-12T00:00:00 | High | 1236416 | G | Metro North | 10 | 25133 | G | G | 5 | Metro North IT has been approached by Metro North Procurement Services (MNPS) to provide ICT advice and guidance into the Central Patient Monitoring Equipment Replacement (CPMER) Project. The Health Technology Equipment Replacement (HTER) program for central monitoring systems is providing funding in financial years 16/18 for physiological monitoring equipment requiring replacement across MNHHS hospital facilities. There is an estimated 312 pieces of equipment, primarily Physiological Monitoring devices, to be replaced under the program across MNHHS hospital facilities. MNHHS implementations are being co-ordinated by MNPS. | 1236416 | 2017-06-28T00:00:00 | DH
24/11/2017 | MNHHS | CISS (Community, Indigenous and Subacute Services) Wi-Fi | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | July 2017: Project reported for first time. | 2017-09-12T00:00:00 | High | 1280798 | G | Metro North | 17 | 675736 | G | G | 6 | The Community, Indigenous and Subacute Services (CISS) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the internal areas of the prioritised CISS sites. 24/11/2017, 24/11/2017,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1280798 | 2017-07-28T00:00:00 | DH
24/11/2017 | EHQ | Cloud First Project | 2018-06-30T00:00:00 | Initiate | G | 2018-07-09T00:00:00 | June 2017: This project was previously called ePulse Cloud First Project. | 2017-08-31T00:00:00 | High | 1750000 | G | eHealth Queensland | 22 | 1694306 | G | G | 7 | The Cloud First project will build internal capability and establish processes within Queensland Health to appropriately utilise cloud services on an ongoing basis. | 4107007 | 2017-01-01T00:00:00 | DH
24/11/2017 | HSQ | Cloud Provision to HSQ | 2016-04-11T00:00:00 | Closed | G | 2017-06-30T00:00:00 | August 2017: This project has been closed due to a review of the project by Health Support Queensland. 24/11/2017, 24/11/2017,July 2017: This project is still on hold. It is anticipated that a governance decision to determine the future of this project will be made by the next reporting period. 24/11/2017, 24/11/2017,June 2017: The latest approved end date for this project is 30 June 2017, which will change pending the continuation of the project. The project is paused due to pending recruitment activities, with no adverse impacts affecting the business while this project is on hold. | 2017-08-31T00:00:00 | Medium | 1540996 | G | Health Support Queensland | 31 | 3002706 | G | G | 8 | To consolidate HSQ applications and migrate to cloud infrastructure to improve system redundancy, system security and business continuity whilst addressing existing issues. | 3196431 | 2014-05-01T00:00:00 | DH
24/11/2017 | CED | Consumer Integrated Mental Health Application (CIMHA) Clinical Notes project (release 3.0) | 2018-02-06T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | August 2017: The project has returned to a 'Green' status, with the project's revised scope, budget and schedule being approved by the project's governance committee in late August 2017. 24/11/2017, 24/11/2017,July 2017: The overall status for this project ('Red') is unchanged from June, however, it is expected that governance approval will be obtained by the next reporting period, returning this project to 'On Track'. 24/11/2017, 24/11/2017,June 2017: This initiative is reporting 'Action required' due to resourcing issues. Project team resources have been unable to be secured within the planned timeframe, delaying the implementation of the project by 4 months. The scope of the project was extended to include additional enhancements, further impacting on project resource and schedule requirements. It is anticipated that this project will return to 'On track' once formal governance approval has been obtained for the extended implementation timeframes and additional resource requirements. | 2017-08-31T00:00:00 | Medium | 1415000 | G | Clinical Excellence | 40 | 349325 | G | G | 9 | Upgrading the CIMHA Mental Health Act module to accommodate a re-architecture of the CIMHA clinical notes module is required to deliver benefits to the clinical workforce associated with data entry efficiencies; improved data sharing across digital platforms; patient level information transfer to third parties to support service integration and data mining to support service improvement and research. | 1969365 | 2017-02-20T00:00:00 | DH
24/11/2017 | EHQ | Critical Infrastructure Upgrades 16-18 | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 | July 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 14689808 | G | eHealth Queensland | 6 | 0 | G | G | 10 | Deliver ICT infrastructure uplifts (data, voice, wireless, cabling, infrastructure design and connectivity) at Multiple Hospital and Health Services (HHS) to better support delivery of business and clinical services. | 13230525 | 2017-07-01T00:00:00 | DH
24/11/2017 | EHQ | Critical Infrastructure Upgrades 17-19 | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 11144283 | G | eHealth Queensland | 6 | 0 | G | G | 11 | The Critical Infrastructure Initiative will upgrade 24/11/2017,93like for like 24/11/2017,94 out of date network and voice asset 24/11/2017,92s within the QH network. FY17-18 will concentrate on the replacement of the end of life stand-alone Wireless LAN (WLAN) access points (AP 24/11/2017,92s) and replace these assets with new integrated WLAN AP 24/11/2017,92s connected to the centralised FLEX controllers in the core of the network. In Year 2 there are some Paging and Voice upgrades planned to remove redundant hardware. | 9180760 | 2017-07-01T00:00:00 | DH
24/11/2017 | EHQ | Critical Network Hardware | 2018-02-28T00:00:00 | Delivery | G | 2018-02-28T00:00:00 | June 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 9500000 | G | eHealth Queensland | 32 | 6930741 | G | G | 12 | The objectives of the project include: 24/11/2017,a) Mitigate the Department of Health risk that core network switches at QH facilities will no longer be supported by the manufacturer from February 2018. 24/11/2017,b) Invest in the replacement of critical ICT network hardware to maintain current capability and reliability of the data network for 120+ enterprise clinical and business applications and provide the foundation for future capability in the enterprise data centres. 24/11/2017,c) Ensure hardware replacement occurs with minimal impact to business operations in Hospital and Health Services or Corporate offices. 24/11/2017,d) Update logical and physical design and architecture documentation for ease of maintenance and management. | 8001607 | 2017-03-06T00:00:00 | DH
24/11/2017 | EHQ | Digital Collaboration Platform Program | 2018-06-29T00:00:00 | Delivery | G | 2018-06-29T00:00:00 |  | 2017-08-31T00:00:00 | High | 11000000 | G | eHealth Queensland | 20 | 5398475 | G | G | 13 | This program will deliver digital collaboration tools for any time, any where, any device including: 24/11/2017,(a) Email and Archiving 24/11/2017,(b) Establishment and Collaboration 24/11/2017,(c) Productivity Suite Enablement | 12921837 | 2015-10-29T00:00:00 | DH
24/11/2017 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate | G | 2017-12-31T00:00:00 |  | 2017-08-31T00:00:00 | High | 1500000 | G | Queensland Ambulance Service | 40 | 423741 | G | G | 14 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 4167216 | 2015-12-01T00:00:00 | DH
24/11/2017 | QAS | e-ARF Redevelopment for iPad | 2016-12-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 |  | 2017-08-31T00:00:00 | High | 2624000 | G | Queensland Ambulance Service | 92 | 1366057 | G | G | 15 | This is an initiative to provide the electronic Ambulance Report Form (eARF) electronic patient care solution via iPads in the field. | 1910813 | 2015-09-02T00:00:00 | DH
24/11/2017 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | July 2017: Project reported for first time. | 2017-09-05T00:00:00 | High | 1283000 | G | Chief Health Officer and Prevention | 7 | 26000 | G | G | 16 | Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1283000 | 2017-03-01T00:00:00 | DH
24/11/2017 | MNHHS | Learning and Performance Management Project | 2017-06-30T00:00:00 | Initiate | G | 2018-11-26T00:00:00 |  | 2017-09-12T00:00:00 | High | 1178190 | G | Metro North | 15 | 598082 | G | G | 35 | Implement an integrated Learning Management and Performance Management system with the capability to deliver online learning and training content, facilitate performance development and maintain centralised records for reporting purposes. | 1178190 | 2016-07-11T00:00:00 | DH
24/11/2017 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery | G | 2018-11-30T00:00:00 | July 2017: Project reported for first time. | 2017-09-12T00:00:00 | High | 4827917 | G | Metro North | 30 | 1679612 | G | G | 17 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (timer) program. 24/11/2017, 24/11/2017,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 24/11/2017, 24/11/2017,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. 24/11/2017, 24/11/2017,Anticipated benefits include: improved patient health outcomes through medication safety and enhance "quality use of medicines"; staff enabled and supported in medication prescribing and administration decisions and processes; increased compliance with medication-related legal, policy and audit requirements; reduced risk (legal, financial, patient safety); improved revenue generation opportunities with PBS script generation; reduction in medication-related harm and incidents; and delivery on health service strategic intent. | 4827917 | 2016-07-01T00:00:00 | DH
24/11/2017 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 3747721 | G | eHealth Queensland | 2 | 0 | G | G | 18 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment. 24/11/2017,a0 24/11/2017,a0The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access. 24/11/2017,a0 | 2521960 | 2017-07-05T00:00:00 | DH
24/11/2017 | QAS | Enterprise Rostering System | 2018-12-31T00:00:00 | Initiate | G | 2018-12-31T00:00:00 |  | 2017-08-31T00:00:00 | High | 1000000 | G | Queensland Ambulance Service | 10 | 412987 | G | G | 19 | The initiative is to provide a centralised electronic rostering system to replace existing aging and disparate manual systems currently being utilised across the state. | 1194682 | 2016-12-01T00:00:00 | DH
24/11/2017 | EHQ | File Services Migration | 2019-06-28T00:00:00 | Delivery | G | 2019-06-28T00:00:00 | July 2017: The project has returned to 'On Track'. The governance committee has approved the revised project schedule and finances. The financials currently reflect the latest approved budget of the initiative. 24/11/2017, 24/11/2017,June 2017: The project was previously called File Services Migration (ePulse). 24/11/2017,The approval of the business case has been delayed. The schedule is being revised by the governance committee, with the project expecting to return to On Track in the next reporting period. | 2017-08-31T00:00:00 | High | 3400000 | G | eHealth Queensland | 15 | 2169105 | G | G | 20 | The purpose of this investment is to adopt a contemporary, simplified file management solution for Queensland Health that enables a more cohesive customer experience. | 4005164 | 2016-08-01T00:00:00 | DH
24/11/2017 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Initiate | G | 2018-12-31T00:00:00 |  | 2017-08-31T00:00:00 | High | 105000000 | G | Metro North | 36 | 29321000 | G | G | 21 | The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 24/11/2017, 24/11/2017,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 24/11/2017,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 24/11/2017, 24/11/2017,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
24/11/2017 | EHQ | Follow Me Desktop - Deployment | 2018-06-30T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 3952980 | G | eHealth Queensland | 5 | 111198 | G | G | 22 | Follow Me Desktop Deployment Project will deliver 24/11/2017,a0the Follow Me Desktop service (FMD) to HHS 24/11/2017,92 in alignment with the Infrastructure Remediation Program (IMP) and iEMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 2153980 | 2017-07-24T00:00:00 | DH
24/11/2017 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 3301500 | G | eHealth Queensland | 2 | 11386 | G | G | 23 | Project Purpose: 24/11/2017,a0To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 3301500 | 2017-07-01T00:00:00 | DH
24/11/2017 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Initiate | G | 2019-06-28T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 1120000 | G | eHealth Queensland | 5 | 0 | G | G | 24 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. 24/11/2017,The project consists of four key initiatives: 24/11/2017,QHPKI service establishment and state-wide certificate migration for wireless devices. 24/11/2017,Establishment of a Security Information and Event Management (SIEM) solution for management and prevention of security incidents. 24/11/2017,Implementation of Intrusion Prevention System (IPS) at two locations to standardise IPS management across the state. 24/11/2017,a0 24/11/2017,State-wide migration to the enhanced proxy service. 24/11/2017,a0 | 560000 | 2017-07-05T00:00:00 | DH
24/11/2017 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery | G | 2018-07-02T00:00:00 |  | 2017-08-31T00:00:00 | High | 3215000 | G | eHealth Queensland | 32 | 3019327 | G | G | 25 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 5598485 | 2015-06-22T00:00:00 | DH
24/11/2017 | EHQ | ieMR Program | 2014-12-31T00:00:00 | Delivery | G | 2018-06-29T00:00:00 | May 2017: The following sites are in scope as part of the planned expansion of the ieMR state-wide rollout: Mackay Base Hospital, Logan Hospital, Beaudesert Hospital, Lady Cilento Children's Hospital (LCCH), Queen Elizabeth II (QEII) Hospital, Redland Hospital, and Townsville Hospital. 24/11/2017, 24/11/2017,April 2017: The Medications, Anaesthetics and Research Support (MARS) System successfully went live at the Princess Alexandra Hospital (PAH) on Sunday 19th of March 2017. Further rollouts are planned at Mackay, Logan and Beaudesert, Lady Cilento Children's Hospital, Redlands and QUII, and Townsville Hospitals by July 2018. 24/11/2017, | 2017-08-31T00:00:00 | High | 0 | G | eHealth Queensland | 80 | 0 | G | G | 26 | The integrated electronic Medical Record (ieMR) system changes the way clinicians access patient information, replacing the paper based system with a secure electronic record. The ieMR solution is focused on improving patient safety and quality of care by providing the right information, at the right place, at the right time. Paper medical records will be progressively transitioned to an electronic format. 24/11/2017,The implementation of the ieMR solution will be delivered by site teams at each of the hospitals in scope. The ieMR solution is being rolled out in a phased approach in consultation with sites to ensure effective implementation. 24/11/2017, 24/11/2017,Please note that financial information is Commercial in Confidence | 0 | 2009-10-01T00:00:00 | DH
24/11/2017 | EHQ | Infrastructure Capacity FY 17-18 | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 1000000 | G | eHealth Queensland | 5 | 4635202 | G | G | 27 | Project Purpose: 24/11/2017,a0 24/11/2017,The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified 24/11/2017,91organic growth 24/11/2017,92 requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. 24/11/2017,Each year the project will maintain a list of devices that are reaching capacity thresholds within the current financial year in the Prioritised Operations List. Prioritisation of the list will be based on the risk impact assessment for each in-scope asset to establish a most-to-least-critical replacement/upgrade ranking. The project will, based on prioritisation, implement/facilitate as many upgrades as the approved budget allows. | 5622032 | 2017-07-01T00:00:00 | DH
24/11/2017 | EHQ | Infrastructure Maintenance Program | 1900-01-01T00:00:00 | Initiate | G | 2022-06-30T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 1161415 | G | eHealth Queensland | 0 | 33340 | G | G | 28 | The Infrastructure Maintenance Program (IMP) 24/11/2017,a0will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 24/11/2017,The scope includes: 24/11/2017,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 24/11/2017,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and 24/11/2017,a0 24/11/2017,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1161414 | 2017-07-03T00:00:00 | DH
24/11/2017 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery | G | 2022-06-30T00:00:00 | July 2017: Project reported for first time. Financials currently reflect the financial year 2017-18 only. | 2017-08-31T00:00:00 | Medium | 14673739 | G | Clinical Excellence | 2 | 179067 | G | G | 29 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 24/11/2017,The ongoing program of work aims to continue and build upon existing functionality by: 24/11/2017,(a) Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 24/11/2017,(b) Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 24/11/2017,(c) Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 24/11/2017,(d) Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 24/11/2017,(e) Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
24/11/2017 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate | G | 2022-12-21T00:00:00 | June 2017: Project reported for first time. | 2017-08-31T00:00:00 | Medium | 6300000 | G | Queensland Ambulance Service | 15 | 292373 | G | G | 30 | Phased delivery of a system supporting QAS business intelligence. | 6300000 | 2017-01-03T00:00:00 | DH
24/11/2017 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | June 2017: Funding approval has been granted for this initiative in June 2017. 24/11/2017, 24/11/2017,May 2017: This project is within the project start-up phase. No funds have been expended to date on project delivery activities. Approval for funding has been granted in June, with the project planning to formally commence within the next reporting period. | 2017-09-04T00:00:00 | High | 33827000 | G | Clinical Excellence | 7 | 2500000 | G | G | 31 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 33827000 | 2017-03-01T00:00:00 | DH
24/11/2017 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 1 | 2016-11-30T00:00:00 | Delivery | G | 2018-02-28T00:00:00 |  | 2017-08-31T00:00:00 | High | 8200000 | G | Health Support Queensland | 60 | 14567743 | G | G | 32 | The IWFM project involves: 24/11/2017,(a) configuring additional functionality (currently available and licensed, but unutilised) within the existing Rostering and Payroll business solutions 24/11/2017,(b) partnering with HHSs to develop refined business models and business processes to support the roster-to-pay process 24/11/2017,(c) undertaking extensive training and change management to support the adoption and effective usage of new functionality and processes | 25060122 | 2016-02-17T00:00:00 | DH
24/11/2017 | EHQ | Interoperability Project | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | July 2017: Additional Investment has been secured from Government, once Governor in Council approval is received project will re-establish. 24/11/2017, 24/11/2017,June 2017: The project is planning to seek funding form CBRC in August 2017. 24/11/2017, 24/11/2017,April 2017: The project has completed a detailed implementation planning study and solutions design to inform scope and budget estimates. 24/11/2017, 24/11/2017,Additional funding for implementation of subsequent stages is still being sought. | 2017-08-31T00:00:00 | High | 23850000 | G | eHealth Queensland | 15 | 4702016 | G | G | 33 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 24/11/2017,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 24/11/2017,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 24/11/2017, | 39190000 | 2015-02-01T00:00:00 | DH
24/11/2017 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Initiate | G | 2019-09-30T00:00:00 |  | 2017-09-05T00:00:00 | High | 0 | G | Health Support Queensland | 48 | 0 | G | G | 34 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 24/11/2017,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. 24/11/2017, 24/11/2017,Please note that financial information is Commercial in Confidence | 0 | 2015-08-28T00:00:00 | DH
24/11/2017 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery | G | 2018-11-30T00:00:00 |  | 2017-09-12T00:00:00 | High | 4030460 | G | Metro North | 35 | 918462 | G | G | 36 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 24/11/2017, 24/11/2017,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 24/11/2017, 24/11/2017,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
24/11/2017 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery | G | 2017-12-31T00:00:00 |  | 2017-09-12T00:00:00 | High | 6299780 | G | Metro North | 75 | 4946737 | G | G | 37 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 6299780 | 2014-06-01T00:00:00 | DH
24/11/2017 | EHQ | Mobile Application System for Bring Your Own Device | 2018-06-30T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | July 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 1639698 | G | eHealth Queensland | 5 | 22260 | G | G | 38 | This project leverages the investment of the previous Bring-Your-Own-Device (BYOD) 24/11/2017,a0projects to extend the capability of device mobility by building the foundations of a Mobile Application Ecosystem - the processes, products and services to enable the managed development of low/no code applications by Health and Hospital Services (HHS). 24/11/2017,a0 This project will also complete the deployment of BYOD laptops and provide recommendations on how cost savings can be made by the organisation around Corporate devices and data plans. 24/11/2017,a0 | 1639698 | 2017-07-10T00:00:00 | DH
24/11/2017 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery | G | 2018-12-31T00:00:00 |  | 2017-08-31T00:00:00 | High | 14100000 | G | eHealth Queensland | 30 | 8889110 | G | G | 39 | This project will move Queensland Health to a modern end user workspace that is: current; delivering collaboration and productivity benefits; able to be accessed anywhere, anytime and on any device; reducing the reliance and expense of on premise infrastructure and support and not constraining the business from taking advantage of modern applications and services. | 25155173 | 2016-05-12T00:00:00 | DH
24/11/2017 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | August 2017: Project reported for first time. This project is internally known as 'M-series replacement' | 2017-08-31T00:00:00 | High | 5600000 | G | eHealth Queensland | 2 | 59572 | G | G | 40 | Project Purpose: 24/11/2017,Queensland Health is driving a huge eHealth Strategy to keep pace with the increasing demand for digital health services, to shift towards a customer-centric health system, and to enable cutting edge health service delivery. 24/11/2017,Central to the eHealth strategy is addressing issues related to ageing systems, in particular addressing the risk to health service delivery, and removing barriers to contemporary practice. 24/11/2017,Currently, eHealth Queensland is hosting a number of mission critical applications on the ageing application server platform. While this platform has provided a robust and highly available environment, it is now seven years old with increased risks to reliability and serviceability, has limited options for expansion, and is unable to provide the agile foundation required for advancing the eHealth Strategy. As such, it is an appropriate time to investigate replacement of the platform. 24/11/2017,This project aims to establish a robust, highly available and secure contemporary platform that has the 24/11/2017,93Scale Out 24/11/2017,94 capability to support the agile eHealth Strategy. | 5600000 | 2017-07-01T00:00:00 | DH
24/11/2017 | CHOPD | My Health for Life | 2020-04-30T00:00:00 | Delivery | G | 2020-04-30T00:00:00 | August 2017: The My health for life platform development schedule has experienced a brief delay to ensure the final product meets high program standards. This has no impact on the overall status of the project. 24/11/2017, 24/11/2017,July 2017: Prior reporting displayed the 'Planned end date' as 30/04/2020. The ICT component of this initiative will be delivered by 31 December 2017, and the project has now been updated to reflect this date. 24/11/2017, 24/11/2017,April 2017: Prior reporting displayed the Original Total Estimated Expenditure as $27M. The ICT component of this initiative is $2,000,000 and the project has now been updated to reflect this value. | 2017-09-04T00:00:00 | High | 27000000 | G | Chief Health Officer and Prevention | 78 | 1570586 | G | G | 41 | The My health for life (MH4L) program represents a $27.24M election commitment that will provide a statewide health risk assessment and lifestyle modification program targeting Queenslanders at high risk of developing type 2 diabetes, cardiovascular disease, obesity and some cancers. 24/11/2017,Delivery of the program will be led by Diabetes Queensland who have been contracted through an open tender process. 24/11/2017,The MH4L ICT solution will be a key enabler within the services procured under the program including internet, social media, process support and data collection/analysis. 24/11/2017,a0 No ICT is expected to be retained after the completion of the MH4L contract. | 2000000 | 2016-05-01T00:00:00 | DH
24/11/2017 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | July 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 1500000 | G | Queensland Ambulance Service | 35 | 333828 | G | G | 42 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1744000 | 2015-10-01T00:00:00 | DH
24/11/2017 | CHOPD | Notifiable Conditions System Replacement | 2018-12-31T00:00:00 | Delivery | G | 2020-02-28T00:00:00 | August 2017: The project has resumed as at 14 August 2017 with the recruitment of key project resources. The percentage complete has been updated to reflect the latest position of the project. 24/11/2017, 24/11/2017,July 2017: Formal governance approval has been provided for this project, with the project planning to recommence in August 2017. 24/11/2017, 24/11/2017,April 2017: Project is on hold as of 31 March 2017 pending formal governance approvals. | 2017-09-05T00:00:00 | High | 12000000 | G | Chief Health Officer and Prevention | 28 | 1896213 | G | G | 43 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 24/11/2017,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
24/11/2017 | EHQ | Patient Administration System (PAS) Replacement Program | 2017-06-30T00:00:00 | Initiate | G | 2017-09-30T00:00:00 | August 2017: The planned end date for this stage of the project was 30/09/2017, which was current as at August to deliver the strategic program business case. This has since been approved in October 2017 by the appropriate governance committee to progress to next stage and to seek further investment funding from Cabinet in 2018 . An updated status will be provided in the next reporting update. 24/11/2017, 24/11/2017,April 2017: This initiative was previously called "Queensland Connected Patient Care Program". | 2017-09-11T00:00:00 | High | 3850000 | G | eHealth Queensland | 79 | 2326410 | G | G | 44 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients 24/11/2017,92 journeys, and ensure that accurate information about our patients is readily available when and where required. 24/11/2017,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 24/11/2017,(a) support for patient engagement 24/11/2017,(b) integrated care 24/11/2017,(c) clinical research 24/11/2017,(d) population health (for patients using public health services) 24/11/2017,(e) performance transparency 24/11/2017,(f) resource planning. | 3850000 | 2015-11-01T00:00:00 | DH
24/11/2017 | MNHHS | Picture Archiving and Communication System (PACS) | 2017-09-29T00:00:00 | Delivery | G | 2017-12-31T00:00:00 |  | 2017-09-12T00:00:00 | High | 3114694 | G | Metro North | 74 | 2071148 | G | G | 45 | Procure and implement a contemporary Picture Archiving and Communication (PACS) system and functionality that will ensure improved service delivery for the MNHHS Medical Imaging Departments (and other PACS users) through replacement of RBWH PACS ensuring that it is scalable and able to meet the ongoing needs of Metro North Hospital and Health Service. | 3656297 | 2016-07-11T00:00:00 | DH
24/11/2017 | EHQ | Project, Program and Portfolio Management Application | 2017-12-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 |  | 2017-08-31T00:00:00 | High | 1344177 | G | eHealth Queensland | 10 | 153061 | G | G | 46 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 24/11/2017, | 157203 | 2017-05-02T00:00:00 | DH
24/11/2017 | SPPD | Queensland Health Integrated Data System initiation (QHIDSi) | 2017-09-30T00:00:00 | Delivery | G | 2017-09-30T00:00:00 | August 2017: The planned end date for this initiative is 30/09/2017, which was current as at August. An updated status will be provided in the next reporting update. 24/11/2017, 24/11/2017,July 2017: The project has experienced delays in finalising procurement which has impacted on the schedule and will return to 'On Track' in the coming months. 24/11/2017, 24/11/2017,April 2017: This initiative was previously called "Queensland Hospital Inpatient Processing System Replacement (QHIPSr) Project" | 2017-08-31T00:00:00 | High | 1800000 | G | Strategy, Policy and Planning | 96 | 890503 | A | A | 47 | This initiative will source and implement an integrated processing solution and configure it as a replacement for QHIPS which processes detailed unit record data on admitted patients from all public acute and psychiatric hospitals and licenced private hospitals and day surgery hospitals within Queensland. The technology of the current QHIPS system is at end of life and is unable to meet evolving business requirements. The project will also train existing Statistical Services Branch (SSB) staff in the use of the licensed software providing for expansion of use of the integrated processing solution as part of business-as-usual operations (e.g. to retire other end of life SSB systems). | 1800000 | 2015-09-07T00:00:00 | DH
24/11/2017 | CED | Queensland Integrated Safety Information Project (QISIP) / Risk Management | 2017-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2017-09-04T00:00:00 | Medium | 4333120 | G | Clinical Excellence | 80 | 7071893 | G | G | 48 | This initiative will source and implement an integrated processing solution and configure it as a replacement for QHIPS which processes detailed unit record data on admitted patients from all public acute and psychiatric hospitals and licensed private hospitals and day surgery hospitals within Queensland. 24/11/2017, | 16273520 | 2013-01-25T00:00:00 | DH
24/11/2017 | MNHHS | Quick Flow Project | 2019-02-01T00:00:00 | Initiate | G | 2019-06-30T00:00:00 | August 2017: This project was previously called the Ambulatory Flow Management (AFM) Project. 24/11/2017, 24/11/2017,July 20t17: The percentage complete has reduced from 10% in June to 2% in July due to revised planning activities. | 2017-09-12T00:00:00 | High | 6408600 | G | Metro North | 3 | 177494 | G | G | 49 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 24/11/2017,The key objectives of the project are to: 24/11/2017,(a) Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 24/11/2017,(b) Improve the outpatient experience across MNHSS facilities and community services 24/11/2017,(c) Improve clinic resource utilisation 24/11/2017,(d) Increase the efficiency of clinical and administrative processes 24/11/2017,(e) Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
24/11/2017 | EHQ | Regional eHealth Initiatives | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 3790000 | G | eHealth Queensland | 6 | 1898205 | G | G | 50 | The Regional eHealth Project (ReHP) is a Wireless LAN and Network Infrastructure uplift project so that sites in Far North Qld are ready to rollout their new eHealth Application. | 3489114 | 2017-07-01T00:00:00 | DH
24/11/2017 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Initiate | G | 2019-12-31T00:00:00 |  | 2017-08-31T00:00:00 | High | 34950000 | G | Cairns and Hinterland | 45 | 5958443 | G | G | 51 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patient 24/11/2017,92s home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
24/11/2017 | EHQ | Replacement of the ICT Service Management system | 2016-06-30T00:00:00 | Delivery | A | 2017-09-29T00:00:00 | August 2017: The planned end date for this initiative is 30/09/2017, which was current as at August. The system has successfully gone live at the end of September, with the project receiving governance committee approval to close at the end of October. The project is also indicating that the project will close with a 'Green' status. 24/11/2017, 24/11/2017,July: The status of this project is unchanged from June. 24/11/2017, 24/11/2017,June 2017: This initiative is still reporting amber in June. The governance committee is reviewing the scope and performance of this initiative in order to ensure the successful delivery of a complete service management solution. It is anticipated that this project will report on track in upcoming reporting periods. | 2017-08-31T00:00:00 | High | 2000000 | A | eHealth Queensland | 94 | 6472293 | A | A | 52 | This project will deliver a new cloud-based tool to improve the end-to-end management of IT support requests and incidents. The project will be delivered in two phases. The first phase has delivered a contemporary solution for IT support staff to manage requests and incidents. The second phase will deliver a new customer focused self-service portal and other system enhancements. | 7275579 | 2015-06-08T00:00:00 | DH
24/11/2017 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Initiate | G | 2020-06-30T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 10500000 | G | eHealth Queensland | 2 | 0 | G | G | 53 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 4500000 | 2017-07-03T00:00:00 | DH
24/11/2017 | EHQ | Storage and Backup Asset Replacement - FY 16/17 | 2017-06-30T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | August 2017: The planned end date for this initiative is 30/09/2017, which was current as at August. An updated status will be provided in the next reporting update. | 2017-08-31T00:00:00 | High | 1000000 | G | eHealth Queensland | 95 | 7889781 | G | G | 54 | To replace or upgrade at risk and/or aging ICT assets to enable modern healthcare delivery. | 7883138 | 2017-07-01T00:00:00 | DH
24/11/2017 | EHQ | Storage Asset Replacement | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | August 2017: Project reported for first time. | 2017-08-31T00:00:00 | High | 1671556 | G | eHealth Queensland | 8 | 6194 | G | G | 55 | The Storage Asset Replacement (SAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the SAR and Backup Asset Replacement (BAR) projects. 24/11/2017,The SAR project seeks to outline architecture for storage that will provide a cost effective, scalable and fit for purpose environment for the future of storage services within Queensland Health. 24/11/2017,a0 Utilising space saving technologies which will enable further cost savings and reduce the requirement for capacity expansion in the short to medium term. 24/11/2017,The existing storage arrays at Cairns, Townsville and Gold Coast are classed as urgent and unavoidable asset replacements. 24/11/2017,a0 These storage arrays are at capacity and will be at the end of extended vendor support in May 2018. | 1671555 | 2017-07-03T00:00:00 | DH
24/11/2017 | EHQ | Telehealth Asset Replacement FY 17-18 | 2018-06-29T00:00:00 | Initiate | G | 2018-06-29T00:00:00 |  | 2017-08-31T00:00:00 | High | 1960000 | G | eHealth Queensland | 4 | 9914267 | G | G | 56 | Project Purpose: 24/11/2017,a0 24/11/2017,a0 24/11/2017,Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector 24/11/2017,a0 24/11/2017,and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. 24/11/2017,The Department of Health defines Telehealth as: 24/11/2017,(a) Live, audio and/or video inter-active link for clinical consultations and educational purposes 24/11/2017,(b) Store and forward Telehealth - this model can involve digital images, video, audio and clinical data being captured ("stored") on the client computer; then at a convenient time transmitted securely ("forwarded") 24/11/2017,a0 to a clinic at another location where they are studied by relevant specialists 24/11/2017,(c) Teleradiology for remote reporting and clinical advice for diagnostic images 24/11/2017,(d) Telehealth services and equipment to monitor people 24/11/2017,92s health in their home. 24/11/2017,Benefits of Telehealth 24/11/2017,(a) Improve patient access to health care 24/11/2017,(b) Reduce travel and inconvenience for patients, families, carers and health professionals 24/11/2017,(c) Provide health professionals with access to peer support and education. 24/11/2017,The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. 24/11/2017,a0 24/11/2017,The priority is to replace those end-of-life assets which pose the greatest risk to effective health service delivery. 24/11/2017,Each year the project will prioritise and maintain the replacement scope in the Prioritised Operations List based on the risk impact assessment for each in-scope asset to establish a most-to-least critical replacement ranking. | 11613266 | 2017-07-03T00:00:00 | DH
24/11/2017 | MNHHS | The Prince Charles Hospital (TPCH) Wi-Fi | 2017-07-27T00:00:00 | Initiate | G | 2018-06-29T00:00:00 | July 2017: Project reported for first time. | 2017-09-12T00:00:00 | High | 1408388 | G | Metro North | 17 | 742249 | G | G | 57 | The Prince Charles Hospital (TPCH) Wi-Fi Project will establish the current standard for wireless local area network (WLAN) coverage within the hospital campus for prioritised TPCH buildings. 24/11/2017, 24/11/2017,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for sites in the near future. | 1408388 | 2017-07-27T00:00:00 | DH
24/11/2017 | CS | Child and Family Services Information and Communication Technology (ICT) Program | 2015-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | Original planned expenditure represented approved budget from start date to 30 June 2016. This program is a multi year program and the revised total expenditure has been updated to include approved funding to 30 June 2018. | 2017-09-30T00:00:00 | Critical | 7645000 | G | Child Safety | 73 | 16109000 | G | G | 1 | This five year program will investigate, provide options and implement ICT solutions to enable Child Safety in addressing recommendations of the Queensland Child Protection Commission of Inquiry. This may include enhancements to current systems, consideration of new systems and enabling activities to address changes to policy, legislation and practice reforms resulting from the outcomes of the Inquiry. | 24181000 | 2013-12-16T00:00:00 | DCCSDS
24/11/2017 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery | A | 2017-09-30T00:00:00 | There have been delays to the project schedule from reprioritisation of resources to community recovery activities associated with Cyclone Debbie. Additionally, the vendor, SMS Management and Technology, has not delivered within the contracted timeframes and we are negotiating with the vendor to ensure completion of the solution. | 2017-09-30T00:00:00 | High | 2208000 | G | Whole of Department | 73 | 2635000 | A | A | 2 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3333000 | 2016-07-01T00:00:00 | DCCSDS
24/11/2017 | WOD | Digital Domestic and Family Violence Prevention | 2019-06-30T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | Multi year project ending June 2019. | 2017-09-30T00:00:00 | Critical | 8050000 | G | Whole of Department | 42 | 2273000 | G | G | 3 | The Digital Domestic and Family Violence Prevention Initiative is the ICT initiative to deliver the ICT components of the government response to the Bryce Report, and also progress Digital Domestic and Family Violence Prevention digital innovations. | 8050000 | 2016-07-01T00:00:00 | DCCSDS
24/11/2017 | WOD | ICT Service Transformation Program | 2016-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | Original planned expenditure represented approved budget from start date to 30 June 2016. This program is a multi year program and the revised total expenditure has been updated to include approved funding to 30 June 2018. | 2017-09-30T00:00:00 | Low | 2916000 | G | Whole of Department | 89 | 5568000 | G | G | 4 | This program includes a number of initiatives to implement service improvement opportunities and essential capital replacement activities. The program ensures that ICT systems and services are replaced in a way that supports the department's strategic direction and includes the digital vision and future ways of work roadmap. | 7555000 | 2014-12-13T00:00:00 | DCCSDS
24/11/2017 | WOD | Reporting and Business Intelligence Project | 2017-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | Original planned expenditure represented approved budget from start date to 30 June 2016. This project is a multi year project and the revised total expenditure has been updated to include approved funding to 30 June 2018 to continue reporting and business intelligence deliverables. | 2017-09-30T00:00:00 | Medium | 750000 | G | Whole of Department | 34 | 3274000 | G | G | 5 | The department has a requirement for business intelligence, data management, information presentation and multi-level reporting | 5691000 | 2015-07-01T00:00:00 | DCCSDS
24/11/2017 | WOD | Social Investment Program | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | The original expenditure includes the approved budget to 30 June 2017 only. The planned expenditure has been revised to include the approved expenditure to 30 June 2018 to complete tranche 1 and 2 of the program. | 2017-09-30T00:00:00 | Critical | 2230000 | G | Whole of Department | 26 | 1311000 | G | G | 6 | The project will implement systems and processes that support the departments social procurement spend and support interventions that are proven to work, offer good value for money and are contributing to the broader objectives of government. | 5028000 | 2016-07-01T00:00:00 | DCCSDS
24/11/2017 | CS | Adoption Client Management System | 2016-06-30T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | Planned end date has been amended to 31 October 2017 due to delays to the project schedule from reprioritisation of resources to community recovery activities associated with Cyclone Debbie, risk mitigation strategies associated with data migration, and to accommodate additional change requests during the execution of user acceptance testing. The revised expenditure and end date have been approved. | 2017-09-30T00:00:00 | Low | 523000 | G | Child Safety | 87 | 1438000 | G | G | 7 | The project will implement a contemporary and more cost effective replacement for the Adoptions Case Management System (ACMS). | 1536000 | 2016-10-01T00:00:00 | DCCSDS
24/11/2017 | WOD | Complaints Management System | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 |  | 2017-09-30T00:00:00 | Low | 466000 | G | Whole of Department | 35 | 83000 | G | G | 8 | The objective of the complaints management system project which was formerly incorporated into the Technology Refresh project is to develop a complaints management system which supports the future DCCSDS business structure. The new system must also meet the recommendations made by the Queensland Ombudsman in his Management of Child Safety Complaints report in which the department has agreed that a full review of data fields for the departments complaints management database is conducted and relevant categories aligned to the departments core business practices and best practice complaints handling process. | 466000 | 2017-07-01T00:00:00 | DCCSDS
24/11/2017 | CS | ICMS Replacement | 2021-06-30T00:00:00 | Initiate | G | 2021-06-30T00:00:00 | A total estimated value will be provided once the proposal has been developed further. | 2017-09-30T00:00:00 | Critical | 0 | G | Child Safety | 6 | 1533321 | G | G | 9 | The ICMS Replacement Program will replace the current child protection and youth justice service delivery system by delivering an integrated child protection and youth justice system focused on effective customer-centric service delivery across government and Non-Government Organisations. 24/11/2017,The initiative will address the significant gaps that have developed between frontline practice and the current ICMS system. The new solution will help deliver improved effectiveness for frontline staff and therefore better outcomes for clients. It will be designed with the flexibility to be adapted over time, to respond to emerging needs and future changes. | 0 | 2017-02-01T00:00:00 | DCCSDS
24/11/2017 | CS | Our Child Project | 2019-02-28T00:00:00 | Initiate | G | 2019-02-28T00:00:00 | Project has commenced initiation activities. | 2017-09-30T00:00:00 | Critical | 4900000 | G | Child Safety | 10 | 648000 | G | G | 10 | The Our Child project will deliver a secure multi-agency information sharing platform that will enhance agencies ability to respond to instances of children missing from out-of-home care. | 4900000 | 2017-03-01T00:00:00 | DCCSDS
24/11/2017 | WOD | Destination Information | 2019-06-30T00:00:00 | Initiate | G | 2019-06-30T00:00:00 |  | 2017-09-30T00:00:00 | Critical | 8500000 | G | Whole of Department | 8 | 902000 | G | G | 11 | The Destination Information initiative will deliver smarter, simpler, better information management by improving the management of electronic information and documents, enabling the ability to file, retrieve and share information, within legislative provisions, in electronic form, removing duplication and reliance on paper based information, enabling better access to relevant information to support families and vulnerable children and enabling improved external information sharing. | 8500000 | 2017-02-01T00:00:00 | DCCSDS
24/11/2017 | Cross-Gov | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery | G | 2018-09-03T00:00:00 | The program continues to meet milestones within the set timeframes. 24/11/2017,Queensland Fire and Emergency Services Human Capital Management solution is tracking to schedule and is expected to go-live with Phase 1 in December 2017. 24/11/2017,The program is currently developing detailed business cases for Queensland Ambulance Service and Queensland Corrective Services Human Capital Management solutions. The agency review process of the final drafts will roll out in October 2017. 24/11/2017,The Queensland Ambulance Service transition to the new payroll system is keeping to set timeframes and on track for delivery in Qtr 3 FY 2017. 24/11/2017,The Program timeframe will remain amber while planning and scheduling for the QFES Payroll implementation is underway. | 2017-09-30T00:00:00 | Critical | 101500000 | G | Cross-Government program led by DSITI | 48 | 49531115 | A | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 24/11/2017, 24/11/2017,* Sustainable and supported HR and Payroll service delivery 24/11/2017,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 24/11/2017,* Strategic HR capability that supports the development, performance and safety of the departments workforce 24/11/2017,* Business Intelligence capability that provides real timely, integrated HR information 24/11/2017,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 24/11/2017,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 24/11/2017,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
24/11/2017 | QPS | Online National Police Certificate | 2017-06-30T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | The National Police Certifcate Content Requirements and Agency Transaction Specification documents were signed off by the business on the 28th of July 2017. The vendor has now commenced the build, with preliminary testing having occurred in September 2017 and continuing through October 2017, with the initial launch expected in November 2017. On 26 September 2017 the Program Management Committee approved an extension to project closure to 31 July 2018. | 2017-10-19T00:00:00 | High | 275000 | G | Queensland Police Service | 42 | 137500 | G | G | 1 | The Online National Police Certificate Project will implement an online service for the community to apply and pay for Name Only National Police Certificates online, rather than presenting at a police station, or using the online services of an Australian Crime Intelligence Commission accredited broker. This will provide improved customer service to the community through a more efficient and reliable QPS service, with no requirement to present at a police station, as well as provide efficiency and time savings to local police stations and the Police Information Centre. | 220000 | 2017-01-01T00:00:00 | QPS
24/11/2017 | QPS | Police Integrity and Professional Standards | 2020-02-17T00:00:00 | Delivery | G | 2020-02-17T00:00:00 | Funding for the Police Integrity and Professional Standards Project has been approved and included in the 2017-18 budget. The Invitation to Offer Process has commenced. | 2017-10-19T00:00:00 | High | 3675008 | G | Queensland Police Service | 15 | 12000 | G | G | 2 | This initiative will deliver a new integrated Police Integrity and Professional Standards IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The Police Integrity and Professional Standards system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The Police Integrity and Professional Standards Project will also complement the Complaints Reform Project established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of the Police Integrity and Professional Standards system will place the QPS in a strong readiness position to fully implement Complaints Reform Project generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 3675008 | 2017-03-07T00:00:00 | QPS
24/11/2017 | QPS | Data Analytics | 2017-07-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project has delivered new capability in all streams. Additional Tactical Analytics capability is being developed with rollout and training to be scheduled closer to the end of this year in time for the 2018 Commonwealth Games. Additional analytics use cases are being explored during the remainder of the Data Lake Proof of Technology. 24/11/2017, 24/11/2017,The Governance Committee approved additional budget and an extension to project closure to facilitate consultation, completion and consideration of the Business Case to further expand QPS data analytics and intelligence capability. | 2017-10-19T00:00:00 | Low | 1730000 | G | Queensland Police Service | 76 | 1790000 | G | G | 3 | Develop the QPS Advanced Data Analytics proof-of-concept. This proof-of-concept is intended to inform a larger suite of data analytics integration and intelligence over the next four years, including the development of predictive and alert models to enhance the operational response to threats, incidents and events. | 2350000 | 2017-02-19T00:00:00 | QPS
24/11/2017 | QPS | Body Worn Cameras | 2018-02-28T00:00:00 | Delivery | G | 2018-02-28T00:00:00 | The Program will complete the deployment of all Stage Two body worn cameras by December 2017 and will then complete transition and closure activities by 30 June 2018. A Business Case for additional funding for a Stage Three rollout in 2018-19 has been prepared for Government consideration. A successful Stage Three rollout would see body worn cameras provided to every frontline operational police officer in Queensland. | 2017-10-19T00:00:00 | Medium Low | 6030000 | G | Queensland Police Service | 75 | 5300000 | G | G | 4 | The Queensland Police Service Body Worn Camera Project is deploying 5100 body worn cameras to frontline police officers. Body worn cameras will be deployed to 168 police stations, 16 tactical crime units, 47 road policing units, and specialist units including dog squads and the Public Safety Response Team in two stages. The cameras integrate with the QPS mobility devices, allowing officers to add metadata to videos and to review videos in the field. A system for storage and allocation of digital camera data will also be implemented as well as policy related to use of the cameras. | 6830000 | 2014-08-25T00:00:00 | QPS
24/11/2017 | PSBA | Weapons Licensing Management System Stage 2a project | 2017-05-31T00:00:00 | Delivery | G | 2017-12-29T00:00:00 | Weapons Licensing Management System Stage 2A Project was officially handed over to The Weapons Licensing Business on Friday 26 May 2017. Since the release of the project on 27 April 2017, statistical performance measures of the expected target performance on the automated assessment and vetting functionality have not been achieved, although the system is working as expected and in accordance with the projects business requirements. The Project Board has since endorsed an extension of the Weapons Licensing Management System Stage 2A Project to the 29 December 2017, for further system enhancement work to improve the expected benefit of Improved Weapons Licensing Productivity, to better align to the Weapons Licensing Management System Stage 2A Business Case. Benefit enhancement analysis is in progress. | 2017-10-19T00:00:00 | Medium | 2500000 | G | Public Safety Business Agency | 97 | 1888776 | G | G | 5 | Improved workflow efficiencies, reduction in work queues, less resources required to process licence renewal and weapons Permit to Acquire, etc. | 2156825 | 2015-11-11T00:00:00 | QPS
24/11/2017 | QCS | Electronic Transfer of Court Results (ETCR) Phase 3 | 2017-12-01T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is on track for completion within time and quality tolerances. It has fallen under cost tolerance as project activities were delayed between April 2017 and July 2017 to allow for other priority work affecting resource assignments. Project activities have now resumed and resource assignments confirmed as the project works towards its initial release. | 2017-10-06T00:00:00 | High | 550150 | A | Corrective Services | 23 | 303186 | G | G | 1 | * The objective of the ETCR project is to improve integration between criminal justice agencies and improve staff efficiency by reducing manual data entry effort | 1223331 | 2016-12-12T00:00:00 | DJAG
24/11/2017 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-06-30T00:00:00 | Delivery | G | 2018-12-31T00:00:00 | Original planned end date was changed from 30 June 2018 to 31 Dec 2018 due to: 24/11/2017, 24/11/2017, 24/11/2017,- initial delays in securing project resources (2016-17 Christmas/New Year shutdown) 24/11/2017, 24/11/2017, 24/11/2017,- high level of project design complexity (heterogeneous environments) 24/11/2017, 24/11/2017, 24/11/2017,- conformity with appropriate probity and procurement governance. 24/11/2017, 24/11/2017, 24/11/2017,- requirement to develop a Significant Procurement Plan (SPP). 24/11/2017, 24/11/2017, 24/11/2017, 24/11/2017,The original project estimated expenditure occurs over two years to implement Core Infrastructure DR and Oracle DR. The variance of revised cost resulting in significant savings is due to implementing a more cost effective solution proposed through the Request for Quote (RFQ) process while utilising contemporary technologies. | 2017-10-06T00:00:00 | High | 7460674 | G | Corporate Services | 10 | 3005285 | G | G | 2 | * Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 5917255 | 2016-10-01T00:00:00 | DJAG
24/11/2017 | QCS | QCS GIS Project | 2017-09-29T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | Original timeframe and expenditure were updated following contract execution to relfelect increased scope, to maximise avaialble budget, and to allow adequate timeframes for integration of third party data. | 2017-10-06T00:00:00 | Medium | 925000 | G | Corrective Services | 55 | 435513 | G | G | 3 | * Procurement and implementation of a GIS that integrates data from multiple systems to improve Business Intelligence through increased analytical capability | 1020500 | 2017-01-30T00:00:00 | DJAG
24/11/2017 | Housing | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The Property and ECC6 Release 1 go live was implemented on 1 November 2017 as planned after successful completion of all key testing and business readiness activities including extensive face to face training with users across the State. 24/11/2017,The project is now focussing on providing comprehensive post go live support to the business during an embedding period in addition to commencing planning for a second stage Tenancy release. | 2017-11-01T00:00:00 | Critical | 56286000 | A | Housing Services | 46 | 56900000 | A | G | 1 | Replace the existing ICT housing solution with an integrated ICT system. | 70675462 | 2013-07-01T00:00:00 | HPW
24/11/2017 | PWAM | iSpace External Hosting Migration Project | 2017-01-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The functionality and changes in the upgraded system have been fully tested from a systems view. The environments for user testing and training are being prepared. The project is targeting go live in early December subject to successful user acceptance testing. 24/11/2017, 24/11/2017,Some contract payments pending formal milestone completion and acceptance. 24/11/2017, | 2017-11-01T00:00:00 | High | 735000 | A | Queensland Government Accommodation Office | 90 | 747058 | A | A | 2 | Version upgrade and migration of the hosting of Queensland Accommodation Office core system to a hosted managed service arrangement. | 1415203 | 2016-05-01T00:00:00 | HPW
24/11/2017 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2017-12-15T00:00:00 | The project is progressing as planned. 24/11/2017, 24/11/2017,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 24/11/2017,June 2017 - Revised schedule approved returning the project to Green. 24/11/2017,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 24/11/2017,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 24/11/2017,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 24/11/2017,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 24/11/2017,December 2016 - The project is progressing as planned. | 2017-10-20T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 88 | 594620 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 24/11/2017, 24/11/2017,* register and maintain their information 24/11/2017,* report fuel sales volume. | 907680 | 2016-04-05T00:00:00 | DEWS
24/11/2017 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing as planned. 24/11/2017, 24/11/2017,August 2017 - Approved extension of timeframe. 24/11/2017,June 2017 - The project is progressing as planned. 24/11/2017,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 24/11/2017,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 24/11/2017,October 2016 - Progress is continuing as planned. 24/11/2017,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 24/11/2017,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 24/11/2017,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-10-20T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 90 | 1255275 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 24/11/2017, 24/11/2017,* support compliance with legislation 24/11/2017,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 24/11/2017,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 24/11/2017,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 24/11/2017, | 1390000 | 2012-04-01T00:00:00 | DEWS
24/11/2017 | BQ | Biosecurity information management system program | 2017-05-31T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The program is progressing as planned 24/11/2017, 24/11/2017,March 2017 - The program is progressing as planned in line with approved change to scope, timeframe, benefits and cost. 24/11/2017,January 2017 - A small scope increase has been proposed, currently progressing through governance processes. 24/11/2017,November 2016 - Note, a scope review is currently under way. 24/11/2017,May 2016 - Program is continuing as planned. Note a small extension to planned end date. 24/11/2017,March 2016 - A re-baseline has brought all parameters back to Green. 24/11/2017,January 2016 - Timeframe, Cost, and Quality remain Amber, pending a business case update due early April 2016. 24/11/2017,November 2015 - Program is still Amber while the Timeframe is being re-baselined. 24/11/2017,September 2015 - The Exception Report has been accepted by the Program Board. Timeframe remains Amber pending a business case update. 24/11/2017,July 2015 - Resources continue to be redirected to assist with emergency response to the Panama banana disease. An Exception Report is being developed to address this. 24/11/2017,May 2015 - As anticipated, the emergency response to the Panama Banana disease outbreak has impacted both the project cost and the Timeframe. 24/11/2017,March 2015 - There is currently an outbreak of Panama banana disease which has potential to impact the schedule of this project. 24/11/2017,January 2015 - Actions are being taken to resolve some current scheduling issues. | 2017-10-20T00:00:00 | Critical | 18080000 | G | Biosecurity Queensland | 90 | 17516000 | G | G | 1 | Deliver an integrated toolkit consisting of various information management technologies and enhanced business processes to improve the management of biosecurity risks in Biosecurity Queensland's day-to-day business operations and in emergency responses. | 19409000 | 2013-07-01T00:00:00 | DAF
24/11/2017 | FQ | Coastal Surveillance Service renewal and enhancement | 2016-07-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The project is progressing as planned. 24/11/2017, 24/11/2017,A further extension to the planned end date was approved with no impact on costs. 24/11/2017,March 2017 - A further extension to the planned end date was approved with no impact on costs as work has slowed, aligning with the vendor's capacity to deliver. 24/11/2017,January 2017 - An extension to the planned end date was approved due to ongoing data verification trials between old and new processes. 24/11/2017,November 2016 - An extension to the planned end date was approved. Note the actual cost to date adjustment due to previously included recurrent operational costs by mistake. 24/11/2017,September 2016 - The planned end date was extended due to upgrades of software and network connectivity taking longer than expected. 24/11/2017,July 2016 - An extension to the planned end date was approved. Note the previous estimated expenditure included recurrent operational costs by mistake. 24/11/2017,March 2016 - The project is continuing as planned. | 2017-10-20T00:00:00 | High | 115782 | G | Fisheries Queensland | 98 | 99947 | G | G | 2 | The primary objectives will be: 24/11/2017, 24/11/2017,* reduction of manual data entry tasks and automation of administration and reporting processes 24/11/2017,* improvement in ability to respond to entanglements and recover equipment in a more timely way 24/11/2017,* a single location for all data 24/11/2017,* direct integration with EHP's StrandNet application. 24/11/2017, | 115782 | 2015-08-01T00:00:00 | DAF
24/11/2017 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery | G | 2018-01-31T00:00:00 | The project is continuing as planned. 24/11/2017, 24/11/2017,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2017-10-20T00:00:00 | Medium | 608146 | G | Forestry Queensland | 75 | 548559 | G | G | 3 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 24/11/2017, 24/11/2017,* the capture, management and integration of data 24/11/2017,* value-adding opportunities for business improvement 24/11/2017,management of risk associated with ongoing use and maintenance of disparate systems. | 706063 | 2016-06-15T00:00:00 | DAF
24/11/2017 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
24/11/2017 | PSBA | Emergency Services Computer Aided Dispatch (ESCAD) Upgrade Program | 2016-09-30T00:00:00 | Delivery | G | 2018-07-03T00:00:00 | Queensland Ambulance Service (QAS) and Queensland Fire and Emergency Services (QFES) successfully completed the User Acceptance Testing (UAT) of Pre-Production and Training environments of the upgraded ESCAD system and the Operator Trainings are proceeding in October 2017. Meanwhile, the Detailed Cut Over Planning is progressing and targets the Cut Over Period in January 2018, subject to any latent technical issues and any unforeseen significant events. The Assurance Gate Review is currently underway to assess the readiness for the upgraded ESCAD system. The Planned expenditure on the Whole of Government ICT Dashboard reflects the total approved budgets funded by QAS and QFES. | 2017-10-16T00:00:00 | Critical | 6774820 | G | Public Safety Business Agency | 72 | 8348933 | G | G | 1 | A program of work for Queensland Ambulance Service and Queensland Fire and Emergency Services to upgrade the Emergency Services Computer Aided Dispatch System, including infrastructure, operating system and application software. | 10289600 | 2015-01-15T00:00:00 | PSBA
24/11/2017 | PSBA | Emergency Vehicle Priority (EVP) Project | 2016-06-30T00:00:00 | Delivery | G | 2017-12-15T00:00:00 | EVP request for further extension to June 2018 pending funding availability. EVP rollout to Cairns has completed and will continue to work with Transport and Main Roads in undertaking further rollouts across Queensland, including Ipswich, Rockhampton and Gladstone. Procurement contract near finalised and Project continuing with procurement of system support managed service with anticipation of a contract in place late October 2017. | 2017-10-16T00:00:00 | High | 3370000 | G | Public Safety Business Agency | 86 | 3794740 | G | G | 2 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 24/11/2017, 24/11/2017,* Responsive vehicle movements 24/11/2017,* Improve road safety 24/11/2017,* Congestion management 24/11/2017,* Community safety | 3794740 | 2013-01-01T00:00:00 | PSBA
24/11/2017 | PSBA | Inter-CAD Electronic Messaging System (ICEMS) | 2017-12-01T00:00:00 | Delivery | G | 2017-12-01T00:00:00 | Stage 3 has been extended to 1/12/17 and delivery is being closely monitored for completion on this date. Please note: The original planned end date has been updated to correct an error that was previously published. | 2017-10-16T00:00:00 | Critical | 560000 | G | Public Safety Business Agency | 92 | 1507030 | G | G | 3 | To implement the ICEMS protocol between the Queensland Police Service (QPS), Queensland Ambulance Service (QAS) and Queensland Fire and Emergency Services (QFES) computer aided dispatch systems to enable Triple Zero data sharing between agencies. | 1674541 | 2015-10-06T00:00:00 | PSBA
24/11/2017 | PSBA | QAS Office 365 Implementation Project | 2017-06-30T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The Queensland Ambulance Service Office 365 Implementation Project is responsible for migrating all Queensland Ambulance Service email mailboxes and archive mailboxes to Office 365. Project is tracking to schedule, budget and has no major issues blocking it from being delivered by 31 October 2017. $400,000 was deferred from FY16/17 to continue the migrations and an additional $400,000 has been allocated. | 2017-10-16T00:00:00 | Medium | 1544817 | G | Public Safety Business Agency | 69 | 1134887 | G | G | 4 | The project will deliver digital transformation for Queensland Ambulance Service (QAS) through the implementation of the Office 365 suite of products to augment the below enhancements to their current business processes. 24/11/2017, 24/11/2017,1. Undertaking smarter meetings; 24/11/2017,2. Facilitating better administration; 24/11/2017,3. Accessing information anywhere, any time; 24/11/2017,4. Engaging and communicating better; 24/11/2017,5. Supporting capability development; 24/11/2017,6. Facilitating business intelligence; and 24/11/2017,7. Enabling efficient workflow and approvals. | 1402889 | 2017-01-23T00:00:00 | PSBA
24/11/2017 | PSBA | QPS Office 365 Pilot and Office Client Upgrade Project | 2017-06-30T00:00:00 | Closed | G | 2017-08-31T00:00:00 | Project complete. | 2017-10-16T00:00:00 | Critical | 1030000 | G | Public Safety Business Agency | 100 | 965484 | G | G | 5 | The project will enable Queensland Police Service (QPS) to evaluate the suitability of the Office 365 services for potential wider rollout across the agency and upgrade all QPS installations of Office 2013 to Office Pro Plus 2016. | 1029692 | 2017-01-30T00:00:00 | PSBA
24/11/2017 | OSR | SPER Program | 2017-12-31T00:00:00 | Delivery | A | 2018-03-30T00:00:00 | * 15/05/2017 - The State Penalties Enforcement Amendment Bill 2017 features Work and Development Orders (WDO), offering Queenslanders experiencing genuine hardship with alternative ways to reduce or pay off their debt was passed in Parliament on the 10th May 2017. The Bill will simplify the fee arrangements, making it easier for our customers to understand their obligations, and facilitate a case management approach to people with SPER debts. The implementation of the ICT system solution (Stage 2) is continuing, and in parallel, SPER are initiating a re-baselining exercise of the implementation scope, approach and schedule. 24/11/2017,* 08/06/2017 - A re-baselining exercise of the implementation scope, approach and schedule is progressing and is anticipated to be completed by 30 June 2017. 24/11/2017,* 17/07/2017 - Expenditure to date: $22.5M has been for the transformation of the SPER function; and $8.7M has been on the build phase of the ICT Implementation (Software as a Service - SaaS). 24/11/2017,Original Planned Expenditure and Cost to date has been updated to include the ICT Implementation Solution. The remaining components of the Program includes further functional design and build of the replacement ICT solution. A revised delivery date is targeted for Quarter 1, 2018. 24/11/2017,* 04/10/2017 - Revised and detailed delivery schedule is being finalised. The SPER Program has completed the implemention of the new governance arrangements focussing on ICT delivery and the management and control of risks, designed to safeguard the new implementation approach. | 2017-10-06T00:00:00 | High | 47200000 | G | State Penalties Enforcement Registry | 46 | 38378000 | A | A | 1 | To maintain the integrity of fines as an effective sanction. To uphold confidence in the justice system. To deliver efficient and effective debt management practices which provide value for money to the State. 24/11/2017, | 47200000 | 2014-01-01T00:00:00 | QR
24/11/2017 | OSR | Contact Centre | 2017-09-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | * 06/04/2017 - Design activities have commenced and are on track for completion by the end of April. Business deployment schedule has been confirmed. Network and infrastructure activities have commenced. 24/11/2017,* 05/05/2017 - Design has been finalised and build activities have commenced. Project on track for delivery by end of September 2017. 24/11/2017,* 06/06/2017 - Project remains on track. Build and unit testing is on schedule for completion on 19th June 2017. Commissioning of a new communications link is planned for the week commencing 12th June. Change Impact Assessment work is in progress. 24/11/2017,* 10/07/2017 - Due to a network freeze in Queensland Treasury the project has been unavoidably delayed, impacting the implementation schedule and the project budget. The project has been re-baselined with the planned end date October 2017 and there is sufficient funds allocated to the 2017/18 budget. 24/11/2017,* 11/08/2017 - Project on track for first deployment scheduled 25th September 2017. System Integration Testing complete and User Acceptance Testing scheduled for commencement 21st August, 2017. 24/11/2017,* 04/10/2017 - First Contact Centre go live completed, with the second deployment scheduled for 9th October. On track to complete all rollouts by end of October 2017. | 2017-10-04T00:00:00 | Medium | 1020000 | G | Office of State Revenue | 95 | 974214 | G | G | 2 | The Office of State Revenue's existing contact centre solution has reached its end of life. As a result, the Office of State Revenue is implementing a new comprehensive call centre solution designed to improve productivity and the client experience across all taxes and the Queensland First Home Owners' Grant administered by the office. | 1080300 | 2017-02-27T00:00:00 | QR
24/11/2017 | OIR | Renewal and Photographic Licensing System (RAPS) Assessor Portal | 2018-07-13T00:00:00 | Delivery | G | 2018-05-10T00:00:00 | * 27/03/2017 - The project has been initiated. Recruitment is now complete and development work has commenced. 24/11/2017,* 02/05/2017 - Resources commencing to undertake the first Development phase. Business requirements analysis is progressing. 24/11/2017,* 02/06/2017 - Contract Lead Developer engaged undertaking prepartion works for first development phase. Business requirements analysis continues to progress. 24/11/2017,* 11/07/2017 - Project scope reviewed to deliver the business and stakeholders critical functionality. Project resources continuing to be recruited during July. 24/11/2017,* 11/08/2017 - Revised project scope, which includes the changes to the schedule, costs and benefits, has been approved. The project has now commenced into the development phase, with business analysis continuing in parallel with early development. 24/11/2017,* 04/10/2017 - Development phase and business analysis continued to progress. Business requirements to be completed by end of October. | 2017-10-04T00:00:00 | High | 766467 | G | Office of Industrial Relations | 20 | 220999 | G | G | 3 | The RAPS Assessor Portal project commenced as an initiative to target improving services for high risk work licensing accredited assessors, registered training organisations and licensing and advisory services. Currently accredited assessors must use a combination of cumbersome paper based processes, smart forms, and an online service that is difficult to use. This project will improve and integrate the external and internal applications and reduce duplicated processes for high-risk work licensing stakeholders whilst meeting legislative requirements. One simplified online service will be delivered for assessors that will save them time and make compliance easier. | 769103 | 2016-12-14T00:00:00 | QR
24/11/2017 | RI | Financial Assurance Information Registry (FAIR) | 2018-07-01T00:00:00 | Initiate | G | 2018-07-01T00:00:00 | * 23/06/2017 - Project continuing in planning phase, appropriate governance mechanisms have been established. 24/11/2017,* 10/07/2017 - Awaiting outcome of public consultation before refining system design and scope. Adjustments made to the project expenditure and planned end date to cater for rounding up and actual go-live date of the ICT solution. 24/11/2017,* 11/08/17 - Preparing for Investment Review, after the review the project will move to the build phase. 24/11/2017,* 04/10/2017 - Project passed Investment Review. Project Manager has commenced and the engagement of the development team is being finalised. | 2017-10-04T00:00:00 | Medium | 15900000 | G | Insurance Commission | 12 | 301107 | G | G | 4 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
24/11/2017 | RI | Information Security Program | 2018-06-30T00:00:00 | Initiate | G | 2018-06-30T00:00:00 | * 06/10/2017 - Project is in initiation phase, undertaking planning, procurement and recruitment activities. | 2017-10-06T00:00:00 | Medium | 0 | G | Office of the Chief Information Officer | 0 | 0 | G | G | 5 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 24/11/2017, | 0 | 2017-10-16T00:00:00 | QR
24/11/2017 | OSR | OSR Transformation Program | 2020-06-30T00:00:00 | Delivery | G | 2020-06-30T00:00:00 | * 04/10/2017 - Undertaking a series of Process Re-design Sprints to allow for the rapid exploration of opportunities that exist within a process, and developing recommedations for a future version of the process. Initial series of sprints will continue through to November 2017. Deployment of the first data stream related initiative, Single Customer View for Individuals ( Phase 1) is on track for go live End October 2017. Commenced project to deliver a pilot for the Virtual Assistant initiative, the pilot is planned for end of November 2017. | 2017-10-04T00:00:00 | High | 66918000 | G | Office of State Revenue | 1 | 122972 | G | G | 6 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 24/11/2017, 24/11/2017,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 66918000 | 2017-08-01T00:00:00 | QR
24/11/2017 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
24/11/2017 | Corporate Services Improvement Systems Board | Corporate Services Reporting Project | 2016-06-30T00:00:00 | Closed | G | 2017-09-30T00:00:00 | The Corporate Services Reporting project closure report was approved by the Project Board in August 2017. This project will no longer report on the ICT Dashboard. | 2017-09-30T00:00:00 | Medium | 1250000 | G | Transactional Services Improvement Program | 100 | 3228807 | G | G | 1 | To improve confidence in the consistency and reliability of workforce management decisions across TMR by delivering a modernised and expanded Business warehouse (BW) reporting and analytics platform | 3252000 | 2015-01-05T00:00:00 | TMR
24/11/2017 | Corporate Services Improvement Systems Board | Human Resource Management Improvement | 2016-06-30T00:00:00 | Closed | G | 2017-09-15T00:00:00 | The Human Resource Management Improvement project has successfully completed its scope and was approved by the program board in September 2017. The Human Resource Management Improvement project will report for one more reporting period before being remov | 2017-09-30T00:00:00 | High | 2500000 | G | Information Technology Branch | 100 | 3732726 | G | G | 2 | To improve people management processes, provide greater workforce reporting and support better workforce decisions by implementing a range of system improvements to the TMR HR data platform. | 4234000 | 2015-01-05T00:00:00 | TMR
24/11/2017 | Corporate Services Improvement Systems Board | Learnzone Improvement Project | 2017-06-30T00:00:00 | Delivery | G | 2017-09-30T00:00:00 | The LearnZone Improvement project is on track. | 2017-09-30T00:00:00 | High | 796000 | G | Transactional Services Improvement Program | 95 | 416823 | G | G | 3 | Innovate, develop and deliver an improved and centralised digital learning service and management function. 24/11/2017, 24/11/2017, | 801000 | 2016-02-01T00:00:00 | TMR
24/11/2017 | Corporate Services Improvement Systems Board | Lotus Notes Decommissioning | 2016-01-31T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project is on track. | 2017-09-30T00:00:00 | High | 8150000 | G | ERP Projects Board | 63 | 1417978 | G | G | 4 | Deliver improved information platform functions for effective ICT Strategy Alignment | 8150000 | 2015-11-01T00:00:00 | TMR
24/11/2017 | Corporate Services Improvement Systems Board | Stop Cheques - Stage 3 | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Stop Cheques Stage 3 project is on track. | 2017-09-30T00:00:00 | Medium | 200000 | G | ERP Projects Board | 20 | 81171 | G | G | 5 | Cheques are inefficient and costly to use, process and administer for both the customer and department. A range of solutions have been developed to reduce the number of cheques that the department produces or receives including refund to card at counter | 200000 | 2017-07-01T00:00:00 | TMR
24/11/2017 | Corporate Services Improvement Systems Board | Risk Management Solution | 2018-07-01T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Risk Management Solution project has not previously reported on the ICT Dashboard. The Risk Management Solution project is on track. | 2017-09-30T00:00:00 | High | 350000 | G | Corporate Services Improvement Systems Board | 20 | 389189 | G | G | 6 | Replace the current risk management approach through the delivery of a new and contemporary enterprise Risk Management solution for TMR . | 710000 | 2017-07-02T00:00:00 | TMR
24/11/2017 | Customer Service, Safety and Regulation Program | R and L Systems Software Upgrade | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The R and L Systems Software Upgrade project is on track. | 2017-09-30T00:00:00 | Medium | 780000 | G | Customer Services, Safety and Regulation Division | 15 | 119300 | G | G | 19 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
24/11/2017 | Corporate Services Improvement Systems Board | Integrated Records Information System (IRIS) | 2018-07-01T00:00:00 | Delivery | G | 2019-06-30T00:00:00 | The IRIS project has not previously reported on the ICT Dashboard. The IRIS project is on track. | 2017-09-30T00:00:00 | High | 7967972 | G | Information Technology Branch | 25 | 1548614 | G | G | 7 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 7967972 | 2017-07-02T00:00:00 | TMR
24/11/2017 | Corporate Services Improvement Systems Board | Transactional Services Improvement Program Enhancements | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The Transactional Services Improvement Program Enhancements Stage 3 is on track. | 2017-09-30T00:00:00 | Low | 200000 | G | Transactional Services Improvement Program | 20 | 94734 | G | G | 8 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolid | 200000 | 2017-07-01T00:00:00 | TMR
24/11/2017 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery | G | 2018-09-30T00:00:00 | The CDOP Online Portal project is on track. | 2017-09-30T00:00:00 | High | 1500000 | G | Customer Services, Safety and Regulation Division | 85 | 691067 | G | G | 9 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal | 1441000 | 2016-01-01T00:00:00 | TMR
24/11/2017 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The eLearner project is currently on track. An exception report to rebaseline the project's end date to June 2018 and additional budget was approved by the Program Board in September 2017. | 2017-09-30T00:00:00 | High | 2500000 | G | Customer Services, Safety and Regulation Division | 93 | 4048652 | G | G | 10 | Implement an online learning and assessment program at the pre-learner and/or learner stage, to replace enhance learning outcomes. | 4176000 | 2015-06-12T00:00:00 | TMR
24/11/2017 | Customer Service, Safety and Regulation Program | Facial Recognition Replacement | 2017-03-31T00:00:00 | Delivery | G | 2017-08-31T00:00:00 | The Facial Recognition project has successfully completed its scope and a project closure report will be submitted to the Program Board for consideration in October 2017 | 2017-09-30T00:00:00 | High | 531250 | G | Customer Services, Safety and Regulation Division | 99 | 596088 | G | G | 11 | To provide Queensland integration with the National Driver Licence Facial Recognition System (NDLFRS) as part of the National Facial Recognition Matching Capability. This project will see the sharing of and upload of TMR facial image holdings to a nationa | 631250 | 2015-07-13T00:00:00 | TMR
24/11/2017 | Customer Service, Safety and Regulation Program | MSQ iBase Project | 2017-06-30T00:00:00 | Delivery | G | 2017-07-28T00:00:00 | The MSQ iBase project has successfully completed its scope and a project closure report will be submitted to the Program Board for consideration in October 2017. | 2017-09-30T00:00:00 | Low | 450000 | G | Customer Services, Safety and Regulation Division | 99 | 227589 | G | G | 18 | The Maritime Safety Queensland ibase Project has commenced as the current incident register platform has been identified as requiring replacement. The future platform will work in collaboration with current field input and smart devices. | 292000 | 2017-01-01T00:00:00 | TMR
24/11/2017 | Customer Service, Safety and Regulation Program | Hardware Security Modules (HSM) | 2016-07-29T00:00:00 | Delivery | G | 2017-08-31T00:00:00 | The HSM project has successfully completed its scope and a project closure report will be submitted to the Program Board for consideration in October 2017 | 2017-09-30T00:00:00 | High | 500000 | G | Customer Services, Safety and Regulation Division | 99 | 390503 | G | G | 12 | The Hardware Security Modules (HSMs) form part of the Queensland Driver Licence smartcard product set introduced in 2010 and generate keys for smartcard authentication and validation by TMR-authorised card readers at TMR Customer Service Centres, QGAP and | 500000 | 2015-08-01T00:00:00 | TMR
24/11/2017 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The Mobile Compliance Information System project is on track. | 2017-09-30T00:00:00 | High | 300000 | G | Customer Services, Safety and Regulation Division | 70 | 549090 | G | G | 13 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 630000 | 2016-11-01T00:00:00 | TMR
24/11/2017 | Customer Service, Safety and Regulation Program | Online Customer Experience Phase 3 | 2017-06-30T00:00:00 | Closed | G | 2017-06-30T00:00:00 | The Online Customer Experience Phase 3 project has successfully completed its scope and was approved by the program board in September 2017. The Online Customer Experience Phase 3 project will report for one more reporting period before being removed fro | 2017-09-30T00:00:00 | Low | 1265000 | G | Customer Services, Safety and Regulation Division | 100 | 1077498 | G | G | 14 | Within the Online Customer Experience Phase 3 Program the following initiatives will be completed: 24/11/2017, eNotices Expansion eReminder 24/11/2017, Re-architecture Authentication 24/11/2017, Disability Parking Permits 24/11/2017, OnlineWeb Chat | 1059481 | 2016-07-01T00:00:00 | TMR
24/11/2017 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery | G | 2017-12-24T00:00:00 | The Ralph Replacement project is on track. | 2017-09-30T00:00:00 | Medium | 500000 | G | Customer Services, Safety and Regulation Division | 57 | 551712 | G | G | 15 | TMR's current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace | 674000 | 2016-07-01T00:00:00 | TMR
24/11/2017 | Customer Service, Safety and Regulation Program | Voice Comms Mgt System | 2017-06-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | The Voice Comms Management System project is on track. | 2017-09-30T00:00:00 | Medium | 828000 | G | Customer Services, Safety and Regulation Division | 50 | 274738 | G | G | 16 | The Voice Comms Management project consists of two replacement of existing Voice Communication and Control Systems at Townsville and Hay Point. | 828000 | 2016-01-01T00:00:00 | TMR
24/11/2017 | Customer Service, Safety and Regulation Program | CTP Tax Invoice Online | 2017-12-31T00:00:00 | Delivery | G | 2017-12-31T00:00:00 | The CTP Tax Invoice Online project is on track. | 2017-09-30T00:00:00 | Medium | 300000 | G | Customer Services, Safety and Regulation Division | 10 | 11696 | G | G | 17 | The Compulsory Third Party Tax Invoice Online project will deliver a new online service which will enable Customers to self-serve and print an electronic version of the CTP Invoice, removing the need for TMR to process paper based invoices, avoiding produ | 300000 | 2017-05-01T00:00:00 | TMR
24/11/2017 | Infrastructure Management and Delivery | Go Everywhere Collect Online (GECO) | 2017-05-26T00:00:00 | Closed | G | 2017-07-28T00:00:00 | The GECO project has successfully completed its scope and was approved by the program board in August 2017. This project will no longer report on the ICT Dashboard. | 2017-09-30T00:00:00 | Low | 187160 | G | Infrastructure Management 24/11/2017,and Delivery | 100 | 309095 | G | G | 20 | Provide a simple, flexible and affordable solution for collecting information from mobile devices (that is, from the field) and managing the information through a back-end system, for use by RoadTek operations and potentially other areas of TMR. | 289564 | 2016-08-01T00:00:00 | TMR
24/11/2017 | Infrastructure Management and Delivery | Access Management System (AMS) - formerly Heavy Vehicle Permit Management System | 2015-10-31T00:00:00 | Paused | A | 2017-06-30T00:00:00 | TMR is taking steps to conclude the Access Management System project, in light of significant changes in the operating environment since it was commenced, including the way permits are issued and the role of the National Heavy Vehicle Regulator with its A | 2017-09-30T00:00:00 | High | 4281564 | A | Infrastructure Management 24/11/2017,and Delivery | 83 | 8307429 | A | A | 21 | Improve heavy vehicle and load movement safety through effective schemes, guidelines and conditions management 24/11/2017, Allow coordinated road operations such that an increase in activity will not result in economic detriment or a loss of safety and public ame | 9001258 | 2013-06-01T00:00:00 | TMR
24/11/2017 | Infrastructure Management and Delivery | Recording Asset Damage and Restoration (RADAR) | 2017-06-19T00:00:00 | Closed | G | 2017-06-19T00:00:00 | The RADAR project project closure report was approved by the Project Board in August 2017. This project will no longer report on the ICT Dashboard. | 2017-09-30T00:00:00 | Low | 161126 | G | Infrastructure Management 24/11/2017,and Delivery | 100 | 161126 | G | G | 22 | The purpose of this project is to develop a mobile data application that will allow for consistent data collection on mobile devices and for the management of photographic evidence and associated data relating to Natural Disaster Relief and Recovery Arran | 211126 | 2016-07-01T00:00:00 | TMR
24/11/2017 | Infrastructure Management and Delivery | Red Crab-Pilot 2-Traffic Guidance Schemes (TGS) | 2017-02-28T00:00:00 | Closed | G | 2017-06-27T00:00:00 | The Red Crab - Pilot 2 TGS project closure report was approved by the Project Board in August 2017. This project will no longer report on the ICT Dashboard. | 2017-09-30T00:00:00 | Low | 192552 | G | Infrastructure Management 24/11/2017,and Delivery | 100 | 166825 | G | G | 23 | The Traffic Guidance Scheme project will develop an interface to record and collect information about traffic interruptions at roadwork sites to enable driver awareness of speed reductions, and provide information about roadwork control effectiveness. | 192552 | 2016-04-01T00:00:00 | TMR
24/11/2017 | Infrastructure Management and Delivery | Red Crab-Pilot 4-Asset Maintenance Management System (AMMS) | 2016-03-01T00:00:00 | Closed | G | 2017-06-30T00:00:00 | The Red Crab Pilot 4 AMMS project closure report was approved by the Project Board in August 2017. This project will no longer report on the ICT Dashboard. | 2017-09-30T00:00:00 | High | 186098 | G | Infrastructure Management 24/11/2017,and Delivery | 100 | 594398 | G | G | 24 | Adapt the Red Crab prototype system to meet the requirement for a RoadTek Asset Maintenance Management System (AMMS), with a view to replacing the current system following a successful pilot. | 667420 | 2015-07-01T00:00:00 | TMR
24/11/2017 | Infrastructure Management and Delivery | Work Improvement Note (WIN) Replacement | 2016-12-19T00:00:00 | Delivery | G | 2017-10-11T00:00:00 | The WIN Replacement project project is on track. | 2017-09-30T00:00:00 | Low | 242612 | G | Infrastructure Management 24/11/2017,and Delivery | 94 | 214317 | G | G | 25 | The Work Improvement Note (WIN) System is used to capture, track, review and report on improvements, potential problems, non-conformances, corrective actions, customer feedback and complaints. The WIN System is an essential component of the overarching bu | 409763 | 2016-02-15T00:00:00 | TMR
24/11/2017 | Infrastructure Management and Delivery | 2018 Commonwealth Games Journey Planner (GJP) | 2017-10-13T00:00:00 | Delivery | G | 2018-04-27T00:00:00 | The 2018 Commonwealth GJP project is on track. | 2017-09-30T00:00:00 | High | 450000 | G | Infrastructure Management 24/11/2017,and Delivery | 65 | 477851 | G | G | 26 | A dedicated Journey Planner application supports this need by providing a single source of truth for all transport information related to the Games, and also allows for rapid changes to routes, schedules, and stops, if any are required, in order to drive | 973899 | 2016-10-16T00:00:00 | TMR
24/11/2017 | Passenger Transport Technology Program | Customer Contact Management Solution (CCMS) | 2017-06-30T00:00:00 | Delivery | G | 2017-11-10T00:00:00 | The CCMS project is on track. | 2017-09-30T00:00:00 | High | 1279000 | G | TransLink | 85 | 1368654 | G | G | 27 | To implement an industry standard, robust and extensible solution to replace the existing Commentline solution. To achieve better performance of the customer contact management functions. To provide the base platform to support the future implementation | 1279000 | 2016-04-01T00:00:00 | TMR
24/11/2017 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery | G | 2018-01-31T00:00:00 | The STAS Auto Forms project is on track. | 2017-09-30T00:00:00 | High | 4166000 | G | TransLink | 59 | 2688057 | G | G | 28 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 4166000 | 2016-04-01T00:00:00 | TMR
24/11/2017 | Policy Planning and Investment Program | Portfolio, Program, Project and Contract Management (3PCM) - Phase 2 and 3 | 2017-03-31T00:00:00 | Delivery | A | 2017-12-22T00:00:00 | The 3PCM project is currently reporting amber for quality as there is a small number of defects from a recent data migration activity that is currently being investigated and resolved. | 2017-09-30T00:00:00 | High | 12757788 | G | Policy, Planning and Investment Division | 97 | 47520523 | G | A | 29 | Define and implement standard, consistently applied processes for planning, managing and delivering the Transport Infrastructure Portfolio across the domains of portfolio, program, project and contract management 24/11/2017, Source and implement an integrated, s | 47670648 | 2012-09-01T00:00:00 | TMR
24/11/2017 | CS | Bandwidth Upgrade Project | 2017-07-31T00:00:00 | Closed | G | 2017-08-02T00:00:00 | The project completed closure on 30 June 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | High | 5551767 | G | Corporate Services | 98 | 4575357 | G | G | 1 | To upgrade internet connectivity for Queensland State Schools, uplifting data speeds to 25kbps per student, improving access to online educational and community resources. 24/11/2017, | 4575357 | 2015-01-12T00:00:00 | DET
24/11/2017 | SS | Early Start | 2015-07-03T00:00:00 | Delivery | G | 2018-07-31T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Medium | 70000 | G | State Schools | 74 | 73522 | G | G | 2 | To provide schools with enhanced reporting functionality, improving their ability to analyse Prep to Year 2 student learning data. | 200992 | 2013-04-03T00:00:00 | DET
24/11/2017 | CS | eDRMS Upgrade Project | 2016-06-30T00:00:00 | Closed | G | 2017-07-04T00:00:00 | The project completed closure on 4 July 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | Critical | 2203000 | G | Corporate Services | 92 | 1734511 | G | G | 3 | To upgrade the key operational system so that it meets current and future demands and aligns with electronic information management practices. | 1680000 | 2015-01-12T00:00:00 | DET
24/11/2017 | PP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Delivery | G | 2018-02-27T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 700000 | G | Policy, Performance and Planning | 74 | 1125550 | G | G | 4 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
24/11/2017 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery | G | 2018-08-10T00:00:00 | The project is tracking to plan. The project is currently subject to procurement activities. | 2017-09-08T00:00:00 | High | 0 | G | Corporate Services | 37 | 0 | G | G | 5 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DET FBS SAP future state landscape for the next five years | 0 | 2017-01-16T00:00:00 | DET
24/11/2017 | SS | Global Learning Environment | 2018-12-30T00:00:00 | Closed | G | 2017-06-02T00:00:00 | The project completed closure on 13 July 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | Critical | 800000 | G | State Schools | 100 | 2552704 | G | G | 6 | To provide an online global learning solution which focuses on the 2018 Commonwealth Games, encouraging learning and collaboration in Queensland, nationally and internationally. | 2492000 | 2014-10-29T00:00:00 | DET
24/11/2017 | DG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery | G | 2018-01-01T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Low | 632585 | G | DG | 79 | 755722 | G | G | 7 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
24/11/2017 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery | G | 2019-12-18T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Critical | 16670000 | G | State Schools | 44 | 7426976 | G | G | 8 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 23470000 | 2015-08-03T00:00:00 | DET
24/11/2017 | PP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | The project is tracking to the revised plan. The project is currently subject to procurement activities. | 2017-09-08T00:00:00 | High | 0 | G | Policy, Performance and Planning | 54 | 0 | G | G | 9 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution | 0 | 2016-03-01T00:00:00 | DET
24/11/2017 | CS | Purchase IT Replacement Project | 2015-09-30T00:00:00 | Closed | G | 2017-09-18T00:00:00 | The project completed closure on 31 July 2017 and will no longer be reported on the ICT Dashboard. | 2017-09-08T00:00:00 | Medium | 248800 | G | Corporate Services | 99 | 905348 | G | G | 10 | To replace the existing system with a solution that meets current and future demands, provides enhanced analytics and improvements to reporting. | 1100000 | 2015-06-29T00:00:00 | DET
24/11/2017 | PP | Research Services 2.0 | 2016-09-30T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Low | 230000 | G | Policy, Performance and Planning | 85 | 404745 | G | G | 11 | To develop a solution that assists in the management of the Department of Education and Training commissioned research proposals and projects, improving resourcing and information dissemination. | 431157 | 2015-11-02T00:00:00 | DET
24/11/2017 | SS | School Budget Solution | 2017-03-31T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 2030000 | G | State Schools | 95 | 6295520 | G | G | 12 | To develop a solution that assists schools with resource management, improving their ability to support students in achieving better educational outcomes. | 6641785 | 2014-12-15T00:00:00 | DET
24/11/2017 | TS | Study Tours Support System Upgrade | 2016-06-30T00:00:00 | Delivery | G | 2017-09-29T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | Medium | 680000 | G | Training and Skills | 96 | 772580 | G | G | 13 | To replace or upgrade the existing Study Tours system with an online solution that has enhanced functionality, improving processes, data quality and tour management. | 779894 | 2015-08-31T00:00:00 | DET
24/11/2017 | TS | Training Management System | 2016-12-31T00:00:00 | Delivery | A | 2018-04-30T00:00:00 | The project is being monitored for cost, schedule and quality. The project is currently subject to procurement activities. | 2017-09-08T00:00:00 | Critical | 0 | A | Training and Skills | 62 | 0 | A | A | 14 | To replace multiple systems with a solution that meets current and future demands, reduces costs and improves the management of vocational and educational training. | 0 | 2013-04-01T00:00:00 | DET
24/11/2017 | SS | Trial of platform for virtual academies | 2017-10-02T00:00:00 | Delivery | G | 2018-12-31T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 151641 | G | State Schools | 40 | 101875 | G | G | 15 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage; safe and secure like-minded student virtual communities; and strategic partnerships with university, industry and business. 24/11/2017, 24/11/2017, | 151641 | 2016-06-21T00:00:00 | DET
24/11/2017 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery | G | 2019-06-28T00:00:00 | The project is tracking to plan. | 2017-09-08T00:00:00 | High | 41000000 | G | Corporate Services | 48 | 25998875 | G | G | 16 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
24/11/2017 | [20 empty] | INVERSTMENT INFO
24/11/2017 | CSG | Coal Seam Gas Groundwater Monitoring Arrangements | 2017-12-31T00:00:00 | Paused | G | 2018-06-30T00:00:00 | Change to the planned end date approved, there is no impact to cost. Initiative now paused until early 2018. 24/11/2017, 24/11/2017,August 2017 - Revised total expenditure (budget) updated to include all operating costs not previously reported. 24/11/2017,June 2017 - Progress is continuing as planned. Still on schedule to complete December 2017. 24/11/2017,December 2016 - Much of the project has been completed and a significant amount of the procurement expenditure for capital equipment has occurred. 24/11/2017,October 2016 - Progress is continuing as planned. 24/11/2017,August 2016 - Cost returned to Green after a review of costs associated with activities remaining, and a correction in actual cost to date adjustment. 24/11/2017,June 2016 - Cost is Amber with a resource review under way. 24/11/2017,February 2016 - Progress is continuing as planned. 24/11/2017, | 2017-11-07T00:00:00 | High | 2380568 | G | Coal Seam Gas Compliance | 95 | 2548371 | G | G | 1 | Enhance availability of groundwater data through improvements to network monitoring of bores for clients and landholders. | 2598256 | 2014-01-13T00:00:00 | DNRM
24/11/2017 | SIMTARS | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery | G | 2017-11-10T00:00:00 | A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 24/11/2017, 24/11/2017,October 2017 - The project is continuing as planned. 24/11/2017,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2017-11-06T00:00:00 | High | 563000 | G | SIMTARS (Safety In Mines Testing and Research Station) | 98 | 589135 | G | G | 2 | The development and delivery of a (replacement) modern and robust Safegas solution: 24/11/2017, 24/11/2017,* risk reduction increasing capability to manage the volume of queries, transactions and data 24/11/2017,* decrease database corruption related to incidents. 24/11/2017, | 619000 | 2017-01-25T00:00:00 | DNRM
24/11/2017 | SO | Mines Infrastructure Risk Mitigation Project | 2019-02-18T00:00:00 | Delivery | G | 2019-02-18T00:00:00 | The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2017-11-14T00:00:00 | High | 1200000 | G | Statewide Operations | 5 | 56000 | G | G | 3 | Migrate systems to supported infrastructure and software to: 24/11/2017, 24/11/2017,* provide a stable, secure, fully supported and flexible solution 24/11/2017,* eliminate the risks to which the geoscience data assets are currently exposed. 24/11/2017, | 1200000 | 2017-08-08T00:00:00 | DNRM
24/11/2017 | GSQ | MinesOnlineMaps - Spatial Presentation Replacement | 2017-06-30T00:00:00 | Paused | G | 2018-04-30T00:00:00 | Project is paused awaiting review of a possible change in direction. Cost remains green while investigation is undertaken to identify if deferral request was processed. | 2017-11-16T00:00:00 | Medium | 531030 | G | Geological Survey of Queensland | 60 | 98271 | G | G | 4 | Provide a web-based mapping solution for the ongoing provision of MinesOnlineMaps (MOMaps) into the future. 24/11/2017, | 531030 | 2016-08-01T00:00:00 | DNRM
24/11/2017 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DPC
24/11/2017 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
24/11/2017 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 24/11/2017,* Move operational accountability and responsibility for print and imaging devices to the service provider 24/11/2017,* Reduce print and imaging costs 24/11/2017,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
24/11/2017 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
24/11/2017 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
24/11/2017 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 24/11/2017, 24/11/2017,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
24/11/2017 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
24/11/2017 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 24/11/2017, 24/11/2017,* reduce operating costs 24/11/2017,* increase capacity 24/11/2017,* improve customer experience 24/11/2017,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
24/11/2017 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
24/11/2017 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 24/11/2017, 24/11/2017, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
24/11/2017 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 24/11/2017, 24/11/2017,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
24/11/2017 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
24/11/2017 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 24/11/2017, | 2017-10-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 40 | 751692 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
24/11/2017 | ESR | Environmental Management Register/Contaminated Land Register - replacement | 2017-06-30T00:00:00 | Paused | G | 2017-06-30T00:00:00 | August 2017 - The project is paused awaiting the outcome of a change request for additional scope - this will return the project to a Green state. 24/11/2017,April 2017 - A minor correction has been made to the revised total estimated expenditure to include $20,000 operating prior years. 24/11/2017,February 2017 - A change request has been approved moving the initiative cost back to Green. 24/11/2017,December 2016 - Project is continuing as planned, with a change request under way to return cost to Green. 24/11/2017,October 2016 - Project delivery activities formally commenced on 2 October 2016. 24/11/2017,August 2016 - The initiative was paused for some time but has now recommenced and moved into delivery. It is progressing as planned. | 2017-10-20T00:00:00 | High | 981680 | A | Environmental Services and Regulation | 78 | 718000 | A | A | 1 | The current system no longer supports efficient delivery of the department's responsibilities. The replacement will: 24/11/2017, 24/11/2017,* mitigate the risks associated with a system that is beyond its useful life 24/11/2017,* improve access to information by individuals, business and industry conducting searches (property lot plan) of the registers 24/11/2017,* support the creation of notices to stakeholders 24/11/2017,* reduce manual tasks through the introduction of automated workflows and customer self-serve and self-correct. 24/11/2017, | 1111680 | 2016-07-01T00:00:00 | EHP
24/11/2017 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP
22/11/2018 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-09-30T00:00:00 | High | 5600000 |  | eHealth Queensland | 48 | 3955341 |  | G | 1 | This project aims to establish a robust, highly available and secure contemporary platform that has the capability to support the agile eHealth Strategy. | 5492863 | 2017-07-03T00:00:00 | DH
22/11/2018 | HSQ | Pathology and Forensic Laboratory System Rehosting Project | 2018-06-30T00:00:00 | Delivery |  | 2018-12-13T00:00:00 | August 2018: This project has returned to 'green'. Approval was granted in August to extend the project's schedule to December 2018. 22/11/2018, 22/11/2018,July 2018: This project is now reporting 'red' due to delays to the infrastructure component of the project. Options are being prepared to minimise the impact to the overall schedule and cost of the project, to be approved in August 2018. 22/11/2018, 22/11/2018,Reason for variance: Latest approved budget includes both operational and capital costs and delays where experienced with the provisioning of required technical infrastructure. | 2018-10-08T00:00:00 | High | 1691324 |  | Health Support Queensland | 71 | 2463225 |  | G | 2 | Delivery of a replacement hardware and visualisation solution for the AUSLAB and AUSCARE systems that will achieve improved resiliency of the architecture, updated operating system and inclusion of virtualisation. AUSLAB and AUSCARE are critical to support laboratories and patient clinical care. | 3246769 | 2017-08-28T00:00:00 | DH
22/11/2018 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2018-09-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 |  | 2018-10-11T00:00:00 | High | 3692973 |  | Metro North | 95 | 1813878 |  | G | 3 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 22/11/2018, 22/11/2018,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Women's Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 22/11/2018, 22/11/2018,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 3692973 | 2015-06-01T00:00:00 | DH
22/11/2018 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-09-30T00:00:00 | High | 11180394 |  | eHealth Queensland | 30 | 748202 |  | G | 4 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 22/11/2018,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work.? Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 10915391 | 2017-07-03T00:00:00 | DH
22/11/2018 | EHQ | Digital Collaboration Platform Program | 2018-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | May 2018: This project has now returned to 'green' with the project's revised schedule being approved. 22/11/2018, 22/11/2018,March 2018: Project activities have continued to be delayed, resulting in this project reporting 'Red'. A project change request has been submitted to the project's governance committee. Successful deployment was recently achieved in Townsville. 22/11/2018, 22/11/2018,January 2018: This project is experiencing delays in pre-migration activities. 22/11/2018, 22/11/2018,Reason for variance: Original budget was reflective of an original estimate based on high level planning. Detailed planning has since refined the estimated budget (including vendor licensing arrangements) which received approval for budget increase in June 2017. | 2018-09-30T00:00:00 | High | 11000000 |  | eHealth Queensland | 37 | 17999815 |  | G | 5 | This program will deliver digital collaboration tools for any time, any where, any device including: 22/11/2018,? Email and Archiving 22/11/2018,? Establishment and Collaboration 22/11/2018,? Productivity Suite Enablement | 22664506 | 2015-10-29T00:00:00 | DH
22/11/2018 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate |  | 2017-12-31T00:00:00 | June 2018: The current proposed date of completion is the 31 December 2019, which is subject to project board approval. 22/11/2018, 22/11/2018,Reason for variance: The original estimated expenditure was projected prior to the Request for Information (RFI) to the open market. Consequently, the planned expenditure was revised based on the market responses following the RFI. | 2018-10-12T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 40 | 671978 |  | G | 6 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 5697000 | 2015-12-01T00:00:00 | DH
22/11/2018 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | May 2018: The project has completed a solution evaluation process, with the project requiring additional schedule and financials as originally approved. The project is expecting to return to 'green' upon receiving change request approval. 22/11/2018, 22/11/2018,Reason for variance: The evaluation process further revised the original budget and implementation was delayed to facilitate extended procurement processes. | 2018-10-08T00:00:00 | High | 1166363 |  | Chief Health Officer and Prevention | 98 | 201744 |  | G | 7 | Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1384239 | 2017-07-24T00:00:00 | DH
22/11/2018 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | September 2018: Technical issues have impacted the current implementation schedule, with the project prioritising the correction of these issues. | 2018-10-11T00:00:00 | High | 4827917 |  | Metro North | 68 | 4389478 |  | A | 8 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (ieMR) program. 22/11/2018, 22/11/2018,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 22/11/2018, 22/11/2018,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. | 4827917 | 2016-07-01T00:00:00 | DH
22/11/2018 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | April 2018: This initiative is now 'in delivery'. | 2018-09-30T00:00:00 | High | 3792744 |  | eHealth Queensland | 26 | 818704 |  | G | 9 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment.??The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access.? | 3723476 | 2017-07-05T00:00:00 | DH
22/11/2018 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | September 2018: The project continues to work with implementation partners to finalise the schedule and cost of go-live. System integration and change management activities are continuing to be a primary focus of the project. Schedule and cost details will be updated upon approval of a change request. 22/11/2018, 22/11/2018,August 2018: The project is reporting red due to schedule delays and an anticipated funding shortfall associated with integration complexities and change management activities required. A change request is progressing to address these concerns. | 2018-10-08T00:00:00 | High | 105000000 |  | Metro North | 63 | 92700918 |  | R | 10 | The current Queensland Health Finance, Asset and Materials Maintenance Information System (FAMMIS) system is based on a heavily customised solution which is almost 20 years old and no longer supported. 22/11/2018,The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 22/11/2018, 22/11/2018,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 22/11/2018,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 22/11/2018, 22/11/2018,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
22/11/2018 | EHQ | Follow Me Desktop - Deployment | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-09-30T00:00:00 | High | 3952980 |  | eHealth Queensland | 68 | 1895090 |  | G | 11 | Follow Me Desktop Deployment Project will deliver: the Follow Me Desktop service (FMD) to HHS' in alignment with the Infrastructure Remediation Program (IMP) and ieMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 3621306 | 2017-07-03T00:00:00 | DH
22/11/2018 | EHQ | Patient Administration System (PAS) Replacement - Business Case Development Project | 2017-06-30T00:00:00 | Initiate |  | 2019-03-29T00:00:00 | Reason for variance: Further funding was provided in 2017-18 and 2018-19 to finalise the start-up activities, including the delivery of a detailed business case and early procurement activities. | 2018-09-30T00:00:00 | High | 3850000 |  | eHealth Queensland | 77 | 6235541 |  | G | 31 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients? journeys, and ensure that accurate information about our patients is readily available when and where required. 22/11/2018, 22/11/2018,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 22/11/2018,? support for patient engagement 22/11/2018,? integrated care 22/11/2018,? clinical research 22/11/2018,? population health (for patients using public health services) 22/11/2018,? performance transparency 22/11/2018,? resource planning. | 11890760 | 2015-11-01T00:00:00 | DH
22/11/2018 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-09-30T00:00:00 | High | 3301500 |  | eHealth Queensland | 32 | 1243806 |  | G | 12 | Project Purpose: To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 2345263 | 2017-07-01T00:00:00 | DH
22/11/2018 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-09-30T00:00:00 | High | 1120000 |  | eHealth Queensland | 65 | 720854 |  | G | 13 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. | 1072242 | 2017-07-05T00:00:00 | DH
22/11/2018 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery |  | 2020-06-26T00:00:00 | Reason for variance: The scope and schedule for IAMP has been extended due to revised timelines to accommodate for extended development, integration, and deployment activities. | 2018-09-30T00:00:00 | High | 3215000 |  | eHealth Queensland | 38 | 6027309 |  | G | 14 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 12206443 | 2015-06-22T00:00:00 | DH
22/11/2018 | EHQ | ieMR Program (Funding Packages 3 and 4) | 2019-04-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | August 2018: The SurgiNet component of ieMR went live at The Townsville Hospital in August 2018. This builds on existing ieMR capability, providing pre and post operative documents directly into the patient chart module, to better support patient care. 22/11/2018, 22/11/2018,July 2018: The Enterprise Schedule Management (ESM) component of ieMR went live at The Townsville Hospital in July 2018. This updated patient scheduling tool will improve inpatient and outpatient scheduling processes. 22/11/2018, 22/11/2018,June 2018: The advanced version of the ieMR system has gone live at the Queen Elizabeth II (QEII) Hospital in June, which includes enhancements to the interface between ieMR and the XRay Radiology Information System. 22/11/2018, 22/11/2018,May: The advanced version of the ieMR system has gone live at the Redland Hospital. Additional clinical reporting was also enabled by ieMR in May. | 2018-09-30T00:00:00 | High | 0 |  | eHealth Queensland | 33 | 0 |  | G | 15 | ieMR will enable improved patient care through the development of a state-wide, authoritative single source of the patient records. 22/11/2018, 22/11/2018,The ieMR will provide clinicians with the ability to: 22/11/2018,* access data that is integrated, accurate and clinically relevant 22/11/2018,* support decision making and better use of information 22/11/2018,* optimise management of patients, resources and provision of services 22/11/2018,* support interaction across a network of providers by making it easier to find providers, transfer information and collaborate with multidisciplinary providers. 22/11/2018,The Program scope (all tranches) is to roll out the ieMR system to 24 hospitals across Queensland. 22/11/2018, 22/11/2018,Please note that financial information for ieMR is Commercial in Confidence | 0 | 2016-11-17T00:00:00 | DH
22/11/2018 | EHQ | Infrastructure Maintenance Program Establishment | 2018-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | March 2018: This initiative has been refocused to the establishment phase of the Infrastructure Maintenance Program, and as such the % complete and original end date have been updated to reflect this phase of the program. The latest approved end date will be updated in a following reporting month. | 2018-09-30T00:00:00 | High | 1161415 |  | eHealth Queensland | 90 | 1186726 |  | G | 16 | The Infrastructure Maintenance Program (IMP)?will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 22/11/2018,The scope includes: 22/11/2018,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 22/11/2018,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and? 22/11/2018,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1922376 | 2017-07-03T00:00:00 | DH
22/11/2018 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery |  | 2022-06-30T00:00:00 |  | 2018-10-08T00:00:00 | High | 14673739 |  | Clinical Excellence | 22 | 2596831 |  | G | 17 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 22/11/2018,The ongoing program of work aims to continue and build upon existing functionality by: 22/11/2018,? Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 22/11/2018,? Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 22/11/2018,? Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 22/11/2018,? Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 22/11/2018,? Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
22/11/2018 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate |  | 2022-12-21T00:00:00 | Reason for variance: Budget was revised following market evaluation. | 2018-10-12T00:00:00 | High | 6300000 |  | Queensland Ambulance Service | 26 | 635438 |  | G | 18 | Phased delivery of a system supporting QAS business intelligence. | 9240000 | 2017-01-03T00:00:00 | DH
22/11/2018 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | Reason for variance: Budget has been revised as a result of reallocation of funding provided under the Specialist Outpatient Strategy to support additional statewide Smart Referrals functionality. 22/11/2018,Schedule has been impacted by only 6months yet still falls within the commitment timeframe. | 2018-10-12T00:00:00 | High | 33827000 |  | Clinical Excellence | 37 | 15740133 |  | G | 19 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 39408218 | 2017-03-01T00:00:00 | DH
22/11/2018 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 1 | 2016-11-30T00:00:00 | Closed |  | 2018-08-31T00:00:00 | September 2018: Stage 1 of this project is now complete. After three successful pilots, the HR solution will commence rollout across the state over the next 12 months. 22/11/2018, 22/11/2018,May 2018: The project has experienced a delay to the completion of Stage 1 due to delays in the governance and assurance process and a change in delivery approach. The project is expecting to complete Stage 1 by the end of August 2018, and is currently seeking final governance approval to confirm additional time and funding to complete this stage. 22/11/2018, 22/11/2018,April 2018: The project has experienced a delay to the completion of Stage 1 due to delays in the governance and assurance process. The project is currently seeking approval to obtain additional time and funding to complete this stage. 22/11/2018, 22/11/2018,Reason for variance: The scope and schedule for Stage 1 of the IWFM Project has been increased to cover additional pilot sites, provide additional system enhancements (primarily to smart form functionality), and to ensure business foundational activities are implemented to prepare HHSs for IWFM implementation. | 2018-10-08T00:00:00 | High | 8200000 |  | Health Support Queensland | 100 | 28487615 |  | G | 20 | The IWFM project involves: 22/11/2018,- configuring additional functionality (currently available and licensed, but unutilised) within the existing Rostering and Payroll business solutions 22/11/2018,- partnering with HHSs to develop refined business models and business processes to support the roster-to-pay process 22/11/2018,- undertaking extensive training and change management to support the adoption and effective usage of new functionality and processes | 28709863 | 2016-02-17T00:00:00 | DH
22/11/2018 | EHQ | Interoperability Project | 2016-04-29T00:00:00 | Delivery |  | 2019-09-29T00:00:00 | Reason for variance: Original funding was reflective of committed funding made available to commence planning activities (including business case development) and implementation of risk mitigation activities of the existing interoperability solution, until such time (late 2017) approval for the implementation of the new solution was granted. | 2018-10-10T00:00:00 | High | 39189509 |  | eHealth Queensland | 33 | 19016336 |  | G | 21 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 22/11/2018,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 22/11/2018,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 22/11/2018, | 39189509 | 2015-02-01T00:00:00 | DH
22/11/2018 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Delivery |  | 2020-12-21T00:00:00 | Reason for variance: The latest budget was revised based on the latest governance approval. The schedule has been revised to accommodate for extended procurement timeframes and additional prototyping activities being added to the scope of the program. | 2018-10-08T00:00:00 | High | 64000000 |  | Health Support Queensland | 56 | 23827282 |  | G | 22 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 22/11/2018,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. | 63558771 | 2015-08-28T00:00:00 | DH
22/11/2018 | GCHHS | Medical Imaging Informatics Solution (MIIS) Risk Mitigation | 2018-12-31T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | September 2018: The project is reporting amber, with the project adjusting scope to ensure the solution aligns with the current budget. In addition, recruitment delays have impacted the project's schedule. 22/11/2018, 22/11/2018,Reason for variance: Revised project delivery costs were approved in March 2018, as part the Stage Gate 3 Business Case. 22/11/2018,Schedule was revised to align with the Digital Healthcare Program (ieMR) on the Gold Coast. | 2018-10-10T00:00:00 | High | 5000000 |  | Gold Coast | 26 | 2815670 |  | A | 23 | The Medical Imaging Informatics Solution (MIIS) Risk Mitigation project has identified an Imaging solution which will address the risks and opportunities described in the Case for Change including the mitigation of patient safety risks, increased efficiency and productivity, improvi.ng medical imaging billing revenue collection and cash flow. The solution has user endorsement from radiologists and clinicians and will be specifically configured to meet GCHHS?s needs. | 12800000 | 2017-04-03T00:00:00 | DH
22/11/2018 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | Reason for variance: The end date of the project was extended to accommodate additional go-live finalisation activities. | 2018-10-11T00:00:00 | High | 4030460 |  | Metro North | 85 | 4197426 |  | G | 24 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 22/11/2018, 22/11/2018,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 22/11/2018, 22/11/2018,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
22/11/2018 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | May 2018: This project has returned to 'green', with the project's schedule and budget being monitored by the project's governance committee. 22/11/2018, 22/11/2018,April 2018: The project is continuing to report 'Red' due to continued delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. 22/11/2018, 22/11/2018,Reason for variance: The budget was extended to accommodate additional implementation scope. | 2018-10-11T00:00:00 | High | 6340000 |  | Metro North | 85 | 6893127 |  | G | 25 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 8161556 | 2014-06-01T00:00:00 | DH
22/11/2018 | EHQ | Metro South and East Queensland ICT Infrastructure Replacement Initiative | 2018-06-29T00:00:00 | Delivery |  | 2019-02-28T00:00:00 |  | 2018-09-30T00:00:00 | High | 4160449 |  | eHealth Queensland | 72 | 1986787 |  | G | 26 | Will replace or uplift out of date end of life ICT assets. | 3583313 | 2017-07-01T00:00:00 | DH
22/11/2018 | EHQ | Metro South East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-04-29T00:00:00 |  | 2018-09-30T00:00:00 | High | 2182844 |  | eHealth Queensland | 84 | 1156606 |  | G | 27 | Will replace or uplift out of date end of life ICT assets. | 2154311 | 2017-07-01T00:00:00 | DH
22/11/2018 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | August 2018: The project has returned to 'green'. Activities to improve project team resourcing and increase key deployment rates are continuing into September. The project will continue to monitor the performance of migration and upgrade activities. 22/11/2018, 22/11/2018,July 2018: The project is now reporting 'amber' due to a lack of technical and deployment resource availability, impacting on the project's schedule. Mitigation actions are in place to reduce the schedule and resourcing impact. 22/11/2018, 22/11/2018,May 2018: This project has now returned to 'green' with the project's revised schedule being approved. 22/11/2018, 22/11/2018,Reason for variance: Original budget was reflective of an original estimate based on high level planning. Detailed planning has since refined the estimated budget (including vendor licensing arrangements) which received approval for budget increase in June 2017. | 2018-09-30T00:00:00 | High | 14100000 |  | eHealth Queensland | 76 | 25081439 |  | G | 28 | A managed operating environment means that everyone within the organisation is running a clean, basic operating system with centralised update management. This includes upgrades of all PC operating systems, preparing QH applications for running on recent operating system environments, and Infrastructure remediation activities to ensure the deployment tools are sufficient and ready for production. | 38741697 | 2016-05-12T00:00:00 | DH
22/11/2018 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | July 2018: The latest approved end date has been updated. 22/11/2018, 22/11/2018,June 2018: The latest approved end date of this project remains at 30 June 2018, pending the approval of a revised implementation date. 22/11/2018, 22/11/2018,Reason for variance: Budget and schedule were revised following a tender process as per responses from the market. | 2018-10-12T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 90 | 980157 |  | G | 29 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1510000 | 2015-10-01T00:00:00 | DH
22/11/2018 | CHOPD | Notifiable Conditions System Replacement | 2019-06-29T00:00:00 | Delivery |  | 2020-02-28T00:00:00 | Reason for variance: Approval to extend project timelines was received November 2014. Business Case was updated and approved in November 2016, including extending the schedule to February 2020. | 2018-10-08T00:00:00 | High | 12750000 |  | Chief Health Officer and Prevention | 45 | 3046758 |  | G | 30 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 22/11/2018,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
22/11/2018 | CSD | Practice Management Enterprise Solution | 2018-11-30T00:00:00 | Delivery |  | 2019-01-31T00:00:00 | September 2018: The project is now reporting red, with the project placing the implementation on hold while technical system issues are resolved. The project's schedule and budget will be adjusted following the approval of a change request to extend the end date of the project. 22/11/2018, 22/11/2018,Reason for variance: The latest approved budget was revised to reflect additional project establishment costs and development, testing and piloting activities. The schedule was also revised following procurement outcomes. | 2018-10-09T00:00:00 | High | 1470000 |  | Corporate Services | 81 | 2297368 |  | R | 32 | The main practice management software used by HHSs to conduct private practice services and billing activities is being replaced. The initiative will procure and implement "like for like" functionality enterprise solution for participating HHSs (15 in total). | 2961432 | 2017-08-01T00:00:00 | DH
22/11/2018 | EHQ | Project, Program and Portfolio Management Application | 2018-03-31T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | May 2018: This project has now returned to 'green' with the project's revised schedule being approved. 22/11/2018, 22/11/2018,April 2018: This project is now reporting 'amber' due to re-aligning the project's schedule and finances to meet changing organisational requirements. The project has submitted | 2018-09-30T00:00:00 | High | 1344177 |  | eHealth Queensland | 58 | 838856 |  | G | 33 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 22/11/2018, | 1531491 | 2017-05-02T00:00:00 | DH
22/11/2018 | EHQ | Queensland State-wide ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-09-30T00:00:00 | High | 3246247 |  | eHealth Queensland | 72 | 2449292 |  | G | 34 | Will replace or uplift out of date end of life ICT assets. | 3183491 | 2017-07-01T00:00:00 | DH
22/11/2018 | EHQ | Queensland State-wide ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-09-30T00:00:00 | High | 3283431 |  | eHealth Queensland | 79 | 3369364 |  | G | 35 | Will replace or uplift out of date end of life ICT assets. | 3273746 | 2017-07-01T00:00:00 | DH
22/11/2018 | MNHHS | Quick Flow Project | 2019-06-30T00:00:00 | Initiate |  | 2019-06-30T00:00:00 |  | 2018-10-11T00:00:00 | High | 6408600 |  | Metro North | 45 | 1990371 |  | G | 36 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 22/11/2018,The key objectives of the project are to: 22/11/2018,? Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 22/11/2018,? Improve the outpatient experience across MNHSS facilities and community services 22/11/2018,? Improve clinic resource utilisation 22/11/2018,? Increase the efficiency of clinical and administrative processes 22/11/2018,? Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
22/11/2018 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | September 2018: The project continues to report red due to additional functional, technical and integration requirements being added to the scope and as a result, is likely to impact the schedule. 22/11/2018, 22/11/2018,August 2018: The design and development phase of the project has been delayed to accommodate additional business and technical requirements. 22/11/2018, 22/11/2018,Reason for variance: The schedule has changed to ensure issues in project implementation are addressed. | 2018-10-11T00:00:00 | High | 34950000 |  | Cairns and Hinterland | 65 | 15490438 |  | R | 37 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patient's home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
22/11/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-02-28T00:00:00 |  | 2018-09-30T00:00:00 | High | 4260336 |  | eHealth Queensland | 79 | 2522282 |  | G | 38 | Will replace or uplift out of date end of life ICT assets. | 4213118 | 2017-07-01T00:00:00 | DH
22/11/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-09-30T00:00:00 | High | 2150147 |  | eHealth Queensland | 72 | 1561002 |  | G | 39 | Will replace or uplift out of date end of life ICT assets. | 2593463 | 2017-07-01T00:00:00 | DH
22/11/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-09-30T00:00:00 | High | 1651750 |  | eHealth Queensland | 72 | 997758 |  | G | 40 | Will replace or uplift out of date end of life ICT assets. | 1643098 | 2017-07-01T00:00:00 | DH
22/11/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-09-30T00:00:00 | High | 4245973 |  | eHealth Queensland | 82 | 3275303 |  | G | 41 | Will replace or uplift out of date end of life ICT assets. | 4216631 | 2017-07-01T00:00:00 | DH
22/11/2018 | EHQ | Service Delivery Excellence Project (SDEP) | 2018-02-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | March 2018: The latest approved end date and percentage complete has been updated. 22/11/2018, 22/11/2018,February 2018: The latest approved end date for this initiative will be updated pending advise from the project. | 2018-09-30T00:00:00 | High | 4822000 |  | eHealth Queensland | 40 | 2197127 |  | G | 42 | The Service Delivery Excellence Project (SDEP) aims to improve the service delivery functions of eHealth Queensland to help the organisation achieve its Customers and services Foundation and Shared Goal: 22/11/2018,Enhance value for customers by streamlining end to end services, processes and delivery models so that we can provide an exceptional customer experience. 22/11/2018,Stage 1 has the primary objective of delivering the Project Initiation Document (PID) for the Service Delivery Excellence Project (SDEP) Stage 2. | 4736721 | 2017-10-03T00:00:00 | DH
22/11/2018 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Delivery |  | 2020-09-30T00:00:00 |  | 2018-09-30T00:00:00 | High | 10500000 |  | eHealth Queensland | 25 | 3464127 |  | G | 43 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 10494349 | 2017-07-03T00:00:00 | DH
22/11/2018 | MNHHS | Royal Brisbane and Women's Hospital Wi-Fi | 2019-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-10-11T00:00:00 | High | 6000000 |  | Metro North | 40 | 356038 |  | G | 44 | The RBWH Wi-Fi Project will provide an uplift and renewal to the latest Queensland Health (QH) standard for wireless local area network (WLAN) coverage within the internal areas of prioritised RBWH buildings in order to support digital healthcare. 22/11/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for the RBWH in the near future. | 6000000 | 2017-10-22T00:00:00 | DH
22/11/2018 | EHQ | Sunshine Coast University Hospital (SCUH) Stage 2 ICT Expansion | 2018-06-30T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | February 2018: This project has been reported for the first time. | 2018-09-30T00:00:00 | High | 3180000 |  | eHealth Queensland | 92 | 3772412 |  | G | 45 | Sunshine Coast University Hospital (SCUH) ICT Stage 1 delivered the ICT required to achieve the successful commissioning of SCUH in March 2017. The SCUH Stage 2 ICT Expansion covers the investment period from 1 July 2017 to 31 December 2018 and is intended to support the planned expansion of SCUH to increase capacity and establish new services. | 3772412 | 2017-07-03T00:00:00 | DH
22/11/2018 | CHQ | Information Sharing Project Phase 2 | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | August 2018: The project is now reporting 'green'. The updated procurement approach was approved by the project's governance committee in August. 22/11/2018, 22/11/2018,July 2018: This project is now reporting 'amber' due to a change in procurement approach, which has impacted on the project's financials and schedule. The project's governance committee is reviewing the updated approach, returning the project to 'green' upon approval (expected to be in September). 22/11/2018, 22/11/2018, | 2018-10-03T00:00:00 | High | 4455455 |  | Childrens Health Queensland | 30 | 1313708 |  | G | 46 | Department of Health, eHealth Queensland, Children's Health Queensland and Mater Health share a common vision for the seamless integration of care across organisational boundaries, in the interests of patient safety, quality, efficiency and improved access to care. This vision of integrated care processes is enabled through seamless access, at the point of care, to necessary health information and efficient transactional capabilities that support the care continuum. | 4455455 | 2018-01-10T00:00:00 | DH
22/11/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Alcohol and Other Drugs (AODS) Consumer Technical Refresh | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | May 2018: This project has been reported for the first time. | 2018-10-10T00:00:00 | High | 1248860 |  | Clinical Excellence | 35 | 364660 |  | G | 47 | This project is refreshing the technical implementation of the CIMHA Consumer module, in preparation for the introduction of new Alcohol and Other Drugs (AODS) system functionality. | 1248860 | 2018-04-16T00:00:00 | DH
22/11/2018 | SPP | Queensland Health Integrated Processing System establishment (QHIDSe) | 2019-10-15T00:00:00 | Delivery |  | 2019-10-15T00:00:00 | May 2018: This project has been reported for the first time. | 2018-10-09T00:00:00 | High | 3257000 |  | Strategy, Policy and Planning | 26 | 1286166 |  | G | 48 | The QHIDSe project will develop in-house the foundation of an integrated processing system (i.e. QHIDS (Queensland Health Integrated Data System) using agile techniques and software development tools enabling QHIDS to be used as a replacement for the Queensland Hospital Inpatient Processing System (QHIPS, which processes the Queensland Hospital Admitted Patient Data Collection) and extended through future initiatives to provide new functionality. | 3257000 | 2018-05-25T00:00:00 | DH
22/11/2018 | HSQ | Modernised Managed Operating Environment (MOE) and Digital Collaboration Platform for HSQ | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | September 2018: The project is continuing to report amber, with the project's schedule being impacted by a dependant project implementation schedule. 22/11/2018, 22/11/2018,July 2018: The project is now reporting 'red' due to project team resourcing issues, as well as technical and scheduling delays of a dependent project impacting on the overall schedule. The project's governance committee is reviewing the project's schedule, with the project expecting to return to 'green' upon approval of an updated delivery approach. 22/11/2018, 22/11/2018,Reason for variance: The original budget reflected the 2017/18 FY spend only. | 2018-10-08T00:00:00 | High | 1057000 |  | Health Support Queensland | 33 | 1388653 |  | A | 49 | Delivery of a fully functional, production managed operating environment and digital collaboration platform packaged to all desktops, laptops and some smart devices within the Health Support Queensland environment. | 3414000 | 2018-01-01T00:00:00 | DH
22/11/2018 | CHOPD | Mosquito-borne Disease Program: Spatial Database Project | 2019-06-21T00:00:00 | Initiate |  | 2019-06-21T00:00:00 | June 2018: This project has been reported for the first time. 22/11/2018, 22/11/2018,Reason for variance: The budget was revised following market scan activities. | 2018-10-08T00:00:00 | High | 852000 |  | Chief Health Officer and Prevention | 59 | 211085 |  | G | 50 | The vector surveillance and control program requires a state-wide surveillance and control solution to assist with the response to the risk of Dengue, Zika and Chikungunya virus outbreaks in vulnerable North Queensland and the mitigation of emerging risks across Central and Southern Queensland. | 1502672 | 2017-07-31T00:00:00 | DH
22/11/2018 | CED | Patient Online Portal (POP) | 2019-12-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | July 2018: This project has commenced reporting for the first time. | 2018-10-12T00:00:00 | High | 15500000 |  | Clinical Excellence | 8 | 2053151 |  | G | 56 | The Patient Online Portal (POP) aims to improve a patient's outpatient journey through greater visibility and enhanced communication capability across specialist services. Additionally, the solution seeks to provide greater flexibility in the provision of outpatient services, allowing patients to better manage their care. | 15500000 | 2018-03-05T00:00:00 | DH
22/11/2018 | EHQ | Telehealth Asset Replacement | 2019-06-28T00:00:00 | Delivery |  | 2019-06-27T00:00:00 | July 2018: This project has commenced reporting for the first time. | 2018-09-30T00:00:00 | High | 1950000 |  | eHealth Queensland | 21 | 121183 |  | G | 51 | Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. | 1950000 | 2018-07-02T00:00:00 | DH
22/11/2018 | MNHHS | Connecting Care information Program (CCI) | 2022-06-30T00:00:00 | Initiate |  | 2022-06-30T00:00:00 | July 2018: This project has commenced reporting for the first time. 22/11/2018, 22/11/2018,Reason for variance: The budget was revised to include an additional financial year. | 2018-10-11T00:00:00 | High | 760455 |  | Metro North | 25 | 987887 |  | G | 52 | The Connecting Care Information Program - CCI -will support streamlining and improvement of clinical and administrative workflows through delivery of key Information Technology (IT) enablers. | 1140000 | 2017-03-21T00:00:00 | DH
22/11/2018 | MNHHS | Metro North Health and Hospital Service Contemporary Workspace Phase 1 | 2019-01-01T00:00:00 | Delivery |  | 2019-01-01T00:00:00 | July 2018: This project has commenced reporting for the first time. 22/11/2018, 22/11/2018,Reason for variance: The latest approved budget includes additional implementation costs and funding for the 18-19 financial year. | 2018-10-11T00:00:00 | High | 233000 |  | Metro North | 48 | 656992 |  | G | 53 | This project is focusing on preparing the Metro North Hospital and Health Service (MNHHS) applications to be ready for contemporary operating system deployment. | 1665831 | 2017-08-01T00:00:00 | DH
22/11/2018 | MNHHS | Metro North Picture Archiving and Communication (PACS) Replacement for The Prince Charles Hospital | 2018-12-03T00:00:00 | Delivery |  | 2018-12-03T00:00:00 | July 2018: This project has commenced reporting for the first time. 22/11/2018, 22/11/2018,Reason for variance: The latest approved budget includes additional funding approved for the 18-19 financial year. | 2018-10-11T00:00:00 | High | 2301451 |  | Metro North | 24 | 624862 |  | G | 54 | Procure and implement a contemporary Picture Archiving and Communication (PACS) System and functionality that will ensure improved Service delivery for the MNHHS Medical Imaging Departments at The Prince Charles Hospital (TPCH). | 2301451 | 2017-12-01T00:00:00 | DH
22/11/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Secure Transfer Project | 2019-01-28T00:00:00 | Initiate |  | 2019-01-28T00:00:00 | July 2018: This project has commenced reporting for the first time. 22/11/2018, 22/11/2018,Reason for variance: The budget was refined after the solution design stage with extended approvals required, impacting the project schedule. | 2018-10-10T00:00:00 | High | 610000 |  | Clinical Excellence | 10 | 125001 |  | G | 55 | The purpose of this initiative is to upgrade the CIMHA application with functionality to automate the sending of selected clinical notes and data securely. This will improve the efficiency and timeliness of information sharing. | 1109521 | 2017-10-16T00:00:00 | DH
22/11/2018 | MNHHS | Digital Transformation Readiness | 2018-12-27T00:00:00 | Initiate |  | 2018-12-27T00:00:00 | July 2018: This project has commenced reporting for the first time. | 2018-10-11T00:00:00 | High | 2771674 |  | Metro North | 28 | 462871 |  | G | 57 | The key objectives of Digital Transformation Readiness are to perform activities in preparation for Metro North Hospital and Health Service (MNHHS) Digital Transformation with a focus on the integrated electronic Medical Record (ieMR) readiness. | 2771674 | 2018-06-29T00:00:00 | DH
22/11/2018 | MNHHS | Referral Lodgement and Tracking (RLaT) | 2019-01-23T00:00:00 | Delivery |  | 2019-01-23T00:00:00 | July 2018: This project has commenced reporting for the first time. | 2018-10-11T00:00:00 | High | 3184098 |  | Metro North | 70 | 2280000 |  | G | 58 | This project will deliver a state-wide capability for referrers to lodge patient referrals electronically with Queensland Health. The referral will be automatically routed to the appropriate Hospital and Health Service (HHS). | 3184098 | 2018-02-09T00:00:00 | DH
22/11/2018 | EHQ | Infrastructure Capacity Expansion FY 18-19 | 2019-06-28T00:00:00 | Delivery |  | 2019-06-26T00:00:00 |  | 2018-09-30T00:00:00 | High | 1192426 |  | eHealth Queensland | 10 | 1992 |  | G | 59 | The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified organic growth requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. | 1192425 | 2018-07-02T00:00:00 | DH
22/11/2018 | EHQ | Storage Asset Replacement FY 18-19 | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-09-30T00:00:00 | High | 4446000 |  | eHealth Queensland | 5 | 28084 |  | G | 60 | The Server Asset Replacement Project is responsible for replacing prioritised, highly utilised and critical server assets which are coming to, or have reached, end-of-financial-life. | 4446000 | 2018-07-02T00:00:00 | DH
22/11/2018 | MNHHS | Digital Dictation Upgrade Project | 2017-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | Reason for variance: The latest approved budget includes funding for 2018/19 financial year. The go-live date and, therefore, the project end date, has been revised in line with customer expectations. | 2018-10-11T00:00:00 | High | 828522 |  | Metro North | 90 | 976268 |  | G | 61 | To replace the current versions of the Digital Dictation Systems in use at MNHHS facilities with the newest release of the product. The new release introduces efficiencies in the workflow process and contributes to patient care improvement through reduction in timeframe to complete patient letters. | 1048522 | 2016-07-25T00:00:00 | DH
22/11/2018 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Project planned expenditure and end date have been revised due to a number of factors: 22/11/2018, 22/11/2018,- The original planned expenditure of $2.2M was a high level estimate and has been refined with the complexity of the processes and system being uncovered as the project was stood up. 22/11/2018, 22/11/2018,- An increased scope and associated effort to ensure maximum benefit is gained from the investment, so that Queenslanders are better supported during natural disasters. 22/11/2018, 22/11/2018,- Delays to project schedule and associated additional resourcing costs as a result of: 22/11/2018, 22/11/2018, - Staff diverted to priority community recovery support roles during activations over the last 12 months, including TC Debbie, TC Nora and the North Queensland floods. During natural disasters, our agency resources are focused on providing critical support to communities and Queenslanders in need. 22/11/2018, 22/11/2018, - Extended vendor delivery times due to defects and quality concerns including system performance. The department is working with the vendor to resolve these issues. | 2018-10-31T00:00:00 | High | 2208000 |  | Department of Communities, Disabilty Services and Seniors | 89 | 3627000 |  | G | 1 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3780000 | 2016-07-01T00:00:00 | DCCSDS
22/11/2018 | Cross-Gov | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | Workplace Health and Safety module final production validation testing has been completed and module has been released to the business. Handover workshops with the business have been completed. The closure report completed and in review and approval process. 22/11/2018, 22/11/2018,The Queensland Corrective Services Human Capital Management Business Case has been approved with detailed project planning and resource engagement completed. Gate 3 Investment Decision review has also been completed. Project implementation has commenced. 22/11/2018, 22/11/2018,The QFES payroll project transitioning to Aurion is progressing to schedule. As further assurance for a successful transition, planning is underway to incorporate an additional Parallel Pay Run for the QAS payroll project, which is likely to extend the implementation schedule by 3 months to March 2019. The change request associated with this additional testing cycle is pending final approval. Detailed planning of the overall Integration requirements for the program continue to be progressed. 22/11/2018, 22/11/2018,At the direction of the Executive Steering Committee (3/07/18) the program scope was increased to include the procurement of a Time and Attendance solution for QFES, QAS and QCS. An ITO process has been undertaken to determine market suitability to agency requirements. | 2018-08-31T00:00:00 | Critical | 101500000 |  | ICT Strategic Project Coordination | 67 | 61881599 |  | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 22/11/2018, 22/11/2018,* Sustainable and supported HR and Payroll service delivery 22/11/2018,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 22/11/2018,* Strategic HR capability that supports the development, performance and safety of the departments workforce 22/11/2018,* Business Intelligence capability that provides real timely, integrated HR information 22/11/2018,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 22/11/2018,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 22/11/2018,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
22/11/2018 | QPS | GPS Tracking (Bail) | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | Legislation provisioning for GPS monitoring of court bailed offenders commenced on 31/3/18. QPS established interim GPS tracking capability leveraging existing contract held by Queensland Corrective Services. 22/11/2018,QPS is now undertaking a WoG open ITO to establish a longer term contract for GPS tracking devices and monitoring of offenders. 22/11/2018,Note: The project is currently undergoing procurement/commercial activity and is therefore not publishing any financial data. | 2018-10-08T00:00:00 | High | 0 |  | Queensland Police Service | 40 | 0 |  | G | 1 | As per the Commencement of the Bail (Domestic Violence) and Another Act Amendment Act 2017 (the Amending Act) on 30 March 2018, Magistrates will be empowered to impose a tracking condition on a defendant granted bail as a condition of their bail undertaking. 22/11/2018,As such the QPS intends to progressively implement an electronic monitoring capability on a State Wide basis. 22/11/2018,An implementation project has commenced to create an electronic monitoring capability for geographically locating and monitoring a defendant on bail for QPS to meet requirements of the Amended Act. 22/11/2018,The GPS Tracking Project is an initial proposal to validate the utility of the technology prior to seeking a longer term solution. | 0 | 2018-03-30T00:00:00 | QPS
22/11/2018 | QPS | Police Integrity and Professional Standards | 2018-08-24T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | Full funding has now been approved for the Police Integrity and Professional Standards (PIPS) IT system. 22/11/2018, 22/11/2018,The Project has received a green assessment for the Gate 3 Quality Assurance Review. 22/11/2018, 22/11/2018,Feb 18: Note: original planned end date amended as previously published information was incorrect. | 2018-10-15T00:00:00 | High | 4142000 |  | Queensland Police Service | 35 | 337200 |  | G | 2 | This initiative will deliver a new integrated Police Integrity and Professional Standards IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The Police Integrity and Professional Standards system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The Police Integrity and Professional Standards Project will also complement the Complaints Reform Project established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of thePolice Integrity and Professional Standards system will place the QPS in a strong readiness position to fully implement Complaints Reform Project-generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 6792000 | 2017-03-07T00:00:00 | QPS
22/11/2018 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Objectives 22/11/2018, 22/11/2018, 22/11/2018,This project will deliver a secondary DR site and hyper-converged system to provide resilience for all departmental business applications in the event of a disaster. 22/11/2018, 22/11/2018,Project Updates 22/11/2018, 22/11/2018, 22/11/2018,Core infrastructure DR implementation 80% complete. All migrated production systems successfully replicating to secondary DR site. 22/11/2018,Oracle system DR implementation is 100% complete. 22/11/2018,Oracle applications DR testing successfully completed. 22/11/2018,Legacy applications that are incompatible with Core infrastructure platform will be migrated to a new DR-capable environment by end of Nov 2018. 22/11/2018,Security DR implementation in progress. Dependency on provisioning of network connectivity has caused delays. 22/11/2018,All end-of-life ICT infrastructure will be decommissioned by Dec 2018. 22/11/2018,The newly implemented DR infrastructure will provide improved stability and life extension to existing business-critical applications. 22/11/2018,DR recovery procedure development, testing strategy and ICT DR Plan updates almost complete. Awaiting endorsement. 22/11/2018,DJAG DR failover testing has been completed and QCS DR testing scheduled to be completed by end of Nov 2018. 22/11/2018, 22/11/2018,Some issues have impacted YTD position however it is anticipated the original completion date will be met. | 2018-10-30T00:00:00 | High | 7314596 |  | Corporate Services | 90 | 5449744 |  | G | 1 | *Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 6512596 | 2016-10-01T00:00:00 | DJAG
22/11/2018 | BCS | Blue Card Services Recommendation 28.1 Project - Blue Card Home Based Care Register | 2018-12-21T00:00:00 | Delivery |  | 2019-01-31T00:00:00 | In July 2016, the Queensland Family and Child Commission QFCC released the When a child is missing Remembering Tiahleigh - A report into Queensland's children missing from out-of-home care report making 29 recommendations. Recommendation 28 required the QFCC to undertake a further review of legislation, policies and practices relating to information sharing between relevant agencies responsible for children in regulated service environments. 22/11/2018,The Recommendation 28 Supplementary Review, A report on information sharing to enhance the safety of children in regulated home based services (Supplementary Review) is the QFCC response to Recommendation 28 and makes 17 recommendations in relation to information sharing between agencies responsible for regulating and monitoring regulated services provided from the home, namely foster and kinship care, family day care and stand alone care services. 22/11/2018,Implementation of the register will require legislative amendment. | 2018-10-30T00:00:00 | High | 1573000 |  | Blue Card Services | 60 | 860628 |  | G | 2 | The objective of this project is to establish a register for recording and reporting on regulated child-related services provided from the home, specifically limited to foster/kinship care, family day care and stand-alone care. As recommended by the Queensland Family and Child Commission (QFCC) within the Recommendation 28 Supplementary Review Report (A report on information sharing to enhance the safety of children in regulated home-based services) this register will: 22/11/2018,a) identify co-located home-based services 22/11/2018,b) enable the Queensland Police Service to have line of sight to the register to access up-to-date information when Police attend a residential address to identify potential risks to children, and 22/11/2018,c) make information available to agencies, including Department of Child Safety, Youth and Women, Department of Education and the Office of the Public Guardian to assist with regulating and/or monitoring specific home-based services. | 1573000 | 2017-04-01T00:00:00 | DJAG
22/11/2018 | HHS_HH | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery |  | 2019-03-31T00:00:00 | The FOPATS Program undertook a significant re-baseline in late 2016 to inform and approve changes to its strategic direction, scope, delivery methodology, timing and costs, including strengthening program governance and revising the Business Case to complete against a two staged implementation, Property and then Tenancy. 22/11/2018, 22/11/2018,Following this review, the Property Release, the first of two stages, was delivered successfully on time on 1 November 2017 and delivered benefits including efficiencies in property management and reporting. 22/11/2018, 22/11/2018,The refreshed business case, the Program budget and planned end date were formally re-baselined in January 2018. This formal approval, coupled with the successful delivery of the first stage Property Release, saw the Program status move to green. 22/11/2018, 22/11/2018,The Program has completed more detailed planning for the second stage Tenancy Release, which will remove the operational dependency on the existing ICT housing solution entirely. Tenancy design activities are now well progressed, with a view to determining a feasible Program end date. 22/11/2018, | 2018-08-31T00:00:00 | Critical | 56286000 |  | Housing and Homelessness | 63 | 77411261 |  | G | 1 | Replace the existing ICT housing solution with an integrated ICT system. | 121597695 | 2013-07-01T00:00:00 | HPW
22/11/2018 | BPAM_QF | Fleet Management System Replacement Project (FMSRP - QFleet) | 2019-09-30T00:00:00 | Initiate |  | 2019-09-30T00:00:00 | Delays in implementation have resulted from the onboarding of appropriate project resourcing. A senior project manager for the partner agencies has been appointed. Project resourcing issues have been addressed and the procurement activities are being urgently actioned. | 2018-08-31T00:00:00 | High | 13939200 |  | QFleet | 23 | 862206 |  | A | 2 | The objective of the FMSRP is the procurement and implementation of a new common Fleet Management System that meets QFleet, QPS, QFES and QAS core business requirements and provides best value for money. It will provide a contemporary, sustainable common Fleet Management System that delivers effective and efficient business services for the agencies now and into the future. | 13937796 | 2017-10-19T00:00:00 | HPW
22/11/2018 | BPAM_QF | Qfleet Car Sharing Model Implementation Project (CSMIP) | 2018-08-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Procurement activity finalised. Contract negotiations continuing with preferred proponent. 22/11/2018, 22/11/2018,Implementation planning, including system testing, commenced. 22/11/2018, | 2018-08-31T00:00:00 | High | 454735 |  | QFleet | 70 | 92498 |  | A | 3 | The objective of the Car Sharing Model Implementation Project (CSMIP) is the procurement and implementation of a fully automated, innovative and sustainable multi-agency car sharing solution delivering effective and efficient short-term motor vehicle hire services for government, now and in the future. | 454735 | 2017-11-20T00:00:00 | HPW
22/11/2018 | DTS_SSQ | Pay Safe Project | 2018-07-31T00:00:00 | Initiate |  | 2019-03-28T00:00:00 | The project was retitled to the Pay Safe Project (previously called the Automated Payments Solution (APS) Project) and was rebaselined in July 2018 to incorporate a comprehensive market engagement activity that evaluated several options and will necessitate a reassessment of the project implementation schedule. | 2018-08-31T00:00:00 | Critical | 1500000 |  | Smart Service Queensland | 26 | 108238 |  | G | 4 | The project will implement an improved capability for offering secure payment card transactions via the telephone. To meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS) when the new VOIP telephony solution is introduced. | 1500000 | 2018-01-29T00:00:00 | HPW
22/11/2018 | BPAM_BLP | Non-Conforming Building Products (NCBP) Website | 2018-08-31T00:00:00 | Closed |  | 2018-08-31T00:00:00 | Total estimated expenditure has been revised to reflect expected savings. Website successfully went live on 21 August 2018. | 2018-08-31T00:00:00 | Critical | 770924 |  | Building Legislation and Policy | 100 | 735732 |  | G | 10 | Development of a website (the Safer Buildings Website) for private building owners to register and submit information through a self-assessment checklist to assess their buildings for the existence of potentially combustible cladding. | 755178 | 2018-05-01T00:00:00 | HPW
22/11/2018 | DTS_SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery |  | 2018-12-22T00:00:00 | The project exception report for the revised schedule has been approved by the Telephony Replacement Project board. 22/11/2018, 22/11/2018,Managing implementation tasks which are progressing towards completion, including re-testing of penetration test defects. 22/11/2018, 22/11/2018,Engagement and testing with contact centre staff is underway. | 2018-08-31T00:00:00 | Critical | 4490634 |  | Smart Service Queensland | 63 | 3938194 |  | G | 5 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 22/11/2018, 22/11/2018,* reduce operating costs 22/11/2018,* increase capacity 22/11/2018,* improve customer experience 22/11/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | HPW
22/11/2018 | DTS_SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Closed |  | 2018-08-31T00:00:00 | Project closed 31/08/2018 | 2018-08-31T00:00:00 | Critical | 3476245 |  | Smart Service Queensland | 100 | 2252482 |  | G | 6 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2348880 | 2015-11-20T00:00:00 | HPW
22/11/2018 | DTS_SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | SSQ is introducing a new VOIP based telephony platform through the Telephony Replacement Project (TRP). SSQ has also implemented a new agent scripting tool via the Content Delivery Solution (CDS) project. The Technology Platform Project (TPP) is delivering the core underlying technology used by both projects and some other shared ICT centric deliverables, such as Load and Performance Testing, and Security Penetration Testing. The core hardware platform has been successfully delivered and is being fully utilised by CDS and partially utilised by TRP. The TPP is currently awaiting readiness of some TRP deliverables before progressing the final TPP deliverables. 22/11/2018, 22/11/2018,Discussion has commenced with vendors for revised quotes and timeframes. This information will form the basis of a re-baseline of the project with new end dates and final budget. | 2018-08-31T00:00:00 | Critical | 3390861 |  | Smart Service Queensland | 82 | 2510036 |  | A | 7 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution and the call recording solution. | 3390862 | 2017-05-15T00:00:00 | HPW
22/11/2018 | DTS_SSQ | Digital Archiving Program - Tranche 1 | 2019-12-30T00:00:00 | Ended |  | 2018-08-10T00:00:00 | Procurement stage closed on 10 August 2018. Digital Archiving As-a-Service contract was executed on 6 August 2018. This will be the final published update on the Digital Archiving Program Procurement Stage. 22/11/2018, 22/11/2018,A new project 'Digital Archiving Program Tranche 1 Transition-In' has commenced and is being reported on the Dashboard. 22/11/2018, 22/11/2018,The expenditure remaining at close of the Procurement Stage will be used for Tranche 1 Transition-In and for two (2) years of ongoing service support and maintenance. | 2018-08-31T00:00:00 | Critical | 12701000 |  | Digital Technology and Services | 100 | 2003483 |  | G | 8 | To ensure the delivery of an as-a-Service eco-system to effectively archive, manage and enable search and discovery of Queensland's permanent high value records. The new digital services will support the Queensland Government's blueprint for innovation and collaboration, providing better outcomes for Queenslanders. | 12701000 | 2017-07-01T00:00:00 | HPW
22/11/2018 | DTS_SSQ | Customer Identity and Details Enhancements FY17-18 | 2018-10-30T00:00:00 | Delivery |  | 2019-03-01T00:00:00 | Following a security assessment performed by an external organisation, additional recommendations were identified to improve security capabilities of the platform and will require architectural design changes. The current scoping and potential implementation of design changes have required amendment to the planned project end date and adjustment to the current project status. | 2018-08-31T00:00:00 | High | 1200000 |  | Smart Service Queensland | 75 | 1459000 |  | A | 9 | Improved technology and functionality to meet agency requirements in customer identity and details to enable agency adoption and uptake driving further value for customers. 22/11/2018, 22/11/2018,* CDM Blueprint 22/11/2018,* Transition to new platform 22/11/2018,* Auth pilot 22/11/2018,* CDM release 2 pilot | 1200000 | 2017-07-01T00:00:00 | HPW
22/11/2018 | CS_CIO | ICT Infrastructure Refresh Project | 2018-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | Progressing as planned. | 2018-08-31T00:00:00 | Medium | 1173338 |  | Chief Information Office | 99 | 833048 |  | G | 11 | To upgrade ICT infrastructure to maintain a fully supported and secure environment and leverage and take advantage of offerings from current DHPW licencing agreements. | 1173338 | 2017-02-13T00:00:00 | HPW
22/11/2018 | DTS_ICTSS | Government Wireless Network Contract and Administration Billing System | 2018-06-30T00:00:00 | Initiate |  | 2019-06-30T00:00:00 | There is a requirement to develop a requirements specification for the Government Wireless Network (GWN) Contract and Administration Billing System. Originally this digital project was being resourced by existing staff within the GWN Contract Directorate, therefore no expenditure has occurred to date. The procurement process has been delayed for the same reason, but has recommenced now that a Project Manager has been sourced and commenced employment. 22/11/2018, 22/11/2018,The next stage in the project had been delayed to September 2018, has now commenced and therefore the end date has moved to 30 June 2019. | 2018-08-31T00:00:00 | High | 0 |  | ICT Strategic Sourcing | 15 | 0 |  | G | 12 | The GWN Contract Directorate seeks a fully managed software-as-a-service solution to replace existing excel spreadsheets and macros that have organically grown in complexity, improve record keeping compliance, and alleviate current single points of failure and reliance. This project is to procure a purposely designed software system that is fully functional, customisable, redundant, reliable, will meet the current and future requirements of the GWN Contract, and replace current Contract Modification and Contractor Performance processes. | 0 | 2017-11-01T00:00:00 | HPW
22/11/2018 | DTS_DAP | Digital Archiving Program Tranche 1 Transition-In | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | Tranche 1 Transition-In is the next activity for the Digital Archiving Program (DAP). 22/11/2018, 22/11/2018,Tranche 1 Transition-In commenced on 7/08/2018 following the execution of the Digital Archiving as-a-Service Contract on 6/08/2018. 22/11/2018, 22/11/2018,The DAP previously reported the Procurement Stage on the Dashboard and closed the reporting line when the Procurement Stage was completed at the time of contract execution. 22/11/2018, 22/11/2018,Tranche 1 is progressing well. State-Supplier engagement has been established and is working effectively. Qld State Archives are positive and enthusiastic and ready to actively contribute to Transition-In. 22/11/2018, 22/11/2018,The expenditure remaining at close of the Procurement Stage will be used for Tranche 1 Transition-In and for two (2) years of ongoing service support and maintenance. 22/11/2018, 22/11/2018, | 2018-08-31T00:00:00 | Medium | 8186387 |  | Digital Archiving Program | 6 | 205557 |  | G | 13 | Deliver archival management and control capability with access, search and discovery for use by QSA, Public Authorities and the Public | 8186387 | 2018-08-07T00:00:00 | HPW
22/11/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 22/11/2018, 22/11/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 22/11/2018,October 2017 - The project is progressing as planned. 22/11/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 22/11/2018,June 2017 - Revised Schedule approved returning the project to Green. 22/11/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 22/11/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 22/11/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 22/11/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 22/11/2018,December 2016 - The project is progressing as planned. | 2017-12-21T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 22/11/2018, 22/11/2018,* register and maintain their information 22/11/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
22/11/2018 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 22/11/2018, 22/11/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 22/11/2018,August 2017 - Approved extension of timeframe. 22/11/2018,June 2017 - The project is progressing as planned. 22/11/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 22/11/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 22/11/2018,October 2016 - Progress is continuing as planned. 22/11/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 22/11/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 22/11/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-21T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 22/11/2018, 22/11/2018,* support compliance with legislation 22/11/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 22/11/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 22/11/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 22/11/2018, | 1390000 | 2012-04-01T00:00:00 | DEWS
22/11/2018 | BQCC | Communication and Stakeholder Engagement Solution | 2018-04-27T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Timeframe will be exceeded due to resourcing issues. This has affected key capability to perform testing and the finalisation of procedures and supporting documentation. A review of timeframe and associate costs is underway. 22/11/2018, 22/11/2018,September 2018 - Timeframe is being monitored closely due to business demands impacting testing and completion of documentation. Project closure is now planned by 30 September 2018. 22/11/2018,August 2018 - The project is progress as planned and is on schedule. 22/11/2018,July 2018 - An extension to the planned end date and additional budget has been approved by the governance committee. 22/11/2018,June 2018 - Hidden complexities around integration with other solutions has affect the timing of user acceptance testing and training schedules. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 22/11/2018,May 2018 - A change to the planned end date and cost has been approved. 22/11/2018,March 2018 - Note adjustment to planned end date corrected due to typographical error. 22/11/2018,February 2018 - The project is progressing as planned. 22/11/2018,December 2017 - The project was approved to move into delivery in October 2017 and is being published for the first time. | 2018-10-12T00:00:00 | Medium | 694000 |  | Biosecurity Queensland Control Centre | 97 | 1011823 |  | R | 1 | Implement a simple, easy to use system that will facilitate the collection of information associated with the National Red Imported Fire Ant Eradication Program and the National Electric Ant Eradication Program. This will include contact management, complaints management, history of interactions, event management, training management, social media interactions, marketing campaign and reporting. | 1048849 | 2017-06-01T00:00:00 | DAF
22/11/2018 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The project is progressing as planned and is on schedule. 22/11/2018, 22/11/2018,July 2018 - The project has re-commenced. Approval has been granted for an extension to the planned end date, and an increase in associated costs. 22/11/2018,June 2018 - Field testing has identified unexpected issues that will impact on the planned end date. Effort is underway with Microsoft to apply a technical fix (patch) to resolve errors. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 22/11/2018,April 2018 - An extension to the planned end date has been approved, returning the project status to Green. 22/11/2018,March 2018 - A minor scope increase has been proposed, affecting both timeframe and cost, which is progressing through the governance process. 22/11/2018,March 2018 - The project is progressing as planned. 22/11/2018,December 2017 - A variation to scope was approved, resulting in a change to the planned end date and total estimated expenditure. 22/11/2018,November 2017 - The project is continuing as planned. 22/11/2018,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2018-10-12T00:00:00 | Medium | 608146 |  | Forestry Queensland | 91 | 1044863 |  | G | 2 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 22/11/2018, 22/11/2018,* the capture, management and integration of data 22/11/2018,* value-adding opportunities for business improvement 22/11/2018,* management of risk associated with ongoing use and maintenance of disparate systems. | 1696431 | 2016-06-15T00:00:00 | DAF
22/11/2018 | FQ | Novel Commercial and Recreational Fishing Apps | 2018-09-30T00:00:00 | Delivery |  | 2019-01-31T00:00:00 | The project is progressing as planned and is on schedule. Note: the approved end date has been updated in accordance with the approved business case. 22/11/2018, 22/11/2018,September 2018 - Contract documentation has been finalised and the first two development cycles are under way. 22/11/2018,August 2018 - The project was approved to move to delivery in July 2018 and is publishing for the first time. | 2018-10-12T00:00:00 | High | 450000 |  | Fisheries Queensland | 40 | 229106 |  | G | 3 | * Provide up-to-date information on the rules and regulations about fishing and marine park zoning in Queensland 22/11/2018,* Achieve better compliance through access to information 22/11/2018,* Increase uptake of the App by providing regulations from other marine agencies 22/11/2018,* Resolve issues with offline access to information. | 450000 | 2018-02-01T00:00:00 | DAF
22/11/2018 | ASQ | Portfolio Activity Reporting Information System | 2018-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The project is progressing as planned and is on schedule. 22/11/2018, 22/11/2018,September 2018 - Extensive stakeholder consultation has been undertaken and included in documentation. 22/11/2018,August 2018 - The project is progressing as planned and is on schedule. 22/11/2018,July 2018 - Project is continuing as planned. 22/11/2018,June 2018 - Refreshed business case approved, the project has been re-baselined returning it to a Green status. 22/11/2018,May 2018 - Funding has been approved to fully implement the project and it is now in delivery. 22/11/2018,February 2018 - The project is paused until a funding source is identified. 22/11/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-10-12T00:00:00 | High | 978000 |  | Agri-Science Queensland | 10 | 360028 |  | G | 4 | Review and consolidate the variety of processes and technologies currently being used to manage the department's research, development and extension, and other projects. | 978000 | 2015-08-13T00:00:00 | DAF
22/11/2018 | BQ | Registered Biosecurity Entity (RBE) Renewal Project | 2019-08-30T00:00:00 | Delivery |  | 2019-08-30T00:00:00 | The project is progressing as planned and is on schedule. 22/11/2018, 22/11/2018,August 2018 - The project was approved to move to delivery in July 2018 and is publishing for the first time. | 2018-10-12T00:00:00 | High | 2821000 |  | Biosecurity Queensland | 8 | 395091 |  | G | 5 | * Develop an efficient end-to-end registration renewal process to allow effective management of renewals 22/11/2018,* Ensure stakeholders are aware of renewal requirements and the importance of maintaining up-to-date information 22/11/2018,* Provide the ability to efficiently communicate with customers about registered biosecurity entity processes and renewals 22/11/2018,* Provide data integration between the online customer portal and the underlying technology solution 22/11/2018,* Minimise administrative overhead. | 2821001 | 2017-11-10T00:00:00 | DAF
22/11/2018 | Ag | Risk Reduction for Customer Service Centre | 2019-04-19T00:00:00 | Delivery |  | 2019-04-19T00:00:00 | The project is progressing as planned and is on schedule. 22/11/2018, 22/11/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-10-12T00:00:00 | High | 1767000 |  | Agriculture | 60 | 958670 |  | G | 6 | Implement a solution to mitigate risk of end of life for the agency's call centre logging application. | 1767000 | 2015-01-30T00:00:00 | DAF
22/11/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
22/11/2018 | PSBA | Emergency Vehicle Priority (EVP) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | Approved scope of EVP rollouts have been completed with vehicle fitouts finished in Rockhampton, Maryborough, Hervey Bay and Gladstone for both Queensland Ambulance Service and Queensland Fire and Emergency Services. Project closure scheduled for completion October 2018. Project scope was expanded to include procurement of a managed service for operational support and maintenance and increasing vehicle deployments to a total of 730 emergency vehicles, resulting in a revised timeframe from the original planned end date of 30-06-2017 to 31-10-2018, and a revised budget from the original expenditure plan of $3.37 million to $4.35 million. | 2018-10-26T00:00:00 | High | 3370000 |  | Public Safety Business Agency | 94 | 4299600 |  | G | 1 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 22/11/2018, 22/11/2018,* Responsive vehicle movements 22/11/2018,* Improve road safety 22/11/2018,* Congestion management 22/11/2018,* Community safety | 4348696 | 2013-01-01T00:00:00 | PSBA
22/11/2018 | OSR | State Penalties Enforcement Registry (SPER) Program | 2017-12-31T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The project completion timeframe has been extended by 6 months, from the end of 2018 to 30 June 2019, with a target go-live date for the new SPER ICT system by May 2019. 22/11/2018,The cost to deliver the new system will be met within the original budget. 22/11/2018,The design and build phase of the new system was completed on time in mid-2018. Vendor system testing and system integration testing with key partner agencies has now been completed. 22/11/2018,Agencies will commence user testing the new system from November 2018. 22/11/2018,The extension of time will allow for extensive user testing with a broad range of fine issuing and referring agencies to ensure the system is reliable and has the highest standard of data integrity and security. 22/11/2018,A significant change management and training program is in progress for both staff and external stakeholders who refer their debts to SPER. | 2018-10-25T00:00:00 | High | 47200000 |  | State Penalties Enforcement Registry | 79 | 57000000 |  | A | 1 | To maintain the integrity of fines as an effective sanction. 22/11/2018,To uphold confidence in the justice system. 22/11/2018,To deliver efficient and effective debt management practices which provide value for money to the State. 22/11/2018, | 62150000 | 2014-01-01T00:00:00 | QR
22/11/2018 | RI | Financial Assurance Information Registry (FAIR) | 2018-07-01T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | The FAIR project was due to be completed by 1 July 2018 to align with commencement of the Financial Provisioning Scheme (FPS). The delivery delay event is marked yes due to a deferral of the legislation to enact the FPS which would permit the scheme to commence. The FAIR project will be operational for FPS commencement. 22/11/2018,The FAIR project required for the FPS commencement is 90 percent complete. Other components of the FPS reforms will be completed in subsequent years. 22/11/2018,The IT system is currently in a testing and maintenance phase ready for eventual scheme commencement. | 2018-09-30T00:00:00 | Medium | 15900000 |  | Insurance Commission | 90 | 8915085 |  | G | 2 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
22/11/2018 | RI | Information Security Program | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The program is on track according to schedule and budget. | 2018-09-30T00:00:00 | Medium | 1960000 |  | Office of the Chief Information Officer | 55 | 673000 |  | G | 3 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 22/11/2018, | 1960000 | 2017-10-16T00:00:00 | QR
22/11/2018 | OSR | Office of State Revenue (OSR) Transformation Program | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | Multiple initiatives in progress focussing on machine learning, analytics, data quality, and business process improvements. 22/11/2018, 22/11/2018,In total 14 digital initiatives have now been successfully delivered, incorporating machine learning tax insights, an intelligent virtual assistant "Sam" across all revenue lines, a series of process automation projects, and the establishment of an enterprise data warehouse allowing OSR to leverage the full value of data in all analytics and intelligence related activities. 22/11/2018, 22/11/2018,Overall program is on track. | 2018-09-30T00:00:00 | High | 73548000 |  | Office of State Revenue | 30 | 19368724 |  | G | 4 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 22/11/2018, 22/11/2018,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 73548000 | 2017-08-01T00:00:00 | QR
22/11/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
22/11/2018 | Corporate Services Improvement Program | Integrated Records Information System (IRIS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | In response to an internal audit review of Transport and Main Road's (TMR) Document Management System (DMS) the Integrated Records and Information System (IRIS) project was stood up in 2015. 22/11/2018,IRIS project was reviewed in 2017, and as a result the project budget was decreased from $7,967,972 down to $6,865,000 (plus contingency) of 10%. 22/11/2018, The project leveraged additional functionality requirements by including TMR's Executive Correspondence System (ECS) replacement into scope. Due to recent risks eventuating, the project has had to absorb additional costs originally scheduled to be offset. | 2018-09-30T00:00:00 | High | 7967972 |  | Corporate Division | 45 | 6404800 |  | A | 1 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 6865000 | 2015-07-01T00:00:00 | TMR
22/11/2018 | Corporate Services Improvement Program | Lotus Notes Decommissioning (OP) | 2016-01-31T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project commenced in October 2015 when concept and stage 1 was approved to engage and investigate business findings around the decommission of legacy lotus notes databases. 22/11/2018,In July 2016, three additional stages aligning to three financial years from 2016/17 through to 2018/19 were further approved via a project initiation and business case. 22/11/2018,Stage 2, 2016/17, focused on analysis and stakeholder engagement to form the scope of the project and define functionality and business requirements for individual applications. 22/11/2018,Stage 3, 2017/18, focused on proof of concepts to inform and validate the plan for stage 4 in 2018/19. The project was impacted in 2017/18 by several resourcing issues, including the departure of the original project manager. 22/11/2018,The project is scheduled to complete work and close down by 30 June 2019, with the exception of the migration of files from the departments legacy Document Management System (DMS). The migration of the DMS will align with the Integrated Records and Information System (IRIS) program and should be complete by the end of 2019. | 2018-09-30T00:00:00 | High | 8150000 |  | Corporate Division | 60 | 3490918 |  | A | 2 | Deliver improved information platform functions for effective ICT Strategy Alignment | 8150000 | 2015-11-01T00:00:00 | TMR
22/11/2018 | Corporate Services Improvement Program | Transactional Services Improvement Program 2018-19 | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | Project successfully commenced 1 July 2018. | 2018-09-30T00:00:00 | High | 400000 |  | Corporate Division | 10 | 89604 |  | G | 3 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. | 400000 | 2018-07-01T00:00:00 | TMR
22/11/2018 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | This commenced in July 2016 with delivery being phased in accordance with the development of the business processes. Original expenditure was 1.5M which has been revised to $1.441M on finalisation and approval of the business case. Phase 1 was completed in July 2017 and the schedule was adjusted in June 2017 to enable the delivery of the Phase 2 capability in mid 2019. 22/11/2018, 22/11/2018,The project is currently on track. | 2018-09-30T00:00:00 | High | 1500000 |  | Customer Services, Safety and Regulation Division | 90 | 1018266 |  | G | 4 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal services currently required. | 1441000 | 2016-01-01T00:00:00 | TMR
22/11/2018 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | The project commenced in mid 2015 with an initial exploratory phase, initially scheduled for delivery in mid 2016. Due to the uncertainty of the solution outcome and market capability the project undertook a multi stage market engagement and procurement process. Once the solution had been fully defined, the schedule was extended by 11 months and the budget increased from $2.5M to $4.1M in January 2017. 22/11/2018, 22/11/2018,Development is now complete. A pilot phase has been successfully completed. The project is now conducting final testing and preparing for a full launch. An Exception Report was approved to extend the end date to 31 October 2018 and an addtional $98k which was approved by the CSSR PB on 29 August 2018. The project is on track to be closed by October 2018. 22/11/2018, 22/11/2018, | 2018-09-30T00:00:00 | High | 2500000 |  | Customer Services, Safety and Regulation Division | 96 | 4191537 |  | G | 5 | Implement an online learning and assessment program at the prelearner and/or learner stage, to enhance learning and outcomes for new drivers. | 4274000 | 2015-06-12T00:00:00 | TMR
22/11/2018 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery |  | 2018-06-28T00:00:00 | This commenced in November 2016 with planned completion in mid 2017. Due to an extended procurement process, and the need to include analytical functionality, the schedule was extended 12 months and the budget increased from $300k to $894k in August 2017. The capability was delivered as scheduled in June 2018 and the project is presently finalising closure with formal closure scheduled for August 2018. However, this is taken longer than expected and may require a re-baseline on schedule in the closure report. 22/11/2018,Project will be closed in October 2018. 22/11/2018, | 2018-09-30T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 99 | 1016536 |  | G | 6 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 989237 | 2016-11-01T00:00:00 | TMR
22/11/2018 | Customer Service, Safety and Regulation Program | Customer Flow Mgmt and Reporting System | 2018-06-30T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | Preproject work commenced during FY15/16 with the initiation of the current project commencing in July 2017. The original budget of 300K was rebaselined to 3M once the post-market business case was finalised and approved to proceed in May 2018. 22/11/2018,The project is on track for delivery to occur within FY18/19. | 2018-09-30T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 75 | 1972536 |  | G | 7 | Replacement of the existing statewide network of customer flow management and reporting systems which is currently supplied by QMatic Australia and will be unsupported in 2017. CSB currently have 43 CSCs around the state that use QMatic systems. Replacement of the existing statewide customer flow management and reporting system which is currently supplied by QMatic Australia and will be unsupported in 2017. | 3083000 | 2015-09-01T00:00:00 | TMR
22/11/2018 | Customer Service, Safety and Regulation Program | Call Centre VOIP Upgrade | 2018-06-30T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Project commenced in July 2017. Due to a resourcing issue. Approval was given to amend the implementation date from June 2018 to August 2018. | 2018-09-30T00:00:00 | High | 1140000 |  | Customer Services, Safety and Regulation Division | 99 | 1073628 |  | G | 8 | The Call Centre VOIP Upgrade has commenced to upgrade the VOIP telephony platform within the department. The proposed solution will see a reduction in call costs, a shift in capability to a contemporary solution utilising an existing investment within the department. | 1140000 | 2017-04-01T00:00:00 | TMR
22/11/2018 | Customer Service, Safety and Regulation Program | Smart Licence Card | 2018-08-21T00:00:00 | Delivery |  | 2019-03-31T00:00:00 | Gate 3 investment decision was approved by 24 May ISC. End of contract has been signed. Project are working on delivery. | 2018-09-30T00:00:00 | High | 723000 |  | Customer Services, Safety and Regulation Division | 82 | 1501154 |  | G | 9 | The project is responsible for managing business analysis and requirements specification activities, developing relevant procurement documentation, overseeing the identification and selection of a suitably qualified vendor, facilitating the transfer of contract management responsibilities from Information Technology Branch (ITB) to Transport Regulation Branch (TRB), and managing the complete transition to a new solution before the extended contract expiry date. The estimated cost for the project is $1.68M over three (3) financial years. | 2717000 | 2016-07-01T00:00:00 | TMR
22/11/2018 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The RALPH project commenced in July 2016. Due to vendor software development issues, changes to the schedule and budget were approved in June 2017. The project is currently over schedule and reporting red. The project is working on rebaselining which is expected to be finalised by November 2018. | 2018-09-30T00:00:00 | Medium | 500000 |  | Customer Services, Safety and Regulation Division | 87 | 756494 |  | R | 10 | TMRs current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace the existing application with a contemporary and supportable alternative to assist the department in maintaining its timely updating of fees and charges. | 734000 | 2016-07-01T00:00:00 | TMR
22/11/2018 | Customer Service, Safety and Regulation Program | Vessel Traffic Services (VTS) | 2016-01-05T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | Preproject work commenced in April 2014 with the initiation of the current project commencing in July 2016. The original budget of $15.2M was rebaselined to $36.2M once the post-market business case was finalised and approved to proceed in April 2017. 22/11/2018, 22/11/2018,The project is on track for delivery in mid 2019. | 2018-09-30T00:00:00 | High | 15224694 |  | Customer Services, Safety and Regulation Division | 55 | 6209775 |  | G | 11 | Replacement of TIM and surface picture software for Reef VTS Phase 1 for the replacement of TIM and surface picture software for Reef VTS. | 36228184 | 2014-04-14T00:00:00 | TMR
22/11/2018 | Customer Service, Safety and Regulation Program | Registration and CTP Certificates Online | 2017-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | The Registration and CTP Certificates Online project commenced in May 2017 as two separate initiatives Registration Online and CTP Tax Invoice Online. Due to common system synergies the projects were merged in March 2018 resulting in the closure date being revised in accordance with the CTP component. An Exception Report was approved to extend the end date to 31 December 2018 and an addtional $233k which was approved by the CSSR PB on 29 August 2018. The project is on track for delivery and closure in late 2018. | 2018-09-30T00:00:00 | Medium | 0 |  | Customer Services, Safety and Regulation Division | 67 | 483728 |  | G | 12 | Create an online service for customers to email or print their registration certificate and CTP tax invoices, to provide customers with more convenience, and reduce reliance on paper and post. | 637000 | 2017-05-01T00:00:00 | TMR
22/11/2018 | Customer Service, Safety and Regulation Program | R and L Systems Software Upgrade - Stage 2 | 2018-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | The R and L System Software Upgrade project commenced in July 2017. The original budget of $780K was rebaselined to $1.255M once the post-market business case was finalised and approved to proceed in September 2017. Delivery was completed as scheduled in June 2018. Project was officially closed on 3 September 2018. | 2018-09-30T00:00:00 | Medium | 780000 |  | Customer Services, Safety and Regulation Division | 100 | 1115450 |  | G | 13 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
22/11/2018 | Passenger Transport Technology Program | Single Integrated Network Project (SNIP) | 2018-09-29T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | Software upgrade for TransLink users planned to complete in September. Rollout of the system to SEQ bus service providers to commence in November. Delays in vendor negotations and reduction in scope has triggered an exception report and rebaselining of the project scope, schedule and budget. An updated project plan has been approved by the governance board. | 2018-09-30T00:00:00 | High | 4992243 |  | TransLink Division | 32 | 858604 |  | G | 14 | Enable implementation of performance based contracts for SEQ buses 22/11/2018,Have a system in place that is consistent and integrated across service providers and TransLink 22/11/2018,Reduce or remove inefficiencies and data inaccuracies that occur in the current processes 22/11/2018,Improve transparency of SEQ bus service providers activities and performance 22/11/2018,Improved customer experience through more accurate and reliable SEQ bus service information 22/11/2018,To improve customer experience through more accurate and reliable service information. 22/11/2018,Contributor for achieving Government objectives. | 3637240 | 2017-02-23T00:00:00 | TMR
22/11/2018 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery |  | 2019-08-30T00:00:00 | Original project commenced in April 2016. 22/11/2018,Budget shortfall identified in November 17. 22/11/2018,In March 18 issues in gathering business data and requirements for new functionality identified. 22/11/2018,The STAS project is reporting amber as a result of unforeseen complexities associated with provisioning and transitioning of business supplied data to the new platform. The project is experiencing delays as resolution activities take place to ensure a good customer experience when the project is released to the public. 22/11/2018,The Project Board approved an exception plan in September which will enable products to be completed and released by the end of March 2019. | 2018-09-30T00:00:00 | High | 4166000 |  | TransLink Division | 68 | 5399590 |  | G | 15 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 6459560 | 2016-04-01T00:00:00 | TMR
22/11/2018 | CS | Asset Assessment System | 2016-06-30T00:00:00 | Delivery |  | 2019-02-15T00:00:00 | The project is reviewing requirements and schedule before commencing next stage. | 2018-09-11T00:00:00 | Medium | 1688788 |  | Corporate Services | 82 | 1890702 |  | G | 1 | To improve the reliability and integrity of asset information, the ability to report on asset information by applying best practice asset management principles. | 2179995 | 2014-02-27T00:00:00 | DET
22/11/2018 | CS | Automated Website Provisioning Tool | 2018-12-21T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | Medium | 1300000 |  | Corporate Services | 95 | 1200818 |  | G | 2 | To reduce the cost and time required to create new school and corporate websites by developing a tool that provisions new websites from a suite of reusable website templates. | 1242160 | 2017-04-03T00:00:00 | DET
22/11/2018 | CS | Copper Disconnection Management | 2021-06-30T00:00:00 | Delivery |  | 2021-06-30T00:00:00 | The project moved into Delivery in August 2018. The project is tracking to plan. | 2018-09-11T00:00:00 | Low | 2155000 |  | Corporate Services | 25 | 1036571 |  | G | 3 | The project will migrate all copper based services mandated for disconnection to an appropriate replacement technology within the required timeframes specified by nbnTM and Telstra ensuring services are not incorrectly disconnected. | 2155000 | 2017-07-03T00:00:00 | DET
22/11/2018 | PPP | Customer Complaints Management System | 2018-12-21T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | Medium | 2753000 |  | Policy, Performance and Planning | 73 | 680439 |  | G | 4 | Improve the management and reporting of customer complaints. | 2753000 | 2017-09-11T00:00:00 | DET
22/11/2018 | SS | Early Start | 2015-07-03T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | Medium | 70000 |  | State Schools | 47 | 73522 |  | G | 5 | To provide schools with enhanced reporting functionality, improving their ability to analyse Prep to Year 2 student learning data. | 200992 | 2013-04-03T00:00:00 | DET
22/11/2018 | PPP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Delivery |  | 2018-09-24T00:00:00 | The project is tracking to plan. Schedule change approved by project board. | 2018-09-11T00:00:00 | High | 700000 |  | Policy, Performance and Planning | 96 | 1474100 |  | G | 6 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
22/11/2018 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery |  | 2018-12-13T00:00:00 | The project is tracking to plan. Schedule change approved by project board. | 2018-09-11T00:00:00 | High | 659131 |  | Corporate Services | 71 | 408409 |  | G | 7 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DoE FBS SAP future state landscape for the next five years. | 619866 | 2017-01-16T00:00:00 | DET
22/11/2018 | CS | Injury Management System | 2017-03-27T00:00:00 | Delivery |  | 2018-10-01T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | Critical | 1900000 |  | Corporate Services | 67 | 1547593 |  | G | 8 | To improve the management of workplace rehabilitation and claims for injured/ill staff | 1828676 | 2016-10-10T00:00:00 | DET
22/11/2018 | ODG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery |  | 2018-10-01T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | Low | 632585 |  | Office of the Director-General | 91 | 877369 |  | G | 9 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
22/11/2018 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | Critical | 16670000 |  | State Schools | 55 | 12241064 |  | G | 10 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 18115935 | 2015-08-03T00:00:00 | DET
22/11/2018 | ECCE | National Quality Standard Assessment and Rating Data Tool | 2018-12-13T00:00:00 | Delivery |  | 2018-12-17T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | High | 467900 |  | Early Childhood and Community Engagement | 50 | 146304 |  | G | 11 | To improve the security and functionality of the tool used for the assessment and quality improvement of early childhood education and care centres. | 467900 | 2018-02-22T00:00:00 | DET
22/11/2018 | PPP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | High | 1502300 |  | Policy, Performance and Planning | 97 | 1250201 |  | G | 12 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution. | 1266210 | 2016-03-01T00:00:00 | DET
22/11/2018 | PPP | Online School Data Profile | 2018-06-30T00:00:00 | Delivery |  | 2020-02-28T00:00:00 | The project moved into Delivery in August 2018. The project is tracking to plan. | 2018-09-11T00:00:00 | Low | 1872000 |  | Policy, Performance and Planning | 16 | 470788 |  | G | 13 | Improved data interaction capabilities for stakeholders accessing school data profiles. Improved efficiency in production and distribution of information contained in school data profiles. | 1700000 | 2017-10-02T00:00:00 | DET
22/11/2018 | PPP | Redevelopment of the Policy and Procedure Register | 2018-03-30T00:00:00 | Delivery |  | 2018-12-14T00:00:00 | The project is being closely monitored for cost, quality and schedule. Schedule change approved by project board. | 2018-09-11T00:00:00 | Medium | 1015000 |  | Policy, Performance and Planning | 76 | 935767 |  | A | 14 | The high level principles endorsed by EMB for the policy management framework which provides the foundation for this initiative include a consistent user experience for customers, regardless of who they are, where they work, and what they may be looking for; a single point of truth, providing access to all departmental policies and procedures; and publish once, with multiple links where appropriate; and that content is authoritative, relevant and meets quality standards for publication, enabling staff and stakeholders to make good decisions. 22/11/2018, | 935765 | 2016-10-13T00:00:00 | DET
22/11/2018 | CS | SABA Platform Upgrade | 2017-11-09T00:00:00 | Delivery |  | 2019-02-12T00:00:00 | The project moved into Delivery in August 2018. The project is tracking to plan. | 2018-09-11T00:00:00 | Medium | 1791556 |  | Corporate Services | 75 | 1641079 |  | G | 15 | The objective of the project is to replace the existing system, currently hosted on obsolete technology, which is at end-of-service-life. In its current state, the system represents a significant business risk, due to the likelihood of increased system failures, further leading to ongoing business outages and increased maintenance and support costs. | 2303846 | 2017-08-01T00:00:00 | DET
22/11/2018 | SS | Trial of Platform for Virtual Academies | 2017-10-02T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | High | 151641 |  | State Schools | 87 | 236700 |  | G | 16 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage; safe and secure like-minded student virtual communities; and strategic partnerships with university, industry and business. 22/11/2018, 22/11/2018, | 141641 | 2016-06-21T00:00:00 | DET
22/11/2018 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | High | 41000000 |  | Corporate Services | 89 | 34998163 |  | G | 17 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
22/11/2018 | OIR | Information Management/Records Management | 2018-12-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | The project moved into Delivery in July 2018. The project is tracking to plan. | 2018-07-30T00:00:00 | High | 1259381 |  | Office Of Industrial Relations | 75 | 796878 |  | G | 18 | This project will deliver an electronic document and records management system (eDRMS) across OIR.nt. | 1259381 | 2017-07-03T00:00:00 | DET
22/11/2018 | OIR | Investigations Management System | 2018-12-14T00:00:00 | Delivery |  | 2018-12-14T00:00:00 | The project moved into Delivery in July 2018. The project is tracking to plan. | 2018-07-30T00:00:00 | Critical | 461742 |  | Office Of Industrial Relations | 25 | 268369 |  | G | 19 | This project will deliver a case management solution for the OIR Investigations unit. | 644711 | 2017-01-07T00:00:00 | DET
22/11/2018 | OIR | Renewal and Photographic Licensing System (RAPS) Assessor Portal | 2018-07-13T00:00:00 | Delivery |  | 2019-09-03T00:00:00 | The project is tracking to plan. | 2018-07-30T00:00:00 | High | 766467 |  | Office Of Industrial Relations | 47 | 716953 |  | G | 20 | The Assessor Portal project will deliver an improved online services for high risk work licensing accredited assessors, registered training organisations and licensing and advisory services. Currently accredited assessors must use a combination of cumbersome paper based processes, smart forms, and an online service that is difficult to use. | 971488 | 2016-12-14T00:00:00 | DET
22/11/2018 | [20 empty] | INVERSTMENT INFO
22/11/2018 | ICRM | Integrated Customer and Revenue Management (ICRM) | 2018-03-30T00:00:00 | Delivery |  | 2021-03-30T00:00:00 | The project is continuing as planned and is on schedule. Update to the Planned End Date made to match approved business case not previously reported. 22/11/2018, 22/11/2018,October 2018 - The project is continuing as planned and is on schedule. 22/11/2018,August 2018 - This project is reporting for the first time and is progressing as planned. | 2018-11-12T00:00:00 | High | 24511345 |  | DNRM Finance | 9 | 3866599 |  | G | 1 | Improvements to the way the agency handles revenue collection: 22/11/2018, 22/11/2018,* selection of a modern, enterprise-class, integrated customer and revenue management solution 22/11/2018,* implementation and deployment of the solution to replace the use of the current at-risk receipting systems. | 24511345 | 2017-01-01T00:00:00 | DNRM
22/11/2018 | QWSR | Dam Safety Regulation Solution | 2016-10-30T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | The project is continuing as planned and is on schedule. 22/11/2018, 22/11/2018,October 2018 - An extension to the approved end date has been endorsed, with no impact on cost. 22/11/2018,September 2018 - Documentation is being finalised; the project remains within accepted tolerances. 22/11/2018,August 2018 - A change request has been approved altering the planned end date to enable completion of end project activities. 22/11/2018,July 2018 - All deliverables have been achieved. Project closure activities are currently under way. 22/11/2018,June 2018 - A change request has been approved altering the planned end date to remediate technical difficulties that have been experienced in the move to production. 22/11/2018,May 2018 - The project is continuing within timeframe tolerance, and is expected to close prior to the end of May 2018. 22/11/2018,March 2018 - The project is continuing as planned. 22/11/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 22/11/2018,August 2017 - Approved extension of timeframe. 22/11/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 22/11/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 22/11/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 22/11/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 22/11/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2018-10-12T00:00:00 | High | 1390000 |  | Queensland Water Supply Regulator | 98 | 1385060 |  | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 22/11/2018, 22/11/2018,* support compliance with legislation 22/11/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 22/11/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 22/11/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. | 1390000 | 2012-04-01T00:00:00 | DNRM
22/11/2018 | Natural Resources | Land Condition Assessment Tool | 2018-04-30T00:00:00 | Delivery |  | 2019-01-25T00:00:00 | The project is currently Amber due to some features being incomplete. 22/11/2018, 22/11/2018,October 2018 - An extension to the approved end date has been endorsed, with no impact on costs. Note the change to the percentage complete, aligning with deliverable achieved thus far. 22/11/2018,September 2018 - An extension to the project end date has been approved to accommodate vendor resource constraints. There is no impact to cost. Discussions are under way with the vendor to ensure resourcing constraints will not impact quality, or further delay delivery. 22/11/2018,August 2018 - The project is continuing as planned, tracking within tolerances for time, cost and quality. 22/11/2018,June 2018 - A change request has been approved altering the planned end date and budget to allow for resolution of unforeseen complexities in deliverables. 22/11/2018,May 2018 - The project timeframe is currently being monitored, with action under way to return it to Green. 22/11/2018,April 2018 - This project is reporting for the first time and is progressing as planned. | 2018-10-31T00:00:00 | Medium | 414000 |  | Operations Support | 70 | 161671 |  | A | 3 | Implement a solution for government, industry and other stakeholders to objectively and consistently assess land conditions, including development of a pictogram-based mobile web application and a data collection tool. | 479000 | 2017-01-12T00:00:00 | DNRM
22/11/2018 | CWeHR | Coal Workers eHealth Records Project | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | The project is progressing with a small adjustment to the expenditure made due to the timing of payment processing. 22/11/2018, 22/11/2018,October 2018 - The project is continuing as planned, tracking within project tolerances. 22/11/2018,August 2018 - This project is reporting for the first time and is progressing as planned. Note finances reported represent Stage 0 and Stage 1. | 2018-11-01T00:00:00 | High | 3894285 |  | Occupational Health and Hygiene - Resources Safety and Health | 5 | 1048426 |  | G | 4 | Improvement in data management and surveillance for coal mine worker health assessments: 22/11/2018, 22/11/2018,* new customer digital interface 22/11/2018,* improved health assessment outcomes through improved access to longitudinal health records 22/11/2018,* enable industry-wide health surveillance through electronic storage and access to health records 22/11/2018,* improved data management using appropriate health management systems and alignment with health record management requirements. | 3894285 | 2017-03-23T00:00:00 | DNRM
22/11/2018 | SO | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery |  | 2019-03-29T00:00:00 | The project is progressing as planned. 22/11/2018, 22/11/2018,August 2018 - The project is continuing as planned, tracking within tolerances for time, cost and quality. 22/11/2018,February 2018 - A change request was approved to alter the scope and associated percentage complete, time-frame and costs. 22/11/2018,December 2017 - Awaiting confirmation of project closure; project is still operating within approved time-frame tolerance. 22/11/2018,November 2017 - A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 22/11/2018,October 2017 - The project is continuing as planned. 22/11/2018,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2018-11-06T00:00:00 | High | 563000 |  | SIMTARS (Safety In Mines Testing and Research Station) | 82 | 904889 |  | G | 5 | The development and delivery of a (replacement) modern and robust Safegas solution: 22/11/2018, 22/11/2018,* risk reduction increasing capability to manage the volume of queries, transactions and data 22/11/2018,* decrease database corruption related to incidents. | 1170000 | 2017-01-25T00:00:00 | DNRM
22/11/2018 | MIRM | Mines Infrastructure Risk Mitigation Project | 2019-02-18T00:00:00 | Closed |  | 2019-02-28T00:00:00 | All deliveries completed for the project with the project approved to close early on 12 November 2018. 22/11/2018, 22/11/2018,October 2018 - The project is ahead of schedule, therefore a change has been endorsed to reduce the approved expenditure. 22/11/2018,September 2018 - The project is progressing as planned. 22/11/2018,August 2018 - The project is continuing as planned, tracking within tolerances for time, cost and quality. 22/11/2018,April 2018 - A minor adjustment to scope has been approved; there is no impact to timeframe or cost. 22/11/2018,March 2018 - The project is continuing as planned. 22/11/2018,November 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-11-13T00:00:00 | High | 1200000 |  | Statewide Operations | 100 | 772200 |  | G | 6 | Migrate systems to supported infrastructure and software to: 22/11/2018, 22/11/2018,* provide a stable, secure, fully supported and flexible solution 22/11/2018,* eliminate the risks to which the geoscience data assets are currently exposed. | 922500 | 2017-08-08T00:00:00 | DNRM
22/11/2018 | DPC | Performance Information Management System (PIMS) Dynamics 365 upgrade and relocation | 2018-10-30T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | The project commenced in May 2018 and is in the final stages of delivery. The new system is now live and has been rolled out across departments. The final deliverables are scheduled for completion at the end of the warranty period on 30 October 2018. | 2018-10-24T00:00:00 | High | 240494 |  | Premier and Cabinet | 95 | 175641 |  | G | 1 | To upgrade the existing PIMS solution from the current 2013 version to Microsoft Dynamics 365 and move the system to Microsoft Online. | 240494 | 2018-05-01T00:00:00 | DPC
22/11/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
22/11/2018 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 22/11/2018,* Move operational accountability and responsibility for print and imaging devices to the service provider 22/11/2018,* Reduce print and imaging costs 22/11/2018,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
22/11/2018 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
22/11/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
22/11/2018 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 22/11/2018, 22/11/2018,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
22/11/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
22/11/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 22/11/2018, 22/11/2018,* reduce operating costs 22/11/2018,* increase capacity 22/11/2018,* improve customer experience 22/11/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
22/11/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
22/11/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 22/11/2018, 22/11/2018, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
22/11/2018 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 22/11/2018, 22/11/2018,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
22/11/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
22/11/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 22/11/2018, 22/11/2018,November 2017 - Actual cost to date corrected due to input error. 22/11/2018, 22/11/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 22/11/2018, | 2017-12-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 57 | 733941 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
22/11/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | An extension to the timeframe has been approved, due to resources constraints. 22/11/2018, 22/11/2018,September 2018 - Closure activities are being finalised; the project remains within accepted tolerances. 22/11/2018,August 2018 - An extension to the timeframe has been approved to allow for closure activities to be finalised. 22/11/2018,July 2018 - Key deliverables have been achieved within project time-frames. Project closure activities are under way, to be finalised within the next two weeks. 22/11/2018,June 2018 - User acceptance testing is almost complete; the solution is about to move into production with project closure activities under way. 22/11/2018,May 2018 - The project is progressing as planned. 22/11/2018,November 2017 - Actual cost to date corrected due to input error. 22/11/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. | 2018-10-12T00:00:00 | Medium | 1750000 |  | Queensland Parks and Wildlife Service | 98 | 1378661 |  | G | 1 | Acquire one or more solution components to operate in conjunction with the agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | EHP
22/11/2018 | QPWS | Augmented Ranger Mobile Application | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project is progressing as planned. 22/11/2018, 22/11/2018,August 2018 - The project has been approved to commence delivery and is publishing for the first time. | 2018-10-12T00:00:00 | Low | 240000 |  | Queensland Parks and Wildlife Service | 30 | 50772 |  | G | 2 | Develop a unique, mobile, optimised solution that uses Augmented Reality to: 22/11/2018, 22/11/2018,* enrich visitors? on-park engagement, experiences and understanding of cultural, historical and ecological points of interests specific to the location 22/11/2018,* provide opportunities for ranger-visitor communications 22/11/2018,* aid collection of real-time visitor data. | 240000 | 2018-02-01T00:00:00 | EHP
22/11/2018 | EPP | Queensland Waste Disposal Levy System | 2019-05-31T00:00:00 | Delivery |  | 2019-05-31T00:00:00 | The project is progressing as planned. 22/11/2018, 22/11/2018,September 2018 - The project has been approved to commence delivery and is publishing for the first time. | 2018-10-12T00:00:00 | Critical | 2248000 |  | Environment Policy and Planning | 20 | 276883 |  | G | 3 | Implement a solution to meet new legislative arrangements for a waste disposal levy, to effectively and efficiently enable: 22/11/2018, 22/11/2018,* site operators to accurately record data 22/11/2018,* reconciliation of waste data and levy liabilities 22/11/2018,* timely access to, and interrogation of, large datasets. | 2248000 | 2018-07-10T00:00:00 | EHP
22/11/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP
23/10/2018 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-08-31T00:00:00 | High | 5600000 |  | eHealth Queensland | 40 | 3727879 |  | G | 1 | This project aims to establish a robust, highly available and secure contemporary platform that has the capability to support the agile eHealth Strategy. | 5492863 | 2017-07-03T00:00:00 | DH
23/10/2018 | HSQ | Pathology and Forensic Laboratory System Rehosting Project | 2018-06-30T00:00:00 | Delivery |  | 2018-12-13T00:00:00 | August: This project has returned to 'green'. Approval was granted in August to extend the project's schedule to December 2018. 23/10/2018, 23/10/2018,July: This project is now reporting 'red' due to delays to the infrastructure component of the project. Options are being prepared to minimise the impact to the overall schedule and cost of the project, to be approved in August 2018. 23/10/2018, 23/10/2018,May: This project was previously known as the 'AUSLAB Rehosting Project'. This project has now returned to green, after receiving governance approval to extend the schedule and budget. | 2018-09-11T00:00:00 | High | 1691324 |  | Health Support Queensland | 73 | 2316000 |  | G | 2 | Delivery of a replacement hardware and visualisation solution for the AUSLAB and AUSCARE systems that will achieve improved resiliency of the architecture, updated operating system and inclusion of virtualisation. AUSLAB and AUSCARE are critical to support laboratories and patient clinical care. | 2963000 | 2017-08-28T00:00:00 | DH
23/10/2018 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2016-08-01T00:00:00 | Delivery |  | 2018-09-30T00:00:00 |  | 2018-09-14T00:00:00 | High | 3692973 |  | Metro North | 95 | 1737318 |  | G | 3 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 23/10/2018, 23/10/2018,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Women?s Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 23/10/2018, 23/10/2018,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 3692973 | 2015-06-01T00:00:00 | DH
23/10/2018 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-08-31T00:00:00 | High | 11180394 |  | eHealth Queensland | 27 | 631322 |  | G | 4 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 23/10/2018,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work.? Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 10915391 | 2017-07-03T00:00:00 | DH
23/10/2018 | EHQ | Critical Network Hardware | 2018-02-28T00:00:00 | Closed |  | 2018-08-31T00:00:00 | August: This project is now complete. The project has replaced a number of end-of-life core switches across 20 facilities, resulting in increased stability of network infrastructure and increased available bandwidth for clinical and business applications. 23/10/2018, 23/10/2018,February: This project has returned to 'on track'. 23/10/2018, 23/10/2018,January: The project is reporting 'Amber' due to limited resource availability and additional technical requirements, impacting the schedule of the project | 2018-08-31T00:00:00 | High | 8636364 |  | eHealth Queensland | 100 | 8242363 |  | G | 5 | The objectives of the project include: 23/10/2018,a) Mitigate the Department of Health risk that core network switches at QH facilities will no longer be supported by the manufacturer from February 2018. 23/10/2018,b) Invest in the replacement of critical ICT network hardware to maintain current capability and reliability of the data network for 120+ enterprise clinical and business applications and provide the foundation for future capability in the enterprise data centres. 23/10/2018,c) Ensure hardware replacement occurs with minimal impact to business operations in Hospital and Health Services or Corporate offices. 23/10/2018,d) Update logical and physical design and architecture documentation for ease of maintenance and management. | 8360652 | 2017-03-06T00:00:00 | DH
23/10/2018 | EHQ | Digital Collaboration Platform Program | 2018-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | May: This project has now returned to 'green' with the project's revised schedule being approved. 23/10/2018, 23/10/2018,March: Project activities have continued to be delayed, resulting in this project reporting 'Red'. A project change request has been submitted to the project's governance committee. Successful deployment was recently achieved in Townsville. 23/10/2018, 23/10/2018,January: This project is experiencing delays in pre-migration activities. 23/10/2018, 23/10/2018,Reason for variance: Original budget was reflective of an original estimate based on high level planning. Detailed planning has since refined the estimated budget (including vendor licensing arrangements) which received approval for budget increase in June 2017. | 2018-08-31T00:00:00 | High | 11000000 |  | eHealth Queensland | 36 | 17043888 |  | G | 6 | This program will deliver digital collaboration tools for any time, any where, any device including: 23/10/2018,? Email and Archiving 23/10/2018,? Establishment and Collaboration 23/10/2018,? Productivity Suite Enablement | 22664506 | 2015-10-29T00:00:00 | DH
23/10/2018 | EHQ | Infrastructure Maintenance Program Establishment | 2018-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | March: This initiative has been refocused to the establishment phase of the Infrastructure Maintenance Program, and as such the % complete and original end date have been updated to reflect this phase of the program. The latest approved end date will be updated in a following reporting month. | 2018-08-31T00:00:00 | High | 1161415 |  | eHealth Queensland | 86 | 1115627 |  | G | 18 | The Infrastructure Maintenance Program (IMP)?will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 23/10/2018,The scope includes: 23/10/2018,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 23/10/2018,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and? 23/10/2018,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1922376 | 2017-07-03T00:00:00 | DH
23/10/2018 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate |  | 2017-12-31T00:00:00 | June: The current proposed date of completion is the 31 December 2019, which is subject to project board approval. 23/10/2018, 23/10/2018,Reason for variance: The original estimated expenditure was projected prior to the Request for Information (RFI) to the open market. Consequently, the planned expenditure was revised based on the market responses following the RFI. | 2018-09-11T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 40 | 645197 |  | G | 7 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 5697000 | 2015-12-01T00:00:00 | DH
23/10/2018 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | May: The project has completed a solution evaluation process, with the project requiring additional schedule and financials as originally approved. The project is expecting to return to 'green' upon receiving change request approval. 23/10/2018, 23/10/2018,April: Further solution clarification is required, which has impacted on the overall delivery timeframe of this initiative by a number of weeks. | 2018-09-11T00:00:00 | High | 1166363 |  | Chief Health Officer and Prevention | 87 | 201744 |  | G | 8 | Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1384239 | 2017-07-24T00:00:00 | DH
23/10/2018 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery |  | 2018-11-30T00:00:00 |  | 2018-09-14T00:00:00 | High | 4827917 |  | Metro North | 68 | 4368627 |  | G | 9 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (ieMR) program. 23/10/2018, 23/10/2018,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 23/10/2018, 23/10/2018,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. | 4827917 | 2016-07-01T00:00:00 | DH
23/10/2018 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | April: This initiative is now 'in delivery'. | 2018-08-31T00:00:00 | High | 3792744 |  | eHealth Queensland | 25 | 758851 |  | G | 10 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment.??The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access.? | 3723476 | 2017-07-05T00:00:00 | DH
23/10/2018 | EHQ | File Services Migration | 2017-06-30T00:00:00 | Closed |  | 2019-06-28T00:00:00 | August: This project is now complete, having delivered a technical proof of concept, documentation, and business implementation processes. These project artefacts will be used at a future date to undertake a state-wide rollout of the File Services platform. 23/10/2018, 23/10/2018,July: A governance decision has been made to close this project, with the project expecting to close in August 2018. | 2018-08-31T00:00:00 | High | 3400000 |  | eHealth Queensland | 100 | 3900744 |  | G | 11 | The purpose of this investment is to adopt a contemporary, simplified file management solution for Queensland Health that enables a more cohesive customer experience. | 3888755 | 2016-08-01T00:00:00 | DH
23/10/2018 | EHQ | Metro South East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-04-29T00:00:00 |  | 2018-08-31T00:00:00 | High | 2182844 |  | eHealth Queensland | 82 | 1049367 |  | G | 30 | Will replace or uplift out of date end of life ICT assets. | 2154311 | 2017-07-01T00:00:00 | DH
23/10/2018 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | August: The project is reporting ?red? due to schedule delays and an anticipated funding shortfall associated with integration complexities and change management activities required. A change request is progressing to address these concerns. 23/10/2018, 23/10/2018,May: The project is currently reporting 'amber' due to the need to refine business requirements, which may have an impact on the project's schedule. 23/10/2018, 23/10/2018,March: The project has returned to 'green' and is continuing with solution testing activities. | 2018-09-13T00:00:00 | High | 105000000 |  | Metro North | 60 | 86159318 |  | R | 12 | The current Queensland Health Finance, Asset and Materials Maintenance Information System (FAMMIS) system is based on a heavily customised solution which is almost 20 years old and no longer supported. 23/10/2018,The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 23/10/2018, 23/10/2018,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 23/10/2018,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 23/10/2018, 23/10/2018,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
23/10/2018 | EHQ | Follow Me Desktop - Deployment | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-08-31T00:00:00 | High | 3952980 |  | eHealth Queensland | 62 | 1752180 |  | G | 13 | Follow Me Desktop Deployment Project will deliver?the Follow Me Desktop service (FMD) to HHS? in alignment with the Infrastructure Remediation Program (IMP) and ieMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 3621306 | 2017-07-03T00:00:00 | DH
23/10/2018 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-08-31T00:00:00 | High | 3301500 |  | eHealth Queensland | 25 | 1138795 |  | G | 14 | Project Purpose:?To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 2345263 | 2017-07-01T00:00:00 | DH
23/10/2018 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-08-31T00:00:00 | High | 1120000 |  | eHealth Queensland | 60 | 689533 |  | G | 15 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. | 1072242 | 2017-07-05T00:00:00 | DH
23/10/2018 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery |  | 2020-06-26T00:00:00 | Reason for variance: The scope and schedule for IAMP has been extended due to revised timelines to accommodate for extended development, integration, and deployment activities. | 2018-08-31T00:00:00 | High | 3215000 |  | eHealth Queensland | 37 | 5811725 |  | G | 16 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 12206443 | 2015-06-22T00:00:00 | DH
23/10/2018 | EHQ | ieMR Program (Funding Packages 3 and 4) | 2019-04-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | August: The SurgiNet component of ieMR went live at The Townsville Hospital in August 2018. This builds on existing ieMR capability, providing pre and post operative documents directly into the patient chart module, to better support patient care. 23/10/2018, 23/10/2018,July: The Enterprise Schedule Management (ESM) component of ieMR went live at The Townsville Hospital in July 2018. This updated patient scheduling tool will improve inpatient and outpatient scheduling processes. 23/10/2018, 23/10/2018,June: The advanced version of the ieMR system has gone live at the Queen Elizabeth II (QEII) Hospital in June, which includes enhancements to the interface between ieMR and the XRay Radiology Information System. 23/10/2018, 23/10/2018,May: The advanced version of the ieMR system has gone live at the Redland Hospital. Additional clinical reporting was also enabled by ieMR in May. | 2018-08-31T00:00:00 | High | 0 |  | eHealth Queensland | 33 | 0 |  | G | 17 | ieMR will enable improved patient care through the development of a state-wide, authoritative single source of the patient records. 23/10/2018, 23/10/2018,The ieMR will provide clinicians with the ability to: 23/10/2018,* access data that is integrated, accurate and clinically relevant 23/10/2018,* support decision making and better use of information 23/10/2018,* optimise management of patients, resources and provision of services 23/10/2018,* support interaction across a network of providers by making it easier to find providers, transfer information and collaborate with multidisciplinary providers. 23/10/2018,The Program scope (all tranches) is to roll out the ieMR system to 24 hospitals across Queensland. 23/10/2018, 23/10/2018,Please note that financial information for ieMR is Commercial in Confidence | 0 | 2016-11-17T00:00:00 | DH
23/10/2018 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery |  | 2022-06-30T00:00:00 |  | 2018-09-11T00:00:00 | High | 14673739 |  | Clinical Excellence | 22 | 2596831 |  | G | 19 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 23/10/2018,The ongoing program of work aims to continue and build upon existing functionality by: 23/10/2018,? Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 23/10/2018,? Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 23/10/2018,? Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 23/10/2018,? Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 23/10/2018,? Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
23/10/2018 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate |  | 2022-12-21T00:00:00 |  | 2018-09-11T00:00:00 | High | 6300000 |  | Queensland Ambulance Service | 26 | 594688 |  | G | 20 | Phased delivery of a system supporting QAS business intelligence. | 9240000 | 2017-01-03T00:00:00 | DH
23/10/2018 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | Reason for variance: Budget has been revised as a result of reallocation of funding provided under the Specialist Outpatient Strategy to support additional statewide Smart Referrals functionality. 23/10/2018,Schedule has been impacted by only 6months yet still falls within the commitment timeframe. | 2018-09-07T00:00:00 | High | 33827000 |  | Clinical Excellence | 37 | 15740133 |  | G | 21 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 39408218 | 2017-03-01T00:00:00 | DH
23/10/2018 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 1 | 2016-11-30T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | May: The project has experienced a delay to the completion of Stage 1 due to delays in the governance and assurance process and a change in delivery approach. The project is expecting to complete Stage 1 by the end of August 2018, and is currently seeking final governance approval to confirm additional time and funding to complete this stage. 23/10/2018, 23/10/2018,April: The project has experienced a delay to the completion of Stage 1 due to delays in the governance and assurance process. The project is currently seeking approval to obtain additional time and funding to complete this stage. 23/10/2018, 23/10/2018,February: Approval delays in obtaining additional funding and a slightly extended schedule has impacted the project's schedule, with approvals expected in the upcoming reporting month. 23/10/2018, 23/10/2018,Reason for variance: The scope and schedule for Stage 1 of the IWFM Project has been increased to cover additional pilot sites, provide additional system enhancements (primarily to smart form functionality), and to ensure business foundational activities are implemented to prepare HHSs for IWFM implementation. | 2018-09-11T00:00:00 | High | 8200000 |  | Health Support Queensland | 97 | 27658665 |  | G | 22 | The IWFM project involves: 23/10/2018,- configuring additional functionality (currently available and licensed, but unutilised) within the existing Rostering and Payroll business solutions 23/10/2018,- partnering with HHSs to develop refined business models and business processes to support the roster-to-pay process 23/10/2018,- undertaking extensive training and change management to support the adoption and effective usage of new functionality and processes | 28709863 | 2016-02-17T00:00:00 | DH
23/10/2018 | EHQ | Interoperability Project | 2016-04-29T00:00:00 | Delivery |  | 2019-09-29T00:00:00 | Reason for variance: Original funding was reflective of committed funding made available to commence planning activities (including business case development) and implementation of risk mitigation activities of the existing interoperability solution, until such time (late 2017) approval for the implementation of the new solution was granted. | 2018-09-12T00:00:00 | High | 39189509 |  | eHealth Queensland | 33 | 18189187 |  | G | 23 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 23/10/2018,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 23/10/2018,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 23/10/2018, | 39189509 | 2015-02-01T00:00:00 | DH
23/10/2018 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Delivery |  | 2020-12-21T00:00:00 |  | 2018-09-11T00:00:00 | High | 64000000 |  | Health Support Queensland | 54 | 23827282 |  | G | 24 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 23/10/2018,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. | 63558771 | 2015-08-28T00:00:00 | DH
23/10/2018 | MNHHS | Learning and Performance Management Project | 2017-06-30T00:00:00 | Closed |  | 2018-11-30T00:00:00 | August: Closure activities have now been completed. This project has implemented an integrated Learning Management and Performance Management system, accessible by locations within the Metro North Health and Hospital Service (HHS). 23/10/2018, 23/10/2018,July: This project has been implemented in July, with project closure activities expected to occur until November 2018. | 2018-09-13T00:00:00 | High | 1178190 |  | Metro North | 100 | 1256661 |  | G | 25 | Implement an integrated Learning Management and Performance Management system with the capability to deliver online learning and training content, facilitate performance development and maintain centralised records for reporting purposes. | 1312191 | 2016-07-11T00:00:00 | DH
23/10/2018 | GCHHS | Medical Imaging Informatics Solution (MIIS) Risk Mitigation | 2018-12-31T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | Reason for variance: Revised project delivery costs were approved in March 2018, as part the Stage Gate 3 Business Case. 23/10/2018,Schedule was revised to align with the Digital Healthcare Program (ieMR) on the Gold Coast. | 2018-09-12T00:00:00 | High | 5000000 |  | Gold Coast | 25 | 2404041 |  | G | 26 | The Medical Imaging Informatics Solution (MIIS) Risk Mitigation project has identified an Imaging solution which will address the risks and opportunities described in the Case for Change including the mitigation of patient safety risks, increased efficiency and productivity, improvi.ng medical imaging billing revenue collection and cash flow. The solution has user endorsement from radiologists and clinicians and will be specifically configured to meet GCHHS?s needs. | 12800000 | 2017-04-03T00:00:00 | DH
23/10/2018 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery |  | 2018-10-30T00:00:00 |  | 2018-09-14T00:00:00 | High | 4030460 |  | Metro North | 85 | 4114249 |  | G | 27 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 23/10/2018, 23/10/2018,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 23/10/2018, 23/10/2018,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
23/10/2018 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | May: This project has returned to 'green', with the project's schedule and budget being monitored by the project's governance committee. 23/10/2018, 23/10/2018,April: The project is continuing to report 'Red' due to continued delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-09-14T00:00:00 | High | 6299780 |  | Metro North | 80 | 6688973 |  | G | 28 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 8161556 | 2014-06-01T00:00:00 | DH
23/10/2018 | EHQ | Metro South and East Queensland ICT Infrastructure Replacement Initiative | 2018-06-29T00:00:00 | Delivery |  | 2019-02-28T00:00:00 |  | 2018-08-31T00:00:00 | High | 4160449 |  | eHealth Queensland | 72 | 1760977 |  | G | 29 | Will replace or uplift out of date end of life ICT assets. | 3583313 | 2017-07-01T00:00:00 | DH
23/10/2018 | EHQ | Mobile Application System for Bring Your Own Device | 2018-06-30T00:00:00 | Closed |  | 2018-08-24T00:00:00 | August: This project is now complete. This project has resulted in increasing staff access to information systems and data on a wide variety of devices, with the ability to deliver low/no code mobile applications by Hospital and Health Services (HHSs) in a managed way. 23/10/2018, 23/10/2018,May: This project is now reporting 'red'. Governance pathways and approvals have impacted on the project's overall schedule. The project is progressing with a change request to update the project's deliverables, which will return the project to 'green' upon approval. | 2018-08-31T00:00:00 | High | 1639698 |  | eHealth Queensland | 100 | 1540429 |  | G | 31 | This project leverages the investment of the previous Bring-Your-Own-Device (BYOD)?projects to extend the capability of device mobility by building the foundations of a Mobile Application Ecosystem - the processes, products and services to enable the managed development of low/no code applications by Health and Hospital Services (HHS).? This project will also complete the deployment of BYOD laptops and provide recommendations on how cost savings can be made by the organisation around Corporate devices and data plans.? | 1536395 | 2017-07-01T00:00:00 | DH
23/10/2018 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery |  | 2018-12-19T00:00:00 | August: The project has returned to 'green'. Activities to improve project team resourcing and increase key deployment rates are continuing into September. The project will continue to monitor the performance of migration and upgrade activities. 23/10/2018, 23/10/2018,July: The project is now reporting 'amber' due to a lack of technical and deployment resource availability, impacting on the project's schedule. Mitigation actions are in place to reduce the schedule and resourcing impact. 23/10/2018, 23/10/2018,May: This project has now returned to 'green' with the project's revised schedule being approved. 23/10/2018, 23/10/2018,Reason for variance: Original budget was reflective of an original estimate based on high level planning. Detailed planning has since refined the estimated budget (including vendor licensing arrangements) which received approval for budget increase in June 2017. | 2018-08-31T00:00:00 | High | 14100000 |  | eHealth Queensland | 69 | 23512439 |  | G | 32 | A managed operating environment means that everyone within the organisation is running a clean, basic operating system with centralised update management. This includes upgrades of all PC operating systems, preparing QH applications for running on recent operating system environments, and Infrastructure remediation activities to ensure the deployment tools are sufficient and ready for production. | 38741697 | 2016-05-12T00:00:00 | DH
23/10/2018 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | July: The latest approved end date has been updated. 23/10/2018, 23/10/2018,June: The latest approved end date of this project remains at 30 June 2018, pending the approval of a revised implementation date. 23/10/2018, 23/10/2018,Reason for variance: Budget and schedule were revised following a tender process as per responses from the market. | 2018-09-11T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 90 | 910083 |  | G | 33 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1510000 | 2015-10-01T00:00:00 | DH
23/10/2018 | CHOPD | Notifiable Conditions System Replacement | 2019-06-29T00:00:00 | Delivery |  | 2020-02-28T00:00:00 | Reason for variance: Approval of extension of project timelines was received November 2014. Business Case was updated and approved in November 2016, and also approved to extending the schedule to February 2020. | 2018-09-07T00:00:00 | High | 12750000 |  | Chief Health Officer and Prevention | 44 | 2957218 |  | G | 34 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 23/10/2018,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
23/10/2018 | EHQ | Patient Administration System (PAS) Replacement - Business Case Development Project | 2017-06-30T00:00:00 | Initiate |  | 2019-03-29T00:00:00 | Reason for variance: Further funding was provided in 2017-18 and 2018-19 to finalise the start-up activities, including the delivery of a detailed business case and early procurement activities. | 2018-08-31T00:00:00 | High | 3850000 |  | eHealth Queensland | 74 | 5871998 |  | G | 35 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients? journeys, and ensure that accurate information about our patients is readily available when and where required. 23/10/2018, 23/10/2018,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 23/10/2018,? support for patient engagement 23/10/2018,? integrated care 23/10/2018,? clinical research 23/10/2018,? population health (for patients using public health services) 23/10/2018,? performance transparency 23/10/2018,? resource planning. | 11890760 | 2015-11-01T00:00:00 | DH
23/10/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-08-31T00:00:00 | High | 2150147 |  | eHealth Queensland | 71 | 1527536 |  | G | 43 | Will replace or uplift out of date end of life ICT assets. | 2593463 | 2017-07-01T00:00:00 | DH
23/10/2018 | CSD | Practice Management Enterprise Solution | 2018-11-30T00:00:00 | Delivery |  | 2019-01-31T00:00:00 |  | 2018-09-13T00:00:00 | High | 1470000 |  | Corporate Services | 78 | 2305024 |  | G | 36 | The main practice management software used by HHSs to conduct private practice services and billing activities is being replaced. The initiative will procure and implement "like for like" functionality enterprise solution for participating HHSs (15 in total). | 2961432 | 2017-08-01T00:00:00 | DH
23/10/2018 | EHQ | Project, Program and Portfolio Management Application | 2018-03-31T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | May: This project has now returned to 'green' with the project's revised schedule being approved. 23/10/2018, 23/10/2018,April: This project is now reporting 'amber' due to re-aligning the project's schedule and finances to meet changing organisational requirements. The project has submitted | 2018-08-31T00:00:00 | High | 1344177 |  | eHealth Queensland | 50 | 733487 |  | G | 37 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 23/10/2018, | 1531491 | 2017-05-02T00:00:00 | DH
23/10/2018 | EHQ | Queensland State-wide ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-08-31T00:00:00 | High | 3246247 |  | eHealth Queensland | 69 | 2314720 |  | G | 38 | Will replace or uplift out of date end of life ICT assets. | 3183491 | 2017-07-01T00:00:00 | DH
23/10/2018 | EHQ | Queensland State-wide ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-08-31T00:00:00 | High | 3283431 |  | eHealth Queensland | 77 | 3314716 |  | G | 39 | Will replace or uplift out of date end of life ICT assets. | 3273746 | 2017-07-01T00:00:00 | DH
23/10/2018 | MNHHS | Quick Flow Project | 2019-06-30T00:00:00 | Initiate |  | 2019-06-30T00:00:00 |  | 2018-09-14T00:00:00 | High | 6408600 |  | Metro North | 97 | 1859661 |  | G | 40 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 23/10/2018,The key objectives of the project are to: 23/10/2018,? Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 23/10/2018,? Improve the outpatient experience across MNHSS facilities and community services 23/10/2018,? Improve clinic resource utilisation 23/10/2018,? Increase the efficiency of clinical and administrative processes 23/10/2018,? Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
23/10/2018 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | August: The design and development phase of the project has been delayed to accommodate additional business and technical requirements. 23/10/2018, 23/10/2018,Reason for variance: The scope has changed to include additional technical and business requirements. | 2018-09-13T00:00:00 | High | 34950000 |  | Cairns and Hinterland | 65 | 14395312 |  | R | 41 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patient?s home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
23/10/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-02-28T00:00:00 |  | 2018-08-31T00:00:00 | High | 4260336 |  | eHealth Queensland | 77 | 2439186 |  | G | 42 | Will replace or uplift out of date end of life ICT assets. | 4213118 | 2017-07-01T00:00:00 | DH
23/10/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-08-31T00:00:00 | High | 1651750 |  | eHealth Queensland | 71 | 1305668 |  | G | 44 | Will replace or uplift out of date end of life ICT assets. | 1643098 | 2017-07-01T00:00:00 | DH
23/10/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-08-31T00:00:00 | High | 4245973 |  | eHealth Queensland | 80 | 3231144 |  | G | 45 | Will replace or uplift out of date end of life ICT assets. | 4216631 | 2017-07-01T00:00:00 | DH
23/10/2018 | EHQ | Service Delivery Excellence Project (SDEP) | 2018-02-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | March: The latest approved end date and percentage complete has been updated. 23/10/2018, 23/10/2018,February: The latest approved end date for this initiative will be updated pending advise from the project. | 2018-08-31T00:00:00 | High | 4822000 |  | eHealth Queensland | 36 | 1987186 |  | G | 46 | The Service Delivery Excellence Project (SDEP) aims to improve the service delivery functions of eHealth Queensland to help the organisation achieve its Customers and services Foundation and Shared Goal: 23/10/2018,Enhance value for customers by streamlining end to end services, processes and delivery models so that we can provide an exceptional customer experience. 23/10/2018,Stage 1 has the primary objective of delivering the Project Initiation Document (PID) for the Service Delivery Excellence Project (SDEP) Stage 2. | 4736721 | 2017-10-03T00:00:00 | DH
23/10/2018 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Delivery |  | 2020-09-30T00:00:00 |  | 2018-08-31T00:00:00 | High | 10500000 |  | eHealth Queensland | 22 | 3296451 |  | G | 47 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 10413570 | 2017-07-03T00:00:00 | DH
23/10/2018 | MNHHS | Royal Brisbane and Women's Hospital Wi-Fi | 2019-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-09-20T00:00:00 | High | 6000000 |  | Metro North | 40 | 3363178 |  | G | 48 | The RBWH Wi-Fi Project will provide an uplift and renewal to the latest Queensland Health (QH) standard for wireless local area network (WLAN) coverage within the internal areas of prioritised RBWH buildings in order to support digital healthcare. 23/10/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for the RBWH in the near future. | 6000000 | 2017-10-22T00:00:00 | DH
23/10/2018 | EHQ | Storage Asset Replacement | 2018-06-29T00:00:00 | Closed |  | 2018-08-31T00:00:00 | August: This project is now complete. The project has achieved the delivery of modern storage infrastructure, reducing the physical footprint and operational costs for storage within the organisation, while increasing performance and capacity at sites with a reduced risk of service failures. | 2018-08-31T00:00:00 | High | 1671556 |  | eHealth Queensland | 100 | 1568902 |  | G | 49 | The Storage Asset Replacement (SAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the SAR and Backup Asset Replacement (BAR) projects. 23/10/2018,The SAR project seeks to outline architecture for storage that will provide a cost effective, scalable and fit for purpose environment for the future of storage services within Queensland Health.? Utilising space saving technologies which will enable further cost savings and reduce the requirement for capacity expansion in the short to medium term. | 1653150 | 2017-07-03T00:00:00 | DH
23/10/2018 | MNHHS | Digital Transformation Readiness | 2018-12-27T00:00:00 | Initiate |  | 2018-12-27T00:00:00 | July: This project has commenced reporting for the first time. | 2018-09-14T00:00:00 | High | 2771674 |  | Metro North | 25 | 195327 |  | G | 62 | The key objectives of Digital Transformation Readiness are to perform activities in preparation for Metro North Hospital and Health Service (MNHHS) Digital Transformation with a focus on the integrated electronic Medical Record (ieMR) readiness. | 2771674 | 2018-06-29T00:00:00 | DH
23/10/2018 | EHQ | Sunshine Coast University Hospital (SCUH) Stage 2 ICT Expansion | 2018-06-30T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | February: This project has been reported for the first time. | 2018-08-31T00:00:00 | High | 3180000 |  | eHealth Queensland | 88 | 4653121 |  | G | 50 | Sunshine Coast University Hospital (SCUH) ICT Stage 1 delivered the ICT required to achieve the successful commissioning of SCUH in March 2017. The SCUH Stage 2 ICT Expansion covers the investment period from 1 July 2017 to 31 December 2018 and is intended to support the planned expansion of SCUH to increase capacity and establish new services. | 4653121 | 2017-07-03T00:00:00 | DH
23/10/2018 | CHQ | Information Sharing Project Phase 2 | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | August: The project is now reporting 'green'. The updated procurement approach was approved by the project's governance committee in August. 23/10/2018, 23/10/2018,July: This project is now reporting 'amber' due to a change in procurement approach, which has impacted on the project's financials and schedule. The project's governance committee is reviewing the updated approach, returning the project to 'green' upon approval (expected to be in September). 23/10/2018, 23/10/2018,March: This project has been reported for the first time. | 2018-09-05T00:00:00 | High | 4455455 |  | Children's Health Queensland | 20 | 1210000 |  | G | 51 | Department of Health, eHealth Queensland, Children?s Health Queensland and Mater Health share a common vision for the seamless integration of care across organisational boundaries, in the interests of patient safety, quality, efficiency and improved access to care. This vision of integrated care processes is enabled through seamless access, at the point of care, to necessary health information and efficient transactional capabilities that support the care continuum. | 4455455 | 2018-01-10T00:00:00 | DH
23/10/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Alcohol and Other Drugs (AODS) Consumer Technical Refresh | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | May: This project has been reported for the first time. | 2018-09-11T00:00:00 | High | 1248860 |  | Clinical Excellence | 30 | 318171 |  | G | 52 | This project is refreshing the technical implementation of the CIMHA Consumer module, in preparation for the introduction of new Alcohol and Other Drugs (AODS) system functionality. | 1248860 | 2018-04-16T00:00:00 | DH
23/10/2018 | SPP | Queensland Health Integrated Processing System establishment (QHIDSe) | 2019-10-15T00:00:00 | Delivery |  | 2019-10-15T00:00:00 | May: This project has been reported for the first time. | 2018-09-04T00:00:00 | High | 3257000 |  | Strategy, Policy and Planning | 19 | 1083964 |  | G | 53 | The QHIDSe project will develop in-house the foundation of an integrated processing system (i.e. QHIDS (Queensland Health Integrated Data System) using agile techniques and software development tools enabling QHIDS to be used as a replacement for the Queensland Hospital Inpatient Processing System (QHIPS, which processes the Queensland Hospital Admitted Patient Data Collection) and extended through future initiatives to provide new functionality. | 3257000 | 2018-05-25T00:00:00 | DH
23/10/2018 | HSQ | Modernised Managed Operating Environment (MOE) and Digital Collaboration Platform for HSQ | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | August: The project is now reporting 'amber', with the project's schedule being aligned with the dependant project implementation schedule. Upon approval of the revised implementation approach, the project is expected to return to 'green' in the next reporting period. 23/10/2018, 23/10/2018,July: The project is now reporting 'red' due to project team resourcing issues, as well as technical and scheduling delays of a dependent project impacting on the overall schedule. The project's governance committee is reviewing the project's schedule, with the project expecting to return to 'green' upon approval of an updated delivery approach. 23/10/2018, 23/10/2018,June: This project has been reported for the first time. 23/10/2018, 23/10/2018,Reason for variance: The original budget reflected the 2017/18 FY spend only. | 2018-09-11T00:00:00 | High | 1057000 |  | Health Support Queensland | 30 | 1211282 |  | A | 54 | Delivery of a fully functional, production managed operating environment and digital collaboration platform packaged to all desktops, laptops and some smart devices within the Health Support Queensland environment. | 3414000 | 2018-01-01T00:00:00 | DH
23/10/2018 | CHOPD | Mosquito-borne Disease Program: Spatial Database Project | 2019-06-21T00:00:00 | Initiate |  | 2019-06-21T00:00:00 | June: This project has been reported for the first time. | 2018-09-07T00:00:00 | High | 852000 |  | Chief Health Officer and Prevention | 57 | 191729 |  | G | 55 | The vector surveillance and control program requires a state-wide surveillance and control solution to assist with the response to the risk of Dengue, Zika and Chikungunya virus outbreaks in vulnerable North Queensland and the mitigation of emerging risks across Central and Southern Queensland. | 1502672 | 2017-07-31T00:00:00 | DH
23/10/2018 | EHQ | Telehealth Asset Replacement | 2019-06-28T00:00:00 | Delivery |  | 2019-06-27T00:00:00 | July: This project has commenced reporting for the first time. | 2018-08-31T00:00:00 | High | 1950000 |  | eHealth Queensland | 15 | 95555 |  | G | 56 | Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. | 1950000 | 2018-07-02T00:00:00 | DH
23/10/2018 | MNHHS | Connecting Care information Program (CCI) | 2022-06-30T00:00:00 | Initiate |  | 2022-06-30T00:00:00 | July: This project has commenced reporting for the first time. | 2018-09-14T00:00:00 | High | 760455 |  | Metro North | 15 | 975347 |  | G | 57 | The Connecting Care Information Program - CCI -will support streamlining and improvement of clinical and administrative workflows through delivery of key Information Technology (IT) enablers. | 1140000 | 2017-03-21T00:00:00 | DH
23/10/2018 | MNHHS | Metro North Health and Hospital Service Contemporary Workspace Phase 1 | 2019-01-01T00:00:00 | Delivery |  | 2019-01-01T00:00:00 | July: This project has commenced reporting for the first time. | 2018-09-14T00:00:00 | High | 233000 |  | Metro North | 44 | 578692 |  | G | 58 | This project is focusing on preparing the Metro North Hospital and Health Service (MNHHS) applications to be ready for contemporary operating system deployment. | 1665831 | 2017-08-01T00:00:00 | DH
23/10/2018 | MNHHS | Metro North Picture Archiving and Communication (PACS) Replacement for The Prince Charles Hospital | 2018-12-03T00:00:00 | Initiate |  | 2018-12-03T00:00:00 | July: This project has commenced reporting for the first time. | 2018-09-14T00:00:00 | High | 2301451 |  | Metro North | 22 | 637687 |  | G | 59 | Procure and implement a contemporary Picture Archiving and Communication (PACS) System and functionality that will ensure improved Service delivery for the MNHHS Medical Imaging Departments at The Prince Charles Hospital (TPCH). | 2301451 | 2017-12-01T00:00:00 | DH
23/10/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Secure Transfer Project | 2019-01-28T00:00:00 | Initiate |  | 2019-01-28T00:00:00 | July: This project has commenced reporting for the first time. | 2018-09-11T00:00:00 | High | 610000 |  | Clinical Excellence | 10 | 125001 |  | G | 60 | The purpose of this initiative is to upgrade the CIMHA application with functionality to automate the sending of selected clinical notes and data securely. This will improve the efficiency and timeliness of information sharing. | 1109521 | 2017-10-16T00:00:00 | DH
23/10/2018 | CED | Patient Online Portal (POP) | 2019-12-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | July: This project has commenced reporting for the first time. | 2018-09-07T00:00:00 | High | 15500000 |  | Clinical Excellence | 8 | 2053151 |  | G | 61 | The Patient Online Portal (POP) aims to improve a patient?s outpatient journey through greater visibility and enhanced communication capability across specialist services. Additionally, the solution seeks to provide greater flexibility in the provision of outpatient services, allowing patients to better manage their care. | 15500000 | 2018-03-05T00:00:00 | DH
23/10/2018 | MNHHS | Referral Lodgement and Tracking (RLaT) | 2019-01-23T00:00:00 | Delivery |  | 2019-01-23T00:00:00 | July: This project has commenced reporting for the first time. | 2018-09-14T00:00:00 | High | 3184098 |  | Metro North | 65 | 2155479 |  | G | 63 | This project will deliver a state-wide capability for referrers to lodge patient referrals electronically with Queensland Health. The referral will be automatically routed to the appropriate Hospital and Health Service (HHS). | 3184098 | 2018-02-09T00:00:00 | DH
23/10/2018 | EHQ | Infrastructure Capacity Expansion FY 18-19 | 2019-06-28T00:00:00 | Initiate |  | 2019-06-28T00:00:00 |  | 2018-08-31T00:00:00 | High | 1192426 |  | eHealth Queensland | 5 | 0 |  | G | 64 | The Infrastructure Capacity Project is responsible for managing capacity requests across the organisation to improve the level of service and accessibility of data across Queensland Health. The project is based on the identified organic growth requirements to replace/upgrade ICT infrastructure or expanding ICT assets to allow services to continue functioning. ICT assets include storage capacity, network switches, wireless and software licensing, etc. | 1192425 | 2018-07-02T00:00:00 | DH
23/10/2018 | EHQ | Storage Asset Replacement FY 18-19 | 2019-06-28T00:00:00 | Initiate |  | 2019-06-28T00:00:00 |  | 2018-08-31T00:00:00 | High | 4446000 |  | eHealth Queensland | 2 | 5000 |  | G | 65 | The Server Asset Replacement Project is responsible for replacing prioritised, highly utilised and critical server assets which are coming to, or have reached, end-of-financial-life. | 4446000 | 2018-07-02T00:00:00 | DH
23/10/2018 | MNHHS | Digital Dictation Upgrade Project | 2017-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 |  | 2018-09-14T00:00:00 | High | 828522 |  | Metro North | 90 | 863130 |  | G | 66 | To replace the current versions of the Digital Dictation Systems in use at MNHHS facilities with the newest release of the product. The new release introduces efficiencies in the workflow process and contributes to patient care improvement through reduction in timeframe to complete patient letters. | 1048522 | 2016-07-25T00:00:00 | DH
23/10/2018 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Project planned expenditure and end date have been revised due to a number of factors: 23/10/2018, 23/10/2018,- The original planned expenditure of $2.2M was a high level estimate and has been refined with the complexity of the processes and system being uncovered as the project was stood up. 23/10/2018, 23/10/2018,- An increased scope and associated effort to ensure maximum benefit is gained from the investment, so that Queenslanders are better supported during natural disasters. 23/10/2018, 23/10/2018,- Delays to project schedule and associated additional resourcing costs as a result of: 23/10/2018, 23/10/2018, - Staff diverted to priority community recovery support roles during activations over the last 12 months, including TC Debbie, TC Nora and the North Queensland floods. During natural disasters, our agency resources are focused on providing critical support to communities and Queenslanders in need. 23/10/2018, 23/10/2018, - Extended vendor delivery times due to defects and quality concerns including system performance. The department is working with the vendor to resolve these issues. | 2018-08-31T00:00:00 | High | 2208000 |  | Department of Communities, Disabilty Services and Seniors | 89 | 3275000 |  | G | 1 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3780000 | 2016-07-01T00:00:00 | DCCSDS
23/10/2018 | Cross-Gov | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | The Queensland Fire and Emergency Services (QFES) Human Capital Management Case Management module delivery has been completed with UAT and Penetration testing finalised for implementation. The Workplace Health and Safety module has completed UAT and will be released into production following completion of agency training. The closure report for this project has commenced. 23/10/2018, 23/10/2018,The Queensland Corrective Services Human Capital Management Business Case has been approved with detailed project planning and resource engagement underway. Gate 3 Investment Decision review has been completed. Project startup planning for implementation has commenced. 23/10/2018, 23/10/2018,The Queensland Ambulance Service (QAS) and QFES payroll projects transitioning to Aurion are progressing to schedule, with QAS being the next for implementation planned for November 2018. 23/10/2018, 23/10/2018,Detailed planning of the Integration requirements for the program continue to be progressed. 23/10/2018, 23/10/2018,At the direction of the Executive Steering Committee (3/07/18) the program scope was increased to include the procurement of a Time and Attendance solution for QFES, QAS and QCS. | 2018-06-30T00:00:00 | Critical | 101500000 |  | Cross-Government program led by DSITI | 65 | 59979631 |  | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 23/10/2018, 23/10/2018,* Sustainable and supported HR and Payroll service delivery 23/10/2018,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 23/10/2018,* Strategic HR capability that supports the development, performance and safety of the departments workforce 23/10/2018,* Business Intelligence capability that provides real timely, integrated HR information 23/10/2018,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 23/10/2018,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 23/10/2018,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
23/10/2018 | QPS | GPS Tracking (Bail) | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | Legislation provisioning for GPS monitoring of court bailed offenders commenced on 31/3/18. QPS established interim GPS tracking capability leveraging existing contract held by Queensland Corrective Services. 23/10/2018,QPS is now undertaking a Whole of Government open Invitation-to-Offer to establish a longer term contract for GPS tracking devices and monitoring of offenders. 23/10/2018,Note: The project is currently undergoing procurement/commercial activity and is therefore not publishing any financial data. | 2018-08-22T00:00:00 | High | 0 |  | Queensland Police Service | 40 | 0 |  | G | 1 | As per the Commencement of the Bail (Domestic Violence) and Another Act Amendment Act 2017 (the Amending Act) on 30 March 2018, Magistrates will be empowered to impose a tracking condition on a defendant granted bail as a condition of their bail undertaking. 23/10/2018,As such the QPS intends to progressively implement an electronic monitoring capability on a State Wide basis. 23/10/2018,An implementation project has commenced to create an electronic monitoring capability for geographically locating and monitoring a defendant on bail for QPS to meet requirements of the Amended Act. 23/10/2018,The GPS Tracking Project is an initial proposal to validate the utility of the technology prior to seeking a longer term solution. | 0 | 2018-03-30T00:00:00 | QPS
23/10/2018 | QPS | Online National Police Certificate | 2017-06-30T00:00:00 | Closed |  | 2018-07-31T00:00:00 | Since the successful launch of Online National Police Certificates 83% of all applications have been submitted online. The project is now officially closed effective 31 July 2018 and has transitioned to business as usual. 23/10/2018, 23/10/2018,Feb 18: The revised project budget has been amended from previously published figures to reflect the increased investment in promotional products. | 2018-08-22T00:00:00 | High | 275000 |  | Queensland Police Service | 100 | 250000 |  | G | 2 | The Online National Police Certificate Project will implement an online service for the community to apply and pay for Name Only National Police Certificates online, rather than presenting at a police station, or using the online services of an Australian Crime Intelligence Commission accredited broker. This will provide improved customer service to the community through a more efficient and reliable QPS service, with no requirement to present at a police station, as well as provide efficiency and time savings to local police stations and the Police Information Centre. | 250000 | 2017-01-01T00:00:00 | QPS
23/10/2018 | QPS | Police Integrity and Professional Standards | 2018-08-24T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | Full funding has now been approved for the Police Integrity and Professional Standards IT system. 23/10/2018, 23/10/2018,The Project has received a green assessment for the Gate 3 Quality Assurance Review and will commence delivery in July 2018 with an approved revised project end date of 31 December 2019. 23/10/2018, 23/10/2018,Feb 18: Note: original planned end date amended as previously published information was incorrect. | 2018-08-22T00:00:00 | High | 4142000 |  | Queensland Police Service | 35 | 307200 |  | G | 3 | This initiative will deliver a new integrated Police Integrity and Professional Standards IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The Police Integrity and Professional Standards system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The Police Integrity and Professional Standards Project will also complement the Complaints Reform Project established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of the Police Integrity and Professional Standards system will place the QPS in a strong readiness position to fully implement Complaints Reform Project-generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 6792000 | 2017-03-07T00:00:00 | QPS
23/10/2018 | QPS | Advanced Data Analytics | 2017-07-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | The Advanced Data Analytics Project was established to progress the QPS advanced analytics strategy and capability. 23/10/2018, 23/10/2018,Demand and Resource Committee on 23 July 2018 noted the Advanced Data Analytics End Project Report and approved the closure of the Advanced Data Analytics Project. 23/10/2018, 23/10/2018,The additional $59,389 expenditure on the project was incurred to extend some resources to support the transition of capabilities into business as usual. This amount is within the accepted QPS tolerance for project variance. 23/10/2018, 23/10/2018,The project delivered more than was proposed in the original submission, leaving legacy capability that has transitioned into business as usual. 23/10/2018, 23/10/2018,Jun 18: The QPS Demand and Resource Committee approved the extension of the project closure date to 30 June 2018 and an additional $1,114,000 in funding to facilitate achievement of the projects objectives. | 2018-08-22T00:00:00 | Low | 1731000 |  | Queensland Police Service | 100 | 2904389 |  | G | 4 | Develop the QPS Advanced Data Analytics proof-of-concept. This proof-of-concept is intended to inform a larger suite of data analytics integration and intelligence over the next four years, including the development of predictive and alert models to enhance the operational response to threats, incidents and events. | 2845000 | 2017-02-19T00:00:00 | QPS
23/10/2018 | QPS | Body Worn Cameras | 2018-02-28T00:00:00 | Closed |  | 2018-06-30T00:00:00 | The Project completed the deployment of all Stage Two body worn cameras in December 2017 and transitioned to business as usual on 30 June 2018. The Project is now going through approval for formal closure. 23/10/2018, 23/10/2018,Feb 2018: The original budget was $6.03M. In May 2017, the QPS Demand and Resource Committee approved an additional $0.860M, making the total approved budget $6.890M | 2018-08-22T00:00:00 | Medium Low | 6030000 |  | Queensland Police Service | 100 | 6890000 |  | G | 5 | The Queensland Police Service Body Worn Camera Project is deploying 5100 body worn cameras to frontline police officers. Body worn cameras will be deployed to 168 police stations, 16 tactical crime units, 47 road policing units, and specialist units including dog squads and the Public Safety Response Team in two stages. The cameras integrate with the QPS mobility devices, allowing officers to add metadata to videos and to review videos in the field. A system for storage and allocation of digital camera data will also be implemented as well as policy related to use of the cameras. | 6890000 | 2014-08-25T00:00:00 | QPS
23/10/2018 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Objectives 23/10/2018, 23/10/2018,This project will deliver a secondary DR site and hyper-converged system to provide resilience for all departmental business applications in the event of a disaster. 23/10/2018, 23/10/2018,Project Updates 23/10/2018, 23/10/2018,Core infrastructure DR implementation 80% complete. All migrated production systems successfully replicating to secondary DR site. 23/10/2018,Oracle system DR implementation is 100% complete 23/10/2018,Oracle applications DR testing successfully completed. 23/10/2018,Legacy applications undergoing case-by-case assessment to identify best option for DR. Anticipated completion by Dec 2018. 23/10/2018,Security DR relocation in progress. 23/10/2018,All end-of-life ICT infrastructure will be decommissioned by Dec 2018. 23/10/2018,The newly implemented DR infrastructure will provide improved stability and life extension to existing business-critical applications. 23/10/2018,DR recovery procedure development, testing strategy and ICT DR Plan update in progress. 23/10/2018,DR testing scheduled for October and November 2018 23/10/2018, 23/10/2018,Some issues have impacted YTD position however it is anticipated the original completion date will be met. | 2018-09-30T00:00:00 | High | 7460674 |  | Corporate Services | 80 | 5218298 |  | G | 1 | *Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 6308664 | 2016-10-01T00:00:00 | DJAG
23/10/2018 | BCS | Blue Card Services Recommendation 28.1 Project - Blue Card Home Based Care Register | 2018-12-21T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | In July 2016, the Queensland Family and Child Commission QFCC released the When a child is missing Remembering Tiahleigh - A report into Queensland's children missing from out-of-home care report making 29 recommendations. Recommendation 28 required the QFCC to undertake a further review of legislation, policies and practices relating to information sharing between relevant agencies responsible for children in regulated service environments. 23/10/2018,The Recommendation 28 Supplementary Review, A report on information sharing to enhance the safety of children in regulated home based services (Supplementary Review) is the QFCC response to Recommendation 28 and makes 17 recommendations in relation to information sharing between agencies responsible for regulating and monitoring regulated services provided from the home, namely foster and kinship care, family day care and stand alone care services. 23/10/2018,Implementation of the register will require legislative amendment. | 2018-08-31T00:00:00 | High | 1573000 |  | Blue Card Services | 60 | 691890 |  | G | 2 | The objective of this project is to establish a register for recording and reporting on regulated child-related services provided from the home, specifically limited to foster/kinship care, family day care and stand-alone care. As recommended by the Queensland Family and Child Commission (QFCC) within the Recommendation 28 Supplementary Review Report (A report on information sharing to enhance the safety of children in regulated home-based services) this register will: 23/10/2018,a) identify co-located home-based services 23/10/2018,b) enable the Queensland Police Service to have line of sight to the register to access up-to-date information when Police attend a residential address to identify potential risks to children, and 23/10/2018,c) make information available to agencies, including Department of Child Safety, Youth and Women, Department of Education and the Office of the Public Guardian to assist with regulating and/or monitoring specific home-based services. | 1573000 | 2017-04-01T00:00:00 | DJAG
23/10/2018 | HHS | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery |  | 2019-03-31T00:00:00 | The FOPATS Program undertook a significant re-baseline in late 2016 to inform and approve changes to its strategic direction, scope, delivery methodology, timing and costs, including strengthening program governance and revising the Business Case to complete against a two staged implementation, Property and then Tenancy. 23/10/2018, 23/10/2018,Following this review, the Property Release, the first of two stages, was delivered successfully on time on 1 November 2017 and delivered benefits including efficiencies in property management and reporting. 23/10/2018, 23/10/2018,The refreshed business case, the Program budget and planned end date were formally re-baselined in January 2018. This formal approval, coupled with the successful delivery of the first stage Property Release, saw the Program status move to green. 23/10/2018, 23/10/2018,The Program has completed more detailed planning for the second stage Tenancy Release, which will remove the operational dependency on the existing ICT housing solution entirely. Tenancy design activities are now well progressed, with a view to determining a feasible Program end date. 23/10/2018, | 2018-06-30T00:00:00 | Critical | 56286000 |  | Housing and Homelessness Services | 62 | 76536997 |  | G | 1 | Replace the existing ICT housing solution with an integrated ICT system. | 121597695 | 2013-07-01T00:00:00 | HPW
23/10/2018 | QGP | Fleet Management System Replacement Project (FMSRP - Qfleet) | 2019-09-30T00:00:00 | Initiate |  | 2019-09-30T00:00:00 | The project is tracking to plan. The project is currently subject to procurement activities and has commenced lead implementation activities. | 2018-06-30T00:00:00 | High | 13939200 |  | Qfleet | 21 | 655518 |  | G | 2 | The objective of the FMSRP is the procurement and implementation of a new common Fleet Management System that meets QFleet, QPS, QFES and QAS core business requirements and provides best value for money. It will provide a contemporary, sustainable common Fleet Management System that delivers effective and efficient business services for the agencies now and into the future. | 13937796 | 2017-10-19T00:00:00 | HPW
23/10/2018 | QGP | Qfleet Car Sharing Model Implementation Project (CSMIP) | 2018-08-31T00:00:00 | Initiate |  | 2018-08-31T00:00:00 | Procurement activity currently nearing a conclusion. Expecting contract award to occur July/August with implementation to commence soon after. 23/10/2018,The Department has recently updated their publishing criteria for initiatives. This project is publishable under our revised publishing criteria. | 2018-06-30T00:00:00 | High | 454735 |  | Qfleet | 50 | 55665 |  | G | 3 | The objective of the Car Sharing Model Implementation Project (CSMIP) is the procurement and implementation of a fully automated, innovative and sustainable multi-agency car sharing solution delivering effective and efficient short-term motor vehicle hire services for government, now and in the future. | 454735 | 2017-11-20T00:00:00 | HPW
23/10/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Smart Service delivers services on behalf of government via both telephone and counter channels. Some of these services involve financial transactions involving credit card payments. 23/10/2018,The Payment Card Industry (PCI) have stipulated compliance security standards that the government (through Smart Service) has to meet. This project was scoped with ensuring these standards were met. Following a recent external assessment it has been confirmed that this objective has been achieved. The project has completed its planned activities and closed on 29 June 2018. | 2018-06-30T00:00:00 | Critical | 516033 |  | Smart Service Queensland | 100 | 1130918 |  | G | 4 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | HPW
23/10/2018 | SSQ | Automated Payments Solution | 2018-07-31T00:00:00 | Initiate |  | 2018-07-31T00:00:00 | Smart Service Queensland (SSQ) is required to continue to take payments over the phone while remaining Payment Card Industry Data Security Standard (PCI DSS) compliant. 23/10/2018, 23/10/2018,SSQ has commenced the introduction of a VOIP solution to replace the existing analogue telephony capability. This forms the basis of the Telephony Replacement Project (TRP). 23/10/2018, 23/10/2018,To continue to meet ongoing PCI-DSS compliance, additional technology is required to enable secure payments over the phone in a VOIP environment. 23/10/2018, 23/10/2018,The Automated Payment Solution (APS) project will ensure this compliance is maintained and the new technology is implemented. The procurement process is progressing. 23/10/2018, 23/10/2018,Up until June 2018 the APS project has been in a project light, discovery phase - determining if viable solutions were available in the marketplace. This is why the project has reported as amber and the budget spend limited. The project will be re-baselined in July 2018, and a new, more accurate project end date will be determined based upon realistic procurement and implementation timeframes for an off the shelf product. 23/10/2018, | 2018-06-30T00:00:00 | Critical | 1500000 |  | Smart Service Queensland | 5 | 29961 |  | A | 5 | The project will implement an improved capability for offering secure payment card transactions via the telephone. To meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS) when the new VOIP telephony solution is introduced. | 1500000 | 2018-01-29T00:00:00 | HPW
23/10/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | The initial re-planning activity was completed in June 2018. However, further review of the schedule was requested and is underway. Once complete an Exception Report will be created for consideration by the Board. | 2018-06-30T00:00:00 | Critical | 4490634 |  | Smart Service Queensland | 63 | 3729727 |  | A | 6 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 23/10/2018, 23/10/2018,* reduce operating costs 23/10/2018,* increase capacity 23/10/2018,* improve customer experience 23/10/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | HPW
23/10/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Project closure and handover activities are underway. | 2018-06-30T00:00:00 | Critical | 3476245 |  | Smart Service Queensland | 98 | 2083254 |  | G | 7 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2348880 | 2015-11-20T00:00:00 | HPW
23/10/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | SSQ is introducing a new VOIP based telephony platform through the Telephony Replacement Project (TRP). SSQ has also implemented a new agent scripting tool via the Content Delivery Solution (CDS) project. The Technology Platform Project (TPP) is delivering the core underlying technology used by both projects and some other shared ICT centric deliverables, such as Load and Performance Testing, and Security Penetration Testing. The core hardware platform has been successfully delivered and is being utilised by CDS and TRP. The TPP is currently awaiting readiness of some TRP deliverables before progressing the final TPP deliverables. | 2018-06-30T00:00:00 | Critical | 3390862 |  | Smart Service Queensland | 82 | 2435825 |  | A | 8 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution and the call recording solution. | 3390862 | 2017-05-15T00:00:00 | HPW
23/10/2018 | DTS | Digital Archiving Program - Tranche 1 | 2019-12-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | Procurement stage is progressing to planned timeframes and milestones with preferred Offeror identified and contract ready for execution. Government approvals to execute underway. Transition-In planning progressing well. | 2018-06-30T00:00:00 | Critical | 12701000 |  | Digital Technology and Services | 95 | 1872402 |  | G | 9 | To ensure the delivery of an as-a-Service eco-system to effectively archive, manage and enable search and discovery of Queensland's permanent high value records. The new digital services will support the Queensland Government's blueprint for innovation and collaboration, providing better outcomes for Queenslanders. | 12701000 | 2017-07-01T00:00:00 | HPW
23/10/2018 | OSSSIO | Customer Identity and Details Enhancements FY17-18 | 2018-10-30T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | The project is on track to deliver as per the project schedule. 23/10/2018,The Department has recently updated their publishing criteria for initiatives. This project is publishable under our revised publishing criteria. | 2018-06-30T00:00:00 | High | 1200000 |  | One-stop Shop Strategy and Implementation Office | 80 | 1185000 |  | G | 10 | Improved technology and functionality to meet agency requirements in customer identity and details to enable agency adoption and uptake driving further value for customers. 23/10/2018, 23/10/2018,* CDM Blueprint 23/10/2018,* Transition to new platform 23/10/2018,* Auth pilot 23/10/2018,* CDM release 2 pilot | 1200000 | 2017-07-01T00:00:00 | HPW
23/10/2018 | PWAM | Non-Conforming Building Products (NCBP) Website | 2018-08-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | The Safer Buildings website is being developed to support the introduction of proposed changes to the Building Regulation 2006. 23/10/2018,The Department has recently updated their publishing criteria for initiatives. This project is publishable under our revised publishing criteria. | 2018-06-30T00:00:00 | Critical | 770924 |  | Public Works and Asset Management | 50 | 305849 |  | G | 11 | Development of a website (the Safer Buildings Website) for private building owners to register and submit information through a self-assessment checklist to assess their buildings for the existence of potentially combustible cladding. | 770924 | 2018-05-01T00:00:00 | HPW
23/10/2018 | CS | ICT Infrastructure Refresh Project | 2018-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | Progressing as planned. 23/10/2018,The Department has recently updated their publishing criteria for initiatives. This project is publishable under our revised publishing criteria. | 2018-06-30T00:00:00 | Medium | 1173338 |  | Corporate Services | 92 | 647941 |  | G | 12 | To upgrade ICT infrastructure to maintain a fully supported and secure environment and leverage and take advantage of offerings from current DHPW licencing agreements. | 1173338 | 2017-02-13T00:00:00 | HPW
23/10/2018 | ICTSS | Government Wireless Network Contract and Administration Billing System | 2018-06-30T00:00:00 | Initiate |  | 2018-12-31T00:00:00 | There is a requirement to develop a requirements specification for the GWN Wireless Network Contract and Administration Billing System. This has not been completed as it was determined additional resources were required to progress this project i.e. a Project Manager. Originally this digital project was being resourced by existing staff within the GWN Contract Directorate, therefore no expenditure has occurred to date. The procurement process has been delayed for the same reason, but has recommenced now that a Project Manager has been sourced and commenced employment with the GWN Contract Directorate on Monday 13 August. 23/10/2018, | 2018-06-30T00:00:00 | High | 0 |  | ICT Strategic Sourcing | 10 | 0 |  | G | 13 | The GWN Contract Directorate seeks a fully managed software as a service solution to replace existing excel spreadsheets and macros that have organically grown in complexity, improve record keeping compliance, and alleviate current single points of failure and reliance. 23/10/2018,The current contract modification process and Public Safety Agencies (GWN service consumers) invoicing is managed via complicated spreadsheets and macros, colloquially called The Mod Register. The management of contract modifications and invoicing via the Mod Register is manually intensive, cumbersome, is pushing the capabilities of Microsoft Excel, prone to macro errors and due to its size is becoming unwieldly to manage. Also, 23/10/2018,Contractor Performance, including the contractor abatement calculation process, is not centrally managed in one system. A variety of Contractor generated reports are manually validated and reconciled, with problematic auditability. 23/10/2018,Communication of information between GWN Contract Directorate, Public Safety Agencies and Contractor is done via email and attachments of spreadsheets and PDFs in these emails. Management and storage of emails and attachments is problematic, especially version history and control. 23/10/2018,There is now a requirement to procure a purposely designed software system that is fully functional, customisable, redundant, reliable, will meet the current and future requirements of the GWN Contract, and replace current Contract Modification and Contractor Performance processes. | 0 | 2017-11-01T00:00:00 | HPW
23/10/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 23/10/2018, 23/10/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 23/10/2018,October 2017 - The project is progressing as planned. 23/10/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 23/10/2018,June 2017 - Revised Schedule approved returning the project to Green. 23/10/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 23/10/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 23/10/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 23/10/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 23/10/2018,December 2016 - The project is progressing as planned. | 2017-12-21T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 23/10/2018, 23/10/2018,* register and maintain their information 23/10/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
23/10/2018 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 23/10/2018, 23/10/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 23/10/2018,August 2017 - Approved extension of timeframe. 23/10/2018,June 2017 - The project is progressing as planned. 23/10/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 23/10/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 23/10/2018,October 2016 - Progress is continuing as planned. 23/10/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 23/10/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 23/10/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-21T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 23/10/2018, 23/10/2018,* support compliance with legislation 23/10/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 23/10/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 23/10/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 23/10/2018, | 1390000 | 2012-04-01T00:00:00 | DEWS
23/10/2018 | BQCC | Communication and Stakeholder Engagement Solution | 2018-04-27T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Timeframe will be exceeded due to resourcing issues. This has affected key capability to perform testing and the finalisation of procedures and supporting documentation. A review of timeframe and associate costs is underway. 23/10/2018, 23/10/2018,September 2018 - Timeframe is being monitored closely due to business demands impacting testing and completion of documentation. Project closure is now planned by 30 September 2018. 23/10/2018,August 2018 - The project is progress as planned and is on schedule. 23/10/2018,July 2018 - An extension to the planned end date and additional budget has been approved by the governance committee. 23/10/2018,June 2018 - Hidden complexities around integration with other solutions has affect the timing of user acceptance testing and training schedules. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 23/10/2018,May 2018 - A change to the planned end date and cost has been approved. 23/10/2018,March 2018 - Note adjustment to planned end date corrected due to typographical error. 23/10/2018,February 2018 - The project is progressing as planned. 23/10/2018,December 2017 - The project was approved to move into delivery in October 2017 and is being published for the first time. | 2018-10-12T00:00:00 | Medium | 694000 |  | Biosecurity Queensland Control Centre | 97 | 1011823 |  | R | 1 | Implement a simple, easy to use system that will facilitate the collection of information associated with the National Red Imported Fire Ant Eradication Program and the National Electric Ant Eradication Program. This will include contact management, complaints management, history of interactions, event management, training management, social media interactions, marketing campaign and reporting. | 1048849 | 2017-06-01T00:00:00 | DAF
23/10/2018 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The project is progressing as planned and is on schedule. 23/10/2018, 23/10/2018,July 2018 - The project has re-commenced. Approval has been granted for an extension to the planned end date, and an increase in associated costs. 23/10/2018,June 2018 - Field testing has identified unexpected issues that will impact on the planned end date. Effort is underway with Microsoft to apply a technical fix (patch) to resolve errors. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 23/10/2018,April 2018 - An extension to the planned end date has been approved, returning the project status to Green. 23/10/2018,March 2018 - A minor scope increase has been proposed, affecting both timeframe and cost, which is progressing through the governance process. 23/10/2018,March 2018 - The project is progressing as planned. 23/10/2018,December 2017 - A variation to scope was approved, resulting in a change to the planned end date and total estimated expenditure. 23/10/2018,November 2017 - The project is continuing as planned. 23/10/2018,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2018-10-12T00:00:00 | Medium | 608146 |  | Forestry Queensland | 91 | 1044863 |  | G | 2 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 23/10/2018, 23/10/2018,* the capture, management and integration of data 23/10/2018,* value-adding opportunities for business improvement 23/10/2018,* management of risk associated with ongoing use and maintenance of disparate systems. | 1696431 | 2016-06-15T00:00:00 | DAF
23/10/2018 | FQ | Novel Commercial and Recreational Fishing Apps | 2018-09-30T00:00:00 | Delivery |  | 2019-01-31T00:00:00 | The project is progressing as planned and is on schedule. Note: the approved end date has been updated in accordance with the approved business case. 23/10/2018, 23/10/2018,September 2018 - Contract documentation has been finalised and the first two development cycles are under way. 23/10/2018,August 2018 - The project was approved to move to delivery in July 2018 and is publishing for the first time. | 2018-10-12T00:00:00 | High | 450000 |  | Fisheries Queensland | 40 | 229106 |  | G | 3 | * Provide up-to-date information on the rules and regulations about fishing and marine park zoning in Queensland 23/10/2018,* Achieve better compliance through access to information 23/10/2018,* Increase uptake of the App by providing regulations from other marine agencies 23/10/2018,* Resolve issues with offline access to information. | 450000 | 2018-02-01T00:00:00 | DAF
23/10/2018 | ASQ | Portfolio Activity Reporting Information System | 2018-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The project is progressing as planned and is on schedule. 23/10/2018, 23/10/2018,September 2018 - Extensive stakeholder consultation has been undertaken and included in documentation. 23/10/2018,August 2018 - The project is progressing as planned and is on schedule. 23/10/2018,July 2018 - Project is continuing as planned. 23/10/2018,June 2018 - Refreshed business case approved, the project has been re-baselined returning it to a Green status. 23/10/2018,May 2018 - Funding has been approved to fully implement the project and it is now in delivery. 23/10/2018,February 2018 - The project is paused until a funding source is identified. 23/10/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-10-12T00:00:00 | High | 978000 |  | Agri-Science Queensland | 10 | 360028 |  | G | 4 | Review and consolidate the variety of processes and technologies currently being used to manage the department's research, development and extension, and other projects. | 978000 | 2015-08-13T00:00:00 | DAF
23/10/2018 | BQ | Registered Biosecurity Entity (RBE) Renewal Project | 2019-08-30T00:00:00 | Delivery |  | 2019-08-30T00:00:00 | The project is progressing as planned and is on schedule. 23/10/2018, 23/10/2018,August 2018 - The project was approved to move to delivery in July 2018 and is publishing for the first time. | 2018-10-12T00:00:00 | High | 2821000 |  | Biosecurity Queensland | 8 | 395091 |  | G | 5 | * Develop an efficient end-to-end registration renewal process to allow effective management of renewals 23/10/2018,* Ensure stakeholders are aware of renewal requirements and the importance of maintaining up-to-date information 23/10/2018,* Provide the ability to efficiently communicate with customers about registered biosecurity entity processes and renewals 23/10/2018,* Provide data integration between the online customer portal and the underlying technology solution 23/10/2018,* Minimise administrative overhead. | 2821001 | 2017-11-10T00:00:00 | DAF
23/10/2018 | Ag | Risk Reduction for Customer Service Centre | 2019-04-19T00:00:00 | Delivery |  | 2019-04-19T00:00:00 | The project is progressing as planned and is on schedule. 23/10/2018, 23/10/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-10-12T00:00:00 | High | 1767000 |  | Agriculture | 60 | 958670 |  | G | 6 | Implement a solution to mitigate risk of end of life for the agency's call centre logging application. | 1767000 | 2015-01-30T00:00:00 | DAF
23/10/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
23/10/2018 | PSBA | Emergency Vehicle Priority (EVP) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | Approved scope of EVP rollouts have been completed with vehicle fitouts finished in Rockhampton, Maryborough, Hervey Bay and Gladstone for both Queensland Ambulance Service and Queensland Fire and Emergency Services. Project closure scheduled for completion October 2018. Project scope was expanded to include procurement of a managed service for operational support and maintenance and increasing vehicle deployments to a total of 730 emergency vehicles, resulting in a revised timeframe from the original planned end date of 30-06-2017 to 31-10-2018, and a revised budget from the original expenditure plan of $3.37 million to $4.36 million. A re-alignment of schedule sub-tasks has resulted in a reduction of the percentage complete; however, the planned end date remains unchanged. | 2018-09-25T00:00:00 | High | 3370000 |  | Public Safety Business Agency | 92 | 4249227 |  | G | 1 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 23/10/2018, 23/10/2018,* Responsive vehicle movements 23/10/2018,* Improve road safety 23/10/2018,* Congestion management 23/10/2018,* Community safety | 4360696 | 2013-01-01T00:00:00 | PSBA
23/10/2018 | OSR | State Penalties Enforcement Registry (SPER) Program | 2017-12-31T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | Expenditure to date - $31.3M has been for the transformation of the SPER function, and $20.3M has been on the build phase of the ICT implementation. The broader SPER transformation program commenced in 2014, with the first stage focussed on building foundational capability. This next phase was the implementation of the new system solution (ICT SaaS) which commenced in 2016. 23/10/2018,Variation - In December 2017 the SPER Program completed a re-baselining effort which approved changes to scope, timing and costs. These changes were made to better reflect an enhanced delivery model, requiring system modifications that support improved business functionality. | 2018-07-30T00:00:00 | High | 47200000 |  | State Penalties Enforcement Registry | 79 | 51641000 |  | A | 1 | To maintain the integrity of fines as an effective sanction. 23/10/2018,To uphold confidence in the justice system. 23/10/2018,To deliver efficient and effective debt management practices which provide value for money to the State. 23/10/2018, | 62150000 | 2014-01-01T00:00:00 | QR
23/10/2018 | RI | Financial Assurance Information Registry (FAIR) | 2018-07-01T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Project cost as at end of July 2018 is $7.315.000. The FAIR project was due to be completed by 1 July 2018 to align with commencement of the Financial Provisioning Scheme (FPS). The delivery delay event is marked yes due to a deferral of the legislation to enact the FPS which would permit the scheme to commence. The FAIR project will be operational for FPS commencement. 23/10/2018,The FAIR project required for the FPS commencement is 90 percent complete. Other components of the FPS reforms will be completed in subsequent years. | 2018-07-30T00:00:00 | Medium | 15900000 |  | Insurance Commission | 90 | 7315000 |  | G | 2 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
23/10/2018 | RI | Information Security Program | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 |  | 2018-07-31T00:00:00 | Medium | 1960000 |  | Office of the Chief Information Officer | 45 | 642500 |  | G | 3 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 23/10/2018, | 1960000 | 2017-10-16T00:00:00 | QR
23/10/2018 | OSR | Office of State Revenue (OSR) Transformation Program | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | Multiple initiatives in progress focussing on machine learning, analytics, data quality, and business process improvements. Overall program is on track. | 2018-07-30T00:00:00 | High | 73548000 |  | Office of State Revenue | 22 | 13538135 |  | G | 4 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 23/10/2018, 23/10/2018,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 73548000 | 2017-08-01T00:00:00 | QR
23/10/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
23/10/2018 | Corporate Services Improvement Program | Integrated Records Information System (IRIS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | In response to an internal audit review of review of Transport and Main Road's (TMR) Document Management System (DMS) the Integrated Records and Information System (IRIS) project was stood up in 2015. An opportunity to further leverage functionality requirements, TMR's Executive Correspondence System (ECS) replacement was also included into scope. 23/10/2018,IRIS project was reviewed in 2017 to ensure achievability, and as a result the project budget was decreased from $7,967,972 down to $6,865,000 (plus contingency) of 10%. 23/10/2018,In April 2018, a scope change with $567,500 budget increase was approved to include the delivery of a General Correspondence System deliverable to the project, maximising return on investment and better outcomes for the customer, bringing total budget to $7,432,500 excluding contingency. | 2018-07-31T00:00:00 | High | 7967972 |  | Corporate Services Improvement Division | 35 | 5783613 |  | G | 1 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 7967972 | 2015-07-01T00:00:00 | TMR
23/10/2018 | Corporate Services Improvement Program | Lotus Notes Decommissioning (OP) | 2016-01-31T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project commenced in October 2015 when concept and stage 1 was approved to engage and investigate business findings around the decommission of legacy lotus notes databases. 23/10/2018,In July 2016, three additional stages aligning to three financial years from 2016/17 through to 2018/19 were further approved via a project initiation and business case. 23/10/2018,Stage 2, 2016/17, focused on analysis and stakeholder engagement to form the scope of the project and define functionality and business requirements for individual applications. 23/10/2018,Stage 3, 2017/18, focused on proof of concepts to inform and validate the plan for stage 4 in 2018/19. The project was impacted in 2017/18 by several resourcing issues, including the departure of the original project manager. 23/10/2018,The project is scheduled to complete work and close down by 30 June 2019, with the exception of the migration of files from the department's legacy Document Management System (DMS). The migration of the DMS will align with the Integrated Records and Information System (IRIS) program and should be complete by the end of 2019. | 2018-07-31T00:00:00 | High | 8150000 |  | Corporate Services Improvement Division | 52 | 3107509 |  | G | 2 | Deliver improved information platform functions for effective ICT Strategy Alignment | 8150000 | 2015-11-01T00:00:00 | TMR
23/10/2018 | Corporate Services Improvement Program | Safety System Replacement Project (SSRP) | 2018-07-30T00:00:00 | Closed |  | 2018-07-30T00:00:00 | Project closed on time and within budget. A new Workplace Health and Safety (WHS) solution has been procured, implemented and declared production ready 28 June 2018. It provides a contemporary workflow-based approach to the recording and management of hazards and incidents, safety conversations, and claims and rehabilitation. The solution is cloud based and offers functionality to support the Departments mobile workforce. 23/10/2018, | 2018-07-31T00:00:00 | Low | 680000 |  | Corporate Services Improvement Division | 100 | 677411 |  | G | 3 | The objective of the SHE project is to replace the current Work Health and Safety ICT solution with an industry standard, cost effective safety management solution that will enable TMR to meet its obligations under the Work Health and Safety 2011 Act, the Right to Information, Information Privacy legislation and the Workers Compensation and Rehabilitation Act 2003 (Qld). | 680000 | 2016-12-05T00:00:00 | TMR
23/10/2018 | Corporate Services Improvement Program | Transactional Services Improvement Program Enhancements | 2015-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Project successfully closed on time and within budget. Project was originally proposed in February 2015 for stage 1, with project brief and project initiation documentation approved in April 2015. Stage 1 was successfully closed out in March 2016. Stage 2 was approved in April 2016, and successfully closed out 30 June 2017. Stage 3 (2017/18) commenced 1 July 2017 and successfully closed 29 June 2018. 23/10/2018,The project added real value and efficiencies through reduced overheads within the department, such as the introduction of web-based Heavy Vehicle Permits. and Improvements were also made to multiple transactional services relating to payments and receipts from customers such as the additional payment options of payWave and AMEX. | 2018-07-16T00:00:00 | Low | 200000 |  | Corporate Services Improvement Division | 100 | 199878 |  | G | 4 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. | 200000 | 2015-02-01T00:00:00 | TMR
23/10/2018 | Corporate Services Improvement Program | TSIP 2018-19 | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | Project successfully commenced 1 July 2018. | 2018-07-31T00:00:00 | High | 400000 |  | Corporate Services Improvement Division | 5 | 24687 |  | G | 5 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. | 400000 | 2018-07-01T00:00:00 | TMR
23/10/2018 | Corporate Services Improvement Program | Stop Cheques - Stage 3 | 2015-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Project successfully closed on time and within budget. Project was originally proposed in February 2015 for stage 1, with project brief and project initiation documentation approved in April 2015. Stage 1 was successfully closed out in March 2016. Stage 2 was approved in April 2016, and successfully closed out 30 June 2017. Stage 3 (2017/18) commenced 1 July 2017 and successfully closed 29 June 2018. 23/10/2018,Customers are already experiencing the increased convenience and reduction of costs resulting from reduced out bound cheques, which include deceased estate cheques, cheques to known vendors, and the expansion of products available for refund at counter such as registration refunds and concessions. | 2018-07-16T00:00:00 | Medium | 200000 |  | Corporate Services Improvement Division | 100 | 200003 |  | G | 6 | Cheques are inefficient and costly to use, process and administer for both the customer and department. A range of solutions have been developed to reduce the number of cheques that the department produces or receives including refund to card at counter, Bulk Bpay solutions and the introduction of new payment methods are being delivered to be more in line with contemporary retail offerings. The outsourcing of cheque production produced a more streamlined process. 23/10/2018,The stop cheques initiative includes 3 elements: 23/10/2018,Outsourcing/cost reduction 23/10/2018,Outbound cheques 23/10/2018,Inbound cheques | 200000 | 2015-02-01T00:00:00 | TMR
23/10/2018 | Corporate Services Improvement Program | Risk Management Solution | 2018-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Project successfully closed on time and within budget. Project was proposed in February 2016, with the project brief and budget for stage 1 (2016/17) approved in October 2016 for $350,000. Stage 1 successfully closed 30 June 2017 with an underspend of $98501. Stage 2 (2017/18) was approved in March 2017 for $710,000, and commenced 1 July 2017. Stage 2 and the project successfully closed 22 June 2018 with an underspend of $1,887. 23/10/2018,The new online enterprise risk management system (RMS) provides significant improvements in efficiency for risk recording and monitoring, and provides increased transparency on risks, risk owners and treatment responsibilities, raising the overall risk maturity at significantly lower, ongoing cost. 23/10/2018, | 2018-07-16T00:00:00 | High | 350000 |  | Corporate Services Improvement Division | 100 | 959610 |  | G | 7 | Replace the current risk management approach through the delivery of a new and contemporary enterprise Risk Management solution for TMR . | 1024435 | 2016-02-01T00:00:00 | TMR
23/10/2018 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | This commenced in July 2016 with delivery being phased in accordance with the development of the business processes. Original expenditure was 1.5M which has been revised to 1.441M on finalisation and approval of the business case. Phase 1 was completed in July 2017 and the schedule was adjusted in June 2017 to enable the delivery of the Phase 2 capability in late 2018. 23/10/2018, 23/10/2018,The project is currently on track. | 2018-07-31T00:00:00 | High | 1500000 |  | Customer Services, Safety and Regulation Division | 90 | 999273 |  | G | 8 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal services currently required. | 1441000 | 2016-01-01T00:00:00 | TMR
23/10/2018 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project commenced in mid 2015 with an initial exploratory phase, initially scheduled for delivery in mid 2016. Due to the uncertainty of the solution outcome and market capability the project undertook a multi-stage market engagement and procurement process. Once the solution had been fully defined, the schedule was extended by 11 months and the budget increased from $2.5M to $4.1M in January 2017. 23/10/2018, 23/10/2018,Development is now complete. A pilot phase has been successfully completed. The project is now conducting final testing and preparing for a full launch. The program is on track for public release from September 2018. | 2018-07-31T00:00:00 | High | 2500000 |  | Customer Services, Safety and Regulation Division | 95 | 4175019 |  | G | 9 | Implement an online learning and assessment program at the pre learner and/or learner stage, to enhance learning and outcomes for new drivers. | 4176000 | 2015-06-12T00:00:00 | TMR
23/10/2018 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery |  | 2018-06-28T00:00:00 | This commenced in November 2016 with planned completion in mid 2017. Due to an extended procurement process, and the need to include analytical functionality, the schedule was extended 12 months and the budget increased from $300k to $894k in August 2017. The capability was delivered as scheduled in June 2018 and the project is presently finalising closure with formal closure scheduled for August 2018. | 2018-07-31T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 99 | 986705 |  | G | 10 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 989237 | 2016-11-01T00:00:00 | TMR
23/10/2018 | Customer Service, Safety and Regulation Program | Customer Flow Mgmt and Reporting System | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | Pre-project work commenced during FY15/16 with the initiation of the current project commencing in July 2017. The original budget of 300K was rebaselined to 3M once the post market business case was finalised and approved to proceed in May 2018. 23/10/2018,The project is on track for delivery to occur within FY18/19. | 2018-07-31T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 61 | 985043 |  | G | 11 | Replacement of the existing state wide network of customer flow management and reporting systems which is currently supplied by QMatic Australia and will be unsupported in 2017. CSB currently have 43 CSCs around the state that use QMatic systems. Replacement of the existing state wide customer flow management and reporting system which is currently supplied by QMatic Australia and will be unsupported in 2017. | 3083000 | 2015-09-01T00:00:00 | TMR
23/10/2018 | Customer Service, Safety and Regulation Program | Call Centre VOIP Upgrade | 2018-06-30T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Project commenced in July 2017. Due to a resourcing issue. Approval was given to amend the implementation date from June 2018 to August 2018. | 2018-07-31T00:00:00 | High | 1140000 |  | Customer Services, Safety and Regulation Division | 75 | 631198 |  | G | 12 | The Call Centre VOIP Upgrade has commenced to upgrade the VOIP telephony platform within the department. The proposed solution will see a reduction in call costs, a shift in capability to a contemporary solution utilising an existing investment within the department. | 1140000 | 2017-04-01T00:00:00 | TMR
23/10/2018 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The RALPH project commenced in July 2016. Due to vendor software development issues, changes to the schedule and budget were approved in June 2017 with a planned completion to occur by 30 June 2018. A further extension was approved for an additional two months. The project remains on track for closure in August 2018. | 2018-07-31T00:00:00 | Medium | 500000 |  | Customer Services, Safety and Regulation Division | 80 | 696470 |  | G | 13 | TMR's current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace the existing application with a contemporary and supportable alternative to assist the department in maintaining its timely updating of fees and charges. | 734000 | 2016-07-01T00:00:00 | TMR
23/10/2018 | Customer Service, Safety and Regulation Program | Vessel Traffic Services (VTS) | 2016-01-05T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | Pre project work commenced in April 2014 with the initiation of the current project commencing in July 2016. The original budget of $15.2M was rebaselined to $36.2M once the post-market business case was finalised and approved to proceed in April 2017. 23/10/2018, 23/10/2018,The project is on track for delivery in mid 2019. | 2018-07-31T00:00:00 | High | 15224694 |  | Customer Services, Safety and Regulation Division | 52 | 5852380 |  | G | 14 | Replacement of TIM and surface picture software for Reef VTS Phase 1 for the replacement of TIM and surface picture software for Reef VTS. | 36228184 | 2014-04-14T00:00:00 | TMR
23/10/2018 | Customer Service, Safety and Regulation Program | Registration and CTP Certificates Online | 2017-12-31T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | The Registration and CTP Certificates Online project commenced in May 2017 as two separate initiatives Registration Online and CTP Tax Invoice Online. Due to common system synergies the projects were merged in March 2018 resulting in the closure date being revised in accordance with the CTP component. The project is on track for delivery and closure in late 2018. | 2018-07-31T00:00:00 | Medium | 0 |  | Customer Services, Safety and Regulation Division | 60 | 430933 |  | G | 15 | Create an online service for customers to email or print their registration certificate and CTP tax invoices, to provide customers with more convenience, and reduce reliance on paper and post. | 450000 | 2017-05-01T00:00:00 | TMR
23/10/2018 | Customer Service, Safety and Regulation Program | RnL Systems Software Upgrade Stage 2 | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The RnL System Software Upgrade project commenced in July 2017. The original budget of $780K was rebaselined to $1.255M once the post-market business case was finalised and approved to proceed in September 2017. Delivery was completed as scheduled in June 2018 with the project now undergoing closure. | 2018-07-31T00:00:00 | Medium | 780000 |  | Customer Services, Safety and Regulation Division | 87 | 1115666 |  | G | 16 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
23/10/2018 | Customer Service, Safety and Regulation Program | Voice Comms Mgt System | 2017-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | The Voice Comms Management System project commenced in Jan 2017 for completion by mid-2018 however resource availability was impacted due to Cyclone Debbie. Delivery of the capability was completed in April 2018 with the project being formally closed on 5 July 2018. | 2018-07-16T00:00:00 | Medium | 828000 |  | Customer Services, Safety and Regulation Division | 100 | 274738 |  | G | 17 | The Voice Comms Management project consists of two replacement of existing Voice Communication and Control Systems at Townsville and Hay Point. | 828000 | 2016-01-01T00:00:00 | TMR
23/10/2018 | Passenger Transport Technology Program | Single Integrated Network Project (SNIP) | 2018-09-29T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | Final testing of the transport schedule system is planned to be completed this month with implementation in TransLink planned for August. Rollout of the system will follow SEQ 4G bus contract renewals. An Exception Report will be considered by the PTT board to consider this change. | 2018-07-31T00:00:00 | High | 4992243 |  | TransLink Division | 30 | 747017 |  | G | 18 | Enable implementation of performance based contracts for SEQ buses 23/10/2018,Have a system in place that is consistent and integrated across service providers and TransLink 23/10/2018,Reduce or remove inefficiencies and data inaccuracies that occur in the current processes 23/10/2018,Improve transparency of SEQ bus service providers activities and performance 23/10/2018,Improved customer experience through more accurate and reliable SEQ bus service information 23/10/2018,To improve customer experience through more accurate and reliable service information. 23/10/2018,Contributor for achieving Government objectives. 23/10/2018, | 4992243 | 2017-02-23T00:00:00 | TMR
23/10/2018 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Original project commenced in April 2016. 23/10/2018,Budget shortfall identified in November 17. 23/10/2018,In March 18 issues in gathering business data and requirements for new functionality identified. 23/10/2018,The STAS project is reporting amber as a result of unforeseen complexities associated with provisioning and transitioning of business supplied data to the new platform. The project is experiencing delays as resolution activities take place to ensure a good customer experience when the project is released to the public. 23/10/2018,An Exception Report will be considered by the PTT board to enable products to be completed and released by end of March 2019. | 2018-07-31T00:00:00 | High | 4166000 |  | TransLink Division | 75 | 5192212 |  | A | 19 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 5303876 | 2016-04-01T00:00:00 | TMR
23/10/2018 | Policy Planning and Investment Program | Portfolio, Program, Project and Contract Management (3PCM) - Phase 2 and 3 | 2017-03-31T00:00:00 | Delivery |  | 2017-12-22T00:00:00 | The Portfolio, Program, Project and Contract Management (3PCM) project commenced in 2012 with an initial original planned expenditure of $12,757,788. The initial estimate uploaded for 3PCM intentionally included only the project initiation, market assessment and business case development. The estimate was clarified at the end of contract negotiations in the post-market business case and revised to $47,908,928. The Portfolio, Program, Project and Contract Management (3PCM) project has successfully completed its scope and the Program Board endorsed the project closure report in July 2018. The Portfolio, Program, Project and Contract Management (3PCM) project will no longer report on the QG ICT Dashboard after the current reporting period. | 2018-07-16T00:00:00 | High | 12757788 |  | Policy, Planning and Investment Division | 99 | 47794126 |  | G | 20 | Define and implement standard, consistently applied processes for planning, managing and delivering the Transport Infrastructure Portfolio across the domains of portfolio, program, project and contract management 23/10/2018,Source and implement an integrated, strategic information communication technology solution that supports the business process and rules and enables a transition away from legacy applications | 47908928 | 2012-09-01T00:00:00 | TMR
23/10/2018 | CS | Asset Assessment System | 2016-06-30T00:00:00 | Delivery |  | 2019-02-15T00:00:00 | The project is reviewing requirements and schedule before commencing next stage. | 2018-09-11T00:00:00 | Medium | 1688788 |  | Corporate Services | 82 | 1890702 |  | G | 1 | To improve the reliability and integrity of asset information, the ability to report on asset information by applying best practice asset management principles. | 2179995 | 2014-02-27T00:00:00 | DET
23/10/2018 | CS | Automated Website Provisioning Tool | 2018-12-21T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | Medium | 1300000 |  | Corporate Services | 95 | 1200818 |  | G | 2 | To reduce the cost and time required to create new school and corporate websites by developing a tool that provisions new websites from a suite of reusable website templates. | 1242160 | 2017-04-03T00:00:00 | DET
23/10/2018 | CS | Copper Disconnection Management | 2021-06-30T00:00:00 | Delivery |  | 2021-06-30T00:00:00 | The project moved into Delivery in August 2018. The project is tracking to plan. | 2018-09-11T00:00:00 | Low | 2155000 |  | Corporate Services | 25 | 1036571 |  | G | 3 | The project will migrate all copper based services mandated for disconnection to an appropriate replacement technology within the required timeframes specified by nbnTM and Telstra ensuring services are not incorrectly disconnected. | 2155000 | 2017-07-03T00:00:00 | DET
23/10/2018 | PPP | Customer Complaints Management System | 2018-12-21T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | Medium | 2753000 |  | Policy, Performance and Planning | 73 | 680439 |  | G | 4 | Improve the management and reporting of customer complaints. | 2753000 | 2017-09-11T00:00:00 | DET
23/10/2018 | SS | Early Start | 2015-07-03T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | Medium | 70000 |  | State Schools | 47 | 73522 |  | G | 5 | To provide schools with enhanced reporting functionality, improving their ability to analyse Prep to Year 2 student learning data. | 200992 | 2013-04-03T00:00:00 | DET
23/10/2018 | PPP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Delivery |  | 2018-09-24T00:00:00 | The project is tracking to plan. Schedule change approved by project board. | 2018-09-11T00:00:00 | High | 700000 |  | Policy, Performance and Planning | 96 | 1474100 |  | G | 6 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
23/10/2018 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery |  | 2018-12-13T00:00:00 | The project is tracking to plan. Schedule change approved by project board. | 2018-09-11T00:00:00 | High | 659131 |  | Corporate Services | 71 | 408409 |  | G | 7 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DoE FBS SAP future state landscape for the next five years. | 619866 | 2017-01-16T00:00:00 | DET
23/10/2018 | CS | Injury Management System | 2017-03-27T00:00:00 | Delivery |  | 2018-10-01T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | Critical | 1900000 |  | Corporate Services | 67 | 1547593 |  | G | 8 | To improve the management of workplace rehabilitation and claims for injured/ill staff | 1828676 | 2016-10-10T00:00:00 | DET
23/10/2018 | ODG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery |  | 2018-10-01T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | Low | 632585 |  | Office of the Director-General | 91 | 877369 |  | G | 9 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
23/10/2018 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | Critical | 16670000 |  | State Schools | 55 | 12241064 |  | G | 10 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 18115935 | 2015-08-03T00:00:00 | DET
23/10/2018 | ECCE | National Quality Standard Assessment and Rating Data Tool | 2018-12-13T00:00:00 | Delivery |  | 2018-12-17T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | High | 467900 |  | Early Childhood and Community Engagement | 50 | 146304 |  | G | 11 | To improve the security and functionality of the tool used for the assessment and quality improvement of early childhood education and care centres. | 467900 | 2018-02-22T00:00:00 | DET
23/10/2018 | PPP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | High | 1502300 |  | Policy, Performance and Planning | 97 | 1250201 |  | G | 12 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution. | 1266210 | 2016-03-01T00:00:00 | DET
23/10/2018 | PPP | Online School Data Profile | 2018-06-30T00:00:00 | Delivery |  | 2020-02-28T00:00:00 | The project moved into Delivery in August 2018. The project is tracking to plan. | 2018-09-11T00:00:00 | Low | 1872000 |  | Policy, Performance and Planning | 16 | 470788 |  | G | 13 | Improved data interaction capabilities for stakeholders accessing school data profiles. Improved efficiency in production and distribution of information contained in school data profiles. | 1700000 | 2017-10-02T00:00:00 | DET
23/10/2018 | PPP | Redevelopment of the Policy and Procedure Register | 2018-03-30T00:00:00 | Delivery |  | 2018-12-14T00:00:00 | The project is being closely monitored for cost, quality and schedule. Schedule change approved by project board. | 2018-09-11T00:00:00 | Medium | 1015000 |  | Policy, Performance and Planning | 76 | 935767 |  | A | 14 | The high level principles endorsed by EMB for the policy management framework which provides the foundation for this initiative include a consistent user experience for customers, regardless of who they are, where they work, and what they may be looking for; a single point of truth, providing access to all departmental policies and procedures; and publish once, with multiple links where appropriate; and that content is authoritative, relevant and meets quality standards for publication, enabling staff and stakeholders to make good decisions. 23/10/2018, | 935765 | 2016-10-13T00:00:00 | DET
23/10/2018 | CS | SABA Platform Upgrade | 2017-11-09T00:00:00 | Delivery |  | 2019-02-12T00:00:00 | The project moved into Delivery in August 2018. The project is tracking to plan. | 2018-09-11T00:00:00 | Medium | 1791556 |  | Corporate Services | 75 | 1641079 |  | G | 15 | The objective of the project is to replace the existing system, currently hosted on obsolete technology, which is at end-of-service-life. In its current state, the system represents a significant business risk, due to the likelihood of increased system failures, further leading to ongoing business outages and increased maintenance and support costs. | 2303846 | 2017-08-01T00:00:00 | DET
23/10/2018 | SS | Trial of Platform for Virtual Academies | 2017-10-02T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | High | 151641 |  | State Schools | 87 | 236700 |  | G | 16 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage; safe and secure like-minded student virtual communities; and strategic partnerships with university, industry and business. 23/10/2018, 23/10/2018, | 141641 | 2016-06-21T00:00:00 | DET
23/10/2018 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project is tracking to plan. | 2018-09-11T00:00:00 | High | 41000000 |  | Corporate Services | 89 | 34998163 |  | G | 17 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
23/10/2018 | OIR | Information Management/Records Management | 2018-12-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | The project moved into Delivery in July 2018. The project is tracking to plan. | 2018-07-30T00:00:00 | High | 1259381 |  | Office Of Industrial Relations | 75 | 796878 |  | G | 18 | This project will deliver an electronic document and records management system (eDRMS) across OIR.nt. | 1259381 | 2017-07-03T00:00:00 | DET
23/10/2018 | OIR | Investigations Management System | 2018-12-14T00:00:00 | Delivery |  | 2018-12-14T00:00:00 | The project moved into Delivery in July 2018. The project is tracking to plan. | 2018-07-30T00:00:00 | Critical | 461742 |  | Office Of Industrial Relations | 25 | 268369 |  | G | 19 | This project will deliver a case management solution for the OIR Investigations unit. | 644711 | 2017-01-07T00:00:00 | DET
23/10/2018 | OIR | Renewal and Photographic Licensing System (RAPS) Assessor Portal | 2018-07-13T00:00:00 | Delivery |  | 2019-09-03T00:00:00 | The project is tracking to plan. | 2018-07-30T00:00:00 | High | 766467 |  | Office Of Industrial Relations | 47 | 716953 |  | G | 20 | The Assessor Portal project will deliver an improved online services for high risk work licensing accredited assessors, registered training organisations and licensing and advisory services. Currently accredited assessors must use a combination of cumbersome paper based processes, smart forms, and an online service that is difficult to use. | 971488 | 2016-12-14T00:00:00 | DET
23/10/2018 | [20 empty] | INVERSTMENT INFO
23/10/2018 | ICRM | Integrated Customer and Revenue Management (ICRM) | 2021-06-30T00:00:00 | Delivery |  | 2021-06-30T00:00:00 | The project is continuing as planned and is on schedule. 23/10/2018, 23/10/2018,August 2018 - This project is reporting for the first time and is progressing as planned. | 2018-10-12T00:00:00 | High | 24511345 |  | DNRM Finance | 8 | 3357353 |  | G | 1 | Improvements to the way the agency handles revenue collection: 23/10/2018, 23/10/2018,* selection of a modern, enterprise-class, integrated customer and revenue management solution 23/10/2018,* implementation and deployment of the solution to replace the use of the current at-risk receipting systems. | 24511345 | 2017-01-01T00:00:00 | DNRM
23/10/2018 | QWSR | Dam Safety Regulation Solution | 2016-10-30T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | An extension to the approved end date has been endorsed, with no affect on cost. 23/10/2018, 23/10/2018,September 2018 - Documentation is being finalised; the project remains within accepted tolerances. 23/10/2018, 23/10/2018,August 2018 - A change request has been approved altering the planned end date to enable completion of end project activities. 23/10/2018, 23/10/2018,July 2018 - All deliverables have been achieved. Project closure activities are currently under way. 23/10/2018, 23/10/2018,June 2018 - A change request has been approved altering the planned end date to remediate technical difficulties that have been experienced in the move to production. 23/10/2018, 23/10/2018,May 2018 - The project is continuing within timeframe tolerance, and is expected to close prior to the end of May 2018. 23/10/2018, 23/10/2018,March 2018 - The project is continuing as planned. 23/10/2018, 23/10/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 23/10/2018, 23/10/2018,August 2017 - Approved extension of timeframe. 23/10/2018, 23/10/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 23/10/2018, 23/10/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 23/10/2018, 23/10/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 23/10/2018, 23/10/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 23/10/2018, 23/10/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2018-10-12T00:00:00 | High | 1390000 |  | Queensland Water Supply Regulator | 98 | 1385060 |  | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 23/10/2018, 23/10/2018,* support compliance with legislation 23/10/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 23/10/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 23/10/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. | 1390000 | 2012-04-01T00:00:00 | DNRM
23/10/2018 | Natural Resources | Land Condition Assessment Tool | 2018-04-30T00:00:00 | Delivery |  | 2019-01-25T00:00:00 | An extension to the approved end date has been endorsed, with no impact on costs. Note the change to the percentage complete, aligning with deliverable achieved thus far. 23/10/2018, 23/10/2018,September 2018 - An extension to the project end date has been approved to accommodate vendor resource constraints. There is no impact to cost. Discussions are under way with the vendor to ensure resourcing constraints will not impact quality, or further delay delivery. 23/10/2018,August 2018 - The project is continuing as planned, tracking within tolerances for time, cost and quality. 23/10/2018,June 2018 - A change request has been approved altering the planned end date and budget to allow for resolution of unforeseen complexities in deliverables. 23/10/2018,May 2018 - The project timeframe is currently being monitored, with action under way to return it to Green. 23/10/2018,April 2018 - This project is reporting for the first time and is progressing as planned. | 2018-10-12T00:00:00 | Medium | 414000 |  | Operations Support | 53 | 117960 |  | G | 3 | Implement a solution for government, industry and other stakeholders to objectively and consistently assess land conditions, including development of a pictogram-based mobile web application and a data collection tool. | 479000 | 2017-01-12T00:00:00 | DNRM
23/10/2018 | CWeHR | Coal Workers eHealth Records Project | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | The project is continuing as planned, tracking within project tolerances. 23/10/2018, 23/10/2018,August 2018 - This project is reporting for the first time and is progressing as planned. Note finances reported represent Stage 0 and Stage 1. | 2018-10-12T00:00:00 | High | 3894285 |  | Occupational Health and Hygiene - Resources Safety and Health | 5 | 1084207 |  | G | 4 | Improvement in data management and surveillance for coal mine worker health assessments: 23/10/2018, 23/10/2018,* new customer digital interface 23/10/2018,* improved health assessment outcomes through improved access to longitudinal health records 23/10/2018,* enable industry-wide health surveillance through electronic storage and access to health records 23/10/2018,* improved data management using appropriate health management systems and alignment with health record management requirements. | 3894285 | 2017-03-23T00:00:00 | DNRM
23/10/2018 | SO | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery |  | 2019-03-29T00:00:00 | The project is progressing as planned. 23/10/2018, 23/10/2018,August 2018 - The project is continuing as planned, tracking within tolerances for time, cost and quality. 23/10/2018,February 2018 - A change request was approved to alter the scope and associated percentage complete, time-frame and costs. 23/10/2018,December 2017 - Awaiting confirmation of project closure; project is still operating within approved time-frame tolerance. 23/10/2018,November 2017 - A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 23/10/2018,October 2017 - The project is continuing as planned. 23/10/2018,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2018-10-12T00:00:00 | High | 563000 |  | SIMTARS (Safety In Mines Testing and Research Station) | 79 | 899829 |  | G | 5 | The development and delivery of a (replacement) modern and robust Safegas solution: 23/10/2018, 23/10/2018,* risk reduction increasing capability to manage the volume of queries, transactions and data 23/10/2018,* decrease database corruption related to incidents. | 1170000 | 2017-01-25T00:00:00 | DNRM
23/10/2018 | MIRM | Mines Infrastructure Risk Mitigation Project | 2019-02-18T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | The project is ahead of schedule, therefore a change has been endorsed to reduce the approved expenditure. 23/10/2018, 23/10/2018,September 2018 - The project is progressing as planned. 23/10/2018,August 2018 - The project is continuing as planned, tracking within tolerances for time, cost and quality. 23/10/2018,April 2018 - A minor adjustment to scope has been approved; there is no impact to timeframe or cost. 23/10/2018,March 2018 - The project is continuing as planned. 23/10/2018,November 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-10-12T00:00:00 | High | 1200000 |  | Statewide Operations | 92 | 723300 |  | G | 6 | Migrate systems to supported infrastructure and software to: 23/10/2018, 23/10/2018,* provide a stable, secure, fully supported and flexible solution 23/10/2018,* eliminate the risks to which the geoscience data assets are currently exposed. | 922500 | 2017-08-08T00:00:00 | DNRM
23/10/2018 | DPC | Performance Information Management System (PIMS) Dynamics 365 upgrade and relocation | 2018-10-30T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | The project commenced in May 2018 and is on track for delivery. The Discovery Phase has been completed and the scope of work for the upgrade project finalised. 23/10/2018,The PIMS Upgrade Oversight Group is meeting regularly to oversee implementation. Development work and initial system testing has been completed. User acceptance testing is underway | 2018-08-01T00:00:00 | High | 240494 |  | Premier and Cabinet | 70 | 78063 |  | G | 1 | To upgrade the existing PIMS solution from the current 2013 version to Microsoft Dynamics 365 and move the system to Microsoft Online. | 240494 | 2018-05-01T00:00:00 | DPC
23/10/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
23/10/2018 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 23/10/2018,* Move operational accountability and responsibility for print and imaging devices to the service provider 23/10/2018,* Reduce print and imaging costs 23/10/2018,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
23/10/2018 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
23/10/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
23/10/2018 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 23/10/2018, 23/10/2018,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
23/10/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
23/10/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 23/10/2018, 23/10/2018,* reduce operating costs 23/10/2018,* increase capacity 23/10/2018,* improve customer experience 23/10/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
23/10/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
23/10/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 23/10/2018, 23/10/2018, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
23/10/2018 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 23/10/2018, 23/10/2018,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
23/10/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
23/10/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 23/10/2018, 23/10/2018,November 2017 - Actual cost to date corrected due to input error. 23/10/2018, 23/10/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 23/10/2018, | 2017-12-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 57 | 733941 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
23/10/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | An extension to the timeframe has been approved, due to resources constraints. 23/10/2018, 23/10/2018,September 2018 - Closure activities are being finalised; the project remains within accepted tolerances. 23/10/2018,August 2018 - An extension to the timeframe has been approved to allow for closure activities to be finalised. 23/10/2018,July 2018 - Key deliverables have been achieved within project time-frames. Project closure activities are under way, to be finalised within the next two weeks. 23/10/2018,June 2018 - User acceptance testing is almost complete; the solution is about to move into production with project closure activities under way. 23/10/2018,May 2018 - The project is progressing as planned. 23/10/2018,November 2017 - Actual cost to date corrected due to input error. 23/10/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. | 2018-10-12T00:00:00 | Medium | 1750000 |  | Queensland Parks and Wildlife Service | 98 | 1378661 |  | G | 1 | Acquire one or more solution components to operate in conjunction with the agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | EHP
23/10/2018 | QPWS | Augmented Ranger Mobile Application | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project is progressing as planned. 23/10/2018, 23/10/2018,August 2018 - The project has been approved to commence delivery and is publishing for the first time. | 2018-10-12T00:00:00 | Low | 240000 |  | Queensland Parks and Wildlife Service | 30 | 50772 |  | G | 2 | Develop a unique, mobile, optimised solution that uses Augmented Reality to: 23/10/2018, 23/10/2018,* enrich visitors? on-park engagement, experiences and understanding of cultural, historical and ecological points of interests specific to the location 23/10/2018,* provide opportunities for ranger-visitor communications 23/10/2018,* aid collection of real-time visitor data. | 240000 | 2018-02-01T00:00:00 | EHP
23/10/2018 | EPP | Queensland Waste Disposal Levy System | 2019-05-31T00:00:00 | Delivery |  | 2019-05-31T00:00:00 | The project is progressing as planned. 23/10/2018, 23/10/2018,September 2018 - The project has been approved to commence delivery and is publishing for the first time. | 2018-10-12T00:00:00 | Critical | 2248000 |  | Environment Policy and Planning | 20 | 276883 |  | G | 3 | Implement a solution to meet new legislative arrangements for a waste disposal levy, to effectively and efficiently enable: 23/10/2018, 23/10/2018,* site operators to accurately record data 23/10/2018,* reconciliation of waste data and levy liabilities 23/10/2018,* timely access to, and interrogation of, large datasets. | 2248000 | 2018-07-10T00:00:00 | EHP
23/10/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP
20/9/2018 | EHQ | Application Server Replacement | 2018-06-29T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-07-31T00:00:00 | High | 5600000 |  | eHealth Queensland | 34 | 3507503 |  | G | 1 | This project aims to establish a robust, highly available and secure contemporary platform that has the capability to support the agile eHealth Strategy. | 5492863 | 2017-07-03T00:00:00 | DH
20/9/2018 | HSQ | Pathology and Forensic Laboratory System Rehosting Project | 2018-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | July: This project is now reporting 'red' due to delays to the infrastructure component of the project. Options are being prepared to minimise the impact to the overall schedule and cost of the project, to be approved in August 2018. 20/9/2018, 20/9/2018,May: This project was previously known as the 'AUSLAB Rehosting Project'. This project has now returned to green, after receiving governance approval to extend the schedule and budget. 20/9/2018, 20/9/2018,April: Delays have been experienced in project deliverables, with refinements needed to the technical implementation, impacting the project's schedule. | 2018-08-13T00:00:00 | High | 1691324 |  | Health Support Queensland | 57 | 2315000 |  | R | 2 | Delivery of a replacement hardware and visualisation solution for the AUSLAB and AUSCARE systems that will achieve improved resiliency of the architecture, updated operating system and inclusion of virtualisation. AUSLAB and AUSCARE are critical to support laboratories and patient clinical care. | 2963000 | 2017-08-28T00:00:00 | DH
20/9/2018 | MNHHS | Automated Medications Distribution System (AMDS) Stage 1 | 2016-08-01T00:00:00 | Delivery |  | 2018-09-30T00:00:00 |  | 2018-08-14T00:00:00 | High | 3692973 |  | Metro North | 95 | 1070953 |  | G | 3 | The Automated Medication Distribution System (AMDS) Project is part of the broader Electronic Medications Management (EMM) Program. 20/9/2018, 20/9/2018,Once Stage One is implementing, the AMDS machines that will manage medication inventory, storage and recording of medication administration in the Departments of Emergency Medicine (DEM) at Royal Brisbane and Womens Hospital (RBWH), The Prince Charles Hospital (TPCH), Caboolture Hospital and Redcliffe Hospital. 20/9/2018, 20/9/2018,Anticipated benefits associated with AMDS include improved patient safety, improved workflow efficiencies and clinical service delivery, reduced costs of drug diversion, and compliance and adherence to relevant legislative requirements, standards and policies. | 3692973 | 2015-06-01T00:00:00 | DH
20/9/2018 | EHQ | Backup Asset Replacement | 2019-06-28T00:00:00 | Delivery |  | 2019-11-07T00:00:00 |  | 2018-07-31T00:00:00 | High | 11180394 |  | eHealth Queensland | 20 | 606549 |  | G | 4 | The Backup Asset Replacement (BAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the BAR and Storage Asset Replacement (SAR) projects. 20/9/2018,The BAR project was prioritised as part of the 2017-2019 eHealth Queensland ICT program of work. Archiving is used for the long-term retention of data records, in line with the retention requirements outlined by the various legislative, statutory and regulatory policies. | 10915391 | 2017-07-03T00:00:00 | DH
20/9/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Clinical Notes project (release 3.0) | 2018-02-06T00:00:00 | Closed |  | 2018-06-29T00:00:00 | July: This project is now complete. This project upgraded the clinical notes function in CIMHA to improve workflow, data quality, clinician productivity and assists in helping clinicians make better decisions at the point of care. 20/9/2018, 20/9/2018,June: This project has been implemented in June, with only final project governance activities remaining. | 2018-08-17T00:00:00 | High | 1415000 |  | Clinical Excellence | 100 | 1943618 |  | G | 5 | Upgrading the CIMHA Mental Health Act module to accommodate a re-architecture of the CIMHA clinical notes module is required to deliver benefits to the clinical workforce associated with data entry efficiencies; improved data sharing across digital platforms; patient level information transfer to third parties to support service integration and data mining to support service improvement and research. | 1969365 | 2017-02-20T00:00:00 | DH
20/9/2018 | EHQ | Critical Network Hardware | 2018-02-28T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | February: This project has returned to 'on track'. 20/9/2018, 20/9/2018,January: The project is reporting 'Amber' due to limited resource availability and additional technical requirements, impacting the schedule of the project | 2018-07-31T00:00:00 | High | 8636364 |  | eHealth Queensland | 87 | 8056929 |  | G | 6 | The objectives of the project include: 20/9/2018,a) Mitigate the Department of Health risk that core network switches at QH facilities will no longer be supported by the manufacturer from February 2018. 20/9/2018,b) Invest in the replacement of critical ICT network hardware to maintain current capability and reliability of the data network for 120+ enterprise clinical and business applications and provide the foundation for future capability in the enterprise data centres. 20/9/2018,c) Ensure hardware replacement occurs with minimal impact to business operations in Hospital and Health Services or Corporate offices. 20/9/2018,d) Update logical and physical design and architecture documentation for ease of maintenance and management. | 8360652 | 2017-03-06T00:00:00 | DH
20/9/2018 | EHQ | Infrastructure Maintenance Program Establishment | 2018-06-29T00:00:00 | Delivery |  | 2022-06-30T00:00:00 | March: This initiative has been refocused to the establishment phase of the Infrastrucutre Maintenance Program, and as such the % complete and original end date have been updated to reflect this phase of the program. The latest approved end date will be updated in a following reporting month. | 2018-07-31T00:00:00 | High | 1161415 |  | eHealth Queensland | 83 | 1054741 |  | G | 19 | The Infrastructure Maintenance Program (IMP)will establish the infrastructure foundation required to deliver accessible, equitable and innovative services, to support Queenslanders in becoming among the healthiest people in the world. 20/9/2018,The scope includes: 20/9/2018,Uplifting infrastructure technologies across Queensland Health facilities, specified in the Infrastructure Utility investment in the eHealth Investment Strategy. Infrastructure may be initiated by other eHealth investment priorities or by other strategic initiatives in the Digital Health Strategy; these are not in scope. 20/9/2018,Sites that are identified as priority sites for facilities and Wide Area Network (WAN) infrastructure uplift and all sites for End User Computing (EUC) and Security uplift; and 20/9/2018,Increasing capacity of upgrading technologies to meet minimum requirement to enable the eHealth strategy and to mitigate risks. | 1922376 | 2017-07-03T00:00:00 | DH
20/9/2018 | EHQ | Digital Collaboration Platform Program | 2018-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | May: May: This project has now returned to 'green' with the project's revised schedule being approved. 20/9/2018, 20/9/2018,March: Project activities have continued to be delayed, resulting in this project reporting 'Red'. A project change request has been submitted to the project's governance committee. Successful deployment was recently achieved in Townsville. 20/9/2018, 20/9/2018,January: This project is experiencing delays in pre-migration activities. | 2018-07-31T00:00:00 | High | 11000000 |  | eHealth Queensland | 35 | 15614829 |  | G | 7 | This program will deliver digital collaboration tools for any time, any where, any device including: 20/9/2018, Email and Archiving 20/9/2018, Establishment and Collaboration 20/9/2018, Productivity Suite Enablement | 22664506 | 2015-10-29T00:00:00 | DH
20/9/2018 | QAS | Dynamic Deployment and Service Delivery Modelling | 2017-12-31T00:00:00 | Initiate |  | 2019-12-31T00:00:00 | June: The current prosposed date of completion is the 31 December 2019, which is subject to project board approval. | 2018-08-09T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 40 | 631420 |  | G | 8 | This initiative will explore opportunities for QAS to enhance its strategic resource planning capabilities and real-time decision support for resource deployment through contemporary, evidence-based approaches to capital asset and resource management through a Request for Information. | 5697000 | 2015-12-01T00:00:00 | DH
20/9/2018 | CHOPD | Electronic List of Approved Medicines | 2018-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | May: The project has completed a solution evaluation process, with the project requiring additional schedule and financials as originally approved. The project is expecting to return to 'green' upon receiving change request approval. 20/9/2018, 20/9/2018,April: Further solution clarification is required, which has impacted on the overall delivery timeframe of this initiative by a number of weeks. | 2018-08-08T00:00:00 | High | 1166363 |  | Chief Health Officer and Prevention | 76 | 166720 |  | G | 9 | Provide the List of Approved Medicines (LAM) to clinicians in a user friendly way and reduce the number of resources they need to access to safely prescribe a LAM listed medicine, whilst addressing issues of LAM database maintenance. Integrate decision support into the system so that local policy documents and commonly used prescribing references are available to LAM users without the need to search additional applications. | 1384239 | 2017-07-24T00:00:00 | DH
20/9/2018 | MNHHS | Electronic Prescribing and Medication Administration (EPMA) | 2018-11-30T00:00:00 | Delivery |  | 2018-11-30T00:00:00 |  | 2018-08-14T00:00:00 | High | 4827917 |  | Metro North | 68 | 4133873 |  | G | 10 | The Electronic Prescribing and Medication Administration (EPMA) Project is part of the broader Electronic Medications Management (EMM) Program and is intended to be complementary to the state-wide i-Electronic Medical Record (ieMR) program. 20/9/2018, 20/9/2018,Once implemented, EPMA will facilitate the electronic generation of prescriptions; transfer of the order to pharmacy and medication supply systems; then facilitate and record the administration of medication to inpatients in Metro North Hospital and Health Service (MNHHS). 20/9/2018, 20/9/2018,The Stage 1 project involves implementing an information communication technology (ICT) solution in two sites in MNHHS in order to investigate the costs and benefits of such an approach. Stage 2 will deliver EPMA capability (with one or more vendor options) into further clinical settings and Stage 3 will implement EPMA across all services and facilities in MNHHS. | 4827917 | 2016-07-01T00:00:00 | DH
20/9/2018 | EHQ | Enterprise Firewall Service (EFS) | 2019-06-28T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | April: This initiative is now 'in delivery'. | 2018-07-31T00:00:00 | High | 3792744 |  | eHealth Queensland | 20 | 605706 |  | G | 11 | The Enterprise Firewall Service Project will re-design the firewall architecture by leveraging virtual firewall technologies to effectively manage the Queensland Health environment.The architecture will support contemporary cloud services connectivity and enable user-based security policies to align with business scenarios such as anywhere access. | 3723476 | 2017-07-05T00:00:00 | DH
20/9/2018 | EHQ | File Services Migration | 2017-06-30T00:00:00 | Delivery |  | 2018-08-10T00:00:00 | July: A governance decision has been made to postpone delivery scope to a future project, with this phase of the project expecting to complete in August 2018. | 2018-07-31T00:00:00 | High | 3400000 |  | eHealth Queensland | 95 | 3827997 |  | G | 12 | The purpose of this investment is to adopt a contemporary, simplified file management solution for Queensland Health that enables a more cohesive customer experience. | 3888755 | 2016-08-01T00:00:00 | DH
20/9/2018 | MNHHS | Financial System Renewal (FSR) Project | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | July: The project is reporting red due to schedule delays and an anticipated funding shortfall associated with integration complexities and change management activities required. A change request is progressing to address these concerns. 20/9/2018, 20/9/2018,May: The project is currently reporting 'amber' due to the need to refine business requirements, which may have an impact on the project's schedule. 20/9/2018, 20/9/2018,March: The project has returned to 'green' and is continuing with solution testing activities. | 2018-08-14T00:00:00 | High | 105000000 |  | Metro North | 55 | 60300000 |  | R | 13 | The current Queensland Health Finance, Asset and Materials Maintenance Information System (FAMMIS) system is based on a heavily customised solution which is almost 20 years old and no longer supported. 20/9/2018,The objective of the FSR project is to upgrade the existing licences, and transition from FAMMIS to a contemporary solution suite, capable of supporting the Department of Health and all Hospital and Health Services across the state. 20/9/2018, 20/9/2018,The project is proceeding in two stages. The first of which involves the development and evaluation of a solution prototype and the development of a solution roll out plan. The second stage, which is scheduled to commence in the second half of 2017 involves solution configuration and deployment (which will occur in 2018). 20/9/2018,Although there are important ICT components of this project, the major focus is on business-led change management, supported by a skills uplift investment program, to enable the adoption of contemporary best practices across finance, procurement and asset/plant maintenance and to minimise/avoid any system customisation. 20/9/2018, 20/9/2018,As the FSR project proceeds, it will inform the business systems roadmap for Queensland Health, which has a number of other potentially related projects under consideration or development. These include a replacement costing system, a replacement practice management system, consolidation of revenue billing systems, and a new patient administration solution; all of which are intended to contribute to improvements in the management and delivery of health services across the state. | 105000000 | 2016-12-07T00:00:00 | DH
20/9/2018 | EHQ | Follow Me Desktop - Deployment | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-07-31T00:00:00 | High | 3952980 |  | eHealth Queensland | 55 | 1599327 |  | G | 14 | Follow Me Desktop Deployment Project will deliverthe Follow Me Desktop service (FMD) to HHS in alignment with the Infrastructure Remediation Program (IMP) and ieMR rollout schedule, performing both the technical and business change necessary to deploy into clinical environments as well as delivering pilots of FMD capability in specific use cases at customer sites and performing operational support activities. | 3621306 | 2017-07-03T00:00:00 | DH
20/9/2018 | EHQ | HBCIS Hardware Refresh | 2018-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-07-31T00:00:00 | High | 3301500 |  | eHealth Queensland | 23 | 1060778 |  | G | 15 | Project Purpose:To replace the HCBIS server and storage infrastructure that has reached end of life with a supported environment including upgrading to the latest supported software versions. To migrate all HBCIS instances onto the new infrastructure ensuring functionality is retained. | 2345263 | 2017-07-01T00:00:00 | DH
20/9/2018 | EHQ | ICT Security Enhancements (ISE) | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-07-31T00:00:00 | High | 1120000 |  | eHealth Queensland | 55 | 689337 |  | G | 16 | The ICT Security Enhancement Project will mature the state of security controls to improve the security posture of the Department against cyber security threats. | 1072242 | 2017-07-05T00:00:00 | DH
20/9/2018 | EHQ | Identity Access Management Project | 2017-06-30T00:00:00 | Delivery |  | 2020-06-26T00:00:00 |  | 2018-07-31T00:00:00 | High | 3215000 |  | eHealth Queensland | 34 | 5609484 |  | G | 17 | This initiative will implement an Identity Management solution that will provide a consolidated view of an identity and provide the ability to centrally manage the lifecycle of an identity. | 12206443 | 2015-06-22T00:00:00 | DH
20/9/2018 | EHQ | ieMR Program (Funding Packages 3 and 4) | 2019-04-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | July: The Enterprise Schedule Management (ESM) component of ieMR went live at The Townsville Hospital in July 2018. This updated patient scheduling tool will improve inpatient and outpatient scheduling processes. 20/9/2018, 20/9/2018,June: The advanced version of the ieMR system has gone live at the Queen Elizabeth II (QEII) Hospital in June, which includes enhancements to the interface between ieMR and the XRay Radiology Information System. 20/9/2018, 20/9/2018,May: The advanced version of the ieMR system has gone live at the Redland Hospital. Additional clinical reporting was also enabled by ieMR in May. | 2018-07-31T00:00:00 | High | 0 |  | eHealth Queensland | 33 | 0 |  | G | 18 | ieMR will enable improved patient care through the development of a state-wide, authoritative single source of the patient records. 20/9/2018, 20/9/2018,The ieMR will provide clinicians with the ability to: 20/9/2018,* access data that is integrated, accurate and clinically relevant 20/9/2018,* support decision making and better use of information 20/9/2018,* optimise management of patients, resources and provision of services 20/9/2018,* support interaction across a network of providers by making it easier to find providers, transfer information and collaborate with multidisciplinary providers. 20/9/2018,The Program scope (all tranches) is to roll out the ieMR system to 24 hospitals across Queensland. 20/9/2018, 20/9/2018,Please note that financial information for ieMR is Commercial in Confidence | 0 | 2016-11-17T00:00:00 | DH
20/9/2018 | CED | Integrated Mental Health Data Reporting (IMHDRR) Development Program | 2022-06-30T00:00:00 | Delivery |  | 2022-06-30T00:00:00 |  | 2018-08-17T00:00:00 | High | 14673739 |  | Clinical Excellence | 22 | 2596831 |  | G | 20 | The overall goal of the Integrated Mental Health Data Reporting Repository (IMHDRR) is to create a central mental health reporting repository that collates data from multiple source systems and provides the mechanisms to report comprehensive information about mental health consumers and services. 20/9/2018,The ongoing program of work aims to continue and build upon existing functionality by: 20/9/2018, Including additional data from current source systems, including data related to the Mental Health Act 2016 and clinical outcome measurement 20/9/2018, Integrating new data sources (such as the Mental Health Establishments Collection and Emergency Department Collection) 20/9/2018, Creating a 'self-service' functionality that will support HHS to improve the basis of planning and decision making through flexible and tailored analysis and reporting. This is a key initiative within Priority 3 of Connecting Care to Recovery 2016-2021 20/9/2018, Supporting access to a broader range of Queensland Health stakeholders to timely and quality mental health data and analysis. 20/9/2018, Supporting utilisation of clinical quality information by HHS and the Department of Health. | 14673739 | 2017-07-01T00:00:00 | DH
20/9/2018 | QAS | Integrated Performance Reporting Solution (Data Warehouse Platform Upgrade) | 2022-12-21T00:00:00 | Initiate |  | 2022-12-21T00:00:00 |  | 2018-08-09T00:00:00 | High | 6300000 |  | Queensland Ambulance Service | 26 | 570835 |  | G | 21 | Phased delivery of a system supporting QAS business intelligence. | 9240000 | 2017-01-03T00:00:00 | DH
20/9/2018 | CED | integrated Referral Management Solution (iRMS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 |  | 2018-08-20T00:00:00 | High | 33827000 |  | Clinical Excellence | 37 | 15000000 |  | G | 22 | integrated Referral Management Solution (iRMS) is focused on changing the way Hospital and Health Services (HHSs) communicate and interact with Primary Healthcare providers. iRMS is a clinical and process redesign project including the implementation of supporting ICT solutions. | 39408218 | 2017-03-01T00:00:00 | DH
20/9/2018 | HSQ | Integrated Workforce Management (IWFM) Project - Stage 1 | 2016-11-30T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | May: The project has experienced a delay to the completion of Stage 1 due to delays in the governance and assurance process and a change in delivery approach. The project is expecting to complete Stage 1 by the end of August 2018, and is currently seeking final governance approval to confirm additional time and funding to complete this stage. 20/9/2018, 20/9/2018,April: The project has experienced a delay to the completion of Stage 1 due to delays in the governance and assurance process. The project is currently seeking approval to obtain additonal time and funding to complete this stage. 20/9/2018, 20/9/2018,February: Approval delays in obtaining additional funding and a slightly extended schedule has impacted the project's schedule, with approvals expected in the upcoming reporting month. | 2018-08-09T00:00:00 | High | 8200000 |  | Health Support Queensland | 95 | 26997674 |  | G | 23 | The IWFM project involves: 20/9/2018,- configuring additional functionality (currently available and licensed, but unutilised) within the existing Rostering and Payroll business solutions 20/9/2018,- partnering with HHSs to develop refined business models and business processes to support the roster-to-pay process 20/9/2018,- undertaking extensive training and change management to support the adoption and effective usage of new functionality and processes | 28709863 | 2016-02-17T00:00:00 | DH
20/9/2018 | EHQ | Interoperability Project | 2016-04-29T00:00:00 | Delivery |  | 2019-09-29T00:00:00 |  | 2018-08-15T00:00:00 | High | 39189509 |  | eHealth Queensland | 31 | 16696546 |  | G | 24 | Information is central to improving healthcare outcomes and providing integrated care for Queensland Health patients in both hospitals and the community. 20/9/2018,Interoperability means information that is captured and exchanged is fit-for-purpose and consistently understood by all participants involved in the care of a patient. 20/9/2018,The Interoperability Project will replace legacy integration and identity management systems to improve reliability, reduce complexity and make information exchange between Queensland Health systems easier and simpler to change and maintain. 20/9/2018, | 39189509 | 2015-02-01T00:00:00 | DH
20/9/2018 | HSQ | Laboratory Information System Program (LIS Program) | 2019-09-30T00:00:00 | Delivery |  | 2020-12-21T00:00:00 |  | 2018-08-09T00:00:00 | High | 64000000 |  | Health Support Queensland | 51 | 22704195 |  | G | 25 | The move to a patient centric healthcare model requires a change in capability for the LIS used by Queensland Health. 20/9/2018,As a result the LIS program has been established to go to market, understand current vendor capability and select a partner though an open tender process. The successful vendor will support us in delivering a core LIS, as well as extended and next generation LIS capability to support healthcare delivery in Queensland. | 63558771 | 2015-08-28T00:00:00 | DH
20/9/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-07-31T00:00:00 | High | 1651750 |  | eHealth Queensland | 60 | 1127770 |  | G | 46 | Will replace or uplift out of date end of life ICT assets. | 1643098 | 2017-07-01T00:00:00 | DH
20/9/2018 | MNHHS | Learning and Performance Management Project | 2017-06-30T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | July: This project has been implemented in July, with project closure activities expected to occur until November 2018. | 2018-08-14T00:00:00 | High | 1178190 |  | Metro North | 98 | 1256661 |  | G | 26 | Implement an integrated Learning Management and Performance Management system with the capability to deliver online learning and training content, facilitate performance development and maintain centralised records for reporting purposes. | 1312191 | 2016-07-11T00:00:00 | DH
20/9/2018 | GCHHS | Medical Imaging Informatics Solution (MIIS) Risk Mitigation | 2018-12-31T00:00:00 | Delivery |  | 2019-12-31T00:00:00 |  | 2018-08-09T00:00:00 | High | 5000000 |  | Gold Coast | 25 | 2253245 |  | G | 27 | The Medical Imaging Informatics Solution (MIIS) Risk Mitigation project has identified an Imaging solution which will address the risks and opportunities described in the Case for Change including the mitigation of patient safety risks, increased efficiency and productivity, improvi.ng medical imaging billing revenue collection and cash flow. The solution has user endorsement from radiologists and clinicians and will be specifically configured to meet GCHHSs needs. | 12800000 | 2017-04-03T00:00:00 | DH
20/9/2018 | MNHHS | Medication Dispensing and Distribution Robotics (MDDR) | 2018-08-01T00:00:00 | Delivery |  | 2018-09-26T00:00:00 |  | 2018-08-14T00:00:00 | High | 4030460 |  | Metro North | 85 | 4001392 |  | G | 28 | The Medication Dispensing and Distribution Robotics (MDDR) project is part of the broader Electronic Medications Management (EMM) Program. 20/9/2018, 20/9/2018,The MDDR project will implement dispensing robotics to automate medication supply and distribution in the Pharmacy Department of the Royal Brisbane Women's Hospital (RBWH) in Stage 1and facilitate major change in service delivery models for the pharmacy. 20/9/2018, 20/9/2018,Anticipated benefits include: improvements in picking and dispensing accuracy; improved discharge medication processing; improved efficiency in inventory management; increased compliance with National Medication safety standards; and, a reduction in inventory adjustments, time to process impress and dispensing. | 4030460 | 2016-07-01T00:00:00 | DH
20/9/2018 | MNHHS | Metro North Radiology Information System (MRIS) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | May: This project has returned to 'green', with the project's schedule and budget being monitored by the project's governance committee. 20/9/2018, 20/9/2018,April: The project is continuing to report 'Red' due to continued delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-08-14T00:00:00 | High | 6299780 |  | Metro North | 80 | 6485868 |  | G | 29 | Procurement and implementation of a Radiology Information System (RIS) across Metro North Hospital and Health Service to replace existing disparate solutions. | 8280461 | 2014-06-01T00:00:00 | DH
20/9/2018 | EHQ | Metro South and East Queensland ICT Infrastructure Replacement Initiative | 2018-06-29T00:00:00 | Delivery |  | 2019-02-28T00:00:00 |  | 2018-07-31T00:00:00 | High | 4160449 |  | eHealth Queensland | 70 | 1688154 |  | G | 30 | Will replace or uplift out of date end of life ICT assets. | 3583313 | 2017-07-01T00:00:00 | DH
20/9/2018 | EHQ | Metro South East Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-04-29T00:00:00 |  | 2018-07-31T00:00:00 | High | 2182844 |  | eHealth Queensland | 60 | 999117 |  | G | 31 | Will replace or uplift out of date end of life ICT assets. | 2154311 | 2017-07-01T00:00:00 | DH
20/9/2018 | EHQ | Mobile Application System for Bring Your Own Device | 2018-06-30T00:00:00 | Delivery |  | 2018-08-24T00:00:00 | May: This project is now reporting 'red'. Governance pathways and approvals have impacted on the project's overall schedule. The project is progressing with a change request to update the project's deliverables, which will return the project to 'green' upon approval. | 2018-07-31T00:00:00 | High | 1639698 |  | eHealth Queensland | 90 | 1538077 |  | G | 32 | This project leverages the investment of the previous Bring-Your-Own-Device (BYOD)projects to extend the capability of device mobility by building the foundations of a Mobile Application Ecosystem - the processes, products and services to enable the managed development of low/no code applications by Health and Hospital Services (HHS). This project will also complete the deployment of BYOD laptops and provide recommendations on how cost savings can be made by the organisation around Corporate devices and data plans. | 1536395 | 2017-07-01T00:00:00 | DH
20/9/2018 | EHQ | Modernised Managed Operating Environment (MOE) State-wide Migration | 2018-12-28T00:00:00 | Delivery |  | 2018-12-19T00:00:00 | July: The project is now reporting 'amber' due to a lack of technical and deployment resource availability, impacting on the project's schedule. Mitigation actions are in place to reduce the schedule and resourcing impact. 20/9/2018, 20/9/2018,May: This project has now returned to 'green' with the project's revised schedule being approved. 20/9/2018, 20/9/2018,April: This project is experiencing delays in pre-migration activities, delays experienced in another dependent project, and requires additional resources. Further finances are required, with the schedule and finance issues being managed via the project's governance committee. | 2018-07-31T00:00:00 | High | 14100000 |  | eHealth Queensland | 62 | 22290356 |  | A | 33 | A managed operating environment means that everyone within the organisation is running a clean, basic operating system with centralised update management. This includes upgrades of all PC operating systems, preparing QH applications for running on recent operating system environments, and Infrastructure remediation activities to ensure the deployment tools are sufficient and ready for production. | 38741697 | 2016-05-12T00:00:00 | DH
20/9/2018 | QAS | Non-Urgent Patient Transport | 2017-06-01T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | July: The latest approved end date has been updated. 20/9/2018, 20/9/2018,June: The latest approved end date of this project remains at 30 June 2018, pending the approval of a revised implementation date. | 2018-08-09T00:00:00 | High | 1500000 |  | Queensland Ambulance Service | 90 | 910083 |  | G | 34 | Conduct of an open tender process for a non-urgent patient transport online request (service ordering) system. | 1481000 | 2015-10-01T00:00:00 | DH
20/9/2018 | CHOPD | Notifiable Conditions System Replacement | 2019-06-29T00:00:00 | Delivery |  | 2020-02-28T00:00:00 |  | 2018-08-09T00:00:00 | High | 12750000 |  | Chief Health Officer and Prevention | 43 | 2852509 |  | G | 35 | Refresh the ICT systems underpinning the monitoring, surveillance, control and mandatory reporting of notifiable conditions in Queensland. 20/9/2018,This project is expected to result in the retirement of the current NoCS system and possibly niche systems for the management of influenza, TB, HAIs and vaccinations. | 11590000 | 2014-11-01T00:00:00 | DH
20/9/2018 | EHQ | Patient Administration System (PAS) Replacement - Business Case Development Project | 2017-06-30T00:00:00 | Initiate |  | 2019-03-29T00:00:00 |  | 2018-07-31T00:00:00 | High | 3850000 |  | eHealth Queensland | 70 | 5477184 |  | G | 36 | Fit for purpose patient administration systems are vital for Queensland Health to provide the best possible level of healthcare for our communities. These applications support our patients journeys, and ensure that accurate information about our patients is readily available when and where required. 20/9/2018, 20/9/2018,The current phase of the PAS Replacement Program is to develop a preliminary business case to introduce contemporary patient administration capabilities across the State enabling improved: 20/9/2018, support for patient engagement 20/9/2018, integrated care 20/9/2018, clinical research 20/9/2018, population health (for patients using public health services) 20/9/2018, performance transparency 20/9/2018, resource planning. | 11890760 | 2015-11-01T00:00:00 | DH
20/9/2018 | MNHHS | Picture Archiving and Communication System (PACS) | 2017-09-29T00:00:00 | Closed |  | 2018-06-29T00:00:00 | July: This project has now completed. This project has implemented a contemporary Picture Archiving and Communication (PACS) system that will improve service delivery for the Metro North HHS Medical Imaging Departments (and other PACS users), and ensures the PACS solution is able to meet the ongoing needs of the Metro North HHS. 20/9/2018, 20/9/2018,May: This project has returned to 'green', with the project's schedule and budget being monitored by the project's governance committee. 20/9/2018, 20/9/2018,April: The project is continuing to report 'Red' due to continued delays resulting from addressing integration complexities. A change request to extend the go-live date for the project is progressing. | 2018-08-14T00:00:00 | High | 3114694 |  | Metro North | 100 | 3365354 |  | G | 37 | Procure and implement a contemporary Picture Archiving and Communication (PACS) system and functionality that will ensure improved service delivery for the MNHHS Medical Imaging Departments (and other PACS users) through replacement of RBWH PACS ensuring that it is scalable and able to meet the ongoing needs of Metro North Hospital and Health Service. | 3656297 | 2016-07-11T00:00:00 | DH
20/9/2018 | CSD | Practice Management Enterprise Solution | 2018-11-30T00:00:00 | Delivery |  | 2019-01-31T00:00:00 |  | 2018-08-07T00:00:00 | High | 1470000 |  | Corporate Services | 72 | 1790000 |  | G | 38 | The main practice management software used by HHSs to conduct private practice services and billing activities is being replaced. The initiative will procure and implement "like for like" functionality enterprise solution for participating HHSs (15 in total). | 2961432 | 2017-08-01T00:00:00 | DH
20/9/2018 | EHQ | Project, Program and Portfolio Management Application | 2018-03-31T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | May: This project has now returned to 'green' with the project's revised schedule being approved. 20/9/2018, 20/9/2018,April: This project is now reporting 'amber' due to re-aligning the project's schedule and finances to meet changing organisational requirements. The project has submitted | 2018-07-31T00:00:00 | High | 1344177 |  | eHealth Queensland | 30 | 697301 |  | G | 39 | The current state of the current Project, Program and Portfolio Management Application (P3MA) in eHealth is approaching end of life. As such, this project shall define, source and deploy a suitable, supported P3MA for eHealth Queensland for the ongoing management of its multiple, complex projects and significant reporting requirements. 20/9/2018, | 1400462 | 2017-05-02T00:00:00 | DH
20/9/2018 | EHQ | Queensland State-wide ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-07-31T00:00:00 | High | 3246247 |  | eHealth Queensland | 66 | 2286070 |  | G | 40 | Will replace or uplift out of date end of life ICT assets. | 3183491 | 2017-07-01T00:00:00 | DH
20/9/2018 | EHQ | Queensland State-wide ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2018-12-31T00:00:00 |  | 2018-07-31T00:00:00 | High | 3283431 |  | eHealth Queensland | 75 | 3129100 |  | G | 41 | Will replace or uplift out of date end of life ICT assets. | 3273746 | 2017-07-01T00:00:00 | DH
20/9/2018 | MNHHS | Quick Flow Project | 2019-06-30T00:00:00 | Initiate |  | 2019-06-30T00:00:00 |  | 2018-08-14T00:00:00 | High | 6408600 |  | Metro North | 72 | 1748839 |  | G | 42 | The primary purpose of the Quick Flow Project is the implementation of a common outpatient workflow and customer experience system across Metro North Health and Hospital Service (MNHHS) facilities and community services. 20/9/2018,The key objectives of the project are to: 20/9/2018, Implement a consistent Ambulatory Flow Management System for MNHHS in a staged approach 20/9/2018, Improve the outpatient experience across MNHSS facilities and community services 20/9/2018, Improve clinic resource utilisation 20/9/2018, Increase the efficiency of clinical and administrative processes 20/9/2018, Ensure appropriate billing for outpatient services provided | 6408600 | 2016-12-05T00:00:00 | DH
20/9/2018 | CHHHS | Regional eHealth Project | 2017-09-01T00:00:00 | Initiate |  | 2019-12-31T00:00:00 |  | 2018-08-09T00:00:00 | High | 34950000 |  | Cairns and Hinterland | 65 | 13507033 |  | G | 43 | The project aims to deliver a primary and community care focused eHealth solution. This will be supported by changes in processes and practices enabled by new and improved eHealth infrastructure and systems that enhance the quality of, and access to, patient and clinical information in primary, community and hospital-based healthcare facilities across Far North Queensland (FNQ). The solution will support patient focused, integrated care and comprehensive healthcare services delivered as close to the patients home as possible. | 34950000 | 2015-10-05T00:00:00 | DH
20/9/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Critical Uplift Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-02-28T00:00:00 |  | 2018-07-31T00:00:00 | High | 4260336 |  | eHealth Queensland | 71 | 2114055 |  | G | 44 | Will replace or uplift out of date end of life ICT assets. | 4213118 | 2017-07-01T00:00:00 | DH
20/9/2018 | EHQ | Regional North and West Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-07-31T00:00:00 | High | 2150147 |  | eHealth Queensland | 69 | 1472529 |  | G | 45 | Will replace or uplift out of date end of life ICT assets. | 2593463 | 2017-07-01T00:00:00 | DH
20/9/2018 | EHQ | Regional South and East Queensland ICT Infrastructure Replacement Initiative | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-07-31T00:00:00 | High | 4245973 |  | eHealth Queensland | 78 | 3102315 |  | G | 47 | Will replace or uplift out of date end of life ICT assets. | 4216631 | 2017-07-01T00:00:00 | DH
20/9/2018 | EHQ | Service Delivery Excellence Project (SDEP) | 2018-02-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | March: The latest approved end date and percentage complete has been updated. 20/9/2018, 20/9/2018,February: The latest approved end date for this initiative will be updated pending advise from the project. | 2018-07-31T00:00:00 | High | 4822000 |  | eHealth Queensland | 30 | 1664862 |  | G | 48 | The Service Delivery Excellence Project (SDEP) aims to improve the service delivery functions of eHealth Queensland to help the organisation achieve its Customers and services Foundation and Shared Goal: 20/9/2018,Enhance value for customers by streamlining end to end services, processes and delivery models so that we can provide an exceptional customer experience. 20/9/2018,Stage 1 has the primary objective of delivering the Project Initiation Document (PID) for the Service Delivery Excellence Project (SDEP) Stage 2. | 4736721 | 2017-10-03T00:00:00 | DH
20/9/2018 | EHQ | Restrict and Secure Privileged ICT Access (RSPIA) | 2020-06-30T00:00:00 | Delivery |  | 2020-09-30T00:00:00 |  | 2018-07-31T00:00:00 | High | 10500000 |  | eHealth Queensland | 20 | 3098415 |  | G | 49 | The project will implement a privileged access management (PAM) solution controlling all administrative/privileged access to the ICT environment through a system that implements and maintains a sound policy, procedures, and governance in relation to privileged access | 10413570 | 2017-07-03T00:00:00 | DH
20/9/2018 | MNHHS | Royal Brisbane and Women's Hospital Wi-Fi | 2019-06-29T00:00:00 | Delivery |  | 2019-06-28T00:00:00 |  | 2018-08-14T00:00:00 | High | 6000000 |  | Metro North | 40 | 2555189 |  | G | 50 | The RBWH Wi-Fi Project will provide an uplift and renewal to the latest Queensland Health (QH) standard for wireless local area network (WLAN) coverage within the internal areas of prioritised RBWH buildings in order to support digital healthcare. 20/9/2018,Queensland Health issued devices such as laptops, tablets and mobile phones will have access to the newly provisioned wireless network. This wireless network infrastructure also lays the foundations needed in order to enable additional applications and services such as Enterprise Bring Your Own Device (BYOD), Guest Wi-Fi access as well as Real Time Location Services (RTLS), realising even further benefits for the RBWH in the near future. | 6000000 | 2017-10-22T00:00:00 | DH
20/9/2018 | EHQ | Storage Asset Replacement | 2018-06-29T00:00:00 | Delivery |  | 2018-08-31T00:00:00 |  | 2018-07-31T00:00:00 | High | 1671556 |  | eHealth Queensland | 90 | 1406489 |  | G | 51 | The Storage Asset Replacement (SAR) project was derived from the Storage and Backup Asset Replacement (SBAR) project which commenced in FY 16/17 under the 2016-2018 eHealth Queensland prioritised ICT program of work. The scope of the SBAR project is the preliminary evaluation and requirements specification for the SAR and Backup Asset Replacement (BAR) projects. 20/9/2018,The SAR project seeks to outline architecture for storage that will provide a cost effective, scalable and fit for purpose environment for the future of storage services within Queensland Health. Utilising space saving technologies which will enable further cost savings and reduce the requirement for capacity expansion in the short to medium term. | 1653150 | 2017-07-03T00:00:00 | DH
20/9/2018 | EHQ | Sunshine Coast University Hospital (SCUH) Stage 2 ICT Expansion | 2018-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | February: This project has been reported for the first time. | 2018-07-31T00:00:00 | High | 3180000 |  | eHealth Queensland | 82 | 4315067 |  | G | 52 | Sunshine Coast University Hospital (SCUH) ICT Stage 1 delivered the ICT required to achieve the successful commissioning of SCUH in March 2017. The SCUH Stage 2 ICT Expansion covers the investment period from 1 July 2017 to 31 December 2018 and is intended to support the planned expansion of SCUH to increase capacity and establish new services. | 4315067 | 2017-07-03T00:00:00 | DH
20/9/2018 | CHQ | Information Sharing Project Phase 2 | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | July: This project is now reporting 'amber' due to a change in procurement approach, which has impacted on the project's financials and schedule. The project's governance committee is reviewing the updated approach, returning the project to 'green' upon approval (expected to be in September). 20/9/2018, 20/9/2018,March: This project has been reported for the first time. | 2018-08-20T00:00:00 | High | 4455455 |  | Children's Health Queensland | 20 | 1088678 |  | A | 53 | Department of Health, eHealth Queensland, Childrens Health Queensland and Mater Health share a common vision for the seamless integration of care across organisational boundaries, in the interests of patient safety, quality, efficiency and improved access to care. This vision of integrated care processes is enabled through seamless access, at the point of care, to necessary health information and efficient transactional capabilities that support the care continuum. | 4455455 | 2018-01-10T00:00:00 | DH
20/9/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Alcohol and Other Drugs (AODS) Consumer Technical Refresh | 2019-06-28T00:00:00 | Initiate |  | 2019-06-28T00:00:00 | May: This project has been reported for the first time. | 2018-08-17T00:00:00 | High | 1248860 |  | Clinical Excellence | 25 | 310120 |  | G | 54 | This project is refreshing the technical implementation of the CIMHA Consumer module, in preparation for the introduction of new Alcohol and Other Drugs (AODS) system functionality. | 1248860 | 2018-04-16T00:00:00 | DH
20/9/2018 | SPP | Queensland Health Integrated Processing System establishment (QHIDSe) | 2019-10-15T00:00:00 | Delivery |  | 2019-10-15T00:00:00 | May: This project has been reported for the first time. | 2018-08-13T00:00:00 | High | 3257000 |  | Strategy, Policy and Planning | 13 | 943035 |  | G | 55 | The QHIDSe project will develop in-house the foundation of an integrated processing system (i.e. QHIDS (Queensland Health Integrated Data System) using agile techniques and software development tools enabling QHIDS to be used as a replacement for the Queensland Hospital Inpatient Processing System (QHIPS, which processes the Queensland Hospital Admitted Patient Data Collection) and extended through future initiatives to provide new functionality. | 3257000 | 2018-05-25T00:00:00 | DH
20/9/2018 | HSQ | Modernised Managed Operating Environment (MOE) and Digital Collaboration Platform for HSQ | 2018-12-31T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | July: The project is now reporting 'red' due to project team resourcing issues, as well as technical and scheduling delays of a depentent project impacting on the overall schedule. The project's governance committee is reviewing the project's schedule, with the project expecting to return to 'green' upon approval of an updated delivery approach. 20/9/2018, 20/9/2018,June: This project has been reported for the first time. | 2018-08-09T00:00:00 | High | 1057000 |  | Health Support Queensland | 25 | 951473 |  | R | 56 | Delivery of a fully functional, production managed operating environment and digital collaboration platform packaged to all desktops, laptops and some smart devices within the Health Support Queensland environment. | 3414000 | 2018-01-01T00:00:00 | DH
20/9/2018 | CHOPD | Mosquito-borne Disease Program: Spatial Database Project | 2019-06-21T00:00:00 | Initiate |  | 2019-06-21T00:00:00 | June: This project has been reported for the first time. | 2018-08-09T00:00:00 | High | 854545 |  | Chief Health Officer and Prevention | 55 | 178677 |  | G | 57 | The vector surveillance and control program requires a state-wide surveillance and control solution to assist with the response to the risk of Dengue, Zika and Chikungunya virus outbreaks in vulnerable North Queensland and the mitigation of emerging risks across Central and Southern Queensland. | 1502672 | 2017-07-31T00:00:00 | DH
20/9/2018 | EHQ | Telehealth Asset Replacement | 2019-06-28T00:00:00 | Initiate |  | 2019-06-28T00:00:00 | July: This project has commenced reporting for the first time. | 2018-07-31T00:00:00 | High | 1950000 |  | eHealth Queensland | 5 | 10822 |  | G | 58 | Telehealth is the delivery of health services and information using telecommunication technology. Telehealth can be leveraged to support new and innovative service delivery models in the health sector and facilitate access to safe, sustainable and appropriate health care that is simple, equitable and timely for all Queenslanders. The Telehealth Asset Replacement Project is responsible for the replacement of prioritised, highly utilised and critical videoconference systems which have reached their end-of-financial-life. | 1950000 | 2018-07-02T00:00:00 | DH
20/9/2018 | MNHHS | Connecting Care information Program (CCI) | 2022-06-30T00:00:00 | Initiate |  | 2022-06-30T00:00:00 | July: This project has commenced reporting for the first time. | 2018-08-14T00:00:00 | High | 760455 |  | Metro North | 15 | 945008 |  | G | 59 | The Connecting Care Information Program - CCI -will support streamlining and improvement of clinical and administrative workflows through delivery of key Information Technology (IT) enablers. | 1159733 | 2017-03-21T00:00:00 | DH
20/9/2018 | MNHHS | Metro North Health and Hospital Service Contemporary Workspace Phase 1 | 2019-01-01T00:00:00 | Delivery |  | 2019-01-01T00:00:00 | July: This project has commenced reporting for the first time. | 2018-08-14T00:00:00 | High | 233000 |  | Metro North | 40 | 578692 |  | G | 60 | This project is focusing on prepraring the Metro North Hospital and Health Service (MNHHS) applications to be ready for contemporary operating system deployment. | 1665831 | 2017-08-01T00:00:00 | DH
20/9/2018 | MNHHS | Metro Norht Picture Archiving and Communication (PACS) Replacement for The Prince Charles Hospital | 2018-12-03T00:00:00 | Initiate |  | 2018-12-03T00:00:00 | July: This project has commenced reporting for the first time. | 2018-08-14T00:00:00 | High | 3101451 |  | Metro North | 22 | 516862 |  | G | 61 | Procure and implement a contemporary Picture Archiving and Communication (PACS) System and functionality that will ensure improved Service delivery for the MNHHS Medical Imaging Departments at The Prince Charles Hospital (TPCH). | 3101451 | 2017-12-01T00:00:00 | DH
20/9/2018 | CED | Consumer Integrated Mental Health Application (CIMHA) Secure Transfer Project | 2019-01-28T00:00:00 | Initiate |  | 2019-01-28T00:00:00 | July: This project has commenced reporting for the first time. | 2018-08-17T00:00:00 | High | 610000 |  | Clinical Excellence | 10 | 125001 |  | G | 62 | The purpose of this initiative is to upgrade the CIMHA application with functionality to automate the sending of selected clinical notes and data securely. This will improve the efficiency and timeliness of information sharing. | 1109521 | 2017-10-16T00:00:00 | DH
20/9/2018 | CED | Patient Online Portal (POP) | 2019-12-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | July: This project has commenced reporting for the first time. | 2018-08-20T00:00:00 | High | 15500000 |  | Clinical Excellence | 8 | 1662524 |  | G | 63 | The Patient Online Portal (POP) aims to improve a patients outpatient journey through greater visibility and enhanced communication capability across specialist services. Additionally, the solution seeks to provide greater flexibility in the provision of outpatient services, allowing patients to better manage their care. | 15500000 | 2018-03-05T00:00:00 | DH
20/9/2018 | MNHHS | Digital Transformation Readiness | 2018-12-27T00:00:00 | Initiate |  | 2018-12-27T00:00:00 | July: This project has commenced reporting for the first time. | 2018-08-14T00:00:00 | High | 2771674 |  | Metro North | 10 | 517341 |  | G | 64 | The key objectives of Digital Transformation Readiness are to perform activities in preparation for Metro North Hospital and Health Service (MNHHS) Digital Transformation with a focus on the integrated electronic Medical Record (ieMR) readiness. | 2771674 | 2018-06-29T00:00:00 | DH
20/9/2018 | MNHHS | Referral Lodgement and Tracking (RLaT) | 2019-01-23T00:00:00 | Delivery |  | 2019-01-23T00:00:00 | July: This project has commenced reporting for the first time. | 2018-08-14T00:00:00 | High | 2783379 |  | Metro North | 43 | 1924629 |  | G | 65 | This project will deliver a state-wide capability for referrers to lodge patient referrals electronically with Queensland Health. The referral will be automatically routed to the appropriate Hospital and Health Service (HHS). | 2783379 | 2018-02-09T00:00:00 | DH
20/9/2018 | WOD | Community Recovery Reform ICT Project | 2017-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Project planned expenditure and end date have been revised due to a number of factors: 20/9/2018, 20/9/2018,- The original planned expenditure of $2.2M was a high level estimate and has been refined with the complexity of the processes and system being uncovered as the project was stood up. 20/9/2018, 20/9/2018,- An increased scope and associated effort to ensure maximum benefit is gained from the investment, so that Queenslanders are better supported during natural disasters. 20/9/2018, 20/9/2018,- Delays to project schedule and associated additional resourcing costs as a result of: 20/9/2018, 20/9/2018, - Staff diverted to priority community recovery support roles during activations over the last 12 months, including TC Debbie, TC Nora and the North Queensland floods. During natural disasters, our agency resources are focused on providing critical support to communities and Queenslanders in need. 20/9/2018, 20/9/2018, - Extended vendor delivery times due to defects and quality concerns including system performance. The department is working with the vendor to resolve these issues. | 2018-06-30T00:00:00 | High | 2208000 |  | Department of Communities, Disabilty Services and Seniors | 89 | 3022000 |  | G | 1 | This project will deliver an integrated streamlined solution to support the department in the management of disasters. | 3780000 | 2016-07-01T00:00:00 | DCCSDS
20/9/2018 | Cross-Gov | Human Resource Information Solution (HRIS) Program | 2017-12-31T00:00:00 | Delivery |  | 2019-12-24T00:00:00 | The Queensland Fire and Emergency Services (QFES) Human Capital Management Case Management module delivery has been completed with UAT and Penetration testing finalised for implementation. The Workplace Health and Safety module has completed UAT and will be released into production following completion of agency training. The closure report for this project has commenced. 20/9/2018, 20/9/2018,The Queensland Corrective Services Human Capital Management Business Case has been approved with detailed project planning and resource engagement underway. Gate 3 Investment Decision review has been completed. Project startup planning for implementation has commenced. 20/9/2018, 20/9/2018,The Queensland Ambulance Service (QAS) and QFES payroll projects transitioning to Aurion are progressing to schedule, with QAS being the next for implementation planned for November 2018. 20/9/2018, 20/9/2018,Detailed planning of the Integration requirements for the program continue to be progressed. 20/9/2018, 20/9/2018,At the direction of the Executive Steering Committee (3/07/18) the program scope was increased to include the procurement of a Time and Attendance solution for QFES, QAS and QCS. | 2018-06-30T00:00:00 | Critical | 101500000 |  | Cross-Government program led by DSITI | 65 | 59979631 |  | A | 1 | The HRIS Program mandate is to replace the existing Queensland Ambulance Service, Queensland Corrective Services, Inspector-General Emergency Management and Queensland Fire and Emergency Services human resource and payroll systems that will meet the following key business outcomes: 20/9/2018, 20/9/2018,* Sustainable and supported HR and Payroll service delivery 20/9/2018,* Operational efficiencies through standardised and automated business processes based on self service capability and workflow 20/9/2018,* Strategic HR capability that supports the development, performance and safety of the departments workforce 20/9/2018,* Business Intelligence capability that provides real timely, integrated HR information 20/9/2018,* Value-for-money outcomes that incorporates innovation and continuous improvement as core themes 20/9/2018,* System architecture that provides integration with dependant departmental systems and supports mobility and portability of staff across government 20/9/2018,* Align with the Commission of Audit Recommendations | 101275371 | 2012-09-03T00:00:00 | CROSS GOV
20/9/2018 | QPS | GPS Tracking (Bail) | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | Legislation provisioning for GPS monitoring of court bailed offenders commenced on 31/3/18. QPS established interim GPS tracking capability leveraging existing contract held by Queensland Corrective Services. 20/9/2018,QPS is now undertaking a Whole of Government open Invitation-to-Offer to establish a longer term contract for GPS tracking devices and monitoring of offenders. 20/9/2018,Note: The project is currently undergoing procurement/commercial activity and is therefore not publishing any financial data. | 2018-08-22T00:00:00 | High | 0 |  | Queensland Police Service | 40 | 0 |  | G | 1 | As per the Commencement of the Bail (Domestic Violence) and Another Act Amendment Act 2017 (the Amending Act) on 30 March 2018, Magistrates will be empowered to impose a tracking condition on a defendant granted bail as a condition of their bail undertaking. 20/9/2018,As such the QPS intends to progressively implement an electronic monitoring capability on a State Wide basis. 20/9/2018,An implementation project has commenced to create an electronic monitoring capability for geographically locating and monitoring a defendant on bail for QPS to meet requirements of the Amended Act. 20/9/2018,The GPS Tracking Project is an initial proposal to validate the utility of the technology prior to seeking a longer term solution. | 0 | 2018-03-30T00:00:00 | QPS
20/9/2018 | QPS | Online National Police Certificate | 2017-06-30T00:00:00 | Closed |  | 2018-07-31T00:00:00 | Since the successful launch of Online National Police Certificates 83% of all applications have been submitted online. The project is now officially closed effective 31 July 2018 and has transitioned to business as usual. 20/9/2018, 20/9/2018,Feb 18: The revised project budget has been amended from previously published figures to reflect the increased investment in promotional products. | 2018-08-22T00:00:00 | High | 275000 |  | Queensland Police Service | 100 | 250000 |  | G | 2 | The Online National Police Certificate Project will implement an online service for the community to apply and pay for Name Only National Police Certificates online, rather than presenting at a police station, or using the online services of an Australian Crime Intelligence Commission accredited broker. This will provide improved customer service to the community through a more efficient and reliable QPS service, with no requirement to present at a police station, as well as provide efficiency and time savings to local police stations and the Police Information Centre. | 250000 | 2017-01-01T00:00:00 | QPS
20/9/2018 | QPS | Police Integrity and Professional Standards | 2018-08-24T00:00:00 | Delivery |  | 2019-12-31T00:00:00 | Full funding has now been approved for the Police Integrity and Professional Standards IT system. 20/9/2018, 20/9/2018,The Project has received a green assessment for the Gate 3 Quality Assurance Review and will commence delivery in July 2018 with an approved revised project end date of 31 December 2019. 20/9/2018, 20/9/2018,Feb 18: Note: original planned end date amended as previously published information was incorrect. | 2018-08-22T00:00:00 | High | 4142000 |  | Queensland Police Service | 35 | 307200 |  | G | 3 | This initiative will deliver a new integrated Police Integrity and Professional Standards IT System replacing multiple existing systems across the suite of business activities undertaken within the Ethical Standards Command. The Police Integrity and Professional Standards system will provide advanced reporting and analytics, as well as improve current business processes, in particular around the management of complaints. The Police Integrity and Professional Standards Project will also complement the Complaints Reform Project established by the QPS to deliver process reform addressing deficiencies in its complaints and discipline systems. Implementation of the Police Integrity and Professional Standards system will place the QPS in a strong readiness position to fully implement Complaints Reform Project-generated changes to disciplinary processes and immediately deliver the benefits of these changes. | 6792000 | 2017-03-07T00:00:00 | QPS
20/9/2018 | QPS | Advanced Data Analytics | 2017-07-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | The Advanced Data Analytics Project was established to progress the QPS advanced analytics strategy and capability. 20/9/2018, 20/9/2018,Demand and Resource Committee on 23 July 2018 noted the Advanced Data Analytics End Project Report and approved the closure of the Advanced Data Analytics Project. 20/9/2018, 20/9/2018,The additional $59,389 expenditure on the project was incurred to extend some resources to support the transition of capabilities into business as usual. This amount is within the accepted QPS tolerance for project variance. 20/9/2018, 20/9/2018,The project delivered more than was proposed in the original submission, leaving legacy capability that has transitioned into business as usual. 20/9/2018, 20/9/2018,Jun 18: The QPS Demand and Resource Committee approved the extension of the project closure date to 30 June 2018 and an additional $1,114,000 in funding to facilitate achievement of the projects objectives. | 2018-08-22T00:00:00 | Low | 1731000 |  | Queensland Police Service | 100 | 2904389 |  | G | 4 | Develop the QPS Advanced Data Analytics proof-of-concept. This proof-of-concept is intended to inform a larger suite of data analytics integration and intelligence over the next four years, including the development of predictive and alert models to enhance the operational response to threats, incidents and events. | 2845000 | 2017-02-19T00:00:00 | QPS
20/9/2018 | QPS | Body Worn Cameras | 2018-02-28T00:00:00 | Closed |  | 2018-06-30T00:00:00 | The Project completed the deployment of all Stage Two body worn cameras in December 2017 and transitioned to business as usual on 30 June 2018. The Project is now going through approval for formal closure. 20/9/2018, 20/9/2018,Feb 2018: The original budget was $6.03M. In May 2017, the QPS Demand and Resource Committee approved an additional $0.860M, making the total approved budget $6.890M | 2018-08-22T00:00:00 | Medium Low | 6030000 |  | Queensland Police Service | 100 | 6890000 |  | G | 5 | The Queensland Police Service Body Worn Camera Project is deploying 5100 body worn cameras to frontline police officers. Body worn cameras will be deployed to 168 police stations, 16 tactical crime units, 47 road policing units, and specialist units including dog squads and the Public Safety Response Team in two stages. The cameras integrate with the QPS mobility devices, allowing officers to add metadata to videos and to review videos in the field. A system for storage and allocation of digital camera data will also be implemented as well as policy related to use of the cameras. | 6890000 | 2014-08-25T00:00:00 | QPS
20/9/2018 | CS | ICT Disaster Recovery Model Project (IDRP) | 2018-06-30T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Objectives 20/9/2018,This project will deliver a secondary DR site and hyper-converged system to provide resilience for all departmental business applications in the event of a disaster. 20/9/2018, 20/9/2018,Project Updates 20/9/2018,Core infrastructure DR implementation 80% complete. All migrated production systems successfully replicating to secondary DR site. 20/9/2018,Oracle system DR implementation is 100% complete 20/9/2018,Legacy applications undergoing case-by-case assessment to identify best option for DR implementation: application upgrade, application replacement, defunct applications to be decommissioned. External vendor engaged to assist. Anticipated completion by Dec 2018. 20/9/2018,Oracle applications DR testing successfully completed. 20/9/2018,All end-of-life ICT infrastructure will be decommissioned by Dec 2018. 20/9/2018,The newly implemented infrastructure will provide improved stability and life extension to existing business-critical applications. 20/9/2018,DR recovery procedure development, testing strategy and ICT DR Plan update in progress. 20/9/2018, 20/9/2018,Some issues have impacted YTD position however it is anticipated the original completion date will be met. 20/9/2018, 20/9/2018,The revised total estimated expenditure has changed due to the approval of additional work packages. | 2018-07-31T00:00:00 | High | 7460674 |  | Corporate Services | 80 | 4836208 |  | G | 1 | *Provide the department with an implemented recovery strategy which can be used in the event of a disaster to restore the ICT systems that underpin any impacted business critical services. | 6257794 | 2016-10-01T00:00:00 | DJAG
20/9/2018 | BCS | Blue Card Services Recommendation 28.1 Project - Blue Card Home Based Care Register | 2018-12-21T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | In July 2016, the Queensland Family and Child Commission QFCC released the When a child is missing Remembering Tialeigh, A report into Queenslands children missing from out of home care report making 29 recommendations. Recommendation 28 required the QFCC to undertake a further review of legislation, policies and practices relating to information sharing between relevant agencies responsible for children in regulated service environments. 20/9/2018,The Recommendation 28 Supplementary Review, A report on information sharing to enhance the safety of children in regulated home based services (Supplementary Review) is the QFCC response to Recommendation 28 and makes 17 recommendations in relation to information sharing between agencies responsible for regulating and monitoring regulated services provided from the home, namely foster and kinship care, family day care and stand alone care services. 20/9/2018,Implementation of the register will require legislative amendment. | 2018-07-31T00:00:00 | High | 1573000 |  | Blue Card Services | 45 | 663540 |  | G | 2 | The objective of this project is to establish a register for recording and reporting on regulated child-related services provided from the home, specifically limited to foster/kinship care, family day care and stand-alone care. As recommended by the Queensland Family and Child Commission (QFCC) within the Recommendation 28 Supplementary Review Report (A report on information sharing to enhance the safety of children in regulated home-based services) this register will: 20/9/2018,a) identify co-located home-based services 20/9/2018,b) enable the Queensland Police Service to have line of sight to the register to access up-to-date information when Police attend a residential address to identify potential risks to children, and 20/9/2018,c) make information available to agencies, including Department of Child Safety, Youth and Women, Department of Education and the Office of the Public Guardian to assist with regulating and/or monitoring specific home-based services. | 1573000 | 2017-04-01T00:00:00 | DJAG
20/9/2018 | HHS | Future of Property and Tenancy Systems | 2017-06-30T00:00:00 | Delivery |  | 2019-03-31T00:00:00 | The FOPATS Program undertook a significant re-baseline in late 2016 to inform and approve changes to its strategic direction, scope, delivery methodology, timing and costs, including strengthening program governance and revising the Business Case to complete against a two staged implementation, Property and then Tenancy. 20/9/2018, 20/9/2018,Following this review, the Property Release, the first of two stages, was delivered successfully on time on 1 November 2017 and delivered benefits including efficiencies in property management and reporting. 20/9/2018, 20/9/2018,The refreshed business case, the Program budget and planned end date were formally re-baselined in January 2018. This formal approval, coupled with the successful delivery of the first stage Property Release, saw the Program status move to green. 20/9/2018, 20/9/2018,The Program has completed more detailed planning for the second stage Tenancy Release, which will remove the operational dependency on the existing ICT housing solution entirely. Tenancy design activities are now well progressed, with a view to determining a feasible Program end date. 20/9/2018, | 2018-06-30T00:00:00 | Critical | 56286000 |  | Housing and Homelessness Services | 62 | 76536997 |  | G | 1 | Replace the existing ICT housing solution with an integrated ICT system. | 121597695 | 2013-07-01T00:00:00 | HPW
20/9/2018 | QGP | Fleet Management System Replacement Project (FMSRP - Qfleet) | 2019-09-30T00:00:00 | Initiate |  | 2019-09-30T00:00:00 | The project is tracking to plan. The project is currently subject to procurement activities and has commenced lead implementation activities. | 2018-06-30T00:00:00 | High | 13939200 |  | Qfleet | 21 | 655518 |  | G | 2 | The objective of the FMSRP is the procurement and implementation of a new common Fleet Management System that meets QFleet, QPS, QFES and QAS core business requirements and provides best value for money. It will provide a contemporary, sustainable common Fleet Management System that delivers effective and efficient business services for the agencies now and into the future. | 13937796 | 2017-10-19T00:00:00 | HPW
20/9/2018 | QGP | Qfleet Car Sharing Model Implementation Project (CSMIP) | 2018-08-31T00:00:00 | Initiate |  | 2018-08-31T00:00:00 | Procurement activity currently nearing a conclusion. Expecting contract award to occur July/August with implementation to commence soon after. 20/9/2018,The Department has recently updated their publishing criteria for initiatives. This project is publishable under our revised publishing criteria. | 2018-06-30T00:00:00 | High | 454735 |  | Qfleet | 50 | 55665 |  | G | 3 | The objective of the Car Sharing Model Implementation Project (CSMIP) is the procurement and implementation of a fully automated, innovative and sustainable multi-agency car sharing solution delivering effective and efficient short-term motor vehicle hire services for government, now and in the future. | 454735 | 2017-11-20T00:00:00 | HPW
20/9/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Smart Service delivers services on behalf of government via both telephone and counter channels. Some of these services involve financial transactions involving credit card payments. 20/9/2018,The Payment Card Industry (PCI) have stipulated compliance security standards that the government (through Smart Service) has to meet. This project was scoped with ensuring these standards were met. Following a recent external assessment it has been confirmed that this objective has been achieved. The project has completed its planned activities and closed on 29 June 2018. | 2018-06-30T00:00:00 | Critical | 516033 |  | Smart Service Queensland | 100 | 1130918 |  | G | 4 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | HPW
20/9/2018 | SSQ | Automated Payments Solution | 2018-07-31T00:00:00 | Initiate |  | 2018-07-31T00:00:00 | Smart Service Queensland (SSQ) is required to continue to take payments over the phone while remaining Payment Card Industry Data Security Standard (PCI DSS) compliant. 20/9/2018, 20/9/2018,SSQ has commenced the introduction of a VOIP solution to replace the existing analogue telephony capability. This forms the basis of the Telephony Replacement Project (TRP). 20/9/2018, 20/9/2018,To continue to meet ongoing PCI-DSS compliance, additional technology is required to enable secure payments over the phone in a VOIP environment. 20/9/2018, 20/9/2018,The Automated Payment Solution (APS) project will ensure this compliance is maintained and the new technology is implemented. The procurement process is progressing. 20/9/2018, 20/9/2018,Up until June 2018 the APS project has been in a project light, discovery phase - determining if viable solutions were available in the marketplace. This is why the project has reported as amber and the budget spend limited. The project will be re-baselined in July 2018, and a new, more accurate project end date will be determined based upon realistic procurement and implementation timeframes for an off the shelf product. 20/9/2018, | 2018-06-30T00:00:00 | Critical | 1500000 |  | Smart Service Queensland | 5 | 29961 |  | A | 5 | The project will implement an improved capability for offering secure payment card transactions via the telephone. To meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS) when the new VOIP telephony solution is introduced. | 1500000 | 2018-01-29T00:00:00 | HPW
20/9/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | The initial re-planning activity was completed in June 2018. However, further review of the schedule was requested and is underway. Once complete an Exception Report will be created for consideration by the Board. | 2018-06-30T00:00:00 | Critical | 4490634 |  | Smart Service Queensland | 63 | 3729727 |  | A | 6 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 20/9/2018, 20/9/2018,* reduce operating costs 20/9/2018,* increase capacity 20/9/2018,* improve customer experience 20/9/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | HPW
20/9/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Project closure and handover activities are underway. | 2018-06-30T00:00:00 | Critical | 3476245 |  | Smart Service Queensland | 98 | 2083254 |  | G | 7 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2348880 | 2015-11-20T00:00:00 | HPW
20/9/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | SSQ is introducing a new VOIP based telephony platform through the Telephony Replacement Project (TRP). SSQ has also implemented a new agent scripting tool via the Content Delivery Solution (CDS) project. The Technology Platform Project (TPP) is delivering the core underlying technology used by both projects and some other shared ICT centric deliverables, such as Load and Performance Testing, and Security Penetration Testing. The core hardware platform has been successfully delivered and is being utilised by CDS and TRP. The TPP is currently awaiting readiness of some TRP deliverables before progressing the final TPP deliverables. | 2018-06-30T00:00:00 | Critical | 3390862 |  | Smart Service Queensland | 82 | 2435825 |  | A | 8 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution and the call recording solution. | 3390862 | 2017-05-15T00:00:00 | HPW
20/9/2018 | DTS | Digital Archiving Program - Tranche 1 | 2019-12-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | Procurement stage is progressing to planned timeframes and milestones with preferred Offeror identified and contract ready for execution. Government approvals to execute underway. Transition-In planning progressing well. | 2018-06-30T00:00:00 | Critical | 12701000 |  | Digital Technology and Services | 95 | 1872402 |  | G | 9 | To ensure the delivery of an as-a-Service eco-system to effectively archive, manage and enable search and discovery of Queensland's permanent high value records. The new digital services will support the Queensland Government's blueprint for innovation and collaboration, providing better outcomes for Queenslanders. | 12701000 | 2017-07-01T00:00:00 | HPW
20/9/2018 | OSSSIO | Customer Identity and Details Enhancements FY17-18 | 2018-10-30T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | The project is on track to deliver as per the project schedule. 20/9/2018,The Department has recently updated their publishing criteria for initiatives. This project is publishable under our revised publishing criteria. | 2018-06-30T00:00:00 | High | 1200000 |  | One-stop Shop Strategy and Implementation Office | 80 | 1185000 |  | G | 10 | Improved technology and functionality to meet agency requirements in customer identity and details to enable agency adoption and uptake driving further value for customers. 20/9/2018, 20/9/2018,* CDM Blueprint 20/9/2018,* Transition to new platform 20/9/2018,* Auth pilot 20/9/2018,* CDM release 2 pilot | 1200000 | 2017-07-01T00:00:00 | HPW
20/9/2018 | PWAM | Non-Conforming Building Products (NCBP) Website | 2018-08-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | The Safer Buildings website is being developed to support the introduction of proposed changes to the Building Regulation 2006. 20/9/2018,The Department has recently updated their publishing criteria for initiatives. This project is publishable under our revised publishing criteria. | 2018-06-30T00:00:00 | Critical | 770924 |  | Public Works and Asset Management | 50 | 305849 |  | G | 11 | Development of a website (the Safer Buildings Website) for private building owners to register and submit information through a self-assessment checklist to assess their buildings for the existence of potentially combustible cladding. | 770924 | 2018-05-01T00:00:00 | HPW
20/9/2018 | CS | ICT Infrastructure Refresh Project | 2018-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | Progressing as planned. 20/9/2018,The Department has recently updated their publishing criteria for initiatives. This project is publishable under our revised publishing criteria. | 2018-06-30T00:00:00 | Medium | 1173338 |  | Corporate Services | 92 | 647941 |  | G | 12 | To upgrade ICT infrastructure to maintain a fully supported and secure environment and leverage and take advantage of offerings from current DHPW licencing agreements. | 1173338 | 2017-02-13T00:00:00 | HPW
20/9/2018 | ICTSS | Government Wireless Network Contract and Administration Billing System | 2018-06-30T00:00:00 | Initiate |  | 2018-12-31T00:00:00 | There is a requirement to develop a requirements specification for the GWN Wireless Network Contract and Administration Billing System. This has not been completed as it was determined additional resources were required to progress this project i.e. a Project Manager. Originally this digital project was being resourced by existing staff within the GWN Contract Directorate, therefore no expenditure has occurred to date. The procurement process has been delayed for the same reason, but has recommenced now that a Project Manager has been sourced and commenced employment with the GWN Contract Directorate on Monday 13 August. 20/9/2018, | 2018-06-30T00:00:00 | High | 0 |  | ICT Strategic Sourcing | 10 | 0 |  | G | 13 | The GWN Contract Directorate seeks a fully managed software as a service solution to replace existing excel spreadsheets and macros that have organically grown in complexity, improve record keeping compliance, and alleviate current single points of failure and reliance. 20/9/2018,The current contract modification process and Public Safety Agencies (GWN service consumers) invoicing is managed via complicated spreadsheets and macros, colloquially called The Mod Register. The management of contract modifications and invoicing via the Mod Register is manually intensive, cumbersome, is pushing the capabilities of Microsoft Excel, prone to macro errors and due to its size is becoming unwieldly to manage. Also, 20/9/2018,Contractor Performance, including the contractor abatement calculation process, is not centrally managed in one system. A variety of Contractor generated reports are manually validated and reconciled, with problematic auditability. 20/9/2018,Communication of information between GWN Contract Directorate, Public Safety Agencies and Contractor is done via email and attachments of spreadsheets and PDFs in these emails. Management and storage of emails and attachments is problematic, especially version history and control. 20/9/2018,There is now a requirement to procure a purposely designed software system that is fully functional, customisable, redundant, reliable, will meet the current and future requirements of the GWN Contract, and replace current Contract Modification and Contractor Performance processes. | 0 | 2017-11-01T00:00:00 | HPW
20/9/2018 | Energy | Biofuel - Fuel Sellers Register | 2017-06-01T00:00:00 | Delivery | G | 2018-03-29T00:00:00 | Project is continuing as planned. 20/9/2018, 20/9/2018,November 2017 - Approved extension of time-frame, additional scope and associated costs due to State Government election affecting launch date. 20/9/2018,October 2017 - The project is progressing as planned. 20/9/2018,August 2017 - Revised schedule approved returning the project to Green for Timeframe, Cost and Quality. Good progress is now being made following re-baselining. 20/9/2018,June 2017 - Revised Schedule approved returning the project to Green. 20/9/2018,June 2017 - A revised project schedule is currently being finalised and the project is being closely monitored. 20/9/2018,April 2017 - A software issue is still being resolved and the timeframe is being closely monitored. 20/9/2018,March 2017 - Quality issues are being resolved and now report as Amber, with a return to Green expected following renegotiation of vendor agreement. Timeframe and Cost are being reviewed in light of impending change to vendor agreement. 20/9/2018,February 2017 - Quality issues are currently being addressed and contingencies are being applied. 20/9/2018,December 2016 - The project is progressing as planned. | 2017-12-21T00:00:00 | Critical | 567500 | G | Governance and Engagement, Energy | 92 | 634172 | G | G | 1 | Develop a modern ICT solution to support the Queensland biofuel mandates (the Liquid Fuel Supply Act 1984 and the Liquid Fuel Supply (Ethanol and Other Biofuels Mandate) Amendment Act 2015). Queensland fuel retailers and wholesalers will be able to: 20/9/2018, 20/9/2018,* register and maintain their information 20/9/2018,* report fuel sales volume. | 967680 | 2016-04-05T00:00:00 | DEWS
20/9/2018 | QWSR | Dam safety regulation solution | 2016-10-30T00:00:00 | Delivery | G | 2018-04-30T00:00:00 | Project is continuing as planned. 20/9/2018, 20/9/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 20/9/2018,August 2017 - Approved extension of timeframe. 20/9/2018,June 2017 - The project is progressing as planned. 20/9/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 20/9/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 20/9/2018,October 2016 - Progress is continuing as planned. 20/9/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 20/9/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 20/9/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2017-12-21T00:00:00 | High | 1390000 | G | Queensland Water Supply Regulator | 91 | 1327606 | G | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 20/9/2018, 20/9/2018,* support compliance with legislation 20/9/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 20/9/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 20/9/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. 20/9/2018, | 1390000 | 2012-04-01T00:00:00 | DEWS
20/9/2018 | FQ | Forestry Mobility Project | 2017-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The project is progressing as planned and is on schedule. 20/9/2018, 20/9/2018,July 2018 - The project has re-commenced. Approval has been granted for an extension to the planned end date, and an increase in associated costs. 20/9/2018,June 2018 - Field testing has identified unexpected issues that will impact on the planned end date. Effort is underway with Microsoft to apply a technical fix (patch) to resolve errors. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 20/9/2018,April 2018 - An extension to the planned end date has been approved, returning the project status to Green. 20/9/2018,March 2018 - A minor scope increase has been proposed, affecting both timeframe and cost, which is progressing through the governance process. 20/9/2018,March 2018 - The project is progressing as planned. 20/9/2018,December 2017 - A variation to scope was approved, resulting in a change to the planned end date and total estimated expenditure. 20/9/2018,November 2017 - The project is continuing as planned. 20/9/2018,June 2017 - The project is continuing as planned, moving into delivery in December 2016. | 2018-09-14T00:00:00 | Medium | 608146 |  | Forestry Queensland | 91 | 999990 |  | G | 1 | Part of the Forestry ICT Renewal (FIR) program, this initiative is an appropriate-scaled solution to support efficient and effective delivery of remote field operations, which will address: 20/9/2018, 20/9/2018,* the capture, management and integration of data 20/9/2018,* value-adding opportunities for business improvement 20/9/2018,* management of risk associated with ongoing use and maintenance of disparate systems. | 1696431 | 2016-06-15T00:00:00 | DAF
20/9/2018 | BQCC | Communication and Stakeholder Engagement Solution | 2018-04-27T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Timeframe is being monitored closely due to business demands impacting testing and completion of documentation. Project closure is now planned by 30 September 2018. 20/9/2018, 20/9/2018,July 2018 - An extension to the planned end date and additional budget has been approved by the governance committee. 20/9/2018,June 2018 - Hidden complexities around integration with other solutions has affected the timing of user acceptance testing and training schedules. Due to the timing of this, the timeframe and cost will be adjusted (re-baselined) returning to a Green status. 20/9/2018,May 2018 - A change to the planned end date and cost has been approved. 20/9/2018,March 2018 - Note adjustment to planned end date corrected due to typographical error. 20/9/2018,February 2018 - The project is progressing as planned. 20/9/2018,December 2017 - The project was approved to move into delivery in October 2017 and is being published for the first time. | 2018-09-14T00:00:00 | Medium | 694000 |  | Biosecurity Queensland Control Centre | 95 | 910985 |  | A | 2 | Implement a simple, easy to use system that will facilitate the collection of information associated with the National Red Imported Fire Ant Eradication Program and the National Electric Ant Eradication Program. This will include contact management, complaints management, history of interactions, event management, training management, social media interactions, marketing campaign and reporting. | 1048849 | 2017-06-01T00:00:00 | DAF
20/9/2018 | ASQ | Portfolio Activity Reporting Information System | 2018-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | Extensive stakeholder consultation has been undertaken and included in documentation. 20/9/2018, 20/9/2018,June 2018 - Refreshed business case approved, the project has been re-baselined returning it to a Green status. 20/9/2018,May 2018 - Funding has been approved to fully implement the project and it is now in delivery. 20/9/2018,February 2018 - The project is paused until a funding source is identified. 20/9/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-09-14T00:00:00 | High | 978000 |  | Agri-Science Queensland | 10 | 323697 |  | G | 3 | Review and consolidate the variety of processes and technologies currently being used to manage the department's research, development and extension, and other projects. | 978000 | 2015-08-13T00:00:00 | DAF
20/9/2018 | Ag | Risk Reduction for Customer Service Centre | 2019-04-19T00:00:00 | Delivery |  | 2019-04-19T00:00:00 | The project is progressing as planned and is on schedule. 20/9/2018, 20/9/2018,December 2017 - The project was approved to move into delivery in November 2017 and is being published for the first time. | 2018-09-14T00:00:00 | High | 1767000 |  | Agriculture | 40 | 885608 |  | G | 4 | Implement a solution to mitigate risk of end of life for the agency's call centre logging application. | 1767000 | 2015-01-30T00:00:00 | DAF
20/9/2018 | FQ | Novel Commercial and Recreational Fishing Apps | 2018-09-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | Contract documentation has been finalised and the first two development cycles are under way. 20/9/2018, 20/9/2018,August 2018 - The project was approved to move to delivery in July 2018 and is publishing for the first time. | 2018-09-14T00:00:00 | High | 450000 |  | Fisheries Queensland | 10 | 224756 |  | G | 5 | * Provide up-to-date information on the rules and regulations about fishing and marine park zoning in Queensland 20/9/2018,* Achieve better compliance through access to information 20/9/2018,* Increase uptake of the App by providing regulations from other marine agencies 20/9/2018,* Resolve issues with offline access to information. | 450000 | 2018-02-01T00:00:00 | DAF
20/9/2018 | BQ | Registered Biosecurity Entity (RBE) Renewal Project | 2019-08-30T00:00:00 | Delivery |  | 2019-08-30T00:00:00 | The project is progressing as planned and is on schedule. 20/9/2018, 20/9/2018,August 2018 - The project was approved to move to delivery in July 2018 and is publishing for the first time. | 2018-09-14T00:00:00 | High | 2821000 |  | Biosecurity Queensland | 8 | 287562 |  | G | 6 | * Develop an efficient end-to-end registration renewal process to allow effective management of renewals 20/9/2018,* Ensure stakeholders are aware of renewal requirements and the importance of maintaining up-to-date information 20/9/2018,* Provide the ability to efficiently communicate with customers about registered biosecurity entity processes and renewals 20/9/2018,* Provide data integration between the online customer portal and the underlying technology solution 20/9/2018,* Minimise administrative overhead. | 2821001 | 2017-11-10T00:00:00 | DAF
20/9/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DSD
20/9/2018 | PSBA | Emergency Services Computer Aided Dispatch (ESCAD) Upgrade Program | 2016-09-30T00:00:00 | Closed |  | 2018-07-03T00:00:00 | The updated ESCAD system cut over for Queensland Ambulance Service (QAS) completed successfully on 17-01-2018, and the Queensland Fire and Emergency Services (QFES) also completed successfully on 24-01-2018. The decommissioning of hardware in the obsolete environments was complete. The Project has concluded on 29-06-2018 as per schedule. 20/9/2018,The ESCAD System Upgrade Project, as major initiative in the program of works, experienced significant technical and implementation issues causing an approved rebaseline in January 2017. This resulted in a revised timeframe from the original plan of 30-09-2016 to 03-07-2018 and a revised approved budget from the original of $6.8 million to $9.4 million for the Program. | 2018-08-17T00:00:00 | Critical | 6774820 |  | Public Safety Business Agency | 100 | 9337507 |  | G | 1 | A program of work for Queensland Ambulance Service and Queensland Fire and Emergency Services to upgrade the Emergency Services Computer Aided Dispatch System, including infrastructure, operating system and application software. | 9380822 | 2015-01-15T00:00:00 | PSBA
20/9/2018 | PSBA | Emergency Vehicle Priority (EVP) Project | 2017-06-30T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | This reporting period there was a reduction in expenditure due cost recoveries. 20/9/2018, 20/9/2018,EVP rollouts continuing in Rockhampton, Maryborough, Hervey Bay and Gladstone for both Queensland Ambulance Service and Queensland Fire and Emergency Services. Procurement of a managed service for operational support and maintenance in progress with implementation and project closure scheduled for completion October 2018. Procurement of the managed service has required an extension of the project scope and schedule. This resulted in a revised timeframe from the original planned end date of 30-06-2017 to 31-10-2018, and a revised budget from the original expenditure plan of $3.4 million to $4.4 million. The approved/planned expenditure figure has been realigned from the estimate at completion to the total project budget, resulting in a $12,366 difference. 20/9/2018,Deferral of $54,315 is pending approval from Treasury. | 2018-08-17T00:00:00 | High | 3370000 |  | Public Safety Business Agency | 94 | 4128398 |  | G | 2 | A joint project between Public Safety Business Agency and Transport and Main Roads for Queensland Ambulance Service, Queensland Fire and Emergency Services, and Queensland Police Service to deliver: 20/9/2018, 20/9/2018,* Responsive vehicle movements 20/9/2018,* Improve road safety 20/9/2018,* Congestion management 20/9/2018,* Community safety | 4382697 | 2013-01-01T00:00:00 | PSBA
20/9/2018 | PSBA | Inter-CAD Electronic Messaging System (ICEMS) | 2016-08-31T00:00:00 | Closed |  | 2018-03-16T00:00:00 | The ICEMS system cut over for Queensland Police Service (QPS) and Queensland Ambulance Service (QAS) completed successfully on 28-07-2017, and ICEMS for the Queensland Fire and Emergency Services (QFES) completed successfully on 24-01-2018. Project closure activities have finalised. The ICEMS Project experienced significant technical and implementation issues causing multiple approved re-baselines between November 2015 and September 2017. This resulted in a revised timeframe from the original planned end date 31-08-2016 to 16-03-2018 and a revised budget from the original planned expenditure of $560K to $1,571K. Further to this, a scope change was undertaken in 2016 to extend ICEMS messaging. The Priority of this initiative has been re-assessed to Medium. The approved/planned expenditure figure has been realigned from the estimate at completion to the total project budget, resulting in a $19,860 difference. 20/9/2018, 20/9/2018,ICEMS End Project Report approved. 20/9/2018,Confirmation and approval from PSBA, QPS Project Management Office, QFES and QAS that the ICEMS Project is completed and closed. | 2018-08-17T00:00:00 | Medium | 560000 |  | Public Safety Business Agency | 100 | 1570688 |  | G | 3 | To implement the ICEMS protocol between the Queensland Police Service (QPS), Queensland Ambulance Service (QAS) and Queensland Fire and Emergency Services (QFES) computer aided dispatch systems to enable Triple Zero data sharing between agencies. | 1591000 | 2015-10-06T00:00:00 | PSBA
20/9/2018 | PSBA | QFES Office 365 Implementation Project | 2018-06-30T00:00:00 | Closed |  | 2018-06-29T00:00:00 | Project has completed. | 2018-08-17T00:00:00 | Medium | 2100000 |  | Public Safety Business Agency | 100 | 1172090 |  | G | 4 | This project will deliver the most up-to-date Office 365 suite of products to all Queensland Fire and Emergency Services (QFES) staff and enable QFES to mobilise its workforce. 20/9/2018, 20/9/2018,* Upgrade QFES technology fleet to the latest Microsoft Office version 20/9/2018,* Cloud services will enable mobility 20/9/2018,* Bridge the technology gaps between Public Safety Agencies (PSA) and allow better collaboration | 1182000 | 2017-11-01T00:00:00 | PSBA
20/9/2018 | PSBA | QPS Office 365 Implementation Project | 2018-02-28T00:00:00 | Closed |  | 2018-06-29T00:00:00 | Project Complete. 20/9/2018, 20/9/2018,The original planned end date of 28-02-2018 has been re-baselined to 30-06-2018 due to delivery of additional scope | 2018-08-17T00:00:00 | Medium | 2207000 |  | Public Safety Business Agency | 100 | 1798019 |  | G | 5 | Phase 1 - Mail Migrations 20/9/2018,The objective of the Queensland Police Service (QPS) Office 365 Implementation Project Phase 1 is to complete the following activities prior to the Frontline and Digital Services Commonwealth Games Change Freeze (mid Feb 2018): 20/9/2018, 20/9/2018,* migrate email, contacts and calendars to Office 365 online services for all QPS staff; and 20/9/2018,* enable anywhere, anytime, any device access to email, contacts and calendar via bring your own (BYO) phone, QPS Officers operational tablets (QLiTEs) and home-use for all QPS staff 20/9/2018, 20/9/2018,Phase 2 - a data migration and a pilot migration of email archives to Office 365 online | 2207000 | 2017-09-07T00:00:00 | PSBA
20/9/2018 | OSR | State Penalties Enforcement Registry (SPER) Program | 2017-12-31T00:00:00 | Delivery |  | 2018-10-31T00:00:00 | Expenditure to date - $31.3M has been for the transformation of the SPER function, and $20.3M has been on the build phase of the ICT implementation. The broader SPER transformation program commenced in 2014, with the first stage focussed on building foundational capability. This next phase was the implementation of the new system solution (ICT SaaS) which commenced in 2016. 20/9/2018,Variation - In December 2017 the SPER Program completed a re-baselining effort which approved changes to scope, timing and costs. These changes were made to better reflect an enhanced delivery model, requiring system modifications that support improved business functionality. | 2018-07-30T00:00:00 | High | 47200000 |  | State Penalties Enforcement Registry | 79 | 51641000 |  | A | 1 | To maintain the integrity of fines as an effective sanction. 20/9/2018,To uphold confidence in the justice system. 20/9/2018,To deliver efficient and effective debt management practices which provide value for money to the State. 20/9/2018, | 62150000 | 2014-01-01T00:00:00 | QR
20/9/2018 | RI | Financial Assurance Information Registry (FAIR) | 2018-07-01T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | Project cost as at end of July 2018 is $7.315.000. The FAIR project was due to be completed by 1 July 2018 to align with commencement of the Financial Provisioning Scheme (FPS). The delivery delay event is marked yes due to a deferral of the legislation to enact the FPS which would permit the scheme to commence. The FAIR project will be operational for FPS commencement. 20/9/2018,The FAIR project required for the FPS commencement is 90 percent complete. Other components of the FPS reforms will be completed in subsequent years. | 2018-07-30T00:00:00 | Medium | 15900000 |  | Insurance Commission | 90 | 7315000 |  | G | 2 | Cabinet has approved the reform of the Financial Assurance System in Queensland to address the inadequacy of surety held by the state to meets its rehabilitation obligations relating to mining and petroleum sites and activities. The Financial Assurance Information Registry (FAIR) will provide a robust and accurate central registry of information pertaining to Financial Assurance relating to mining interests in Queensland. The registry will be accessible to Queensland Government officers in Dept. of Environment and Heritage Protection, Dept. of Natural Resources and Mines and Queensland Treasury. | 15900000 | 2017-05-01T00:00:00 | QR
20/9/2018 | RI | Information Security Program | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 |  | 2018-07-31T00:00:00 | Medium | 1960000 |  | Office of the Chief Information Officer | 45 | 642500 |  | G | 3 | The potential of digital technologies depends on the extent to which we can trust the Internet and cyberspace. The Information Security program will: mitigate Treasury's cyber security risk profile; review and implement information security policy; mitigate workplace health and safety risk; enhance a risk management regime; create a trusted environment to implement digital and data initiatives. 20/9/2018, | 1960000 | 2017-10-16T00:00:00 | QR
20/9/2018 | OSR | Office of State Revenue (OSR) Transformation Program | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | Multiple initiatives in progress focussing on machine learning, analytics, data quality, and business process improvements. Overall program is on track. | 2018-07-30T00:00:00 | High | 73548000 |  | Office of State Revenue | 22 | 13538135 |  | G | 4 | The OSR Transformation Program will create a revenue services model for the future, focussing on clients, staff and the community. Key investment objectives include: enhanced customer service offerings; real time, up front compliance programs; improved data accuracy and identity management; automated processing and advanced analytics. 20/9/2018, 20/9/2018,The OSR Transformation Program will be delivered over three years across six streams of activity - Business Process Re-design; Data; Analytics; Client Centric; Workforce Capability and Platform Renewal. | 73548000 | 2017-08-01T00:00:00 | QR
20/9/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DATSIP
20/9/2018 | Corporate Services Improvement Program | Integrated Records Information System (IRIS) | 2019-06-30T00:00:00 | Delivery |  | 2019-12-30T00:00:00 | In response to an internal audit review of review of Transport and Main Road's (TMR) Document Management System (DMS) the Integrated Records and Information System (IRIS) project was stood up in 2015. An opportunity to further leverage functionality requirements, TMR's Executive Correspondence System (ECS) replacement was also included into scope. 20/9/2018,IRIS project was reviewed in 2017 to ensure achievability, and as a result the project budget was decreased from $7,967,972 down to $6,865,000 (plus contingency) of 10%. 20/9/2018,In April 2018, a scope change with $567,500 budget increase was approved to include the delivery of a General Correspondence System deliverable to the project, maximising return on investment and better outcomes for the customer, bringing total budget to $7,432,500 excluding contingency. | 2018-07-31T00:00:00 | High | 7967972 |  | Corporate Services Improvement Division | 35 | 5783613 |  | G | 1 | Centralised electronic document and recordkeeping management system that will enable TMR staff to easily and quickly manage electronic and physical records in a way that ensures they are available to evidence decision making. | 7967972 | 2015-07-01T00:00:00 | TMR
20/9/2018 | Corporate Services Improvement Program | Lotus Notes Decommissioning (OP) | 2016-01-31T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | The Lotus Notes Decommissioning project commenced in October 2015 when concept and stage 1 was approved to engage and investigate business findings around the decommission of legacy lotus notes databases. 20/9/2018,In July 2016, three additional stages aligning to three financial years from 2016/17 through to 2018/19 were further approved via a project initiation and business case. 20/9/2018,Stage 2, 2016/17, focused on analysis and stakeholder engagement to form the scope of the project and define functionality and business requirements for individual applications. 20/9/2018,Stage 3, 2017/18, focused on proof of concepts to inform and validate the plan for stage 4 in 2018/19. The project was impacted in 2017/18 by several resourcing issues, including the departure of the original project manager. 20/9/2018,The project is scheduled to complete work and close down by 30 June 2019, with the exception of the migration of files from the department's legacy Document Management System (DMS). The migration of the DMS will align with the Integrated Records and Information System (IRIS) program and should be complete by the end of 2019. | 2018-07-31T00:00:00 | High | 8150000 |  | Corporate Services Improvement Division | 52 | 3107509 |  | G | 2 | Deliver improved information platform functions for effective ICT Strategy Alignment | 8150000 | 2015-11-01T00:00:00 | TMR
20/9/2018 | Corporate Services Improvement Program | Safety System Replacement Project (SSRP) | 2018-07-30T00:00:00 | Closed |  | 2018-07-30T00:00:00 | Project closed on time and within budget. A new Workplace Health and Safety (WHS) solution has been procured, implemented and declared production ready 28 June 2018. It provides a contemporary workflow-based approach to the recording and management of hazards and incidents, safety conversations, and claims and rehabilitation. The solution is cloud based and offers functionality to support the Departments mobile workforce. 20/9/2018, | 2018-07-31T00:00:00 | Low | 680000 |  | Corporate Services Improvement Division | 100 | 677411 |  | G | 3 | The objective of the SHE project is to replace the current Work Health and Safety ICT solution with an industry standard, cost effective safety management solution that will enable TMR to meet its obligations under the Work Health and Safety 2011 Act, the Right to Information, Information Privacy legislation and the Workers Compensation and Rehabilitation Act 2003 (Qld). | 680000 | 2016-12-05T00:00:00 | TMR
20/9/2018 | Corporate Services Improvement Program | Transactional Services Improvement Program Enhancements | 2015-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Project successfully closed on time and within budget. Project was originally proposed in February 2015 for stage 1, with project brief and project initiation documentation approved in April 2015. Stage 1 was successfully closed out in March 2016. Stage 2 was approved in April 2016, and successfully closed out 30 June 2017. Stage 3 (2017/18) commenced 1 July 2017 and successfully closed 29 June 2018. 20/9/2018,The project added real value and efficiencies through reduced overheads within the department, such as the introduction of web-based Heavy Vehicle Permits. and Improvements were also made to multiple transactional services relating to payments and receipts from customers such as the additional payment options of payWave and AMEX. | 2018-07-16T00:00:00 | Low | 200000 |  | Corporate Services Improvement Division | 100 | 199878 |  | G | 4 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. | 200000 | 2015-02-01T00:00:00 | TMR
20/9/2018 | Corporate Services Improvement Program | TSIP 2018-19 | 2019-06-30T00:00:00 | Delivery |  | 2019-06-30T00:00:00 | Project successfully commenced 1 July 2018. | 2018-07-31T00:00:00 | High | 400000 |  | Corporate Services Improvement Division | 5 | 24687 |  | G | 5 | The Transactional Services Improvement projects focus are to improve modernise and streamline the TMR Transactional Services relating to payments and receipts from external customers. The intention is to increase efficiency reduce overhead and to consolidate the payment transactional service options for the organisation. This brings the TMR service offering more in to line with the current and future methods available and consistent with public online experience expectations. | 400000 | 2018-07-01T00:00:00 | TMR
20/9/2018 | Corporate Services Improvement Program | Stop Cheques - Stage 3 | 2015-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Project successfully closed on time and within budget. Project was originally proposed in February 2015 for stage 1, with project brief and project initiation documentation approved in April 2015. Stage 1 was successfully closed out in March 2016. Stage 2 was approved in April 2016, and successfully closed out 30 June 2017. Stage 3 (2017/18) commenced 1 July 2017 and successfully closed 29 June 2018. 20/9/2018,Customers are already experiencing the increased convenience and reduction of costs resulting from reduced out bound cheques, which include deceased estate cheques, cheques to known vendors, and the expansion of products available for refund at counter such as registration refunds and concessions. | 2018-07-16T00:00:00 | Medium | 200000 |  | Corporate Services Improvement Division | 100 | 200003 |  | G | 6 | Cheques are inefficient and costly to use, process and administer for both the customer and department. A range of solutions have been developed to reduce the number of cheques that the department produces or receives including refund to card at counter, Bulk Bpay solutions and the introduction of new payment methods are being delivered to be more in line with contemporary retail offerings. The outsourcing of cheque production produced a more streamlined process. 20/9/2018,The stop cheques initiative includes 3 elements: 20/9/2018,Outsourcing/cost reduction 20/9/2018,Outbound cheques 20/9/2018,Inbound cheques | 200000 | 2015-02-01T00:00:00 | TMR
20/9/2018 | Corporate Services Improvement Program | Risk Management Solution | 2018-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | Project successfully closed on time and within budget. Project was proposed in February 2016, with the project brief and budget for stage 1 (2016/17) approved in October 2016 for $350,000. Stage 1 successfully closed 30 June 2017 with an underspend of $98501. Stage 2 (2017/18) was approved in March 2017 for $710,000, and commenced 1 July 2017. Stage 2 and the project successfully closed 22 June 2018 with an underspend of $1,887. 20/9/2018,The new online enterprise risk management system (RMS) provides significant improvements in efficiency for risk recording and monitoring, and provides increased transparency on risks, risk owners and treatment responsibilities, raising the overall risk maturity at significantly lower, ongoing cost. 20/9/2018, | 2018-07-16T00:00:00 | High | 350000 |  | Corporate Services Improvement Division | 100 | 959610 |  | G | 7 | Replace the current risk management approach through the delivery of a new and contemporary enterprise Risk Management solution for TMR . | 1024435 | 2016-02-01T00:00:00 | TMR
20/9/2018 | Customer Service, Safety and Regulation Program | Camera Detected Offence Program (CDOP) Online Portal | 2017-06-30T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | This commenced in July 2016 with delivery being phased in accordance with the development of the business processes. Original expenditure was 1.5M which has been revised to 1.441M on finalisation and approval of the business case. Phase 1 was completed in July 2017 and the schedule was adjusted in June 2017 to enable the delivery of the Phase 2 capability in late 2018. 20/9/2018, 20/9/2018,The project is currently on track. | 2018-07-31T00:00:00 | High | 1500000 |  | Customer Services, Safety and Regulation Division | 90 | 999273 |  | G | 8 | Online public service for CDOP offences. The portal will enable the registered owner to nominate the offending driver immediately and eliminate the need for travel time to locate an authorised witness (for the statutory declaration) and subsequent postal services currently required. | 1441000 | 2016-01-01T00:00:00 | TMR
20/9/2018 | Customer Service, Safety and Regulation Program | eLearner Driver | 2017-07-31T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The project commenced in mid 2015 with an initial exploratory phase, initially scheduled for delivery in mid 2016. Due to the uncertainty of the solution outcome and market capability the project undertook a multi-stage market engagement and procurement process. Once the solution had been fully defined, the schedule was extended by 11 months and the budget increased from $2.5M to $4.1M in January 2017. 20/9/2018, 20/9/2018,Development is now complete. A pilot phase has been successfully completed. The project is now conducting final testing and preparing for a full launch. The program is on track for public release from September 2018. | 2018-07-31T00:00:00 | High | 2500000 |  | Customer Services, Safety and Regulation Division | 95 | 4175019 |  | G | 9 | Implement an online learning and assessment program at the pre learner and/or learner stage, to enhance learning and outcomes for new drivers. | 4176000 | 2015-06-12T00:00:00 | TMR
20/9/2018 | Customer Service, Safety and Regulation Program | Mobile Compliance Information System | 2017-05-08T00:00:00 | Delivery |  | 2018-06-28T00:00:00 | This commenced in November 2016 with planned completion in mid 2017. Due to an extended procurement process, and the need to include analytical functionality, the schedule was extended 12 months and the budget increased from $300k to $894k in August 2017. The capability was delivered as scheduled in June 2018 and the project is presently finalising closure with formal closure scheduled for August 2018. | 2018-07-31T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 99 | 986705 |  | G | 10 | Providing greater capability for field officers to complete more of their work in the field, rather than returning to office and entering data in various systems. | 989237 | 2016-11-01T00:00:00 | TMR
20/9/2018 | Customer Service, Safety and Regulation Program | Customer Flow Mgmt and Reporting System | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | Pre-project work commenced during FY15/16 with the initiation of the current project commencing in July 2017. The original budget of 300K was rebaselined to 3M once the post market business case was finalised and approved to proceed in May 2018. 20/9/2018,The project is on track for delivery to occur within FY18/19. | 2018-07-31T00:00:00 | High | 300000 |  | Customer Services, Safety and Regulation Division | 61 | 985043 |  | G | 11 | Replacement of the existing state wide network of customer flow management and reporting systems which is currently supplied by QMatic Australia and will be unsupported in 2017. CSB currently have 43 CSCs around the state that use QMatic systems. Replacement of the existing state wide customer flow management and reporting system which is currently supplied by QMatic Australia and will be unsupported in 2017. | 3083000 | 2015-09-01T00:00:00 | TMR
20/9/2018 | Customer Service, Safety and Regulation Program | Call Centre VOIP Upgrade | 2018-06-30T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Project commenced in July 2017. Due to a resourcing issue. Approval was given to amend the implementation date from June 2018 to August 2018. | 2018-07-31T00:00:00 | High | 1140000 |  | Customer Services, Safety and Regulation Division | 75 | 631198 |  | G | 12 | The Call Centre VOIP Upgrade has commenced to upgrade the VOIP telephony platform within the department. The proposed solution will see a reduction in call costs, a shift in capability to a contemporary solution utilising an existing investment within the department. | 1140000 | 2017-04-01T00:00:00 | TMR
20/9/2018 | Customer Service, Safety and Regulation Program | RALPH Replacement | 2017-06-30T00:00:00 | Delivery |  | 2018-06-29T00:00:00 | The RALPH project commenced in July 2016. Due to vendor software development issues, changes to the schedule and budget were approved in June 2017 with a planned completion to occur by 30 June 2018. A further extension was approved for an additional two months. The project remains on track for closure in August 2018. | 2018-07-31T00:00:00 | Medium | 500000 |  | Customer Services, Safety and Regulation Division | 80 | 696470 |  | G | 13 | TMR's current Transport Registration and Integrated Licensing System (TRAILS) interface application, that effects changes to product fees on an annual and quarterly basis, is unsupported technology and at risk of failing. This initiative seeks to replace the existing application with a contemporary and supportable alternative to assist the department in maintaining its timely updating of fees and charges. | 734000 | 2016-07-01T00:00:00 | TMR
20/9/2018 | Customer Service, Safety and Regulation Program | Vessel Traffic Services (VTS) | 2016-01-05T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | Pre project work commenced in April 2014 with the initiation of the current project commencing in July 2016. The original budget of $15.2M was rebaselined to $36.2M once the post-market business case was finalised and approved to proceed in April 2017. 20/9/2018, 20/9/2018,The project is on track for delivery in mid 2019. | 2018-07-31T00:00:00 | High | 15224694 |  | Customer Services, Safety and Regulation Division | 52 | 5852380 |  | G | 14 | Replacement of TIM and surface picture software for Reef VTS Phase 1 for the replacement of TIM and surface picture software for Reef VTS. | 36228184 | 2014-04-14T00:00:00 | TMR
20/9/2018 | Customer Service, Safety and Regulation Program | Registration and CTP Certificates Online | 2017-12-31T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | The Registration and CTP Certificates Online project commenced in May 2017 as two separate initiatives Registration Online and CTP Tax Invoice Online. Due to common system synergies the projects were merged in March 2018 resulting in the closure date being revised in accordance with the CTP component. The project is on track for delivery and closure in late 2018. | 2018-07-31T00:00:00 | Medium | 0 |  | Customer Services, Safety and Regulation Division | 60 | 430933 |  | G | 15 | Create an online service for customers to email or print their registration certificate and CTP tax invoices, to provide customers with more convenience, and reduce reliance on paper and post. | 450000 | 2017-05-01T00:00:00 | TMR
20/9/2018 | Customer Service, Safety and Regulation Program | RnL Systems Software Upgrade Stage 2 | 2018-06-30T00:00:00 | Delivery |  | 2018-06-30T00:00:00 | The RnL System Software Upgrade project commenced in July 2017. The original budget of $780K was rebaselined to $1.255M once the post-market business case was finalised and approved to proceed in September 2017. Delivery was completed as scheduled in June 2018 with the project now undergoing closure. | 2018-07-31T00:00:00 | Medium | 780000 |  | Customer Services, Safety and Regulation Division | 87 | 1115666 |  | G | 16 | Upgrade the technical support environment used in the development of the Registration and Licensing systems including Transport Registration and industry licensing system and Online Services. | 1255935 | 2017-07-01T00:00:00 | TMR
20/9/2018 | Customer Service, Safety and Regulation Program | Voice Comms Mgt System | 2017-06-30T00:00:00 | Closed |  | 2018-06-30T00:00:00 | The Voice Comms Management System project commenced in Jan 2017 for completion by mid-2018 however resource availability was impacted due to Cyclone Debbie. Delivery of the capability was completed in April 2018 with the project being formally closed on 5 July 2018. | 2018-07-16T00:00:00 | Medium | 828000 |  | Customer Services, Safety and Regulation Division | 100 | 274738 |  | G | 17 | The Voice Comms Management project consists of two replacement of existing Voice Communication and Control Systems at Townsville and Hay Point. | 828000 | 2016-01-01T00:00:00 | TMR
20/9/2018 | Passenger Transport Technology Program | Single Integrated Network Project (SNIP) | 2018-09-29T00:00:00 | Delivery |  | 2018-09-30T00:00:00 | Final testing of the transport schedule system is planned to be completed this month with implementation in TransLink planned for August. Rollout of the system will follow SEQ 4G bus contract renewals. An Exception Report will be considered by the PTT board to consider this change. | 2018-07-31T00:00:00 | High | 4992243 |  | TransLink Division | 30 | 747017 |  | G | 18 | Enable implementation of performance based contracts for SEQ buses 20/9/2018,Have a system in place that is consistent and integrated across service providers and TransLink 20/9/2018,Reduce or remove inefficiencies and data inaccuracies that occur in the current processes 20/9/2018,Improve transparency of SEQ bus service providers activities and performance 20/9/2018,Improved customer experience through more accurate and reliable SEQ bus service information 20/9/2018,To improve customer experience through more accurate and reliable service information. 20/9/2018,Contributor for achieving Government objectives. 20/9/2018, | 4992243 | 2017-02-23T00:00:00 | TMR
20/9/2018 | Passenger Transport Technology Program | School Transport Assistance Scheme (STAS) Auto Forms | 2018-01-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Original project commenced in April 2016. 20/9/2018,Budget shortfall identified in November 17. 20/9/2018,In March 18 issues in gathering business data and requirements for new functionality identified. 20/9/2018,The STAS project is reporting amber as a result of unforeseen complexities associated with provisioning and transitioning of business supplied data to the new platform. The project is experiencing delays as resolution activities take place to ensure a good customer experience when the project is released to the public. 20/9/2018,An Exception Report will be considered by the PTT board to enable products to be completed and released by end of March 2019. | 2018-07-31T00:00:00 | High | 4166000 |  | TransLink Division | 75 | 5192212 |  | A | 19 | To reduce the amount of manual handling and processing of information associated with the departments School Transport Assistance Scheme (STAS), by modernising and providing digital enablement and workflows. | 5303876 | 2016-04-01T00:00:00 | TMR
20/9/2018 | Policy Planning and Investment Program | Portfolio, Program, Project and Contract Management (3PCM) - Phase 2 and 3 | 2017-03-31T00:00:00 | Delivery |  | 2017-12-22T00:00:00 | The Portfolio, Program, Project and Contract Management (3PCM) project commenced in 2012 with an initial original planned expenditure of $12,757,788. The initial estimate uploaded for 3PCM intentionally included only the project initiation, market assessment and business case development. The estimate was clarified at the end of contract negotiations in the post-market business case and revised to $47,908,928. The Portfolio, Program, Project and Contract Management (3PCM) project has successfully completed its scope and the Program Board endorsed the project closure report in July 2018. The Portfolio, Program, Project and Contract Management (3PCM) project will no longer report on the QG ICT Dashboard after the current reporting period. | 2018-07-16T00:00:00 | High | 12757788 |  | Policy, Planning and Investment Division | 99 | 47794126 |  | G | 20 | Define and implement standard, consistently applied processes for planning, managing and delivering the Transport Infrastructure Portfolio across the domains of portfolio, program, project and contract management 20/9/2018,Source and implement an integrated, strategic information communication technology solution that supports the business process and rules and enables a transition away from legacy applications | 47908928 | 2012-09-01T00:00:00 | TMR
20/9/2018 | CS | Asset Assessment System | 2016-06-30T00:00:00 | Delivery |  | 2019-02-15T00:00:00 | The project is reviewing requirements and schedule before commencing next stage. | 2018-08-08T00:00:00 | High | 1688788 |  | Corporate Services | 82 | 1890702 |  | G | 1 | To improve the reliability and integrity of asset information, the ability to report on asset information by applying best practice asset management principles. | 2179995 | 2014-02-27T00:00:00 | DET
20/9/2018 | CS | Automated Website Provisioning Tool | 2017-08-18T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | The project is tracking to plan. | 2018-08-08T00:00:00 | Medium | 1300000 |  | Corporate Services | 94 | 1132673 |  | G | 2 | To reduce the cost and time required to create new school and corporate websites by developing a tool that provisions new websites from a suite of reusable website templates. | 1242160 | 2017-04-03T00:00:00 | DET
20/9/2018 | PPP | Customer Complaints Management System | 2018-12-21T00:00:00 | Delivery |  | 2018-12-21T00:00:00 | The project is tracking to plan. | 2018-08-08T00:00:00 | Medium | 2753000 |  | Policy, Performance and Planning | 64 | 602336 |  | G | 3 | Improve the management and reporting of customer complaints. | 2753000 | 2017-09-11T00:00:00 | DET
20/9/2018 | SS | Early Start | 2015-07-03T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | The project is tracking to plan. | 2018-08-08T00:00:00 | High | 70000 |  | State Schools | 47 | 73522 |  | G | 4 | To provide schools with enhanced reporting functionality, improving their ability to analyse Prep to Year 2 student learning data. | 200992 | 2013-04-03T00:00:00 | DET
20/9/2018 | PPP | English as Additional Language/Dialect Resource | 2014-01-30T00:00:00 | Delivery |  | 2018-09-14T00:00:00 | The project is tracking to plan. | 2018-08-08T00:00:00 | Medium | 700000 |  | Policy, Performance and Planning | 92 | 1472845 |  | G | 5 | To provide an online professional development course for teachers of Indigenous students who are EAL/D learners. | 1500000 | 2011-02-23T00:00:00 | DET
20/9/2018 | CS | Finance Infrastructure and Managed Services Renewal Project | 2018-08-01T00:00:00 | Delivery |  | 2018-12-07T00:00:00 | The project is tracking to plan. The project is undergoing procurement/commercial activities with no financial information being published. | 2018-08-08T00:00:00 | Medium | 0 |  | Corporate Services | 71 | 0 |  | G | 6 | To improve the value of service and quality of service with the provisioning of the latest hardware and technology to support DET FBS SAP future state landscape for the next five years | 0 | 2017-01-16T00:00:00 | DET
20/9/2018 | CS | Injury Management System | 2017-03-27T00:00:00 | Delivery |  | 2018-10-01T00:00:00 | The project is tracking to plan. | 2018-08-08T00:00:00 | Medium | 1900000 |  | Corporate Services | 67 | 1466704 |  | G | 7 | To improve the management of workplace rehabilitation and claims for injured/ill staff | 1828676 | 2016-10-10T00:00:00 | DET
20/9/2018 | ODG | Legal Case Management System | 2016-06-30T00:00:00 | Delivery |  | 2018-10-01T00:00:00 | The project is tracking to plan. | 2018-08-08T00:00:00 | Medium | 632585 |  | Office of the Director-General | 91 | 877369 |  | G | 8 | To replace existing manual systems and processes with a single solution that improves efficiency and productivity. | 879131 | 2015-12-10T00:00:00 | DET
20/9/2018 | SS | NAPLAN Online Program | 2019-08-21T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | The project is tracking to plan. | 2018-08-08T00:00:00 | Medium | 16670000 |  | State Schools | 55 | 11981721 |  | G | 9 | To provide Queensland State Schools with the facility to perform NAPLAN testing online, making examinations more efficient, improving administration and analytics. | 18115941 | 2015-08-03T00:00:00 | DET
20/9/2018 | ppp | National Quality Standard Assessment and Rating Data Tool | 2018-12-13T00:00:00 | Delivery |  | 2018-12-17T00:00:00 | The project is tracking to plan. | 2018-08-08T00:00:00 | Medium | 467900 |  | Policy, Performance and Planning | 18 | 79930 |  | G | 10 | To improve the security and functionality of the tool used for the assessment and quality improvement of early childhood education and care centres. | 467900 | 2018-02-22T00:00:00 | DET
20/9/2018 | PPP | Online Collection and Survey Solution | 2017-04-01T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project is tracking to plan. | 2018-08-08T00:00:00 | Medium | 1502300 |  | Policy, Performance and Planning | 97 | 1250201 |  | G | 11 | To reduce the risk of business continuity in online data collection through the establishment of a new contracted solution that is more efficient and integrated than the existing solution | 1266210 | 2016-03-01T00:00:00 | DET
20/9/2018 | PPP | Redevelopment of the Policy and Procedure Register | 2018-03-30T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | The project is being closely monitored for cost, quality and schedule. | 2018-08-08T00:00:00 | Medium | 1015000 |  | Policy, Performance and Planning | 69 | 887836 |  | A | 12 | The high level principles endorsed by EMB for the policy management framework which provides the foundation for this initiative include a consistent user experience for customers, regardless of who they are, where they work, and what they may be looking for; a single point of truth, providing access to all departmental policies and procedures; and publish once, with multiple links where appropriate; and that content is authoritative, relevant and meets quality standards for publication, enabling staff and stakeholders to make good decisions. 20/9/2018, | 652238 | 2016-10-13T00:00:00 | DET
20/9/2018 | SS | Trial of Platform for Virtual Academies | 2017-10-02T00:00:00 | Delivery |  | 2018-12-31T00:00:00 | The project is tracking to plan. | 2018-08-08T00:00:00 | Medium | 151641 |  | State Schools | 83 | 236700 |  | G | 13 | To boost student engagement and achievement in STEM and languages through: innovative online teaching and learning; accessible and agile online solutions, which overcome barriers associated with regional demographics, remoteness and/or socio-economic disadvantage; safe and secure like-minded student virtual communities; and strategic partnerships with university, industry and business. 20/9/2018, 20/9/2018, | 141641 | 2016-06-21T00:00:00 | DET
20/9/2018 | CS | Wireless Upgrade Project | 2017-06-30T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project is tracking to plan. | 2018-08-08T00:00:00 | High | 41000000 |  | Corporate Services | 89 | 34998163 |  | G | 14 | To enhance, extend and improve the Wi-Fi coverage in schools to support the use of mobile devices for teaching, learning and administration. This is a multi-year initiative. Budget is allocated each financial year. | 45000000 | 2014-09-01T00:00:00 | DET
20/9/2018 | OIR | Information management/Records management | 2018-12-31T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | The project moved into Delivery in July 2018. The project is tracking to plan. | 2018-07-30T00:00:00 | High | 1259381 |  | Office Of Industrial Relations | 75 | 796878 |  | G | 15 | This project will deliver an electronic document and records management system (eDRMS) across OIR.nt. | 1259381 | 2017-07-03T00:00:00 | DET
20/9/2018 | OIR | Investigations Management System | 2018-12-14T00:00:00 | Delivery |  | 2018-12-14T00:00:00 | The project moved into Delivery in July 2018. The project is tracking to plan. | 2018-07-30T00:00:00 | Critical | 461742 |  | Office Of Industrial Relations | 25 | 268369 |  | G | 16 | This project will deliver a case management solution for the OIR Investigations unit. | 644711 | 2017-01-07T00:00:00 | DET
20/9/2018 | OIR | Renewal and Photographic Licensing System (RAPS) Assessor Portal | 2018-07-13T00:00:00 | Delivery |  | 2019-09-03T00:00:00 | The project is tracking to plan. | 2018-07-30T00:00:00 | High | 766467 |  | Office Of Industrial Relations | 47 | 716953 |  | G | 17 | The Assessor Portal project will deliver an improved online services for high risk work licensing accredited assessors, registered training organisations and licensing and advisory services. Currently accredited assessors must use a combination of cumbersome paper based processes, smart forms, and an online service that is difficult to use. | 971488 | 2016-12-14T00:00:00 | DET
20/9/2018 | [20 empty] | INVERSTMENT INFO
20/9/2018 | ICRM | Integrated Customer and Revenue Management (ICRM) | 2021-06-30T00:00:00 | Delivery |  | 2021-06-30T00:00:00 | The project is continuing as planned and is on schedule. 20/9/2018, 20/9/2018,August 2018 - This project is reporting for the first time and is progressing as planned. | 2018-09-14T00:00:00 | High | 24511345 |  | DNRM Finance | 7 | 3338918 |  | G | 1 | Improvements to the way the agency handles revenue collection: 20/9/2018, 20/9/2018,* selection of a modern, enterprise-class, integrated customer and revenue management solution 20/9/2018,* implementation and deployment of the solution to replace the use of the current at-risk receipting systems. | 24511345 | 2017-01-01T00:00:00 | DNRM
20/9/2018 | QWSR | Dam Safety Regulation Solution | 2016-10-30T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Documentation is being finalised; the project remains within accepted tolerances. 20/9/2018, 20/9/2018,August 2018 - A change request has been approved altering the planned end date to enable completion of end project activities. 20/9/2018, 20/9/2018,July 2018 - All deliverables have been achieved. Project closure activities are currently under way. 20/9/2018, 20/9/2018,June 2018 - A change request has been approved altering the planned end date to remediate technical difficulties that have been experienced in the move to production. 20/9/2018, 20/9/2018,May 2018 - The project is continuing within timeframe tolerance, and is expected to close prior to the end of May 2018. 20/9/2018, 20/9/2018,March 2018 - The project is continuing as planned. 20/9/2018, 20/9/2018,November 2017 - Approved extension of time-frame; progress has slowed due to resource availability impacting the schedule, with no impact to cost. 20/9/2018, 20/9/2018,August 2017 - Approved extension of timeframe. 20/9/2018, 20/9/2018,February 2017 - Timeframe has moved back to Green with an approved extension to the planned end date. 20/9/2018, 20/9/2018,December 2016 - Resource unavailability due to competing priorities has impacted the schedule. 20/9/2018, 20/9/2018,August 2016 - Delays have been resolved and good progress is now being made following re-baselining of the schedule. 20/9/2018, 20/9/2018,June 2016 - Progress is continuing as planned. Percentage complete amended due to previous data input error. 20/9/2018, 20/9/2018,April 2016 - Initiative has moved into delivery and is progressing as planned. | 2018-09-14T00:00:00 | High | 1390000 |  | Queensland Water Supply Regulator | 98 | 1385060 |  | G | 2 | Develop a modern ICT solution to support the regulation of referable dams within Queensland. It is critical for ensuring the safety of the community and continuity of water supply for those communities and to: 20/9/2018, 20/9/2018,* support compliance with legislation 20/9/2018,* implement recommendations from the Queensland Floods Commission of Inquiry - interim and final reports, particularly in regard to Emergency Action Plans (EAPs) for referable dams and prioritisation of dam safety audits 20/9/2018,* address gaps and improve business processes - making processes more consistent and standardised in order to efficiently meet regulatory requirements 20/9/2018,* provide the opportunity for improved or new business capability, such as a central repository for Dam Safety regulatory information and improved reporting and spatial analysis. | 1390000 | 2012-04-01T00:00:00 | DNRM
20/9/2018 | Natural Resources | Land Condition Assessment Tool | 2018-04-30T00:00:00 | Delivery |  | 2018-11-30T00:00:00 | An extension to the project end date has been approved to accommodate vendor resource constraints. There is no impact to cost. Discussions are under way with the vendor to ensure resourcing constraints will not impact quality, or further delay delivery. 20/9/2018, 20/9/2018,August 2018 - The project is continuing as planned, tracking within tolerances for time, cost and quality. 20/9/2018, 20/9/2018,June 2018 - A change request has been approved altering the planned end date and budget to allow for resolution of unforeseen complexities in deliverables. 20/9/2018, 20/9/2018,May 2018 - The project timeframe is currently being monitored, with action under way to return it to Green. 20/9/2018, 20/9/2018,April 2018 - This project is reporting for the first time and is progressing as planned. | 2018-09-14T00:00:00 | Medium | 414000 |  | Operations Support | 73 | 117960 |  | G | 3 | Implement a solution for government, industry and other stakeholders to objectively and consistently assess land conditions, including development of a pictogram-based mobile web application and a data collection tool. | 479000 | 2017-01-12T00:00:00 | DNRM
20/9/2018 | CWeHR | Coal Workers eHealth Records Project | 2020-06-30T00:00:00 | Delivery |  | 2020-06-30T00:00:00 | The project is continuing as planned, tracking within project tolerances. 20/9/2018, 20/9/2018,August 2018 - This project is reporting for the first time and is progressing as planned. Note finances reported represent Stage 0 and Stage 1. | 2018-09-14T00:00:00 | High | 3894285 |  | Occupational Health and Hygiene - Resources Safety and Health | 5 | 792640 |  | G | 4 | Improvement in data management and surveillance for coal mine worker health assessments: 20/9/2018, 20/9/2018,* new customer digital interface 20/9/2018,* improved health assessment outcomes through improved access to longitudinal health records 20/9/2018,* enable industry-wide health surveillance through electronic storage and access to health records 20/9/2018,* improved data management using appropriate health management systems and alignment with health record management requirements. | 3894285 | 2017-03-23T00:00:00 | DNRM
20/9/2018 | SO | Mines Gas Monitoring Solution Replacement (Phase 1) | 2017-09-20T00:00:00 | Delivery |  | 2019-03-29T00:00:00 | The project is progressing as planned. 20/9/2018, 20/9/2018,August 2018 - The project is continuing as planned, tracking within tolerances for time, cost and quality. 20/9/2018, 20/9/2018,February 2018 - A change request was approved to alter the scope and associated percentage complete, time-frame and costs. 20/9/2018, 20/9/2018,December 2017 - Awaiting confirmation of project closure; project is still operating within approved time-frame tolerance. 20/9/2018, 20/9/2018,November 2017 - A change to the planned end date and revised total estimated expenditure was approved. Project closure documents are being developed. 20/9/2018, 20/9/2018,October 2017 - The project is continuing as planned. 20/9/2018, 20/9/2018,September 2017 - The project is continuing as planned, moving into delivery in August 2017. | 2018-09-14T00:00:00 | High | 563000 |  | SIMTARS (Safety In Mines Testing and Research Station) | 74 | 861722 |  | G | 5 | The development and delivery of a (replacement) modern and robust Safegas solution: 20/9/2018, 20/9/2018,* risk reduction increasing capability to manage the volume of queries, transactions and data 20/9/2018,* decrease database corruption related to incidents. | 1170000 | 2017-01-25T00:00:00 | DNRM
20/9/2018 | MIRM | Mines Infrastructure Risk Mitigation Project | 2019-02-18T00:00:00 | Delivery |  | 2019-02-28T00:00:00 | The project is progressing as planned. 20/9/2018, 20/9/2018,August 2018 - The project is continuing as planned, tracking within tolerances for time, cost and quality. 20/9/2018, 20/9/2018,April 2018 - A minor adjustment to scope has been approved; there is no impact to timeframe or cost. 20/9/2018, 20/9/2018,March 2018 - The project is continuing as planned. 20/9/2018, 20/9/2018,November 2017 - The project was approved to move into delivery in October 2017 and is reporting for the first time. | 2018-09-14T00:00:00 | High | 1200000 |  | Statewide Operations | 75 | 665775 |  | G | 6 | Migrate systems to supported infrastructure and software to: 20/9/2018, 20/9/2018,* provide a stable, secure, fully supported and flexible solution 20/9/2018,* eliminate the risks to which the geoscience data assets are currently exposed. | 1200000 | 2017-08-08T00:00:00 | DNRM
20/9/2018 | DPC | Performance Information Management System (PIMS) Dynamics 365 upgrade and relocation | 2018-10-30T00:00:00 | Delivery |  | 2018-10-30T00:00:00 | The project commenced in May 2018 and is on track for delivery. The Discovery Phase has been completed and the scope of work for the upgrade project finalised. 20/9/2018,The PIMS Upgrade Oversight Group is meeting regularly to oversee implementation. Development work and initial system testing has been completed. User acceptance testing is underway | 2018-08-01T00:00:00 | High | 240494 |  | Premier and Cabinet | 70 | 78063 |  | G | 1 | To upgrade the existing PIMS solution from the current 2013 version to Microsoft Dynamics 365 and move the system to Microsoft Online. | 240494 | 2018-05-01T00:00:00 | DPC
20/9/2018 | CIO | CBD Consolidation - Terrica Place Relocation Project | 2017-12-30T00:00:00 | Delivery | G | 2017-12-30T00:00:00 | Project continues to progress in line with set timeframes, budget and quality. Some minor matters with technology installation, however this is not expected to impact timeframes. | 2017-10-10T00:00:00 | Medium | 800000 | G | Chief Information Office | 85 | 680152 | G | G | 1 | To relocate staff from 80, 100 and 111 George Street and Forestry House, 160 Mary Street by December 2017 as part of the ongoing whole-of-government long-term accommodation strategy for the Brisbane CBD. | 1041000 | 2016-09-01T00:00:00 | DSITI
20/9/2018 | CIO | Print and Imaging as-a-Service (PIaaS) Implementation | 2017-06-30T00:00:00 | Delivery | G | 2017-10-30T00:00:00 | The project is undertaking necessary risk management activities during final implementation of Print and Imaging as a Service. The Project Board are closely monitorin. | 2017-10-16T00:00:00 | High | 144000 | A | Chief Information Office | 85 | 176000 | A | A | 2 | * Implement PIaaS across the department to align with the whole-of-Government PIaaS Strategy 20/9/2018,* Move operational accountability and responsibility for print and imaging devices to the service provider 20/9/2018,* Reduce print and imaging costs 20/9/2018,* Leverage innovative technologies. | 176000 | 2016-01-01T00:00:00 | DSITI
20/9/2018 | QSS | Finance Systems Futures 2 Upgrade | 2017-10-27T00:00:00 | Delivery | G | 2017-10-27T00:00:00 | The project continues to progress in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | Critical | 10381481 | G | Queensland Shared Services | 92 | 8568425 | G | G | 3 | Finance Systems Futures 2 will upgrade the 19 agencies from the consolidated rest-of-Government finance solution platform to a vendor supported solution. | 10381481 | 2016-11-03T00:00:00 | DSITI
20/9/2018 | QSS | Single Agency Payroll Upgrade | 2017-11-30T00:00:00 | Delivery | G | 2017-11-30T00:00:00 | The project is progressing in line with agreed timeframes, budget and quality. | 2017-09-30T00:00:00 | High | 1800000 | G | Queensland Shared Services | 78 | 915485 | G | G | 4 | Upgrade an agency payroll solution to ensure payroll systems are maintained and under vendor support. | 1800000 | 2017-03-01T00:00:00 | DSITI
20/9/2018 | SD | Scientific Information for Land Owners (SILO) climate database redevelopment - Enhancements 2017-18 | 2017-10-31T00:00:00 | Delivery | G | 2017-10-31T00:00:00 | The SILO Enhancement project is focused on data integrity prior to the scheduled system release. The Project Board is monitoring the progress against the set timeframes. | 2017-09-30T00:00:00 | High | 100000 | G | Science | 70 | 61487 | A | A | 5 | To ensure the continued delivery of climate data to internal and external programs dependent upon SILO. 20/9/2018, 20/9/2018,SILO is considered a foundation dataset and failure to deliver this service will result in the department not being able to meet its obligations to Queensland Government customer agencies. The customer departments use the information provided to meet legislative and other whole-of-government obligations. It is also an important resource for many external researchers and businesses (e.g. Agribusiness). | 100000 | 2017-07-01T00:00:00 | DSITI
20/9/2018 | SSQ | Payment Card Industry (PCI) Remediation Implementation | 2016-01-29T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is working to have the automated payment solution finalised by 31 October. Achieving this milestone will allows the PCI project to continue operating within the set budget and timeframes. | 2017-09-30T00:00:00 | Critical | 516033 | G | Smart Service Queensland | 84 | 924570 | G | G | 6 | The Smart Service Queensland PCI Remediation Implementation Project is implementing identified remediation actions required to meet Payment Card Industry Data Security Standards version 3.2 (PCI DSS). | 1432215 | 2014-07-25T00:00:00 | DSITI
20/9/2018 | SSQ | Smart Service Telephony Replacement Project | 2016-01-12T00:00:00 | Delivery | G | 2018-03-30T00:00:00 | The project is progressing in line with set timeframes, product quality and costs. The Project Board continues to closely monitor the dependencies linked with the Content Delivery Solution project. | 2017-09-30T00:00:00 | Critical | 4490634 | G | Smart Service Queensland | 61 | 2272510 | G | G | 7 | To transition our current telephony platform to a digital platform as it is beyond its expected functional life, and is expensive to operate and maintain. The Telephony Replacement Project aims to: 20/9/2018, 20/9/2018,* reduce operating costs 20/9/2018,* increase capacity 20/9/2018,* improve customer experience 20/9/2018,* provide new functionality. | 4150981 | 2015-04-02T00:00:00 | DSITI
20/9/2018 | SSQ | Content Delivery Solution | 2017-03-31T00:00:00 | Delivery | A | 2018-01-31T00:00:00 | The testing phase of the Content Delivery project continues to progress. The Project Board is currently assessing deliverables to determine if there's any impact on timeframes. | 2017-09-30T00:00:00 | Critical | 3476245 | G | Smart Service Queensland | 64 | 1099318 | G | A | 8 | The Smart Service Queensland Content Delivery Solution Project will provide a platform for Smart Service where all channels are managed through one routing engine and one set of reporting and management tools; and support future Omni-Channel initiatives that require integration between channels, such as customers switching from web chat to a voice call. | 2175301 | 2015-11-20T00:00:00 | DSITI
20/9/2018 | SSQ | Technology Platform Project (TPP) | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project continues to progress in line with set timeframes, budget and quality. 20/9/2018, 20/9/2018, | 2017-09-30T00:00:00 | Critical | 3390861 | G | Smart Service Queensland | 62 | 1182575 | G | G | 9 | The Technology Platform Project is providing the technical capability required to support the design, implementation and ongoing maintenance of the content delivery solution, telephony solution, call recording solution and the broader Business Modernisation Program. | 3390862 | 2017-05-15T00:00:00 | DSITI
20/9/2018 | QGCIO | QGCIO Website refresh | 2017-10-31T00:00:00 | Closed | G | 2017-10-31T00:00:00 | Project closure activities are now complete and the QGCIO beta website went live on 13 October 2017. The qgcio.qld.gov.au site will be live on 26 October 2017. 20/9/2018, 20/9/2018,The website project was run using an Agile approach and delivered a website with a contemporary design and innovative features designed to support an evergrowing clientbase. The site features a streamlined self-service user registration for government users, push notification system for government policy decisions and a new collaboration forum. | 2017-10-13T00:00:00 | Medium | 260000 | G | QGCIO | 100 | 258680 | G | G | 10 | The Queensland Government Chief Information Office (QGCIO) is developing a refreshed QGCIO website which will cater for both an external to government view and capability, and an internal to government view and capability. | 260000 | 2017-03-01T00:00:00 | DSITI
20/9/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DTESB
20/9/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery | G | 2018-06-30T00:00:00 | The project is progressing as planned. 20/9/2018, 20/9/2018,November 2017 - Actual cost to date corrected due to input error. 20/9/2018, 20/9/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. 20/9/2018, | 2017-12-20T00:00:00 | Medium | 1750000 | G | Queensland Parks and Wildlife Service | 57 | 733941 | G | G | 1 | Acquire one or more solution components to operate in conjunction with the Agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | NPSR
20/9/2018 | QPWS | Strategic Asset Management | 2018-06-30T00:00:00 | Delivery |  | 2018-08-31T00:00:00 | Closure activities are being finalised; the project remains within accepted tolerances. 20/9/2018, 20/9/2018,August 2018 - An extension to the timeframe has been approved to allow for closure activities to be finalised. 20/9/2018, 20/9/2018,July 2018 - Key deliverables have been achieved within project time-frames. Project closure activities are under way, to be finalised within the next two weeks. 20/9/2018, 20/9/2018,June 2018 - User acceptance testing is almost complete; the solution is about to move into production with project closure activities under way. 20/9/2018, 20/9/2018,May 2018 - The project is progressing as planned. 20/9/2018, 20/9/2018,November 2017 - Actual cost to date corrected due to input error. 20/9/2018, 20/9/2018,October 2017 - The project is continuing as planned, moving into delivery in September 2017, and publishing for the first time in October 2017. | 2018-09-14T00:00:00 | Medium | 1750000 |  | Queensland Parks and Wildlife Service | 98 | 1378661 |  | G | 1 | Acquire one or more solution components to operate in conjunction with the agency finance system in order to support whole-of-life asset management. | 2112630 | 2016-11-14T00:00:00 | EHP
20/9/2018 | QPWS | Augmented Ranger Mobile Application | 2019-06-28T00:00:00 | Delivery |  | 2019-06-28T00:00:00 | The project is progressing as planned. 20/9/2018, 20/9/2018,August 2018 - The project has been approved to commence delivery and is publishing for the first time. | 2018-09-14T00:00:00 | Low | 240000 |  | Queensland Parks and Wildlife Service | 30 | 50772 |  | G | 2 | Develop a unique, mobile, optimised solution that uses Augmented Reality to: 20/9/2018, 20/9/2018,* enrich visitors? on-park engagement, experiences and understanding of cultural, historical and ecological points of interests specific to the location 20/9/2018,* provide opportunities for ranger-visitor communications 20/9/2018,* aid collection of real-time visitor data. | 240000 | 2018-02-01T00:00:00 | EHP
20/9/2018 | EPP | Queensland Waste Disposal Levy System | 2019-05-31T00:00:00 | Delivery |  | 2019-05-31T00:00:00 | The project has been approved to commence delivery and is publishing for the first time. | 2018-09-14T00:00:00 | Critical | 2248000 |  | Environment Policy and Planning | 5 | 143751 |  | G | 3 | Implement a solution to meet new legislative arrangements for a waste disposal levy, to effectively and efficiently enable: 20/9/2018, 20/9/2018,* site operators to accurately record data 20/9/2018,* reconciliation of waste data and levy liabilities 20/9/2018,* timely access to, and interrogation of, large datasets. | 2248000 | 2018-07-10T00:00:00 | EHP
20/9/2018 | [9 empty] | 0 |  |  | 0 | 0 |  |  | 1 |  | 0 |  | DILGP